## All Results
WTG | Pile Type | Design Cat. | Pile Length (m) | Pile Weight (t) | Wp (MN) | Wp (kN) | Design Embedment (m) | Vibro Target Depth (m) | Water Depth (m) | Hammer | Hammer Weight Air (t) | Hammer Weight Sub (t) | Hammer Energy (kJ) | W_hammer_sub (kN) | W_total (kN) | SRD Method | SWP Pile Only (m) | SWP Pile+Hammer (m) | Pile Run Start (m) | Pile Run End (m) | Max Velocity Pile Only (m/s) | Max Velocity Pile+Hammer (m/s) | Risk Level | False Floors Count | True Arrest Depth (m)
WTG-01 | DP | 2 | 56.2 | 236.4934 | 2.32 | 2320 | 52.3 | 22 | 26.52 | MENCK MHU 1900S | 249 | 200 | 1900 | 1962 | 4282 | AH-FF | 11 | 13 | 0.75 | 18 | 9.932 | 8.272 | CAUTION | 17 | 38.56
WTG-01 | DP | 2 | 56.2 | 236.4934 | 2.32 | 2320 | 52.3 | 22 | 26.52 | MENCK MHU 1900S | 249 | 200 | 1900 | 1962 | 4282 | AH-NFF | 10.25 | 12.25 | 0.75 | 17 | 9.808 | 8.117 | OK | 17 | 38.56
WTG-01 | DP | 2 | 56.2 | 236.4934 | 2.32 | 2320 | 52.3 | 22 | 26.52 | MENCK MHU 1900S | 249 | 200 | 1900 | 1962 | 4282 | MEAN | 10.5 | 13 | 0.75 | 17.5 | 9.867 | 8.189 | OK | 17 | 38.56
WTG-01 | DP | 2 | 56.2 | 236.4934 | 2.32 | 2320 | 52.3 | 22 | 26.52 | MENCK MHU 1900S | 249 | 200 | 1900 | 1962 | 4282 | VERGOTE | 11 | 13 | 0.75 | 18 | 9.962 | 8.292 | CAUTION | 17 | 38.56
WTG-02 | DP | 2 | 46.5 | 236.4934 | 2.32 | 2320 | 45 | 17 | 15.9 | MENCK MHU 1900S | 249 | 200 | 1900 | 1962 | 4282 | AH-FF | 6.75 | 11.25 | 0.75 | 14.5 | 9.736 | 7.65 | CAUTION | 35 | 39.94
WTG-02 | DP | 2 | 46.5 | 236.4934 | 2.32 | 2320 | 45 | 17 | 15.9 | MENCK MHU 1900S | 249 | 200 | 1900 | 1962 | 4282 | AH-NFF | 6.75 | 9.75 | 0.75 | 13.75 | 9.717 | 7.623 | CAUTION | 35 | 39.94
WTG-02 | DP | 2 | 46.5 | 236.4934 | 2.32 | 2320 | 45 | 17 | 15.9 | MENCK MHU 1900S | 249 | 200 | 1900 | 1962 | 4282 | MEAN | 6.75 | 11 | 0.75 | 14.25 | 9.726 | 7.629 | CAUTION | 35 | 39.94
WTG-02 | DP | 2 | 46.5 | 236.4934 | 2.32 | 2320 | 45 | 17 | 15.9 | MENCK MHU 1900S | 249 | 200 | 1900 | 1962 | 4282 | VERGOTE | 6.75 | 11.25 | 0.75 | 15.75 | 10.398 | 8.566 | CAUTION | 35 | 39.94
WTG-03 | DP | 2 | 47.5 | 183.4862 | 1.8 | 1800 | 46 | 18 | 29.45 | MENCK MHU 1900S | 249 | 200 | 1900 | 1962 | 3762 | AH-FF | 3.5 | 11 | 0.75 | 13.25 | 6.975 | 5.908 | OK | 13 | 27.98
WTG-03 | DP | 2 | 47.5 | 183.4862 | 1.8 | 1800 | 46 | 18 | 29.45 | MENCK MHU 1900S | 249 | 200 | 1900 | 1962 | 3762 | AH-NFF | 3.5 | 10 | 0.75 | 12 | 6.769 | 5.661 | OK | 13 | 27.98
WTG-03 | DP | 2 | 47.5 | 183.4862 | 1.8 | 1800 | 46 | 18 | 29.45 | MENCK MHU 1900S | 249 | 200 | 1900 | 1962 | 3762 | MEAN | 3.5 | 10.75 | 0.75 | 12.5 | 6.836 | 5.779 | OK | 13 | 27.98
WTG-03 | DP | 2 | 47.5 | 183.4862 | 1.8 | 1800 | 46 | 18 | 29.45 | MENCK MHU 1900S | 249 | 200 | 1900 | 1962 | 3762 | VERGOTE | 3.5 | 11 | 0.75 | 13.75 | 8.06 | 6.508 | OK | 13 | 27.98
WTG-04 | IP | 2 | 42 | 177.37 | 1.74 | 1740 | 40.5 | 19 | 23.12 | MENCK MHU 1900S | 249 | 200 | 1900 | 1962 | 3702 | AH-FF | 9.25 | 12.75 | 0.75 | 16 | 9.043 | 7.362 | CAUTION | 24 | 33.18
WTG-04 | IP | 2 | 42 | 177.37 | 1.74 | 1740 | 40.5 | 19 | 23.12 | MENCK MHU 1900S | 249 | 200 | 1900 | 1962 | 3702 | AH-NFF | 9.25 | 11.75 | 0.75 | 15.25 | 8.863 | 7.2 | CAUTION | 24 | 33.18
WTG-04 | IP | 2 | 42 | 177.37 | 1.74 | 1740 | 40.5 | 19 | 23.12 | MENCK MHU 1900S | 249 | 200 | 1900 | 1962 | 3702 | MEAN | 9.25 | 12 | 0.75 | 15.5 | 8.952 | 7.276 | CAUTION | 24 | 33.18
WTG-04 | IP | 2 | 42 | 177.37 | 1.74 | 1740 | 40.5 | 19 | 23.12 | MENCK MHU 1900S | 249 | 200 | 1900 | 1962 | 3702 | VERGOTE | 9.25 | 12.75 | 0.75 | 16.5 | 9.2 | 7.567 | CAUTION | 24 | 33.18
WTG-05 | DP | 2 | 53.5 | 209.9898 | 2.06 | 2060 | 52 | 17 | 22.5 | MENCK MHU 1900S | 249 | 200 | 1900 | 1962 | 4022 | AH-FF | 3.75 | 6.75 | 0.75 | 8.25 | 5.784 | 4.79 | OK | 41 | 38.12
WTG-05 | DP | 2 | 53.5 | 209.9898 | 2.06 | 2060 | 52 | 17 | 22.5 | MENCK MHU 1900S | 249 | 200 | 1900 | 1962 | 4022 | AH-NFF | 3.75 | 6.25 | 0.75 | 7.5 | 5.71 | 4.673 | OK | 41 | 38.12
WTG-05 | DP | 2 | 53.5 | 209.9898 | 2.06 | 2060 | 52 | 17 | 22.5 | MENCK MHU 1900S | 249 | 200 | 1900 | 1962 | 4022 | MEAN | 3.75 | 6.75 | 0.75 | 8 | 5.741 | 4.727 | OK | 41 | 38.12
WTG-05 | DP | 2 | 53.5 | 209.9898 | 2.06 | 2060 | 52 | 17 | 22.5 | MENCK MHU 1900S | 249 | 200 | 1900 | 1962 | 4022 | VERGOTE | 3.75 | 6.75 | 0.75 | 10 | 7.905 | 6.272 | OK | 41 | 38.12
WTG-06 | IP | 2 | 36.4 | 152.9052 | 1.5 | 1500 | 34.9 | 18 | 23.31 | MENCK MHU 1900S | 249 | 200 | 1900 | 1962 | 3462 | AH-FF | 2 | 2 | 0.75 | 2.75 | 4.745 | 3.692 | OK | 39 | 31.84
WTG-06 | IP | 2 | 36.4 | 152.9052 | 1.5 | 1500 | 34.9 | 18 | 23.31 | MENCK MHU 1900S | 249 | 200 | 1900 | 1962 | 3462 | AH-NFF | 2 | 2 | 0.75 | 2.75 | 4.744 | 3.339 | OK | 39 | 31.84
WTG-06 | IP | 2 | 36.4 | 152.9052 | 1.5 | 1500 | 34.9 | 18 | 23.31 | MENCK MHU 1900S | 249 | 200 | 1900 | 1962 | 3462 | MEAN | 2 | 2 | 0.75 | 2.75 | 4.745 | 3.339 | OK | 39 | 31.84
WTG-06 | IP | 2 | 36.4 | 152.9052 | 1.5 | 1500 | 34.9 | 18 | 23.31 | MENCK MHU 1900S | 249 | 200 | 1900 | 1962 | 3462 | VERGOTE | 2 | 2 | 0.75 | 8.25 | 5.459 | 4.302 | OK | 39 | 31.84
WTG-07 | IP | 2 | 39.5 | 166.157 | 1.63 | 1630 | 37.9 | 18 | 24.26 | MENCK MHU 1900S | 249 | 200 | 1900 | 1962 | 3592 | AH-FF | 7 | 11.25 | 0.75 | 13.25 | 8.212 | 6.441 | OK | 29 | 31.32
WTG-07 | IP | 2 | 39.5 | 166.157 | 1.63 | 1630 | 37.9 | 18 | 24.26 | MENCK MHU 1900S | 249 | 200 | 1900 | 1962 | 3592 | AH-NFF | 7 | 10.25 | 0.75 | 12.5 | 8.115 | 6.365 | OK | 29 | 31.32
WTG-07 | IP | 2 | 39.5 | 166.157 | 1.63 | 1630 | 37.9 | 18 | 24.26 | MENCK MHU 1900S | 249 | 200 | 1900 | 1962 | 3592 | MEAN | 7 | 10.5 | 0.75 | 12.75 | 8.164 | 6.403 | OK | 29 | 31.32
WTG-07 | IP | 2 | 39.5 | 166.157 | 1.63 | 1630 | 37.9 | 18 | 24.26 | MENCK MHU 1900S | 249 | 200 | 1900 | 1962 | 3592 | VERGOTE | 7 | 11.25 | 0.75 | 13.75 | 8.563 | 6.687 | OK | 29 | 31.32
WTG-08 | IP | 2 | 37.6 | 181.4475 | 1.78 | 1780 | 36 | 30.8 | 18.91 | MENCK MHU 1900S | 249 | 200 | 1900 | 1962 | 3742 | AH-FF | 4.5 | 8.75 | 0.75 | 14.75 | 7.248 | 6.002 | OK | 35 | 31.88
WTG-08 | IP | 2 | 37.6 | 181.4475 | 1.78 | 1780 | 36 | 30.8 | 18.91 | MENCK MHU 1900S | 249 | 200 | 1900 | 1962 | 3742 | AH-NFF | 4.5 | 8.75 | 0.75 | 12.75 | 7.233 | 5.87 | OK | 35 | 31.88
WTG-08 | IP | 2 | 37.6 | 181.4475 | 1.78 | 1780 | 36 | 30.8 | 18.91 | MENCK MHU 1900S | 249 | 200 | 1900 | 1962 | 3742 | MEAN | 4.5 | 8.75 | 0.75 | 13.5 | 7.241 | 5.92 | OK | 35 | 31.88
WTG-08 | IP | 2 | 37.6 | 181.4475 | 1.78 | 1780 | 36 | 30.8 | 18.91 | MENCK MHU 1900S | 249 | 200 | 1900 | 1962 | 3742 | VERGOTE | 4.5 | 8.75 | 0.75 | 18 | 9.411 | 7.509 | OK | 35 | 31.88
WTG-09 | IP | 1 | 39.5 | 176.3507 | 1.73 | 1730 | 38 | 19 | 17.87 | MENCK MHU 1900S | 249 | 200 | 1900 | 1962 | 3692 | AH-FF | 5.25 | 5.5 | 0.75 | 8 | 7.88 | 6.023 | OK | 13 | 30.62
WTG-09 | IP | 1 | 39.5 | 176.3507 | 1.73 | 1730 | 38 | 19 | 17.87 | MENCK MHU 1900S | 249 | 200 | 1900 | 1962 | 3692 | AH-NFF | 5.25 | 5.5 | 0.75 | 8 | 7.832 | 5.995 | OK | 13 | 30.62
WTG-09 | IP | 1 | 39.5 | 176.3507 | 1.73 | 1730 | 38 | 19 | 17.87 | MENCK MHU 1900S | 249 | 200 | 1900 | 1962 | 3692 | MEAN | 5.25 | 5.5 | 0.75 | 8 | 7.855 | 6.009 | OK | 13 | 30.62
WTG-09 | IP | 1 | 39.5 | 176.3507 | 1.73 | 1730 | 38 | 19 | 17.87 | MENCK MHU 1900S | 249 | 200 | 1900 | 1962 | 3692 | VERGOTE | 5.25 | 5.5 | 0.75 | 13 | 8.148 | 6.359 | OK | 13 | 30.62
WTG-10 | IP | 1 | 39.6 | 163.0989 | 1.6 | 1600 | 38.1 | 27 | 29.68 | MENCK MHU 1900S | 249 | 200 | 1900 | 1962 | 3562 | AH-FF | 1.75 | 2 | 0.75 | 2.25 | 8.688 | 13.52 | OK | 9 | 29.14
WTG-10 | IP | 1 | 39.6 | 163.0989 | 1.6 | 1600 | 38.1 | 27 | 29.68 | MENCK MHU 1900S | 249 | 200 | 1900 | 1962 | 3562 | AH-NFF | 1.75 | 2 | 0.75 | 2.25 | 5.323 | 11.321 | OK | 9 | 29.14
WTG-10 | IP | 1 | 39.6 | 163.0989 | 1.6 | 1600 | 38.1 | 27 | 29.68 | MENCK MHU 1900S | 249 | 200 | 1900 | 1962 | 3562 | MEAN | 1.75 | 2 | 0.75 | 2.25 | 6.987 | 12.413 | OK | 9 | 29.14
WTG-10 | IP | 1 | 39.6 | 163.0989 | 1.6 | 1600 | 38.1 | 27 | 29.68 | MENCK MHU 1900S | 249 | 200 | 1900 | 1962 | 3562 | VERGOTE | 1.75 | 2 | 0.75 | 29 | 9.617 | 8.519 | ATTENTION | 9 | 29.14
WTG-11 | IP | 2 | 26.7 | 110.0917 | 1.08 | 1080 | 25.2 | 15 | 29.46 | MENCK MHU 1900S | 249 | 200 | 1900 | 1962 | 3042 | AH-FF | 5 | 10.25 | 0.75 | 11 | 5.861 | 4.73 | CAUTION | 5 | 22.64
WTG-11 | IP | 2 | 26.7 | 110.0917 | 1.08 | 1080 | 25.2 | 15 | 29.46 | MENCK MHU 1900S | 249 | 200 | 1900 | 1962 | 3042 | AH-NFF | 4.75 | 9.75 | 0.75 | 10.25 | 5.757 | 4.593 | OK | 5 | 22.64
WTG-11 | IP | 2 | 26.7 | 110.0917 | 1.08 | 1080 | 25.2 | 15 | 29.46 | MENCK MHU 1900S | 249 | 200 | 1900 | 1962 | 3042 | MEAN | 5 | 9.75 | 0.75 | 10.75 | 5.805 | 4.661 | OK | 5 | 22.64
WTG-11 | IP | 2 | 26.7 | 110.0917 | 1.08 | 1080 | 25.2 | 15 | 29.46 | MENCK MHU 1900S | 249 | 200 | 1900 | 1962 | 3042 | VERGOTE | 5 | 10.25 | 0.75 | 11.25 | 6.263 | 4.923 | CAUTION | 5 | 22.64
WTG-12 | IP | 2 | 37.9 | 155.9633 | 1.53 | 1530 | 36.4 | 16 | 29.43 | MENCK MHU 1900S | 249 | 200 | 1900 | 1962 | 3492 | AH-FF | 1.75 | 8.25 | 0.75 | 8.25 | 3.956 | 3.471 | OK | 8 | 18.88
WTG-12 | IP | 2 | 37.9 | 155.9633 | 1.53 | 1530 | 36.4 | 16 | 29.43 | MENCK MHU 1900S | 249 | 200 | 1900 | 1962 | 3492 | AH-NFF | 1.75 | 7.25 | 0.75 | 7.25 | 3.955 | 3.325 | OK | 8 | 18.88
WTG-12 | IP | 2 | 37.9 | 155.9633 | 1.53 | 1530 | 36.4 | 16 | 29.43 | MENCK MHU 1900S | 249 | 200 | 1900 | 1962 | 3492 | MEAN | 1.75 | 8 | 0.75 | 7.75 | 3.955 | 3.393 | OK | 8 | 18.88
WTG-12 | IP | 2 | 37.9 | 155.9633 | 1.53 | 1530 | 36.4 | 16 | 29.43 | MENCK MHU 1900S | 249 | 200 | 1900 | 1962 | 3492 | VERGOTE | 1.75 | 8.25 | 0.75 | 10.25 | 6.609 | 5.005 | OK | 8 | 18.88
WTG-13 | IP | 2 | 20.9 | 87.6656 | 0.86 | 860 | 17.1 | 13 | 26.44 | MENCK MHU 1900S | 249 | 200 | 1900 | 1962 | 2822 | AH-FF | 2 | 2 | 0.75 | 3.25 | 3.877 | 2.64 | OK | 17 | 16.84
WTG-13 | IP | 2 | 20.9 | 87.6656 | 0.86 | 860 | 17.1 | 13 | 26.44 | MENCK MHU 1900S | 249 | 200 | 1900 | 1962 | 2822 | AH-NFF | 2 | 2 | 0.75 | 3.25 | 3.835 | 2.623 | OK | 17 | 16.84
WTG-13 | IP | 2 | 20.9 | 87.6656 | 0.86 | 860 | 17.1 | 13 | 26.44 | MENCK MHU 1900S | 249 | 200 | 1900 | 1962 | 2822 | MEAN | 2 | 2 | 0.75 | 3.25 | 3.856 | 2.632 | OK | 17 | 16.84
WTG-13 | IP | 2 | 20.9 | 87.6656 | 0.86 | 860 | 17.1 | 13 | 26.44 | MENCK MHU 1900S | 249 | 200 | 1900 | 1962 | 2822 | VERGOTE | 2 | 2 | 0.75 | 4.5 | 3.877 | 2.839 | OK | 17 | 16.84
WTG-14 | IP | 3 | 21.7 | 90.7238 | 0.89 | 890 | 20.2 | 14.2 | 23.67 | MENCK MHU 1900S | 249 | 200 | 1900 | 1962 | 2852 | AH-FF | 5 | 10 | 0.75 | 10.25 | 6.319 | 4.863 | CAUTION | 8 | 19.62
WTG-14 | IP | 3 | 21.7 | 90.7238 | 0.89 | 890 | 20.2 | 14.2 | 23.67 | MENCK MHU 1900S | 249 | 200 | 1900 | 1962 | 2852 | AH-NFF | 5 | 9.5 | 0.75 | 9.75 | 6.281 | 4.798 | OK | 8 | 19.62
WTG-14 | IP | 3 | 21.7 | 90.7238 | 0.89 | 890 | 20.2 | 14.2 | 23.67 | MENCK MHU 1900S | 249 | 200 | 1900 | 1962 | 2852 | MEAN | 5 | 9.75 | 0.75 | 10 | 6.3 | 4.83 | OK | 8 | 19.62
WTG-14 | IP | 3 | 21.7 | 90.7238 | 0.89 | 890 | 20.2 | 14.2 | 23.67 | MENCK MHU 1900S | 249 | 200 | 1900 | 1962 | 2852 | VERGOTE | 5 | 10 | 0.75 | 10.25 | 6.33 | 4.871 | CAUTION | 8 | 19.62
WTG-15 | DP | 1 | 53.8 | 212.0285 | 2.08 | 2080 | 52.3 | 27 | 21.18 | MENCK MHU 1900S | 249 | 200 | 1900 | 1962 | 4042 | AH-FF | 12.75 | 23 | 0.75 | 25.5 | 11.785 | 9.651 | CAUTION | 16 | 28.74
WTG-15 | DP | 1 | 53.8 | 212.0285 | 2.08 | 2080 | 52.3 | 27 | 21.18 | MENCK MHU 1900S | 249 | 200 | 1900 | 1962 | 4042 | AH-NFF | 12.75 | 21.5 | 0.75 | 24 | 11.642 | 9.559 | CAUTION | 16 | 28.74
WTG-15 | DP | 1 | 53.8 | 212.0285 | 2.08 | 2080 | 52.3 | 27 | 21.18 | MENCK MHU 1900S | 249 | 200 | 1900 | 1962 | 4042 | MEAN | 12.75 | 22.75 | 0.75 | 24.75 | 11.714 | 9.605 | CAUTION | 16 | 28.74
WTG-15 | DP | 1 | 53.8 | 212.0285 | 2.08 | 2080 | 52.3 | 27 | 21.18 | MENCK MHU 1900S | 249 | 200 | 1900 | 1962 | 4042 | VERGOTE | 12.75 | 23 | 0.75 | 27 | 12.016 | 9.92 | ATTENTION | 16 | 28.74
WTG-16 | DP | 1 | 50 | 253.8226 | 2.49 | 2490 | 48.5 | 24 | 16.98 | MENCK MHU 1900S | 249 | 200 | 1900 | 1962 | 4452 | AH-FF | 10.25 | 10.5 | 0.75 | 18.5 | 11.95 | 9.612 | OK | 18 | 33.76
WTG-16 | DP | 1 | 50 | 253.8226 | 2.49 | 2490 | 48.5 | 24 | 16.98 | MENCK MHU 1900S | 249 | 200 | 1900 | 1962 | 4452 | AH-NFF | 10.25 | 10.5 | 0.75 | 18 | 11.913 | 9.586 | OK | 18 | 33.76
WTG-16 | DP | 1 | 50 | 253.8226 | 2.49 | 2490 | 48.5 | 24 | 16.98 | MENCK MHU 1900S | 249 | 200 | 1900 | 1962 | 4452 | MEAN | 10.25 | 10.5 | 0.75 | 18.25 | 11.931 | 9.599 | OK | 18 | 33.76
WTG-16 | DP | 1 | 50 | 253.8226 | 2.49 | 2490 | 48.5 | 24 | 16.98 | MENCK MHU 1900S | 249 | 200 | 1900 | 1962 | 4452 | VERGOTE | 10.25 | 10.5 | 0.75 | 21.25 | 12.283 | 10.005 | CAUTION | 18 | 33.76
WTG-17 | IP | 3 | 17.7 | 76.4526 | 0.75 | 750 | 16.2 | 10.2 | 23.56 | MENCK MHU 1900S | 249 | 200 | 1900 | 1962 | 2712 | AH-FF | 1.75 | 1.75 | 0.75 | 2.25 | 3.841 | 3.61 | OK | 16 | 13.32
WTG-17 | IP | 3 | 17.7 | 76.4526 | 0.75 | 750 | 16.2 | 10.2 | 23.56 | MENCK MHU 1900S | 249 | 200 | 1900 | 1962 | 2712 | AH-NFF | 1.75 | 1.75 | 0.75 | 2.25 | 3.839 | 2.449 | OK | 16 | 13.32
WTG-17 | IP | 3 | 17.7 | 76.4526 | 0.75 | 750 | 16.2 | 10.2 | 23.56 | MENCK MHU 1900S | 249 | 200 | 1900 | 1962 | 2712 | MEAN | 1.75 | 1.75 | 0.75 | 2.25 | 3.84 | 2.449 | OK | 16 | 13.32
WTG-17 | IP | 3 | 17.7 | 76.4526 | 0.75 | 750 | 16.2 | 10.2 | 23.56 | MENCK MHU 1900S | 249 | 200 | 1900 | 1962 | 2712 | VERGOTE | 1.75 | 1.75 | 0.75 | 3.75 | 4.133 | 6.605 | OK | 16 | 13.32
WTG-18 | IP | 2 | 25.3 | 103.9755 | 1.02 | 1020 | 23.8 | 17.8 | 29.79 | MENCK MHU 1900S | 249 | 200 | 1900 | 1962 | 2982 | AH-FF | 5.25 | 13 | 0.75 | 12.75 | 5.998 | 4.804 | OK | 3 | 22.14
WTG-18 | IP | 2 | 25.3 | 103.9755 | 1.02 | 1020 | 23.8 | 17.8 | 29.79 | MENCK MHU 1900S | 249 | 200 | 1900 | 1962 | 2982 | AH-NFF | 5 | 12 | 0.75 | 11.5 | 5.891 | 4.673 | OK | 3 | 22.14
WTG-18 | IP | 2 | 25.3 | 103.9755 | 1.02 | 1020 | 23.8 | 17.8 | 29.79 | MENCK MHU 1900S | 249 | 200 | 1900 | 1962 | 2982 | MEAN | 5 | 12.5 | 0.75 | 12 | 5.945 | 4.735 | OK | 3 | 22.14
WTG-18 | IP | 2 | 25.3 | 103.9755 | 1.02 | 1020 | 23.8 | 17.8 | 29.79 | MENCK MHU 1900S | 249 | 200 | 1900 | 1962 | 2982 | VERGOTE | 5.25 | 13 | 0.75 | 13 | 6.208 | 4.897 | OK | 3 | 22.14
WTG-19 | IP | 2 | 42 | 172.2732 | 1.69 | 1690 | 40.5 | 19 | 31.21 | MENCK MHU 1900S | 249 | 200 | 1900 | 1962 | 3652 | AH-FF | 8.5 | 17.75 | 0.75 | 19.5 | 9.34 | 7.36 | ATTENTION | 8 | 38.84
WTG-19 | IP | 2 | 42 | 172.2732 | 1.69 | 1690 | 40.5 | 19 | 31.21 | MENCK MHU 1900S | 249 | 200 | 1900 | 1962 | 3652 | AH-NFF | 8.5 | 17.75 | 0.75 | 18.75 | 9.26 | 7.292 | CAUTION | 8 | 38.84
WTG-19 | IP | 2 | 42 | 172.2732 | 1.69 | 1690 | 40.5 | 19 | 31.21 | MENCK MHU 1900S | 249 | 200 | 1900 | 1962 | 3652 | MEAN | 8.5 | 17.75 | 0.75 | 19 | 9.299 | 7.326 | ATTENTION | 8 | 38.84
WTG-19 | IP | 2 | 42 | 172.2732 | 1.69 | 1690 | 40.5 | 19 | 31.21 | MENCK MHU 1900S | 249 | 200 | 1900 | 1962 | 3652 | VERGOTE | 8.5 | 17.75 | 0.75 | 20 | 10.089 | 7.825 | ATTENTION | 8 | 38.84
WTG-20 | IP | 2 | 42.2 | 174.3119 | 1.71 | 1710 | 40.7 | 16 | 30.26 | MENCK MHU 1900S | 249 | 200 | 1900 | 1962 | 3672 | AH-FF | 4.25 | 8.25 | 0.75 | 9 | 5.224 | 4.34 | OK | 6 | 35.56
WTG-20 | IP | 2 | 42.2 | 174.3119 | 1.71 | 1710 | 40.7 | 16 | 30.26 | MENCK MHU 1900S | 249 | 200 | 1900 | 1962 | 3672 | AH-NFF | 4 | 7.5 | 0.75 | 8 | 5.132 | 4.194 | OK | 6 | 35.56
WTG-20 | IP | 2 | 42.2 | 174.3119 | 1.71 | 1710 | 40.7 | 16 | 30.26 | MENCK MHU 1900S | 249 | 200 | 1900 | 1962 | 3672 | MEAN | 4 | 7.75 | 0.75 | 8.5 | 5.164 | 4.264 | OK | 6 | 35.56
WTG-20 | IP | 2 | 42.2 | 174.3119 | 1.71 | 1710 | 40.7 | 16 | 30.26 | MENCK MHU 1900S | 249 | 200 | 1900 | 1962 | 3672 | VERGOTE | 4.25 | 8.25 | 0.75 | 9.5 | 6.096 | 4.789 | OK | 6 | 35.56
WTG-21 | IP | 2 | 49.2 | 204.893 | 2.01 | 2010 | 47.7 | 20 | 29.18 | MENCK MHU 1900S | 249 | 200 | 1900 | 1962 | 3972 | AH-FF | 6 | 10 | 0.75 | 12 | 6.794 | 5.607 | OK | 9 | 39.24
WTG-21 | IP | 2 | 49.2 | 204.893 | 2.01 | 2010 | 47.7 | 20 | 29.18 | MENCK MHU 1900S | 249 | 200 | 1900 | 1962 | 3972 | AH-NFF | 5.25 | 8.25 | 0.75 | 10.75 | 6.671 | 5.436 | OK | 9 | 39.24
WTG-21 | IP | 2 | 49.2 | 204.893 | 2.01 | 2010 | 47.7 | 20 | 29.18 | MENCK MHU 1900S | 249 | 200 | 1900 | 1962 | 3972 | MEAN | 5.5 | 9 | 0.75 | 11.25 | 6.727 | 5.514 | OK | 9 | 39.24
WTG-21 | IP | 2 | 49.2 | 204.893 | 2.01 | 2010 | 47.7 | 20 | 29.18 | MENCK MHU 1900S | 249 | 200 | 1900 | 1962 | 3972 | VERGOTE | 6 | 10 | 0.75 | 12.25 | 7.282 | 5.894 | OK | 9 | 39.24
WTG-22 | DP | 1 | 51.9 | 201.8349 | 1.98 | 1980 | 48.5 | 24 | 26.04 | MENCK MHU 1900S | 249 | 200 | 1900 | 1962 | 3942 | AH-FF | 10 | 14.75 | 0.75 | 17.25 | 9.151 | 7.604 | OK | 11 | 24.46
WTG-22 | DP | 1 | 51.9 | 201.8349 | 1.98 | 1980 | 48.5 | 24 | 26.04 | MENCK MHU 1900S | 249 | 200 | 1900 | 1962 | 3942 | AH-NFF | 9.75 | 12.75 | 0.75 | 16.25 | 8.912 | 7.389 | OK | 11 | 24.46
WTG-22 | DP | 1 | 51.9 | 201.8349 | 1.98 | 1980 | 48.5 | 24 | 26.04 | MENCK MHU 1900S | 249 | 200 | 1900 | 1962 | 3942 | MEAN | 9.75 | 13.75 | 0.75 | 16.75 | 9.03 | 7.49 | OK | 11 | 24.46
WTG-22 | DP | 1 | 51.9 | 201.8349 | 1.98 | 1980 | 48.5 | 24 | 26.04 | MENCK MHU 1900S | 249 | 200 | 1900 | 1962 | 3942 | VERGOTE | 10 | 14.75 | 0.75 | 17.75 | 9.282 | 7.684 | OK | 11 | 24.46
WTG-23 | IP | 1 | 40.2 | 170.2345 | 1.67 | 1670 | 38.7 | 30 | 22 | MENCK MHU 1900S | 249 | 200 | 1900 | 1962 | 3632 | AH-FF | 13 | 13.25 | 0.75 | 24.5 | 11.536 | 9.317 | OK | 15 | 28.92
WTG-23 | IP | 1 | 40.2 | 170.2345 | 1.67 | 1670 | 38.7 | 30 | 22 | MENCK MHU 1900S | 249 | 200 | 1900 | 1962 | 3632 | AH-NFF | 13 | 13.25 | 0.75 | 21.25 | 11.407 | 9.234 | OK | 15 | 28.92
WTG-23 | IP | 1 | 40.2 | 170.2345 | 1.67 | 1670 | 38.7 | 30 | 22 | MENCK MHU 1900S | 249 | 200 | 1900 | 1962 | 3632 | MEAN | 13 | 13.25 | 0.75 | 22.5 | 11.47 | 9.276 | OK | 15 | 28.92
WTG-23 | IP | 1 | 40.2 | 170.2345 | 1.67 | 1670 | 38.7 | 30 | 22 | MENCK MHU 1900S | 249 | 200 | 1900 | 1962 | 3632 | VERGOTE | 13 | 13.25 | 0.75 | 26.5 | 12.12 | 9.681 | CAUTION | 15 | 28.92
WTG-24 | DP | 1 | 44.4 | 242.6096 | 2.38 | 2380 | 42.5 | 15 | 19.26 | MENCK MHU 1900S | 249 | 200 | 1900 | 1962 | 4342 | AH-FF | 9.5 | 13.5 | 0.75 | 14.75 | 8.053 | 6.959 | CAUTION | 10 | 31.72
WTG-24 | DP | 1 | 44.4 | 242.6096 | 2.38 | 2380 | 42.5 | 15 | 19.26 | MENCK MHU 1900S | 249 | 200 | 1900 | 1962 | 4342 | AH-NFF | 8.25 | 13 | 0.75 | 14.25 | 7.628 | 6.526 | CAUTION | 10 | 31.72
WTG-24 | DP | 1 | 44.4 | 242.6096 | 2.38 | 2380 | 42.5 | 15 | 19.26 | MENCK MHU 1900S | 249 | 200 | 1900 | 1962 | 4342 | MEAN | 9 | 13.5 | 0.75 | 14.5 | 7.823 | 6.729 | CAUTION | 10 | 31.72
WTG-24 | DP | 1 | 44.4 | 242.6096 | 2.38 | 2380 | 42.5 | 15 | 19.26 | MENCK MHU 1900S | 249 | 200 | 1900 | 1962 | 4342 | VERGOTE | 9.5 | 13.5 | 0.75 | 19 | 8.758 | 7.382 | ATTENTION | 10 | 31.72
WTG-25 | IP | 1 | 35.1 | 156.9827 | 1.54 | 1540 | 33.6 | 17 | 17.72 | MENCK MHU 1900S | 249 | 200 | 1900 | 1962 | 3502 | AH-FF | 2 | 5.75 | 0.75 | 6.25 | 4.095 | 3.485 | OK | 23 | 26.66
WTG-25 | IP | 1 | 35.1 | 156.9827 | 1.54 | 1540 | 33.6 | 17 | 17.72 | MENCK MHU 1900S | 249 | 200 | 1900 | 1962 | 3502 | AH-NFF | 2 | 5.75 | 0.75 | 6.25 | 4.094 | 3.292 | OK | 23 | 26.66
WTG-25 | IP | 1 | 35.1 | 156.9827 | 1.54 | 1540 | 33.6 | 17 | 17.72 | MENCK MHU 1900S | 249 | 200 | 1900 | 1962 | 3502 | MEAN | 2 | 5.75 | 0.75 | 6.25 | 4.094 | 3.387 | OK | 23 | 26.66
WTG-25 | IP | 1 | 35.1 | 156.9827 | 1.54 | 1540 | 33.6 | 17 | 17.72 | MENCK MHU 1900S | 249 | 200 | 1900 | 1962 | 3502 | VERGOTE | 2 | 5.75 | 0.75 | 11.5 | 7.034 | 5.481 | OK | 23 | 26.66
WTG-26 | IP | 3 | 14.7 | 59.1233 | 0.58 | 580 | 13.2 | 5.3 | 31 | MENCK MHU 1900S | 249 | 200 | 1900 | 1962 | 2542 | AH-FF | 2.5 | 3.75 | 0.75 | 4.5 | 4.884 | 3.234 | CAUTION | 6 | 10.88
WTG-26 | IP | 3 | 14.7 | 59.1233 | 0.58 | 580 | 13.2 | 5.3 | 31 | MENCK MHU 1900S | 249 | 200 | 1900 | 1962 | 2542 | AH-NFF | 2.5 | 3.75 | 0.75 | 4.5 | 4.878 | 3.221 | CAUTION | 6 | 10.88
WTG-26 | IP | 3 | 14.7 | 59.1233 | 0.58 | 580 | 13.2 | 5.3 | 31 | MENCK MHU 1900S | 249 | 200 | 1900 | 1962 | 2542 | MEAN | 2.5 | 3.75 | 0.75 | 4.5 | 4.881 | 3.228 | CAUTION | 6 | 10.88
WTG-26 | IP | 3 | 14.7 | 59.1233 | 0.58 | 580 | 13.2 | 5.3 | 31 | MENCK MHU 1900S | 249 | 200 | 1900 | 1962 | 2542 | VERGOTE | 2.5 | 3.75 | 0.75 | 6.5 | 5.838 | 3.883 | ATTENTION | 6 | 10.88
OSS | OSS | 0 | 37.5 | 226.2997 | 2.22 | 2220 | 35.5 | 25 | 26.5 | MENCK MHU 1900S | 249 | 200 | 1900 | 1962 | 4182 | AH-FF | 10.25 | 13.5 | 0.75 | 17.75 | 9.257 | 7.767 | OK | 16 | 27.4
OSS | OSS | 0 | 37.5 | 226.2997 | 2.22 | 2220 | 35.5 | 25 | 26.5 | MENCK MHU 1900S | 249 | 200 | 1900 | 1962 | 4182 | AH-NFF | 10 | 13.5 | 0.75 | 16.75 | 9.058 | 7.561 | OK | 16 | 27.4
OSS | OSS | 0 | 37.5 | 226.2997 | 2.22 | 2220 | 35.5 | 25 | 26.5 | MENCK MHU 1900S | 249 | 200 | 1900 | 1962 | 4182 | MEAN | 10 | 13.5 | 0.75 | 17.25 | 9.148 | 7.662 | OK | 16 | 27.4
OSS | OSS | 0 | 37.5 | 226.2997 | 2.22 | 2220 | 35.5 | 25 | 26.5 | MENCK MHU 1900S | 249 | 200 | 1900 | 1962 | 4182 | VERGOTE | 10.25 | 13.5 | 0.75 | 18 | 9.289 | 7.79 | OK | 16 | 27.4

## Pile Specifications
WTG | Pile Type | Design Category | OD (m) | Wall Thickness (mm) | ID (m) | Total Length (m) | Wp (MN) | Wp (kN) | Wp (t) | Design Embedment (m) | Vibro Target Depth (m) | Water Depth (m)
WTG-01 | DP | 2 | 3.5 | 70 | 3.36 | 56.2 | 2.32 | 2320 | 236.5 | 52.3 | 22 | 26.52
WTG-02 | DP | 2 | 3.5 | 70 | 3.36 | 46.5 | 2.32 | 2320 | 236.5 | 45 | 17 | 15.9
WTG-03 | DP | 2 | 3.5 | 70 | 3.36 | 47.5 | 1.8 | 1800 | 183.5 | 46 | 18 | 29.45
WTG-04 | IP | 2 | 3.5 | 70 | 3.36 | 42 | 1.74 | 1740 | 177.4 | 40.5 | 19 | 23.12
WTG-05 | DP | 2 | 3.5 | 70 | 3.36 | 53.5 | 2.06 | 2060 | 210 | 52 | 17 | 22.5
WTG-06 | IP | 2 | 3.5 | 70 | 3.36 | 36.4 | 1.5 | 1500 | 152.9 | 34.9 | 18 | 23.31
WTG-07 | IP | 2 | 3.5 | 70 | 3.36 | 39.5 | 1.63 | 1630 | 166.2 | 37.9 | 18 | 24.26
WTG-08 | IP | 2 | 3.5 | 70 | 3.36 | 37.6 | 1.78 | 1780 | 181.4 | 36 | 30.8 | 18.91
WTG-09 | IP | 1 | 3.5 | 70 | 3.36 | 39.5 | 1.73 | 1730 | 176.4 | 38 | 19 | 17.87
WTG-10 | IP | 1 | 3.5 | 70 | 3.36 | 39.6 | 1.6 | 1600 | 163.1 | 38.1 | 27 | 29.68
WTG-11 | IP | 2 | 3.5 | 70 | 3.36 | 26.7 | 1.08 | 1080 | 110.1 | 25.2 | 15 | 29.46
WTG-12 | IP | 2 | 3.5 | 70 | 3.36 | 37.9 | 1.53 | 1530 | 156 | 36.4 | 16 | 29.43
WTG-13 | IP | 2 | 3.5 | 70 | 3.36 | 20.9 | 0.86 | 860 | 87.7 | 17.1 | 13 | 26.44
WTG-14 | IP | 3 | 3.5 | 70 | 3.36 | 21.7 | 0.89 | 890 | 90.7 | 20.2 | 14.2 | 23.67
WTG-15 | DP | 1 | 3.5 | 70 | 3.36 | 53.8 | 2.08 | 2080 | 212 | 52.3 | 27 | 21.18
WTG-16 | DP | 1 | 3.5 | 70 | 3.36 | 50 | 2.49 | 2490 | 253.8 | 48.5 | 24 | 16.98
WTG-17 | IP | 3 | 3.5 | 70 | 3.36 | 17.7 | 0.75 | 750 | 76.5 | 16.2 | 10.2 | 23.56
WTG-18 | IP | 2 | 3.5 | 70 | 3.36 | 25.3 | 1.02 | 1020 | 104 | 23.8 | 17.8 | 29.79
WTG-19 | IP | 2 | 3.5 | 70 | 3.36 | 42 | 1.69 | 1690 | 172.3 | 40.5 | 19 | 31.21
WTG-20 | IP | 2 | 3.5 | 70 | 3.36 | 42.2 | 1.71 | 1710 | 174.3 | 40.7 | 16 | 30.26
WTG-21 | IP | 2 | 3.5 | 70 | 3.36 | 49.2 | 2.01 | 2010 | 204.9 | 47.7 | 20 | 29.18
WTG-22 | DP | 1 | 3.5 | 70 | 3.36 | 51.9 | 1.98 | 1980 | 201.8 | 48.5 | 24 | 26.04
WTG-23 | IP | 1 | 3.5 | 70 | 3.36 | 40.2 | 1.67 | 1670 | 170.2 | 38.7 | 30 | 22
WTG-24 | DP | 1 | 3.5 | 70 | 3.36 | 44.4 | 2.38 | 2380 | 242.6 | 42.5 | 15 | 19.26
WTG-25 | IP | 1 | 3.5 | 70 | 3.36 | 35.1 | 1.54 | 1540 | 157 | 33.6 | 17 | 17.72
WTG-26 | IP | 3 | 3.5 | 70 | 3.36 | 14.7 | 0.58 | 580 | 59.1 | 13.2 | 5.3 | 31

## Hammer Specification
Hammer | Ram Weight (t) | Hammer Housing (t) | Total Weight Air (t) | Total Weight Sub (t) | Total Weight Air (kN) | Total Weight Sub (kN) | Max Energy (kJ)
MENCK MHU 1900S | 92 | 158 | 249 | 200 | 2442.7 | 1962 | 1900

## SRD WTG-01
Depth (m) | SRD AH-FF (kN) | SRD AH-NFF (kN) | SRD MEAN (kN) | SRD AH-FF-LB (kN) | SRD AH-FF-UB (kN) | SRD AH-NFF-LB (kN) | SRD AH-NFF-UB (kN) | Static Cap (kN) | Shaft AH-FF (kN) | Tip AH-FF (kN) | Shaft AH-NFF (kN) | Tip AH-NFF (kN) | Shaft SC (kN) | Tip SC (kN)
0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.75 | 43 | 43 | 43 | 34.4 | 53.8 | 34.4 | 53.8 | 24.3 | 2.6 | 40.4 | 2.7 | 40.4 | 2.5 | 21.8
2 | 44.5 | 44.6 | 44.5 | 35.6 | 55.6 | 35.6 | 55.7 | 27.2 | 5.6 | 38.9 | 5.7 | 38.9 | 5.4 | 21.8
2.25 | 46.8 | 46.9 | 46.8 | 37.4 | 58.5 | 37.5 | 58.6 | 30.4 | 8.4 | 38.4 | 8.5 | 38.4 | 8.2 | 22.2
2.5 | 49 | 49.3 | 49.2 | 39.2 | 61.3 | 39.4 | 61.6 | 33.7 | 11.4 | 37.6 | 11.7 | 37.6 | 11.4 | 22.3
2.75 | 54.6 | 55 | 54.8 | 43.6 | 68.2 | 44 | 68.7 | 38.6 | 14.3 | 40.2 | 14.7 | 40.2 | 14.5 | 24
3 | 75.2 | 75.8 | 75.5 | 60.2 | 94 | 60.6 | 94.7 | 51.3 | 18.5 | 56.7 | 19 | 56.7 | 18.7 | 32.6
3.25 | 169.7 | 170.5 | 170.1 | 135.8 | 212.2 | 136.4 | 213.2 | 169.9 | 35.3 | 134.4 | 36.1 | 134.4 | 35.5 | 134.4
3.5 | 131.9 | 133.2 | 132.5 | 105.5 | 164.8 | 106.5 | 166.5 | 102 | 60.9 | 71 | 62.2 | 71 | 61.5 | 40.5
3.75 | 199 | 201.1 | 200.1 | 159.2 | 248.8 | 160.9 | 251.4 | 151.1 | 92.2 | 106.8 | 94.2 | 106.8 | 93.4 | 57.7
4 | 489.7 | 492.9 | 491.3 | 391.8 | 612.2 | 394.3 | 616.2 | 489.7 | 140.4 | 349.4 | 143.5 | 349.4 | 140.3 | 349.4
4.25 | 421.2 | 426.5 | 423.8 | 336.9 | 526.5 | 341.2 | 533.1 | 423.3 | 209.1 | 212 | 214.5 | 212 | 211.2 | 212
4.5 | 475 | 483 | 479 | 380 | 593.8 | 386.4 | 603.8 | 479.8 | 261.4 | 213.6 | 269.4 | 213.6 | 266.2 | 213.6
4.75 | 512 | 523.3 | 517.7 | 409.6 | 640.1 | 418.6 | 654.1 | 520.1 | 313.1 | 198.9 | 324.4 | 198.9 | 321.1 | 198.9
5 | 574.7 | 589.7 | 582.2 | 459.8 | 718.4 | 471.7 | 737.1 | 586.2 | 367.9 | 206.8 | 382.8 | 206.8 | 379.4 | 206.8
5.25 | 630.4 | 649.7 | 640 | 504.3 | 788 | 519.7 | 812.1 | 646.2 | 426.1 | 204.3 | 445.3 | 204.3 | 441.9 | 204.3
5.5 | 697 | 721.1 | 709 | 557.6 | 871.2 | 576.9 | 901.3 | 717.6 | 482 | 215 | 506.1 | 215 | 502.7 | 215
5.75 | 801.6 | 831 | 816.3 | 641.2 | 1001.9 | 664.8 | 1038.7 | 827.2 | 533.2 | 268.4 | 562.6 | 268.4 | 558.8 | 268.4
6 | 848.7 | 884.1 | 866.4 | 679 | 1060.9 | 707.2 | 1105.1 | 880.3 | 606.1 | 242.6 | 641.5 | 242.6 | 637.7 | 242.6
6.25 | 913.3 | 955.2 | 934.3 | 730.6 | 1141.6 | 764.2 | 1194 | 951.4 | 669.3 | 243.9 | 711.3 | 243.9 | 707.5 | 243.9
6.5 | 1020.9 | 1070.1 | 1045.5 | 816.7 | 1276.1 | 856.1 | 1337.7 | 1064.3 | 757.9 | 262.9 | 807.2 | 262.9 | 801.4 | 262.9
6.75 | 1082.2 | 1139.6 | 1110.9 | 865.7 | 1352.7 | 911.7 | 1424.5 | 1133.8 | 826 | 256.2 | 883.5 | 256.2 | 877.7 | 256.2
7 | 1181.4 | 1247.6 | 1214.5 | 945.1 | 1476.7 | 998.1 | 1559.6 | 1241.9 | 901.7 | 279.7 | 968 | 279.7 | 962.2 | 279.7
7.25 | 1260 | 1335.7 | 1297.9 | 1008 | 1575 | 1068.6 | 1669.7 | 1329.9 | 968.1 | 291.9 | 1043.8 | 291.9 | 1038 | 291.9
7.5 | 1321.7 | 1407.5 | 1364.6 | 1057.4 | 1652.1 | 1126 | 1759.4 | 1401.7 | 1042.9 | 278.8 | 1128.7 | 278.8 | 1122.9 | 278.8
7.75 | 1381.2 | 1477.7 | 1429.4 | 1104.9 | 1726.5 | 1182.2 | 1847.1 | 1471.9 | 1117.5 | 263.6 | 1214.1 | 263.6 | 1208.3 | 263.6
8 | 1454.6 | 1562.5 | 1508.5 | 1163.7 | 1818.2 | 1250 | 1953.1 | 1556.5 | 1204.8 | 249.8 | 1312.7 | 249.8 | 1306.7 | 249.8
8.25 | 1604.1 | 1724.2 | 1664.2 | 1283.3 | 2005.2 | 1379.3 | 2155.2 | 1718.2 | 1276.7 | 327.4 | 1396.7 | 327.4 | 1390.8 | 327.4
8.5 | 1719.3 | 1852.1 | 1785.7 | 1375.4 | 2149.1 | 1481.7 | 2315.1 | 1846.1 | 1353.6 | 365.7 | 1486.4 | 365.7 | 1480.4 | 365.7
8.75 | 1686.8 | 1832.9 | 1759.9 | 1349.4 | 2108.5 | 1466.3 | 2291.2 | 1826.9 | 1424.5 | 262.3 | 1570.7 | 262.3 | 1564.7 | 262.3
9 | 1746.7 | 1906.7 | 1826.7 | 1397.4 | 2183.4 | 1525.3 | 2383.3 | 1900.7 | 1492.8 | 253.9 | 1652.8 | 253.9 | 1646.8 | 253.9
9.25 | 1853.5 | 2027.7 | 1940.6 | 1482.8 | 2316.8 | 1622.2 | 2534.6 | 2021.7 | 1551.1 | 302.3 | 1725.4 | 302.3 | 1719.4 | 302.3
9.5 | 1890.6 | 2079.6 | 1985.1 | 1512.4 | 2363.2 | 1663.7 | 2599.5 | 2073.6 | 1630.3 | 260.2 | 1819.4 | 260.2 | 1813.4 | 260.2
9.75 | 2001.2 | 2205.6 | 2103.4 | 1601 | 2501.5 | 1764.5 | 2757 | 2199.6 | 1701.6 | 299.6 | 1906 | 299.6 | 1900 | 299.6
10 | 2093.6 | 2313.9 | 2203.7 | 1674.8 | 2616.9 | 1851.1 | 2892.4 | 2307.9 | 1791.7 | 301.9 | 2012 | 301.9 | 2006 | 301.9
10.25 | 2145.2 | 2382.1 | 2263.6 | 1716.2 | 2681.5 | 1905.7 | 2977.6 | 2376.1 | 1859.8 | 285.4 | 2096.7 | 285.4 | 2090.7 | 285.4
10.5 | 2218.1 | 2472 | 2345.1 | 1774.5 | 2772.7 | 1977.6 | 3090 | 2466 | 1931.2 | 286.9 | 2185.1 | 286.9 | 2179.1 | 286.9
10.75 | 2303 | 2574.4 | 2438.7 | 1842.4 | 2878.7 | 2059.5 | 3218 | 2568.4 | 2006.8 | 296.2 | 2278.2 | 296.2 | 2272.2 | 296.2
11 | 2385.7 | 2675.2 | 2530.5 | 1908.6 | 2982.1 | 2140.2 | 3344.1 | 2669.3 | 2094.3 | 291.5 | 2383.8 | 291.5 | 2377.8 | 291.5
11.25 | 2466.7 | 2774.9 | 2620.8 | 1973.3 | 3083.3 | 2219.9 | 3468.6 | 2768.9 | 2164.6 | 302.1 | 2472.8 | 302.1 | 2466.8 | 302.1
11.5 | 2894.7 | 3222.1 | 3058.4 | 2315.8 | 3618.4 | 2577.7 | 4027.7 | 3204.4 | 2229.4 | 665.3 | 2556.8 | 665.3 | 2539.1 | 665.3
11.75 | 3053.9 | 3402.4 | 3228.2 | 2443.1 | 3817.4 | 2721.9 | 4253 | 3384.7 | 2471.9 | 582 | 2820.4 | 582 | 2802.7 | 582
12 | 3390.5 | 3762.9 | 3576.7 | 2712.4 | 4238.1 | 3010.3 | 4703.6 | 3743.6 | 2713.9 | 676.6 | 3086.3 | 676.6 | 3067 | 676.6
12.25 | 3957.9 | 4357.2 | 4157.6 | 3166.4 | 4947.4 | 3485.7 | 5446.5 | 4337.9 | 2943.5 | 1014.5 | 3342.7 | 1014.5 | 3323.5 | 1014.5
12.5 | 3853 | 4281.3 | 4067.2 | 3082.4 | 4816.2 | 3425.1 | 5351.7 | 4261 | 3122.1 | 730.9 | 3550.4 | 730.9 | 3530.1 | 730.9
12.75 | 3596.9 | 4056.5 | 3826.7 | 2877.5 | 4496.1 | 3245.2 | 5070.6 | 3923.2 | 3326.6 | 270.3 | 3786.2 | 270.3 | 3765.9 | 157.3
13 | 4415.4 | 4907.8 | 4661.6 | 3532.4 | 5519.3 | 3926.2 | 6134.7 | 4882.7 | 3474.5 | 940.9 | 3966.9 | 940.9 | 3941.8 | 940.9
13.25 | 4358.3 | 4885.7 | 4622 | 3486.6 | 5447.9 | 3908.5 | 6107.1 | 4860.6 | 3664.3 | 694 | 4191.7 | 694 | 4166.5 | 694
13.5 | 4541.3 | 5105.7 | 4823.5 | 3633 | 5676.6 | 4084.6 | 6382.2 | 5080.6 | 3874.2 | 667.1 | 4438.6 | 667.1 | 4413.5 | 667.1
13.75 | 4564.8 | 5168 | 4866.4 | 3651.8 | 5706 | 4134.4 | 6460 | 4875.1 | 4004.1 | 560.7 | 4607.4 | 560.7 | 4582.3 | 292.9
14 | 4741.1 | 5384.6 | 5062.9 | 3792.9 | 5926.4 | 4307.7 | 6730.8 | 5355.1 | 4179.5 | 561.6 | 4823 | 561.6 | 4793.4 | 561.6
14.25 | 4866.1 | 5551.2 | 5208.7 | 3892.9 | 6082.7 | 4441 | 6939 | 5519.7 | 4266.5 | 599.7 | 4951.5 | 599.7 | 4920.1 | 599.7
14.5 | 4887.1 | 5614.9 | 5251 | 3909.7 | 6108.9 | 4491.9 | 7018.6 | 5357.4 | 4402.5 | 484.6 | 5130.3 | 484.6 | 5095.5 | 261.8
14.75 | 4778.5 | 5550.2 | 5164.4 | 3822.8 | 5973.1 | 4440.2 | 6937.8 | 5424.8 | 4546.3 | 232.2 | 5318.1 | 232.2 | 5282.6 | 142.2
15 | 5252 | 6068.5 | 5660.3 | 4201.6 | 6565 | 4854.8 | 7585.6 | 6032.2 | 4652.3 | 599.7 | 5468.8 | 599.7 | 5432.5 | 599.7
15.25 | 5282.1 | 6144.3 | 5713.2 | 4225.7 | 6602.6 | 4915.4 | 7680.3 | 6107.3 | 4748.5 | 533.6 | 5610.7 | 533.6 | 5573.7 | 533.6
15.5 | 5381.7 | 6290.2 | 5836 | 4305.4 | 6727.1 | 5032.2 | 7862.8 | 6251.3 | 4853.6 | 528.2 | 5762.1 | 528.2 | 5723.2 | 528.2
15.75 | 5603.6 | 6559.4 | 6081.5 | 4482.9 | 7004.5 | 5247.5 | 8199.2 | 6518.6 | 4944.2 | 659.4 | 5900 | 659.4 | 5859.2 | 659.4
16 | 6013.5 | 7017.6 | 6515.5 | 4810.8 | 7516.8 | 5614 | 8771.9 | 6976.7 | 5123.7 | 889.8 | 6127.8 | 889.8 | 6087 | 889.8
16.25 | 6069.5 | 7123.7 | 6596.6 | 4855.6 | 7586.9 | 5699 | 8904.7 | 7082.9 | 5312.1 | 757.4 | 6366.4 | 757.4 | 6325.5 | 757.4
16.5 | 6358.7 | 7465.1 | 6911.9 | 5087 | 7948.4 | 5972.1 | 9331.4 | 7419.4 | 5484.4 | 874.4 | 6590.7 | 874.4 | 6545 | 874.4
16.75 | 6055.9 | 7216.3 | 6636.1 | 4844.7 | 7569.9 | 5773 | 9020.4 | 7011.4 | 5678.8 | 377.1 | 6839.2 | 377.1 | 6793.5 | 217.9
17 | 6476.1 | 7691.6 | 7083.9 | 5180.9 | 8095.2 | 6153.3 | 9614.5 | 7644.1 | 5809.5 | 666.6 | 7024.9 | 666.6 | 6977.5 | 666.6
17.25 | 6661.3 | 7933.2 | 7297.3 | 5329.1 | 8326.7 | 6346.6 | 9916.5 | 7885.7 | 5953.5 | 707.8 | 7225.4 | 707.8 | 7177.9 | 707.8
17.5 | 7089.6 | 8419.2 | 7754.4 | 5671.7 | 8862 | 6735.4 | 10524 | 8359.8 | 6095.3 | 994.3 | 7424.9 | 994.3 | 7365.4 | 994.3
17.75 | 7218.2 | 8607.3 | 7912.7 | 5774.5 | 9022.7 | 6885.9 | 10759.2 | 8546.9 | 6291.5 | 926.7 | 7680.7 | 926.7 | 7620.2 | 926.7
18 | 7039.3 | 8489.4 | 7764.3 | 5631.4 | 8799.1 | 6791.5 | 10611.8 | 8429 | 6448.2 | 591.1 | 7898.3 | 591.1 | 7837.9 | 591.1
18.25 | 6714 | 8225.7 | 7469.8 | 5371.2 | 8392.5 | 6580.5 | 10282.1 | 8084.5 | 6491.1 | 222.9 | 8002.8 | 222.9 | 7941.8 | 142.7
18.5 | 7037.9 | 8610.8 | 7824.3 | 5630.3 | 8797.3 | 6888.6 | 10763.5 | 8546.1 | 6468.5 | 569.3 | 8041.5 | 569.3 | 7976.7 | 569.3
18.75 | 6680.5 | 8314.3 | 7497.4 | 5344.4 | 8350.7 | 6651.4 | 10392.9 | 8156.8 | 6437.5 | 243.1 | 8071.2 | 243.1 | 8002.7 | 154.1
19 | 7051.8 | 8746.1 | 7899 | 5641.4 | 8814.8 | 6996.9 | 10932.6 | 8674.8 | 6489.3 | 562.6 | 8183.6 | 562.6 | 8112.3 | 562.6
19.25 | 6700.4 | 8455.3 | 7577.9 | 5360.3 | 8375.5 | 6764.3 | 10569.2 | 8296.9 | 6467.7 | 232.7 | 8222.6 | 232.7 | 8147.7 | 149.3
19.5 | 6708.4 | 8523.4 | 7615.9 | 5366.7 | 8385.5 | 6818.7 | 10654.3 | 8347 | 6446.5 | 261.8 | 8261.6 | 261.8 | 8182 | 165.1
19.75 | 6682.3 | 8557.2 | 7619.7 | 5345.8 | 8352.9 | 6845.7 | 10696.5 | 8397.9 | 6461 | 221.3 | 8335.9 | 221.3 | 8254.1 | 143.8
20 | 7110.2 | 9044.6 | 8077.4 | 5688.2 | 8887.8 | 7235.7 | 11305.8 | 8958.9 | 6447.2 | 663 | 8381.6 | 663 | 8295.9 | 663
20.25 | 6711.4 | 8705.4 | 7708.4 | 5369.1 | 8389.3 | 6964.3 | 10881.7 | 8533.6 | 6474.2 | 237.2 | 8468.1 | 237.2 | 8380.6 | 153
20.5 | 6725.3 | 8778.4 | 7751.8 | 5380.2 | 8406.6 | 7022.7 | 10973 | 8586.2 | 6452.4 | 272.8 | 8505.5 | 272.8 | 8413.9 | 172.3
20.75 | 6696.8 | 8808.8 | 7752.8 | 5357.5 | 8371.1 | 7047.1 | 11011 | 8639.2 | 6478.4 | 218.4 | 8590.4 | 218.4 | 8495.7 | 143.5
21 | 6663.7 | 8834.3 | 7749 | 5330.9 | 8329.6 | 7067.5 | 11042.9 | 8662.5 | 6446 | 217.7 | 8616.7 | 217.7 | 8519.2 | 143.4
21.25 | 6631.5 | 8860.3 | 7745.9 | 5305.2 | 8289.4 | 7088.2 | 11075.4 | 8685.6 | 6413.4 | 218.1 | 8642.2 | 218.1 | 8541.8 | 143.9
21.5 | 6627.4 | 8913.9 | 7770.6 | 5301.9 | 8284.2 | 7131.1 | 11142.3 | 8724.7 | 6385.3 | 242.1 | 8671.8 | 242.1 | 8567.4 | 157.3
21.75 | 6620.1 | 8963.8 | 7791.9 | 5296.1 | 8275.1 | 7171.1 | 11204.8 | 8761.1 | 6358.1 | 262 | 8701.8 | 262 | 8592.8 | 168.3
22 | 6514.6 | 8915.2 | 7714.9 | 5211.6 | 8143.2 | 7132.2 | 11144 | 8394.5 | 6356.5 | 158 | 8757.2 | 158 | 4630.7 | 3763.8
22.25 | 6679.2 | 9136.7 | 7908 | 5343.4 | 8349 | 7309.4 | 11420.9 | 8925.8 | 6408.8 | 270.4 | 8866.4 | 270.4 | 8752.3 | 173.5
22.5 | 6639.3 | 9153.6 | 7896.4 | 5311.5 | 8299.2 | 7322.9 | 11442 | 8945.4 | 6385.1 | 254.2 | 8899.4 | 254.2 | 8780.3 | 165.1
22.75 | 6624.1 | 9194.7 | 7909.4 | 5299.3 | 8280.2 | 7355.7 | 11493.3 | 8977.4 | 6360.8 | 263.3 | 8931.3 | 263.3 | 8807.1 | 170.3
23 | 7181.1 | 9807.5 | 8494.3 | 5744.9 | 8976.4 | 7846 | 12259.4 | 9678.2 | 6367.4 | 813.7 | 8993.8 | 813.7 | 8864.5 | 813.7
23.25 | 7239.6 | 9922.6 | 8581.1 | 5791.7 | 9049.5 | 7938.1 | 12403.2 | 9793 | 6510.5 | 729.1 | 9193.5 | 729.1 | 9063.9 | 729.1
23.5 | 6820.1 | 9560.1 | 8190.1 | 5456.1 | 8525.1 | 7648.1 | 11950.1 | 9332.1 | 6548 | 272.1 | 9287.9 | 272.1 | 9156.1 | 176.1
23.75 | 7417.4 | 10214.3 | 8815.8 | 5933.9 | 9271.7 | 8171.4 | 12767.9 | 10079.8 | 6620.4 | 797 | 9417.3 | 797 | 9282.8 | 797
24 | 7427.2 | 10281.8 | 8854.5 | 5941.7 | 9284 | 8225.4 | 12852.2 | 10146 | 6725.7 | 701.5 | 9580.3 | 701.5 | 9444.5 | 701.5
24.25 | 7070.1 | 9982.8 | 8526.4 | 5656.1 | 8837.6 | 7986.2 | 12478.5 | 9754.3 | 6804.7 | 265.4 | 9717.4 | 265.4 | 9581 | 173.3
24.5 | 7070.4 | 10041.2 | 8555.8 | 5656.4 | 8838.1 | 8032.9 | 12551.5 | 9797 | 6782.4 | 288 | 9753.2 | 288 | 9611.1 | 185.9
24.75 | 8057.2 | 11085.7 | 9571.4 | 6445.7 | 10071.5 | 8868.5 | 13857.1 | 10935 | 6787.7 | 1269.5 | 9816.2 | 1269.5 | 9665.6 | 1269.5
25 | 7342.7 | 10429.8 | 8886.3 | 5874.2 | 9178.4 | 8343.9 | 13037.3 | 10124.4 | 6948.7 | 394.1 | 10035.8 | 394.1 | 9882.1 | 242.2
25.25 | 7319.4 | 10465.5 | 8892.4 | 5855.5 | 9149.2 | 8372.4 | 13081.8 | 10160.6 | 6946.4 | 373 | 10092.4 | 373 | 9928.8 | 231.8
25.5 | 7198.1 | 10402.9 | 8800.5 | 5758.5 | 8997.7 | 8322.3 | 13003.6 | 10139.4 | 6929.9 | 268.2 | 10134.7 | 268.2 | 9963 | 176.4
25.75 | 7235.2 | 10498.3 | 8866.7 | 5788.2 | 9044 | 8398.6 | 13122.9 | 10201.5 | 6904.9 | 330.3 | 10168 | 330.3 | 9991.4 | 210.2
26 | 7629.4 | 10950.5 | 9289.9 | 6103.5 | 9536.7 | 8760.4 | 13688.1 | 10765.9 | 6905.7 | 723.7 | 10226.8 | 723.7 | 10042.2 | 723.7
26.25 | 7710.7 | 11089.5 | 9400.1 | 6168.5 | 9638.4 | 8871.6 | 13861.9 | 10900.6 | 6915.5 | 795.2 | 10294.4 | 795.2 | 10105.4 | 795.2
26.5 | 7286 | 10722.9 | 9004.5 | 5828.8 | 9107.5 | 8578.3 | 13403.7 | 10437 | 7006.4 | 279.6 | 10443.3 | 279.6 | 10253.2 | 183.9
26.75 | 7385.9 | 10881 | 9133.4 | 5908.7 | 9232.4 | 8704.8 | 13601.2 | 10551.5 | 7020.1 | 365.8 | 10515.2 | 365.8 | 10321.1 | 230.4
27 | 7496.1 | 11049.1 | 9272.6 | 5996.9 | 9370.1 | 8839.3 | 13811.4 | 10651.2 | 7011.7 | 484.4 | 10564.7 | 484.4 | 10359.6 | 291.6
27.25 | 7949.9 | 11561 | 9755.4 | 6359.9 | 9937.3 | 9248.8 | 14451.2 | 11351.2 | 7152.7 | 797.2 | 10763.8 | 797.2 | 10554 | 797.2
27.5 | 8004 | 11674.2 | 9839.1 | 6403.2 | 10005 | 9339.3 | 14592.7 | 11461.7 | 7246.8 | 757.2 | 10917 | 757.2 | 10704.6 | 757.2
27.75 | 7569.9 | 11299.5 | 9434.7 | 6056 | 9462.4 | 9039.6 | 14124.4 | 10995.5 | 7300.1 | 269.8 | 11029.7 | 269.8 | 10815.6 | 179.9
28 | 8497.4 | 12286.2 | 10391.8 | 6797.9 | 10621.7 | 9829 | 15357.8 | 12065.2 | 7333.8 | 1163.6 | 11122.6 | 1163.6 | 10901.6 | 1163.6
28.25 | 8089.9 | 11938.6 | 10014.3 | 6471.9 | 10112.4 | 9550.9 | 14923.3 | 11440.9 | 7441.5 | 648.4 | 11290.3 | 648.4 | 11066.2 | 374.7
28.5 | 9464.3 | 13373.8 | 11419.1 | 7571.4 | 11830.4 | 10699.1 | 16717.3 | 13139 | 7681.1 | 1783.2 | 11590.7 | 1783.2 | 11355.8 | 1783.2
28.75 | 9549.4 | 13524.1 | 11536.7 | 7639.5 | 11936.7 | 10819.2 | 16905.1 | 13289.2 | 8132.6 | 1416.8 | 12107.3 | 1416.8 | 11872.4 | 1416.8
29 | 10121.3 | 14166.2 | 12143.8 | 8097 | 12651.6 | 11333 | 17707.8 | 13055.1 | 8444.7 | 1676.6 | 12489.6 | 1676.6 | 12224.3 | 830.8
29.25 | 9107.5 | 13224.9 | 11166.2 | 7286 | 11384.4 | 10579.9 | 16531.1 | 12677.1 | 8536.8 | 570.7 | 12654.2 | 570.7 | 12338.2 | 339
29.5 | 9686.7 | 13877.1 | 11781.9 | 7749.4 | 12108.4 | 11101.6 | 17346.3 | 13553.6 | 8640.4 | 1046.4 | 12830.7 | 1046.4 | 12507.3 | 1046.4
29.75 | 9831.9 | 14095.9 | 11963.9 | 7865.5 | 12289.9 | 11276.7 | 17619.9 | 13768.4 | 8731.7 | 1100.2 | 12995.7 | 1100.2 | 12668.2 | 1100.2
30 | 9847.1 | 14185.7 | 12016.4 | 7877.7 | 12308.8 | 11348.6 | 17732.2 | 13858.3 | 8942.4 | 904.7 | 13281 | 904.7 | 12953.5 | 904.7
30.25 | 9926 | 14340.2 | 12133.1 | 7940.8 | 12407.5 | 11472.2 | 17925.3 | 14012.8 | 9067 | 859 | 13481.2 | 859 | 13153.8 | 859
30.5 | 10004.4 | 14494.8 | 12249.6 | 8003.5 | 12505.5 | 11595.8 | 18118.5 | 14167.3 | 9203.3 | 801.1 | 13693.7 | 801.1 | 13366.3 | 801.1
30.75 | 10081.5 | 14648.5 | 12365 | 8065.2 | 12601.9 | 11718.8 | 18310.7 | 14321.1 | 9292.4 | 789.1 | 13859.5 | 789.1 | 13532 | 789.1
31 | 10175.1 | 14819.1 | 12497.1 | 8140.1 | 12718.9 | 11855.3 | 18523.9 | 14491.6 | 9398 | 777.1 | 14042 | 777.1 | 13714.5 | 777.1
31.25 | 10253.6 | 14974.6 | 12614.1 | 8202.9 | 12817 | 11979.7 | 18718.2 | 14645.7 | 9454.1 | 799.5 | 14175.1 | 799.5 | 13846.3 | 799.5
31.5 | 9753.9 | 14552.1 | 12153 | 7803.2 | 12192.4 | 11641.7 | 18190.1 | 13944.5 | 9482.6 | 271.4 | 14280.7 | 271.4 | 7660 | 6284.5
31.75 | 10647.7 | 15522.7 | 13085.2 | 8518.2 | 13309.6 | 12418.2 | 19403.4 | 15161.2 | 9493.2 | 1154.5 | 14368.2 | 1154.5 | 14006.7 | 1154.5
32 | 14499 | 19451.5 | 16975.2 | 11599.2 | 18123.8 | 15561.2 | 24314.4 | 16177.9 | 9610.2 | 4888.8 | 14562.7 | 4888.8 | 14116 | 2061.9
32.25 | 11708.1 | 16743.2 | 14225.6 | 9366.5 | 14635.1 | 13394.6 | 20929 | 15183.1 | 9847.8 | 1860.3 | 14882.9 | 1860.3 | 14260 | 923.1
32.5 | 14517.3 | 19642.1 | 17079.7 | 11613.8 | 18146.6 | 15713.7 | 24552.7 | 16651.5 | 10456.2 | 4061.1 | 15581 | 4061.1 | 14879.6 | 1772
32.75 | 15053.2 | 20275.7 | 17664.5 | 12042.6 | 18816.6 | 16220.6 | 25344.6 | 16910.9 | 10729.2 | 4324 | 15951.7 | 4324 | 15040.9 | 1869.9
33 | 17569.4 | 22896.4 | 20232.9 | 14055.5 | 21961.8 | 18317.1 | 28620.4 | 17859.3 | 11062.4 | 6507 | 16389.3 | 6507 | 15226.5 | 2632.8
33.25 | 28891.8 | 34336.5 | 31614.1 | 23113.5 | 36114.8 | 27469.2 | 42920.6 | 21416.4 | 11720.8 | 17171 | 17165.5 | 17171 | 15497 | 5919.5
33.5 | 38750.5 | 44352.2 | 41551.4 | 31000.4 | 48438.1 | 35481.8 | 55440.3 | 24203.4 | 13093.4 | 25657.1 | 18695.2 | 25657.1 | 15917.9 | 8285.5
33.75 | 49421.8 | 55249.1 | 52335.5 | 39537.5 | 61777.3 | 44199.3 | 69061.4 | 26985.2 | 14725.6 | 34696.2 | 20552.9 | 34696.2 | 16313.8 | 10671.4
34 | 46949.4 | 53035.8 | 49992.6 | 37559.5 | 58686.7 | 42428.6 | 66294.7 | 26426.5 | 14466.5 | 32482.9 | 20552.9 | 32482.9 | 16313.8 | 10112.7
34.25 | 44516.5 | 50852.6 | 47684.6 | 35613.2 | 55645.7 | 40682.1 | 63565.8 | 25867.9 | 14216.8 | 30299.7 | 20552.9 | 30299.7 | 16313.8 | 9554.1
34.5 | 42123.8 | 48700.5 | 45412.2 | 33699 | 52654.7 | 38960.4 | 60875.7 | 25309.2 | 13976.2 | 28147.6 | 20552.9 | 28147.6 | 16313.8 | 8995.4
34.75 | 39771.8 | 46580.6 | 43176.2 | 31817.4 | 49714.8 | 37264.5 | 58225.7 | 24750.5 | 13744.2 | 26027.6 | 20552.9 | 26027.6 | 16313.8 | 8436.8
35 | 37461.4 | 44493.9 | 40977.6 | 29969.1 | 46826.7 | 35595.1 | 55617.4 | 24191.9 | 13520.4 | 23941 | 20552.9 | 23941 | 16313.8 | 7878.1
35.25 | 35193.4 | 42441.9 | 38817.7 | 28154.8 | 43991.8 | 33953.5 | 53052.4 | 23633.2 | 13304.4 | 21889 | 20552.9 | 21889 | 16313.8 | 7319.4
35.5 | 32969.3 | 40426.2 | 36697.7 | 26375.4 | 41211.6 | 32340.9 | 50532.7 | 23074.6 | 13096 | 19873.2 | 20552.9 | 19873.2 | 16313.8 | 6760.8
35.75 | 30790.3 | 38448.5 | 34619.4 | 24632.2 | 38487.9 | 30758.8 | 48060.6 | 22515.9 | 12894.7 | 17895.5 | 20552.9 | 17895.5 | 16313.8 | 6202.1
36 | 28658.4 | 36511 | 32584.7 | 22926.7 | 35822.9 | 29208.8 | 45638.7 | 21957.3 | 12700.3 | 15958 | 20552.9 | 15958 | 16313.8 | 5643.5
36.25 | 26575.7 | 34616.2 | 30595.9 | 21260.5 | 33219.6 | 27692.9 | 43270.2 | 21398.6 | 12512.5 | 14063.2 | 20552.9 | 14063.2 | 16313.8 | 5084.8
36.5 | 24545 | 32767.1 | 28656.1 | 19636 | 30681.3 | 26213.7 | 40958.9 | 20839.9 | 12330.8 | 12214.2 | 20552.9 | 12214.2 | 16313.8 | 4526.2
36.75 | 22569.9 | 30967.7 | 26768.8 | 18056 | 28212.4 | 24774.1 | 38709.6 | 20281.3 | 12155.2 | 10414.8 | 20552.9 | 10414.8 | 16313.8 | 3967.5
37 | 20654.9 | 29222.5 | 24938.7 | 16523.9 | 25818.6 | 23378 | 36528.2 | 19722.6 | 11985.3 | 8669.6 | 20552.9 | 8669.6 | 16313.8 | 3408.9
37.25 | 18805.8 | 27537.9 | 23171.8 | 15044.6 | 23507.2 | 22030.3 | 34422.4 | 19164 | 11820.8 | 6985 | 20552.9 | 6985 | 16313.8 | 2850.2
37.5 | 17030.9 | 25922.2 | 21476.5 | 13624.7 | 21288.6 | 20737.8 | 32402.8 | 18605.3 | 11661.6 | 5369.3 | 20552.9 | 5369.3 | 16313.8 | 2291.5
37.75 | 15342.1 | 24387.7 | 19864.9 | 12273.7 | 19177.6 | 19510.2 | 30484.6 | 18046.7 | 11507.3 | 3834.8 | 20552.9 | 3834.8 | 16313.8 | 1732.9
38 | 13758.8 | 22953.8 | 18356.3 | 11007 | 17198.5 | 18363.1 | 28692.3 | 17488 | 11357.9 | 2400.9 | 20552.9 | 2400.9 | 16313.8 | 1174.2
38.25 | 12317.8 | 21657.7 | 16987.7 | 9854.2 | 15397.3 | 17326.1 | 27072.1 | 16929.3 | 11213.1 | 1104.8 | 20552.9 | 1104.8 | 16313.8 | 615.6
38.5 | 20609.1 | 41213.1 | 30911.1 | 16487.3 | 25761.4 | 32970.5 | 51516.4 | 15749.8 | 20545.8 | 63.4 | 41149.8 | 63.4 | 13814.1 | 1935.8
38.75 | 21829.4 | 42875.4 | 32352.4 | 17463.5 | 27286.7 | 34300.3 | 53594.2 | 22093.6 | 20309.8 | 1519.5 | 41355.8 | 1519.5 | 20574 | 1519.5
39 | 22071.8 | 43542.1 | 32806.9 | 17657.4 | 27589.7 | 34833.6 | 54427.6 | 22760.3 | 20531.6 | 1540.1 | 42001.9 | 1540.1 | 21220.1 | 1540.1
39.25 | 22127.3 | 44008 | 33067.6 | 17701.8 | 27659.1 | 35206.4 | 55010 | 23226.2 | 20749.4 | 1377.9 | 42630.2 | 1377.9 | 21848.4 | 1377.9
39.5 | 22416.3 | 44691.5 | 33553.9 | 17933.1 | 28020.4 | 35753.2 | 55864.3 | 23897.3 | 20602 | 1814.4 | 42877.1 | 1814.4 | 22082.9 | 1814.4
39.75 | 21851.4 | 44505.8 | 33178.6 | 17481.1 | 27314.2 | 35604.6 | 55632.2 | 23711.6 | 20701.1 | 1150.2 | 43355.5 | 1150.2 | 22561.3 | 1150.2
40 | 22374.6 | 45393.9 | 33884.3 | 17899.7 | 27968.3 | 36315.2 | 56742.4 | 24599.7 | 20743.6 | 1631.1 | 43762.9 | 1631.1 | 22968.7 | 1631.1
40.25 | 22517 | 45889.9 | 34203.4 | 18013.6 | 28146.2 | 36711.9 | 57362.4 | 25095.7 | 21137.7 | 1379.2 | 44510.7 | 1379.2 | 23716.5 | 1379.2
40.5 | 22709.3 | 46427.7 | 34568.5 | 18167.5 | 28386.6 | 37142.2 | 58034.6 | 25633.5 | 21473.3 | 1236 | 45191.7 | 1236 | 24397.5 | 1236
40.75 | 22747.9 | 46800.6 | 34774.3 | 18198.3 | 28434.9 | 37440.5 | 58500.8 | 26006.4 | 21528 | 1219.9 | 45580.7 | 1219.9 | 24786.5 | 1219.9
41 | 22788.8 | 47165.2 | 34977 | 18231.1 | 28486 | 37732.1 | 58956.5 | 26371 | 21693.1 | 1095.7 | 46069.5 | 1095.7 | 25275.3 | 1095.7
41.25 | 22793.9 | 47483.7 | 35138.8 | 18235.1 | 28492.3 | 37987 | 59354.6 | 26689.5 | 21743.2 | 1050.7 | 46433.1 | 1050.7 | 25638.9 | 1050.7
41.5 | 22871.5 | 47864.5 | 35368 | 18297.2 | 28589.4 | 38291.6 | 59830.6 | 27070.3 | 21780.8 | 1090.7 | 46773.8 | 1090.7 | 25979.6 | 1090.7
41.75 | 22900 | 48186.3 | 35543.2 | 18320 | 28625.1 | 38549.1 | 60232.9 | 27392.1 | 21798.5 | 1101.6 | 47084.8 | 1101.6 | 26290.6 | 1101.6
42 | 22926.6 | 48496.8 | 35711.7 | 18341.3 | 28658.3 | 38797.4 | 60621 | 27702.3 | 21826.4 | 1100.2 | 47396.6 | 1100.2 | 26602.1 | 1100.2
42.25 | 22981.9 | 48827.2 | 35904.6 | 18385.5 | 28727.4 | 39061.8 | 61034 | 28032.7 | 21835.7 | 1146.2 | 47681.1 | 1146.2 | 26886.6 | 1146.2
42.5 | 23049.4 | 49161.4 | 36105.4 | 18439.5 | 28811.7 | 39329.1 | 61451.7 | 28366.9 | 21891.7 | 1157.7 | 48003.7 | 1157.7 | 27209.2 | 1157.7
42.75 | 23272.1 | 49643.3 | 36457.7 | 18617.7 | 29090.1 | 39714.7 | 62054.1 | 28848.8 | 21968.5 | 1303.7 | 48339.7 | 1303.7 | 27545.2 | 1303.7
43 | 23529.5 | 50153.4 | 36841.5 | 18823.6 | 29411.9 | 40122.7 | 62691.8 | 29358.5 | 22113.4 | 1416.1 | 48737.3 | 1416.1 | 27942.3 | 1416.1
43.25 | 23522.9 | 50393.9 | 36958.4 | 18818.3 | 29403.7 | 40315.2 | 62992.4 | 29599 | 22315 | 1207.9 | 49186 | 1207.9 | 28391 | 1207.9
43.5 | 23695.3 | 50807.8 | 37251.5 | 18956.2 | 29619.1 | 40646.3 | 63509.8 | 30012.9 | 22457.9 | 1237.3 | 49570.5 | 1237.3 | 28775.5 | 1237.3
43.75 | 23579.1 | 50927.6 | 37253.3 | 18863.3 | 29473.9 | 40742.1 | 63659.5 | 30132.6 | 22492.7 | 1086.4 | 49841.2 | 1086.4 | 29046.2 | 1086.4
44 | 22710.4 | 50288.3 | 36499.4 | 18168.4 | 28388.1 | 40230.6 | 62860.4 | 26623 | 22357 | 353.4 | 49934.9 | 353.4 | 18329.6 | 8293.4
44.25 | 22902.5 | 50703.8 | 36803.2 | 18322 | 28628.2 | 40563 | 63379.7 | 28929.8 | 22437 | 465.6 | 50238.2 | 465.6 | 18485.1 | 10444.7
44.5 | 23596.2 | 51615.1 | 37605.6 | 18876.9 | 29495.2 | 41292.1 | 64518.9 | 30803.3 | 22387.3 | 1208.8 | 50406.3 | 1208.8 | 29594.4 | 1208.8
44.75 | 23585 | 51816.6 | 37700.8 | 18868 | 29481.2 | 41453.3 | 64770.8 | 31004.8 | 22457.4 | 1127.6 | 50689 | 1127.6 | 29877.2 | 1127.6
45 | 22969.3 | 51409 | 37189.1 | 18375.4 | 28711.6 | 41127.2 | 64261.3 | 30222.1 | 22454.8 | 514.5 | 50894.6 | 514.5 | 18838.4 | 11383.7
45.25 | 23209.9 | 51854.2 | 37532 | 18567.9 | 29012.3 | 41483.4 | 64817.8 | 30834.4 | 22652.7 | 557.2 | 51297 | 557.2 | 30476.3 | 358
45.5 | 24428.2 | 53273.2 | 38850.7 | 19542.6 | 30535.3 | 42618.6 | 66591.6 | 32440.8 | 22711.2 | 1717.1 | 51556.2 | 1717.1 | 30723.7 | 1717.1
45.75 | 23446.2 | 52489.3 | 37967.8 | 18757 | 29307.8 | 41991.5 | 65611.7 | 31456 | 22883.9 | 562.3 | 51927.1 | 562.3 | 31094.6 | 361.4
46 | 24395 | 53632.6 | 39013.8 | 19516 | 30493.7 | 42906.1 | 67040.7 | 32789.5 | 22887.4 | 1507.5 | 52125 | 1507.5 | 31281.9 | 1507.5
46.25 | 24657.2 | 54086 | 39371.6 | 19725.8 | 30821.5 | 43268.8 | 67607.5 | 33233.1 | 22935.4 | 1721.8 | 52364.1 | 1721.8 | 31511.3 | 1721.8
46.5 | 25765.4 | 55383 | 40574.2 | 20612.4 | 32206.8 | 44306.4 | 69228.8 | 34523.2 | 23179.4 | 2586 | 52797 | 2586 | 31937.1 | 2586
46.75 | 26029.2 | 55838.3 | 40933.8 | 20823.4 | 32536.5 | 44670.7 | 69797.9 | 34978.5 | 23933.3 | 2095.9 | 53742.4 | 2095.9 | 32882.6 | 2095.9
47 | 26252.9 | 56256.9 | 41254.9 | 21002.3 | 32816.2 | 45005.5 | 70321.1 | 35397 | 24500.6 | 1752.4 | 54504.5 | 1752.4 | 33644.6 | 1752.4
47.25 | 26947.5 | 57148.7 | 42048.1 | 21558 | 33684.4 | 45719 | 71435.9 | 36288.9 | 24936.2 | 2011.3 | 55137.4 | 2011.3 | 34277.6 | 2011.3
47.5 | 27536.2 | 57936.3 | 42736.2 | 22028.9 | 34420.2 | 46349 | 72420.3 | 37076.4 | 25410 | 2126.2 | 55810.1 | 2126.2 | 34950.2 | 2126.2
47.75 | 29460.2 | 60060.1 | 44760.2 | 23568.2 | 36825.3 | 48048.1 | 75075.1 | 39185.1 | 25779.9 | 3680.4 | 56379.7 | 3680.4 | 35504.7 | 3680.4
48 | 32842.6 | 63650.2 | 48246.4 | 26274.1 | 41053.3 | 50920.2 | 79562.8 | 42761.7 | 26894.4 | 5948.2 | 57702 | 5948.2 | 36813.4 | 5948.2
48.25 | 32275.8 | 63315.1 | 47795.4 | 25820.6 | 40344.7 | 50652.1 | 79143.9 | 42426.6 | 28820.3 | 3455.4 | 59859.7 | 3455.4 | 38971.1 | 3455.4
48.5 | 34389.7 | 65680.5 | 50035.1 | 27511.8 | 42987.1 | 52544.4 | 82100.7 | 44792 | 30265.8 | 4123.9 | 61556.7 | 4123.9 | 40668.1 | 4123.9
48.75 | 42384.7 | 73948.5 | 58166.6 | 33907.7 | 52980.8 | 59158.8 | 92435.6 | 53059.9 | 31934.6 | 10450 | 63498.4 | 10450 | 42609.9 | 10450
49 | 47364.7 | 79245 | 63304.8 | 37891.7 | 59205.8 | 63396 | 99056.2 | 49863.2 | 33969.5 | 13395.1 | 65849.9 | 13395.1 | 44725 | 5138.2
49.25 | 58058.4 | 90290.3 | 74174.4 | 46446.8 | 72573.1 | 72232.2 | 112862.9 | 53215.2 | 34955.2 | 23103.3 | 67187 | 23103.3 | 45114.2 | 8101
49.5 | 65329.5 | 97963.3 | 81646.4 | 52263.6 | 81661.8 | 78370.7 | 122454.2 | 55277.3 | 36566.3 | 28763.2 | 69200.1 | 28763.2 | 45543.1 | 9734.3

## SRD WTG-02
Depth (m) | SRD AH-FF (kN) | SRD AH-NFF (kN) | SRD MEAN (kN) | SRD AH-FF-LB (kN) | SRD AH-FF-UB (kN) | SRD AH-NFF-LB (kN) | SRD AH-NFF-UB (kN) | Static Cap (kN) | Shaft AH-FF (kN) | Tip AH-FF (kN) | Shaft AH-NFF (kN) | Tip AH-NFF (kN) | Shaft SC (kN) | Tip SC (kN)
0.5 | 76.2 | 76.3 | 76.3 | 61 | 95.3 | 61.1 | 95.4 | 34 | 5.1 | 71.1 | 5.3 | 71.1 | 3.6 | 30.4
0.75 | 73.4 | 73.7 | 73.6 | 58.7 | 91.8 | 59 | 92.1 | 36.2 | 7.9 | 65.5 | 8.2 | 65.5 | 5.8 | 30.4
1 | 74.1 | 74.6 | 74.3 | 59.2 | 92.6 | 59.7 | 93.2 | 40 | 12.2 | 61.9 | 12.7 | 61.9 | 9.5 | 30.4
1.25 | 74.2 | 75 | 74.6 | 59.4 | 92.8 | 60 | 93.8 | 42.6 | 15.1 | 59.2 | 15.9 | 59.2 | 12.2 | 30.4
1.5 | 76.9 | 78.1 | 77.5 | 61.5 | 96.1 | 62.4 | 97.6 | 46.9 | 19.6 | 57.3 | 20.7 | 57.3 | 16.5 | 30.4
1.75 | 158.8 | 160.3 | 159.6 | 127 | 198.5 | 128.3 | 200.4 | 84.2 | 24.3 | 134.5 | 25.8 | 134.5 | 20.8 | 63.5
2 | 99.7 | 101.7 | 100.7 | 79.7 | 124.6 | 81.4 | 127.1 | 63.5 | 32.1 | 67.6 | 34.1 | 67.6 | 27 | 36.5
2.25 | 98.9 | 101.5 | 100.2 | 79.1 | 123.6 | 81.2 | 126.8 | 66.2 | 36.2 | 62.7 | 38.7 | 62.7 | 31.2 | 35
2.5 | 104.8 | 107.9 | 106.3 | 83.8 | 130.9 | 86.3 | 134.9 | 72.2 | 40.8 | 64 | 44 | 64 | 36 | 36.2
2.75 | 109.4 | 113.2 | 111.3 | 87.5 | 136.7 | 90.5 | 141.5 | 77.5 | 45.2 | 64.2 | 49 | 64.2 | 40.6 | 36.9
3 | 113.4 | 117.9 | 115.7 | 90.8 | 141.8 | 94.3 | 147.4 | 82.9 | 50.1 | 63.3 | 54.6 | 63.3 | 45.9 | 37
3.25 | 120.5 | 125.6 | 123.1 | 96.4 | 150.6 | 100.5 | 157.1 | 89.6 | 54.8 | 65.7 | 60 | 65.7 | 51 | 38.6
3.5 | 131.4 | 137.3 | 134.3 | 105.1 | 164.2 | 109.8 | 171.6 | 98.6 | 60.3 | 71.1 | 66.2 | 71.1 | 56.8 | 41.8
3.75 | 147.5 | 154.3 | 150.9 | 118 | 184.4 | 123.4 | 192.8 | 110.1 | 65.8 | 81.8 | 72.5 | 81.8 | 62.7 | 47.5
4 | 166.6 | 174.2 | 170.4 | 133.3 | 208.2 | 139.3 | 217.7 | 124.9 | 75.5 | 91.1 | 83.1 | 91.1 | 72.4 | 52.5
4.25 | 151.9 | 160.4 | 156.1 | 121.5 | 189.8 | 128.3 | 200.5 | 121.5 | 81 | 70.8 | 89.5 | 70.8 | 78.5 | 43
4.5 | 164.7 | 174.2 | 169.5 | 131.8 | 205.9 | 139.4 | 217.8 | 132.1 | 87.3 | 77.4 | 96.8 | 77.4 | 85.4 | 46.7
4.75 | 356.8 | 367.3 | 362 | 285.4 | 446 | 293.8 | 459.1 | 223.3 | 97 | 259.8 | 107.5 | 259.8 | 94 | 129.3
5 | 226.1 | 237.9 | 232 | 180.9 | 282.6 | 190.4 | 297.4 | 189.8 | 142.1 | 84 | 154 | 84 | 138.9 | 50.9
5.25 | 227.6 | 241 | 234.3 | 182 | 284.4 | 192.8 | 301.3 | 195.2 | 148.8 | 78.8 | 162.3 | 78.8 | 146.5 | 48.7
5.5 | 383.7 | 398.8 | 391.2 | 306.9 | 479.6 | 319 | 498.5 | 382.2 | 169.1 | 214.5 | 184.3 | 214.5 | 167.7 | 214.5
5.75 | 460.9 | 478.1 | 469.5 | 368.7 | 576.2 | 382.5 | 597.6 | 455.9 | 214.1 | 246.9 | 231.2 | 246.9 | 209 | 246.9
6 | 502.6 | 522.4 | 512.5 | 402.1 | 628.3 | 417.9 | 653 | 499.7 | 260.5 | 242.1 | 280.2 | 242.1 | 257.5 | 242.1
6.25 | 513.6 | 536.2 | 524.9 | 410.9 | 642 | 429 | 670.3 | 397.8 | 272.7 | 240.9 | 295.3 | 240.9 | 270.5 | 127.2
6.5 | 846.2 | 872.1 | 859.1 | 676.9 | 1057.7 | 697.6 | 1090.1 | 568.6 | 336.3 | 509.9 | 362.2 | 509.9 | 329.3 | 239.3
6.75 | 4022.9 | 4055.3 | 4039.1 | 3218.3 | 5028.6 | 3244.2 | 5069.1 | 1601.5 | 514.9 | 3508 | 547.3 | 3508 | 398.6 | 1203
7 | 2177.5 | 2222.5 | 2200 | 1742 | 2721.8 | 1778 | 2778.1 | 1067.1 | 633.5 | 1544 | 678.5 | 1544 | 455.8 | 611.3
7.25 | 3052.9 | 3113.7 | 3083.3 | 2442.3 | 3816.2 | 2490.9 | 3892.1 | 1435.8 | 802 | 2250.9 | 862.7 | 2250.9 | 593.3 | 842.5
7.5 | 2189.6 | 2271 | 2230.3 | 1751.6 | 2736.9 | 1816.8 | 2838.8 | 1178.3 | 952.4 | 1237.2 | 1033.9 | 1237.2 | 663.3 | 515
7.75 | 2494.1 | 2600.5 | 2547.3 | 1995.3 | 3117.6 | 2080.4 | 3250.7 | 1418.7 | 1168.5 | 1325.6 | 1275 | 1325.6 | 869.9 | 548.8
8 | 2028.1 | 2162.7 | 2095.4 | 1622.5 | 2535.1 | 1730.2 | 2703.4 | 1747 | 1383.2 | 644.9 | 1517.8 | 644.9 | 1102.1 | 644.9
8.25 | 2107.9 | 2272.5 | 2190.2 | 1686.3 | 2634.8 | 1818 | 2840.7 | 1856.1 | 1487.4 | 620.5 | 1652.1 | 620.5 | 1235.6 | 620.5
8.5 | 2271.6 | 2466.9 | 2369.2 | 1817.2 | 2839.4 | 1973.5 | 3083.7 | 2048.1 | 1583.2 | 688.4 | 1778.6 | 688.4 | 1359.7 | 688.4
8.75 | 2031.4 | 2258.1 | 2144.7 | 1625.1 | 2539.3 | 1806.5 | 2822.6 | 1676.4 | 1686.6 | 344.8 | 1913.2 | 344.8 | 1494 | 182.4
9 | 2508.4 | 2766.8 | 2637.6 | 2006.7 | 3135.4 | 2213.4 | 3458.5 | 2346.5 | 1799.2 | 709.2 | 2057.6 | 709.2 | 1637.3 | 709.2
9.25 | 3380.6 | 3671.9 | 3526.2 | 2704.4 | 4225.7 | 2937.5 | 4589.8 | 2399.5 | 1924.5 | 1456 | 2215.8 | 1456 | 1788 | 611.5
9.5 | 2709.1 | 3034.6 | 2871.9 | 2167.3 | 3386.3 | 2427.7 | 3793.3 | 2245 | 2053.5 | 655.6 | 2379 | 655.6 | 1929 | 316
9.75 | 3924.8 | 4285.9 | 4105.3 | 3139.8 | 4906 | 3428.7 | 5357.3 | 2717.3 | 2125.7 | 1799.1 | 2486.8 | 1799.1 | 1980.8 | 736.5
10 | 3569.3 | 3968.6 | 3768.9 | 2855.4 | 4461.6 | 3174.8 | 4960.7 | 2747 | 2342.7 | 1226.6 | 2742 | 1226.6 | 2209.4 | 537.5
10.25 | 3228.3 | 3668 | 3448.1 | 2582.6 | 4035.3 | 2934.4 | 4585 | 2715.5 | 2467.6 | 760.7 | 2907.3 | 760.7 | 2352.9 | 362.6
10.5 | 3713 | 4194.8 | 3953.9 | 2970.4 | 4641.2 | 3355.8 | 5243.5 | 3601.9 | 2572.9 | 1140 | 3054.8 | 1140 | 2461.9 | 1140
10.75 | 3831.3 | 4358 | 4094.7 | 3065.1 | 4789.2 | 3486.4 | 5447.5 | 3765.1 | 2844.3 | 987.1 | 3370.9 | 987.1 | 2778 | 987.1
11 | 4083.8 | 4658.7 | 4371.3 | 3267.1 | 5104.8 | 3727 | 5823.4 | 4018.4 | 3064.6 | 1019.2 | 3639.5 | 1019.2 | 2999.2 | 1019.2
11.25 | 4858.8 | 5486 | 5172.4 | 3887 | 6073.5 | 4388.8 | 6857.5 | 4839.7 | 3325.7 | 1533.1 | 3952.9 | 1533.1 | 3306.6 | 1533.1
11.5 | 5082.9 | 5765.5 | 5424.2 | 4066.3 | 6353.6 | 4612.4 | 7206.9 | 5090.2 | 3598.9 | 1484 | 4281.5 | 1484 | 3606.2 | 1484
11.75 | 7075.3 | 7818.3 | 7446.8 | 5660.2 | 8844.1 | 6254.6 | 9772.9 | 5035.8 | 3784.8 | 3290.5 | 4527.8 | 3290.5 | 3777 | 1258.7
12 | 5017.4 | 5824.7 | 5421 | 4013.9 | 6271.7 | 4659.7 | 7280.8 | 5037.3 | 4112.2 | 905.2 | 4919.5 | 905.2 | 4132.2 | 905.2
12.25 | 5249.8 | 6125.8 | 5687.8 | 4199.8 | 6562.2 | 4900.6 | 7657.2 | 5338.5 | 4370.4 | 879.4 | 5246.4 | 879.4 | 4459.1 | 879.4
12.5 | 5207.4 | 6154.1 | 5680.7 | 4165.9 | 6509.2 | 4923.3 | 7692.6 | 5366.8 | 4602.3 | 605.1 | 5549 | 605.1 | 4761.7 | 605.1
12.75 | 5647.7 | 6666.7 | 6157.2 | 4518.1 | 7059.6 | 5333.3 | 8333.3 | 5879.3 | 4778.5 | 869.2 | 5797.5 | 869.2 | 5010.2 | 869.2
13 | 6079.2 | 7172.2 | 6625.7 | 4863.4 | 7599 | 5737.8 | 8965.3 | 6384.9 | 5021.1 | 1058.1 | 6114.1 | 1058.1 | 5326.8 | 1058.1
13.25 | 7062.3 | 8231.5 | 7646.9 | 5649.8 | 8827.8 | 6585.2 | 10289.3 | 7440.3 | 5226.8 | 1835.4 | 6396 | 1835.4 | 5604.8 | 1835.4
13.5 | 6963.5 | 8210.4 | 7587 | 5570.8 | 8704.4 | 6568.3 | 10263 | 6459.3 | 5319.9 | 1643.7 | 6566.7 | 1643.7 | 5736.7 | 722.5
13.75 | 6651 | 7977.2 | 7314.1 | 5320.8 | 8313.7 | 6381.8 | 9971.5 | 7136.8 | 5564.3 | 1086.6 | 6890.6 | 1086.6 | 6050.1 | 1086.6
14 | 7570.7 | 8979.4 | 8275 | 6056.6 | 9463.4 | 7183.5 | 11224.2 | 8138.9 | 5867.7 | 1703.1 | 7276.3 | 1703.1 | 6435.9 | 1703.1
14.25 | 7496.2 | 8990.9 | 8243.6 | 5997 | 9370.3 | 7192.7 | 11238.6 | 8150.5 | 6153 | 1343.3 | 7647.7 | 1343.3 | 6807.2 | 1343.3
14.5 | 7586.1 | 9170.9 | 8378.5 | 6068.9 | 9482.6 | 7336.8 | 11463.7 | 8330.5 | 6494.5 | 1091.6 | 8079.3 | 1091.6 | 7238.9 | 1091.6
14.75 | 7707.2 | 9385.7 | 8546.4 | 6165.7 | 9633.9 | 7508.5 | 11732.1 | 8545.2 | 6772.1 | 935 | 8450.7 | 935 | 7610.2 | 935
15 | 8055.7 | 9829.9 | 8942.8 | 6444.6 | 10069.7 | 7864 | 12287.4 | 8974.5 | 6919.3 | 1136.4 | 8693.5 | 1136.4 | 7838.1 | 1136.4
15.25 | 8626.3 | 10497.7 | 9562 | 6901 | 10782.9 | 8398.2 | 13122.1 | 9631.7 | 7135.5 | 1490.8 | 9006.9 | 1490.8 | 8140.9 | 1490.8
15.5 | 8608.5 | 10580.2 | 9594.3 | 6886.8 | 10760.6 | 8464.2 | 13225.3 | 9714.2 | 7439.9 | 1168.6 | 9411.7 | 1168.6 | 8545.6 | 1168.6
15.75 | 8702.5 | 10776.8 | 9739.7 | 6962 | 10878.2 | 8621.5 | 13471 | 9910.8 | 7641 | 1061.5 | 9715.3 | 1061.5 | 8849.3 | 1061.5
16 | 8544.9 | 10723 | 9633.9 | 6835.9 | 10681.1 | 8578.4 | 13403.8 | 9857 | 7853.3 | 691.5 | 10031.5 | 691.5 | 9165.4 | 691.5
16.25 | 8826.9 | 11109.8 | 9968.4 | 7061.5 | 11033.6 | 8887.9 | 13887.3 | 10243.8 | 7999.8 | 827.1 | 10282.8 | 827.1 | 9416.7 | 827.1
16.5 | 9160.8 | 11549.3 | 10355 | 7328.6 | 11450.9 | 9239.4 | 14436.6 | 10683.2 | 8193.6 | 967.2 | 10582.1 | 967.2 | 9716.1 | 967.2
16.75 | 9263.5 | 11759.2 | 10511.3 | 7410.8 | 11579.3 | 9407.3 | 14699 | 10893.1 | 8400.6 | 862.8 | 10896.3 | 862.8 | 10030.3 | 862.8
17 | 9265.9 | 11870.2 | 10568.1 | 7412.7 | 11582.4 | 9496.2 | 14837.8 | 11004.2 | 8618.7 | 647.2 | 11223 | 647.2 | 10357 | 647.2
17.25 | 9572.3 | 12285.9 | 10929.1 | 7657.8 | 11965.4 | 9828.7 | 15357.3 | 11419.8 | 8732.1 | 840.2 | 11445.7 | 840.2 | 10579.6 | 840.2
17.5 | 9710.4 | 12533.7 | 11122.1 | 7768.3 | 12138 | 10026.9 | 15667.1 | 11667.6 | 8907.1 | 803.3 | 11730.4 | 803.3 | 10864.3 | 803.3
17.75 | 9334.5 | 12268.2 | 10801.3 | 7467.6 | 11668.1 | 9814.5 | 15335.2 | 11275.5 | 9014.4 | 320.1 | 11948 | 320.1 | 11082 | 193.5
18 | 9865.6 | 12909.6 | 11387.6 | 7892.5 | 12332 | 10327.6 | 16136.9 | 12042.8 | 9138.8 | 726.8 | 12182.7 | 726.8 | 11316 | 726.8
18.25 | 10045.3 | 13200 | 11622.7 | 8036.2 | 12556.6 | 10560 | 16500.1 | 12333.3 | 9282.7 | 762.6 | 12437.5 | 762.6 | 11570.7 | 762.6
18.5 | 10111.7 | 13378.1 | 11744.9 | 8089.4 | 12639.7 | 10702.4 | 16722.6 | 12511.3 | 9453.2 | 658.5 | 12719.6 | 658.5 | 11852.8 | 658.5
18.75 | 10297.1 | 13675.4 | 11986.2 | 8237.6 | 12871.3 | 10940.3 | 17094.3 | 12808.7 | 9589.9 | 707.2 | 12968.3 | 707.2 | 12101.5 | 707.2
19 | 10463.7 | 13954.8 | 12209.2 | 8370.9 | 13079.6 | 11163.9 | 17443.5 | 13088.1 | 9790.7 | 673 | 13281.8 | 673 | 12415.1 | 673
19.25 | 10710.5 | 14314.9 | 12512.7 | 8568.4 | 13388.1 | 11451.9 | 17893.7 | 13444.9 | 9825.4 | 885 | 13429.9 | 885 | 12559.9 | 885
19.5 | 10217.4 | 13934.7 | 12076 | 8173.9 | 12771.7 | 11147.7 | 17418.3 | 12910.3 | 9841.2 | 376.2 | 13558.5 | 376.2 | 12685.4 | 224.8
19.75 | 10421.3 | 14250.6 | 12336 | 8337.1 | 13026.7 | 11400.5 | 17813.2 | 13126.8 | 9862.8 | 558.6 | 13692 | 558.6 | 12813.6 | 313.2
20 | 10826.9 | 14768.3 | 12797.6 | 8661.5 | 13533.6 | 11814.6 | 18460.4 | 13886.8 | 10031.2 | 795.6 | 13972.7 | 795.6 | 13091.2 | 795.6
20.25 | 10962.4 | 15017.1 | 12989.8 | 8769.9 | 13703 | 12013.7 | 18771.4 | 14135.6 | 10169 | 793.4 | 14223.7 | 793.4 | 13342.3 | 793.4
20.5 | 10633.7 | 14801.9 | 12717.8 | 8507 | 13292.1 | 11841.6 | 18502.4 | 13746.4 | 10216.9 | 416.7 | 14385.2 | 416.7 | 13499.6 | 246.9
20.75 | 11428 | 15709.3 | 13568.7 | 9142.4 | 14285 | 12567.5 | 19636.7 | 14820.6 | 10323.9 | 1104.1 | 14605.3 | 1104.1 | 13716.6 | 1104.1
21 | 11645.8 | 16041.4 | 13843.6 | 9316.7 | 14557.3 | 12833.1 | 20051.7 | 15152.5 | 10514.9 | 1131 | 14910.4 | 1131 | 14021.5 | 1131
21.25 | 11249 | 15759.7 | 13504.3 | 8999.2 | 14061.2 | 12607.8 | 19699.6 | 14603.6 | 10646.3 | 602.6 | 15157 | 602.6 | 14265.9 | 337.7
21.5 | 11912.4 | 16538.7 | 14225.5 | 9529.9 | 14890.5 | 13231 | 20673.4 | 15643.7 | 10804 | 1108.4 | 15430.3 | 1108.4 | 14535.3 | 1108.4
21.75 | 11595.3 | 16338.2 | 13966.7 | 9276.2 | 14494.1 | 13070.6 | 20422.7 | 15441.9 | 10894.5 | 700.8 | 15637.4 | 700.8 | 14741.1 | 700.8
22 | 11878.7 | 16737.7 | 14308.2 | 9503 | 14848.4 | 13390.2 | 20922.2 | 15836.9 | 10956.8 | 921.9 | 15815.8 | 921.9 | 14915 | 921.9
22.25 | 12045.2 | 17020.9 | 14533 | 9636.1 | 15056.5 | 13616.7 | 21276.1 | 16120 | 11110.8 | 934.3 | 16086.5 | 934.3 | 15185.7 | 934.3
22.5 | 12519.7 | 17612.8 | 15066.2 | 10015.7 | 15649.6 | 14090.2 | 22016 | 16712 | 11297.3 | 1222.4 | 16390.4 | 1222.4 | 15489.6 | 1222.4
22.75 | 12440.9 | 17653.2 | 15047.1 | 9952.8 | 15551.2 | 14122.6 | 22066.5 | 16752.4 | 11492.1 | 948.8 | 16704.4 | 948.8 | 15803.6 | 948.8
23 | 12838.2 | 18170.5 | 15504.3 | 10270.6 | 16047.7 | 14536.4 | 22713.1 | 17267.9 | 11663.3 | 1174.9 | 16995.6 | 1174.9 | 16093 | 1174.9
23.25 | 12796.8 | 18250.6 | 15523.7 | 10237.4 | 15996 | 14600.5 | 22813.2 | 16919.7 | 11883.8 | 913 | 17337.6 | 913 | 16435.1 | 484.7
23.5 | 13082.4 | 18659.7 | 15871.1 | 10465.9 | 16353 | 14927.8 | 23324.7 | 17754.3 | 12158.3 | 924.2 | 17735.6 | 924.2 | 16830.1 | 924.2
23.75 | 12624.9 | 18326.8 | 15475.9 | 10099.9 | 15781.1 | 14661.5 | 22908.6 | 17253.7 | 12204.2 | 420.7 | 17906.1 | 420.7 | 16998.6 | 255
24 | 13217.1 | 19043.5 | 16130.3 | 10573.7 | 16521.4 | 15234.8 | 23804.4 | 18132.1 | 12398.9 | 818.3 | 18225.3 | 818.3 | 17313.9 | 818.3
24.25 | 14013.7 | 19966 | 16989.9 | 11211 | 17517.1 | 15972.8 | 24957.6 | 19054.6 | 12564.1 | 1449.6 | 18516.4 | 1449.6 | 17605 | 1449.6
24.5 | 13120.3 | 19200.1 | 16160.2 | 10496.3 | 16400.4 | 15360 | 24000.1 | 17926.8 | 12723.7 | 396.6 | 18803.4 | 396.6 | 9625.7 | 8301.1
24.75 | 14174.1 | 20381.3 | 17277.7 | 11339.3 | 17717.6 | 16305.1 | 25476.7 | 19465.6 | 12883.6 | 1290.5 | 19090.8 | 1290.5 | 18175 | 1290.5
25 | 13501.7 | 19838.8 | 16670.3 | 10801.4 | 16877.1 | 15871.1 | 24798.5 | 16337.3 | 13216.5 | 285.2 | 19553.7 | 285.2 | 10010.5 | 6326.9
25.25 | 14808.6 | 21278.5 | 18043.6 | 11846.9 | 18510.8 | 17022.8 | 26598.2 | 20362.3 | 13510.6 | 1298 | 19980.5 | 1298 | 19064.3 | 1298
25.5 | 15059.4 | 21665.2 | 18362.3 | 12047.5 | 18824.3 | 17332.2 | 27081.5 | 20747.1 | 13781.3 | 1278.1 | 20387.1 | 1278.1 | 19469 | 1278.1
25.75 | 15072.1 | 21815.7 | 18443.9 | 12057.7 | 18840.1 | 17452.6 | 27269.6 | 20897.6 | 14028.7 | 1043.4 | 20772.3 | 1043.4 | 19854.1 | 1043.4
26 | 15254.4 | 22137.2 | 18695.8 | 12203.5 | 19068 | 17709.8 | 27671.5 | 21218.8 | 14188.1 | 1066.3 | 21070.9 | 1066.3 | 20152.6 | 1066.3
26.25 | 14742.7 | 21765.3 | 18254 | 11794.1 | 18428.3 | 17412.3 | 27206.7 | 20059.7 | 14303.4 | 439.2 | 21326.1 | 439.2 | 10917.7 | 9142
26.5 | 15332.8 | 22495 | 18913.9 | 12266.2 | 19165.9 | 17996 | 28118.7 | 21572.7 | 14360.6 | 972.1 | 21522.8 | 972.1 | 20600.6 | 972.1
26.75 | 15259.5 | 22561 | 18910.3 | 12207.6 | 19074.4 | 18048.8 | 28201.3 | 21636.6 | 14383.8 | 875.7 | 21685.3 | 875.7 | 20760.9 | 875.7
27 | 14730.3 | 22170.5 | 18450.4 | 11784.3 | 18412.9 | 17736.4 | 27713.1 | 17869.9 | 14431.4 | 298.9 | 21871.5 | 298.9 | 11204.3 | 6665.5
27.25 | 14664.3 | 22242.3 | 18453.3 | 11731.5 | 18330.4 | 17793.9 | 27802.9 | 17590.1 | 14383.7 | 280.6 | 21961.7 | 280.6 | 11257.5 | 6332.6
27.5 | 14591.3 | 22305.8 | 18448.5 | 11673 | 18239.1 | 17844.6 | 27882.2 | 18064.6 | 14287.7 | 303.6 | 22002.1 | 303.6 | 11291.4 | 6773.3
27.75 | 14590 | 22439.5 | 18514.7 | 11672 | 18237.5 | 17951.6 | 28049.4 | 19453 | 14213.2 | 376.8 | 22062.7 | 376.8 | 11332.7 | 8120.2
28 | 14429.9 | 22413.2 | 18421.6 | 11543.9 | 18037.4 | 17930.6 | 28016.5 | 17706.7 | 14151.2 | 278.8 | 22134.5 | 278.8 | 11379.8 | 6326.9
28.25 | 14360.6 | 22476.3 | 18418.5 | 11488.5 | 17950.8 | 17981.1 | 28095.4 | 18269.9 | 14054 | 306.7 | 22169.7 | 306.7 | 11410 | 6859.9
28.5 | 14409 | 22655.8 | 18532.4 | 11527.2 | 18011.3 | 18124.7 | 28319.8 | 19675.3 | 14029.7 | 379.3 | 22276.5 | 379.3 | 11474.2 | 8201
28.75 | 14236.5 | 22613.4 | 18425 | 11389.2 | 17795.6 | 18090.7 | 28266.8 | 18026.6 | 13949.2 | 287.3 | 22326.2 | 287.3 | 11511.1 | 6515.4
29 | 14198.4 | 22704.1 | 18451.3 | 11358.7 | 17748 | 18163.3 | 28380.2 | 18970.3 | 13863 | 335.4 | 22368.8 | 335.4 | 11546.7 | 7423.7
29.25 | 14672.2 | 23305.5 | 18988.9 | 11737.8 | 18340.3 | 18644.4 | 29131.8 | 22329.3 | 13836.3 | 835.9 | 22469.6 | 835.9 | 21493.4 | 835.9
29.5 | 14081.2 | 22841 | 18461.1 | 11265 | 17601.5 | 18272.8 | 28551.3 | 18504.9 | 13777.5 | 303.7 | 22537.3 | 303.7 | 11650.8 | 6854.1
29.75 | 13998.9 | 22884 | 18441.4 | 11199.1 | 17498.6 | 18307.2 | 28605 | 18652.2 | 13689.6 | 309.3 | 22574.7 | 309.3 | 11682.6 | 6969.5
30 | 13923.2 | 22932.3 | 18427.7 | 11138.6 | 17404 | 18345.8 | 28665.4 | 18822.1 | 13607.2 | 316 | 22616.3 | 316 | 11717.9 | 7104.2
30.25 | 13932.7 | 23064.7 | 18498.7 | 11146.2 | 17415.9 | 18451.7 | 28830.8 | 19034.5 | 13609.7 | 323.1 | 22741.6 | 323.1 | 11787.8 | 7246.6
30.5 | 13873.1 | 23127.1 | 18500.1 | 11098.5 | 17341.4 | 18501.7 | 28908.9 | 19297.6 | 13538.6 | 334.5 | 22792.6 | 334.5 | 11827.8 | 7469.8
30.75 | 13879.7 | 23254.8 | 18567.2 | 11103.8 | 17349.6 | 18603.8 | 29068.4 | 19935.9 | 13514.3 | 365.4 | 22889.4 | 365.4 | 11885 | 8051
31 | 13750 | 23245.1 | 18497.5 | 11000 | 17187.6 | 18596 | 29056.3 | 18972.6 | 13439 | 311.1 | 22934 | 311.1 | 11922.2 | 7050.4
31.25 | 14566 | 24179.8 | 19372.9 | 11652.8 | 18207.4 | 19343.9 | 30224.8 | 23157.2 | 13414.6 | 1151.4 | 23028.5 | 1151.4 | 22005.9 | 1151.4
31.5 | 14447 | 24179.6 | 19313.3 | 11557.6 | 18058.7 | 19343.7 | 30224.5 | 23157 | 13531.4 | 915.6 | 23264 | 915.6 | 22241.4 | 915.6
31.75 | 13979.5 | 23830.7 | 18905.1 | 11183.6 | 17474.4 | 19064.6 | 29788.4 | 21809.3 | 13528.8 | 450.8 | 23380 | 450.8 | 12167 | 9642.3
32 | 13900.5 | 23869.8 | 18885.2 | 11120.4 | 17375.6 | 19095.8 | 29837.3 | 19792.1 | 13565.5 | 335 | 23534.8 | 335 | 12253 | 7539.1
32.25 | 14754.3 | 24841.1 | 19797.7 | 11803.4 | 18442.8 | 19872.9 | 31051.4 | 23807.1 | 13628 | 1126.2 | 23714.9 | 1126.2 | 22680.8 | 1126.2
32.5 | 14104.9 | 24309.6 | 19207.3 | 11283.9 | 17631.1 | 19447.7 | 30387 | 21293.8 | 13700.4 | 404.4 | 23905.2 | 404.4 | 12450 | 8843.7
32.75 | 14065.7 | 24387.8 | 19226.8 | 11252.6 | 17582.1 | 19510.3 | 30484.8 | 20718 | 13696.7 | 369 | 24018.8 | 369 | 12515 | 8203
33 | 15427.1 | 25865.8 | 20646.4 | 12341.6 | 19283.8 | 20692.7 | 32332.3 | 24820.8 | 13753.9 | 1673.2 | 24192.6 | 1673.2 | 23147.6 | 1673.2
33.25 | 15754.5 | 26311.9 | 21033.2 | 12603.6 | 19693.1 | 21049.5 | 32889.9 | 25266.9 | 14159.1 | 1595.3 | 24716.6 | 1595.3 | 23671.5 | 1595.3
33.5 | 16126.4 | 26807.2 | 21466.8 | 12901.1 | 20158 | 21445.8 | 33509 | 25762.2 | 14665 | 1461.4 | 25345.9 | 1461.4 | 24300.8 | 1461.4
33.75 | 16416.5 | 27224.6 | 21820.6 | 13133.2 | 20520.7 | 21779.7 | 34030.7 | 26179.5 | 15016.3 | 1400.3 | 25824.3 | 1400.3 | 24779.3 | 1400.3
34 | 16604.5 | 27542.3 | 22073.4 | 13283.6 | 20755.6 | 22033.8 | 34427.9 | 26497.3 | 15289.3 | 1315.2 | 26227.1 | 1315.2 | 25182.1 | 1315.2
34.25 | 15905.6 | 26974.2 | 21439.9 | 12724.4 | 19881.9 | 21579.4 | 33717.8 | 24993.4 | 15372.4 | 533.2 | 26441.1 | 533.2 | 13761.7 | 11231.7
34.5 | 16193.3 | 27392.8 | 21793.1 | 12954.7 | 20241.7 | 21914.3 | 34241 | 26041.1 | 15470.9 | 722.5 | 26670.4 | 722.5 | 25615.2 | 425.9
34.75 | 17036.2 | 28367.3 | 22701.8 | 13629 | 21295.3 | 22693.9 | 35459.2 | 27306.7 | 15700.2 | 1336 | 27031.3 | 1336 | 25970.7 | 1336
35 | 16160 | 27624.2 | 21892.1 | 12928 | 20200 | 22099.3 | 34530.2 | 23166.8 | 15753.4 | 406.6 | 27217.6 | 406.6 | 14172.9 | 8993.8
35.25 | 16839.9 | 28436.4 | 22638.2 | 13472 | 21049.9 | 22749.1 | 35545.4 | 27365.7 | 15759.4 | 1080.5 | 27355.8 | 1080.5 | 26285.2 | 1080.5
35.5 | 16130.7 | 27859.1 | 21994.9 | 12904.6 | 20163.4 | 22287.3 | 34823.8 | 22226.5 | 15784.3 | 346.5 | 27512.6 | 346.5 | 14337.2 | 7889.3
35.75 | 16829.7 | 28689.1 | 22759.4 | 13463.8 | 21037.2 | 22951.3 | 35861.4 | 27608.6 | 15768.7 | 1061.1 | 27628 | 1061.1 | 26547.5 | 1061.1
36 | 16720 | 28709.9 | 22715 | 13376 | 20900 | 22967.9 | 35887.4 | 27625.2 | 15775 | 945 | 27764.9 | 945 | 26680.2 | 945
36.25 | 16960.2 | 29079.8 | 23020 | 13568.2 | 21200.3 | 23263.9 | 36349.8 | 27987 | 15721.3 | 1238.9 | 27840.9 | 1238.9 | 26748.1 | 1238.9
36.5 | 16929.6 | 29179 | 23054.3 | 13543.7 | 21162.1 | 23343.2 | 36473.8 | 28086.2 | 15924.5 | 1005.2 | 28173.9 | 1005.2 | 27081 | 1005.2
36.75 | 17277.1 | 29656.5 | 23466.8 | 13821.7 | 21596.4 | 23725.2 | 37070.6 | 28558.4 | 15986.8 | 1290.3 | 28366.2 | 1290.3 | 27268.1 | 1290.3
37 | 16633.1 | 29143.4 | 22888.2 | 13306.4 | 20791.3 | 23314.8 | 36429.3 | 25465.4 | 16148.7 | 484.3 | 28659.1 | 484.3 | 14963 | 10502.4
37.25 | 17364 | 30005.5 | 23684.7 | 13891.2 | 21705 | 24004.4 | 37506.8 | 28902.4 | 16243.9 | 1120.1 | 28885.3 | 1120.1 | 27782.3 | 1120.1
37.5 | 17469.5 | 30242 | 23855.8 | 13975.6 | 21836.9 | 24193.6 | 37802.5 | 29132.3 | 16361.2 | 1108.4 | 29133.7 | 1108.4 | 28024 | 1108.4
37.75 | 17483.7 | 30388.3 | 23936 | 13987 | 21854.6 | 24310.6 | 37985.4 | 29278.6 | 16525.6 | 958.1 | 29430.2 | 958.1 | 28320.5 | 958.1
38 | 17539.4 | 30576 | 24057.7 | 14031.5 | 21924.3 | 24460.8 | 38220 | 29464.4 | 16559.6 | 979.8 | 29596.2 | 979.8 | 28484.5 | 979.8
38.25 | 16929.2 | 30097.3 | 23513.3 | 13543.4 | 21161.5 | 24077.9 | 37621.7 | 23605.7 | 16578.4 | 350.8 | 29746.5 | 350.8 | 15533.5 | 8072.1
38.5 | 16820.3 | 30119 | 23469.7 | 13456.2 | 21025.4 | 24095.2 | 37648.8 | 23125.9 | 16496.9 | 323.4 | 29795.6 | 323.4 | 15575.2 | 7550.7
38.75 | 16745.3 | 30173.4 | 23459.3 | 13396.2 | 20931.6 | 24138.7 | 37716.7 | 23358.5 | 16412.3 | 333 | 29840.4 | 333 | 15613.5 | 7745
39 | 16671.8 | 30228 | 23449.9 | 13337.4 | 20839.7 | 24182.4 | 37785 | 23547.4 | 16331.6 | 340.2 | 29887.8 | 340.2 | 15654.3 | 7893.2
39.25 | 16597.9 | 30281.1 | 23439.5 | 13278.3 | 20747.3 | 24224.9 | 37851.4 | 23742.1 | 16250 | 347.8 | 29933.3 | 347.8 | 15693 | 8049
39.5 | 16512 | 30321.1 | 23416.6 | 13209.6 | 20640 | 24256.9 | 37901.4 | 23586.7 | 16174.9 | 337.1 | 29984 | 337.1 | 15735.9 | 7850.8
39.75 | 16439 | 30372.9 | 23406 | 13151.2 | 20548.8 | 24298.3 | 37966.2 | 23728.4 | 16097 | 342 | 30031 | 342 | 15775.6 | 7952.8
40 | 16396.7 | 30454.3 | 23425.5 | 13117.4 | 20495.9 | 24363.4 | 38067.9 | 24185 | 16033.9 | 362.8 | 30091.5 | 362.8 | 15822.3 | 8362.7
40.25 | 16349.8 | 30530.1 | 23439.9 | 13079.8 | 20437.2 | 24424 | 38162.6 | 24534.6 | 15971.6 | 378.2 | 30151.9 | 378.2 | 15867.8 | 8666.7
40.5 | 16425.7 | 30727.7 | 23576.7 | 13140.5 | 20532.1 | 24582.2 | 38409.7 | 26076.9 | 15969.8 | 455.8 | 30271.9 | 455.8 | 15940.1 | 10136.8
40.75 | 16923.9 | 31347.4 | 24135.7 | 13539.2 | 21154.9 | 25077.9 | 39184.3 | 29748.1 | 15983.3 | 940.6 | 30406.8 | 940.6 | 29202.5 | 545.6
41 | 17209.9 | 31755.9 | 24482.9 | 13767.9 | 21512.4 | 25404.7 | 39694.9 | 30110 | 16204.5 | 1005.4 | 30750.5 | 1005.4 | 29532.6 | 577.4
41.25 | 24024 | 38694.6 | 31359.3 | 19219.2 | 30030 | 30955.7 | 48368.3 | 32806.8 | 16438.2 | 7585.8 | 31108.9 | 7585.8 | 29692.6 | 3114.2
41.5 | 24188.1 | 38995.5 | 31591.8 | 19350.5 | 30235.1 | 31196.4 | 48744.4 | 33369.1 | 17295.7 | 6892.4 | 32103.1 | 6892.4 | 30490.5 | 2878.5
41.75 | 28281.1 | 43241.4 | 35761.2 | 22624.9 | 35351.3 | 34593.1 | 54051.8 | 34830.5 | 17823.7 | 10457.4 | 32784.1 | 10457.4 | 30751.3 | 4079.2
42 | 29474.9 | 44606.4 | 37040.7 | 23580 | 36843.7 | 35685.1 | 55758 | 35312.9 | 18539.4 | 10935.5 | 33670.9 | 10935.5 | 31073.6 | 4239.3
42.25 | 47502.8 | 62831.3 | 55167.1 | 38002.3 | 59378.5 | 50265.1 | 78539.2 | 40713.5 | 19589.7 | 27913.2 | 34918.2 | 27913.2 | 31445.9 | 9267.7
42.5 | 39643.9 | 55227.7 | 47435.8 | 31715.1 | 49554.9 | 44182.2 | 69034.7 | 38446.1 | 21193.8 | 18450.1 | 36777.6 | 18450.1 | 31874.7 | 6571.4
42.75 | 39717.2 | 55600.6 | 47658.9 | 31773.8 | 49646.5 | 44480.5 | 69500.8 | 38579 | 22174.5 | 17542.7 | 38057.9 | 17542.7 | 32270.4 | 6308.7
43 | 45554.1 | 61771.6 | 53662.8 | 36443.3 | 56942.6 | 49417.3 | 77214.5 | 40403.1 | 23204.7 | 22349.3 | 39422.2 | 22349.3 | 32674.5 | 7728.6
43.25 | 43603.1 | 60191.6 | 51897.4 | 34882.5 | 54503.9 | 48153.3 | 75239.5 | 39933.3 | 24250.7 | 19352.4 | 40839.2 | 19352.4 | 33070.3 | 6862.9
43.5 | 46961.3 | 63958.3 | 55459.8 | 37569 | 58701.6 | 51166.7 | 79947.9 | 41003.5 | 25449.6 | 21511.7 | 42446.6 | 21511.7 | 33499.2 | 7504.3
43.75 | 45055.3 | 62499.2 | 53777.3 | 36044.2 | 56319.1 | 49999.4 | 78124 | 40569.1 | 26393.3 | 18662 | 43837.2 | 18662 | 33895 | 6674.1
44 | 39676.2 | 57592.2 | 48634.2 | 31741 | 49595.3 | 46073.7 | 71990.2 | 39099.1 | 27057 | 12619.3 | 44972.9 | 12619.3 | 34276.3 | 4822.8
44.25 | 44519.4 | 62919.3 | 53719.4 | 35615.5 | 55649.3 | 50335.5 | 78649.2 | 40787.4 | 27629.3 | 16890.1 | 46029.3 | 16890.1 | 34631.3 | 6156
44.5 | 32465.2 | 51363.1 | 41914.1 | 25972.1 | 40581.5 | 41090.5 | 64203.9 | 39632.3 | 28517.8 | 3947.4 | 47415.7 | 3947.4 | 35684.9 | 3947.4
44.75 | 37231.8 | 56638.6 | 46935.2 | 29785.4 | 46539.7 | 45310.9 | 70798.2 | 44907.8 | 29909.5 | 7322.3 | 49316.3 | 7322.3 | 37585.5 | 7322.3
45 | 37686 | 57621.1 | 47653.5 | 30148.8 | 47107.5 | 46096.9 | 72026.3 | 45711.7 | 31703.8 | 5982.2 | 51638.9 | 5982.2 | 39729.5 | 5982.2
45.25 | 44838.6 | 65359.2 | 55098.9 | 35870.9 | 56048.2 | 52287.4 | 81699 | 53449.9 | 35214.7 | 9623.8 | 55735.4 | 9623.8 | 43826 | 9623.8
45.5 | 54678.8 | 75866.8 | 65272.8 | 43743.1 | 68348.5 | 60693.4 | 94833.5 | 63957.4 | 39225.5 | 15453.3 | 60413.5 | 15453.3 | 48504.2 | 15453.3
45.75 | 58992.3 | 80951.9 | 69972.1 | 47193.8 | 73740.4 | 64761.5 | 101189.8 | 69042.5 | 41391.8 | 17600.5 | 63351.4 | 17600.5 | 51442 | 17600.5
46 | 52626.3 | 75357.6 | 63992 | 42101 | 65782.9 | 60286.1 | 94197.1 | 63448.3 | 40620 | 12006.3 | 63351.4 | 12006.3 | 51442 | 12006.3
46.25 | 46283.3 | 69763.4 | 58023.3 | 37026.6 | 57854.1 | 55810.7 | 87204.3 | 57854.1 | 39871.2 | 6412 | 63351.4 | 6412 | 51442 | 6412
46.5 | 51878.6 | 77435.3 | 64657 | 41502.9 | 64848.3 | 61948.3 | 96794.2 | 65526 | 51060.8 | 817.8 | 76617.5 | 817.8 | 64708.2 | 817.8
46.75 | 87328.7 | 113969.1 | 100648.9 | 69863 | 109160.9 | 91175.3 | 142461.4 | 101625.1 | 52245.8 | 35082.9 | 78886.2 | 35082.9 | 66542.1 | 35082.9

## SRD WTG-03
Depth (m) | SRD AH-FF (kN) | SRD AH-NFF (kN) | SRD MEAN (kN) | SRD AH-FF-LB (kN) | SRD AH-FF-UB (kN) | SRD AH-NFF-LB (kN) | SRD AH-NFF-UB (kN) | Static Cap (kN) | Shaft AH-FF (kN) | Tip AH-FF (kN) | Shaft AH-NFF (kN) | Tip AH-NFF (kN) | Shaft SC (kN) | Tip SC (kN)
0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | 106.5 | 106.5 | 106.5 | 85.2 | 133.1 | 85.2 | 133.1 | 106.5 | 10.5 | 95.9 | 10.6 | 95.9 | 10.6 | 95.9
2.25 | 138.4 | 138.7 | 138.5 | 110.7 | 173 | 110.9 | 173.4 | 84.2 | 33.6 | 104.8 | 33.9 | 104.8 | 33.8 | 50.5
2.5 | 289 | 290 | 289.5 | 231.2 | 361.3 | 232 | 362.5 | 289.3 | 73.6 | 215.4 | 74.6 | 215.4 | 73.9 | 215.4
2.75 | 364.7 | 367.1 | 365.9 | 291.8 | 455.9 | 293.7 | 458.9 | 366.5 | 131.2 | 233.5 | 133.6 | 233.5 | 133 | 233.5
3 | 433.6 | 438.4 | 436 | 346.8 | 541.9 | 350.7 | 548 | 437.8 | 191.9 | 241.7 | 196.8 | 241.7 | 196.1 | 241.7
3.25 | 887.9 | 896 | 892 | 710.3 | 1109.9 | 716.8 | 1120 | 495.3 | 238.5 | 649.4 | 246.6 | 649.4 | 244.1 | 251.2
3.5 | 3169.7 | 3183.1 | 3176.4 | 2535.7 | 3962.1 | 2546.5 | 3978.9 | 1156.7 | 336 | 2833.7 | 349.5 | 2833.7 | 283.5 | 873.1
3.75 | 1606.9 | 1630.8 | 1618.9 | 1285.5 | 2008.6 | 1304.7 | 2038.5 | 1502.5 | 436.7 | 1170.1 | 460.7 | 1170.1 | 332.4 | 1170.1
4 | 1401.7 | 1440.2 | 1420.9 | 1121.4 | 1752.1 | 1152.2 | 1800.2 | 1286.4 | 601.5 | 800.2 | 640 | 800.2 | 486.2 | 800.2
4.25 | 1343.2 | 1400 | 1371.6 | 1074.6 | 1679 | 1120 | 1750 | 829.8 | 706.4 | 636.8 | 763.2 | 636.8 | 567.2 | 262.6
4.5 | 886 | 963.6 | 924.8 | 708.8 | 1107.6 | 770.9 | 1204.5 | 764.3 | 885.6 | 0.5 | 963.1 | 0.5 | 763.9 | 0.5
4.75 | 1263.3 | 1363 | 1313.2 | 1010.7 | 1579.2 | 1090.4 | 1703.8 | 1163.7 | 964.2 | 299.2 | 1063.9 | 299.2 | 864.6 | 299.2
5 | 1280.9 | 1402.7 | 1341.8 | 1024.7 | 1601.2 | 1122.2 | 1753.4 | 1202.9 | 991.7 | 289.2 | 1113.5 | 289.2 | 913.7 | 289.2
5.25 | 1430.9 | 1574.4 | 1502.7 | 1144.7 | 1788.6 | 1259.6 | 1968.1 | 1368.7 | 1006.2 | 424.7 | 1149.7 | 424.7 | 944 | 424.7
5.5 | 1445.3 | 1611.4 | 1528.3 | 1156.2 | 1806.6 | 1289.1 | 2014.2 | 1405.7 | 1141.1 | 304.1 | 1307.2 | 304.1 | 1101.5 | 304.1
5.75 | 1491.6 | 1680.5 | 1586.1 | 1193.3 | 1864.5 | 1344.4 | 2100.7 | 1474 | 1160.8 | 330.8 | 1349.7 | 330.8 | 1143.1 | 330.8
6 | 1489.9 | 1701.5 | 1595.7 | 1191.9 | 1862.4 | 1361.2 | 2126.9 | 1494.6 | 1207.9 | 282 | 1419.6 | 282 | 1212.7 | 282
6.25 | 1353.5 | 1587.7 | 1470.6 | 1082.8 | 1691.9 | 1270.2 | 1984.7 | 1325.3 | 1225.7 | 127.8 | 1459.9 | 127.8 | 1251.2 | 74.1
6.5 | 1579.3 | 1835.7 | 1707.5 | 1263.4 | 1974.1 | 1468.6 | 2294.7 | 1626.4 | 1254.8 | 324.5 | 1511.2 | 324.5 | 1301.9 | 324.5
6.75 | 1622.9 | 1901.6 | 1762.2 | 1298.3 | 2028.6 | 1521.2 | 2376.9 | 1690.8 | 1285.7 | 337.2 | 1564.4 | 337.2 | 1353.7 | 337.2
7 | 1749.6 | 2050.6 | 1900.1 | 1399.7 | 2187 | 1640.5 | 2563.3 | 1838.2 | 1348.6 | 401 | 1649.6 | 401 | 1437.2 | 401
7.25 | 1647.9 | 1971.7 | 1809.8 | 1318.3 | 2059.9 | 1577.4 | 2464.7 | 1663.5 | 1436.6 | 211.3 | 1760.4 | 211.3 | 1547.7 | 115.8
7.5 | 2119.3 | 2466.6 | 2292.9 | 1695.4 | 2649.1 | 1973.3 | 3083.2 | 2253.3 | 1545 | 574.3 | 1892.3 | 574.3 | 1678.9 | 574.3
7.75 | 1994.6 | 2366.4 | 2180.5 | 1595.7 | 2493.3 | 1893.1 | 2958 | 2152.7 | 1632.3 | 362.3 | 2004.1 | 362.3 | 1790.4 | 362.3
8 | 2062.2 | 2458.9 | 2260.6 | 1649.8 | 2577.8 | 1967.1 | 3073.6 | 2245 | 1707.4 | 354.8 | 2104.1 | 354.8 | 1890.2 | 354.8
8.25 | 1914.4 | 2336.1 | 2125.2 | 1531.5 | 2393 | 1868.9 | 2920.2 | 2118.4 | 1751.4 | 162.9 | 2173.2 | 162.9 | 1955.4 | 162.9
8.5 | 2498.5 | 2945.8 | 2722.2 | 1998.8 | 3123.1 | 2356.7 | 3682.3 | 2716.4 | 1851.3 | 647.2 | 2298.6 | 647.2 | 2069.2 | 647.2
8.75 | 3165.3 | 3639.8 | 3402.5 | 2532.3 | 3956.7 | 2911.8 | 4549.7 | 3404.4 | 1961.9 | 1203.4 | 2436.4 | 1203.4 | 2201 | 1203.4
9 | 2739.2 | 3242.7 | 2991 | 2191.4 | 3424.1 | 2594.2 | 4053.4 | 3006.3 | 2205.2 | 534 | 2708.7 | 534 | 2472.2 | 534
9.25 | 2654.1 | 3188.2 | 2921.2 | 2123.3 | 3317.7 | 2550.6 | 3985.3 | 2774.5 | 2284.9 | 369.2 | 2819 | 369.2 | 2581.8 | 192.7
9.5 | 2960.9 | 3526.3 | 3243.6 | 2368.7 | 3701.2 | 2821.1 | 4407.9 | 3287 | 2421.9 | 539 | 2987.3 | 539 | 2748 | 539
9.75 | 3079 | 3677.1 | 3378 | 2463.2 | 3848.7 | 2941.7 | 4596.4 | 3437.6 | 2520.5 | 558.5 | 3118.6 | 558.5 | 2879.1 | 558.5
10 | 3352.7 | 3984.2 | 3668.5 | 2682.2 | 4190.9 | 3187.3 | 4980.2 | 3744.4 | 2615.9 | 736.8 | 3247.4 | 736.8 | 3007.6 | 736.8
10.25 | 3149.4 | 3814.9 | 3482.2 | 2519.5 | 3936.8 | 3051.9 | 4768.6 | 3574.5 | 2688 | 461.4 | 3353.5 | 461.4 | 3113.1 | 461.4
10.5 | 3408.5 | 4108.2 | 3758.4 | 2726.8 | 4260.7 | 3286.6 | 5135.3 | 3866.5 | 2768.1 | 640.4 | 3467.9 | 640.4 | 3226.1 | 640.4
10.75 | 3506.5 | 4241.7 | 3874.1 | 2805.2 | 4383.1 | 3393.4 | 5302.2 | 3998.9 | 2893.7 | 612.8 | 3629 | 612.8 | 3386.1 | 612.8
11 | 3933.9 | 4705.5 | 4319.7 | 3147.1 | 4917.3 | 3764.4 | 5881.9 | 4462.7 | 3045.4 | 888.4 | 3817.1 | 888.4 | 3574.3 | 888.4
11.25 | 4020.7 | 4830.5 | 4425.6 | 3216.5 | 5025.8 | 3864.4 | 6038.1 | 4587.7 | 3204.7 | 816 | 4014.5 | 816 | 3771.7 | 816
11.5 | 4437.5 | 5287.2 | 4862.3 | 3550 | 5546.8 | 4229.7 | 6609 | 5043.5 | 3373 | 1064.5 | 4222.7 | 1064.5 | 3979.1 | 1064.5
11.75 | 3896.5 | 4787.9 | 4342.2 | 3117.2 | 4870.7 | 3830.4 | 5984.9 | 4385.1 | 3544.2 | 352.3 | 4435.6 | 352.3 | 4191.6 | 193.4
12 | 4499.2 | 5433.3 | 4966.3 | 3599.3 | 5624 | 4346.7 | 6791.7 | 5185 | 3697.6 | 801.5 | 4631.8 | 801.5 | 4383.5 | 801.5
12.25 | 4523.5 | 5502.8 | 5013.1 | 3618.8 | 5654.4 | 4402.2 | 6878.4 | 5254.4 | 3884.7 | 638.8 | 4863.9 | 638.8 | 4615.6 | 638.8
12.5 | 4704.4 | 5730.1 | 5217.3 | 3763.5 | 5880.5 | 4584.1 | 7162.6 | 5481.8 | 4016 | 688.4 | 5041.7 | 688.4 | 4793.4 | 688.4
12.75 | 5434.2 | 6508 | 5971.1 | 4347.4 | 6792.7 | 5206.4 | 8135 | 6259.6 | 4218.8 | 1215.4 | 5292.6 | 1215.4 | 5044.2 | 1215.4
13 | 5084.1 | 6208.3 | 5646.2 | 4067.3 | 6355.2 | 4966.7 | 7760.4 | 5960 | 4418.4 | 665.7 | 5542.6 | 665.7 | 5294.2 | 665.7
13.25 | 5032 | 6207.5 | 5619.8 | 4025.6 | 6290 | 4966 | 7759.4 | 5957.9 | 4477.2 | 554.9 | 5652.7 | 554.9 | 5403 | 554.9
13.5 | 5159.2 | 6386.4 | 5772.8 | 4127.3 | 6449 | 5109.1 | 7982.9 | 6136.7 | 4583 | 576.1 | 5810.2 | 576.1 | 5560.6 | 576.1
13.75 | 5362 | 6641.6 | 6001.8 | 4289.6 | 6702.5 | 5313.3 | 8302 | 6391.6 | 4680 | 682 | 5959.6 | 682 | 5709.6 | 682
14 | 5032.6 | 6365.1 | 5698.8 | 4026.1 | 6290.7 | 5092 | 7956.3 | 5999.7 | 4755.4 | 277.2 | 6087.9 | 277.2 | 5836.3 | 163.4
14.25 | 5431 | 6816.5 | 6123.7 | 4344.8 | 6788.7 | 5453.2 | 8520.6 | 6562.9 | 4808.3 | 622.7 | 6193.7 | 622.7 | 5940.2 | 622.7
14.5 | 5161.2 | 6599.9 | 5880.5 | 4128.9 | 6451.5 | 5279.9 | 8249.9 | 6219.8 | 4860.4 | 300.7 | 6299.2 | 300.7 | 6043.9 | 175.9
14.75 | 5557.7 | 7050 | 6303.8 | 4446.1 | 6947.1 | 5640 | 8812.5 | 6794.3 | 4965.5 | 592.2 | 6457.8 | 592.2 | 6202.1 | 592.2
15 | 5264.5 | 6810.9 | 6037.7 | 4211.6 | 6580.6 | 5448.7 | 8513.7 | 6443.4 | 4993.1 | 271.4 | 6539.5 | 271.4 | 6280.9 | 162.5
15.25 | 5304.1 | 6904.4 | 6104.3 | 4243.3 | 6630.2 | 5523.5 | 8630.5 | 6533 | 5028.4 | 275.8 | 6628.7 | 275.8 | 6367.9 | 165.1
15.5 | 5299.6 | 6953.9 | 6126.8 | 4239.7 | 6624.5 | 5563.1 | 8692.4 | 6609.2 | 5080.6 | 219 | 6734.9 | 219 | 6472.5 | 136.7
15.75 | 5826 | 7534.2 | 6680.1 | 4660.8 | 7282.5 | 6027.4 | 9417.8 | 7269.8 | 5119.5 | 706.5 | 6827.8 | 706.5 | 6563.3 | 706.5
16 | 5450.4 | 7212.9 | 6331.6 | 4360.3 | 6813 | 5770.3 | 9016.1 | 6844.8 | 5188.2 | 262.1 | 6950.7 | 262.1 | 6685.2 | 159.6
16.25 | 6104.8 | 7921.5 | 7013.2 | 4883.8 | 7630.9 | 6337.2 | 9901.9 | 7652.8 | 5223.1 | 881.6 | 7039.9 | 881.6 | 6771.2 | 881.6
16.5 | 5915.4 | 7786.8 | 6851.1 | 4732.3 | 7394.2 | 6229.4 | 9733.5 | 7516.8 | 5306.6 | 608.7 | 7178 | 608.7 | 6908.1 | 608.7
16.75 | 6117.8 | 8044.1 | 7081 | 4894.3 | 7647.3 | 6435.3 | 10055.1 | 7771.8 | 5383.3 | 734.5 | 7309.6 | 734.5 | 7037.2 | 734.5
17 | 5744.1 | 7726 | 6735.1 | 4595.2 | 7180.1 | 6180.8 | 9657.6 | 7355.2 | 5489 | 255.1 | 7470.9 | 255.1 | 7197.5 | 157.7
17.25 | 6210.8 | 8248.3 | 7229.5 | 4968.6 | 7763.5 | 6598.7 | 10310.4 | 7969.3 | 5462.7 | 748.1 | 7500.2 | 748.1 | 7221.2 | 748.1
17.5 | 6162.6 | 8255.6 | 7209.1 | 4930.1 | 7703.2 | 6604.5 | 10319.5 | 7974.9 | 5543.4 | 619.1 | 7636.5 | 619.1 | 7355.7 | 619.1
17.75 | 6241 | 8389.8 | 7315.4 | 4992.8 | 7801.3 | 6711.8 | 10487.2 | 8106.2 | 5573.5 | 667.6 | 7722.2 | 667.6 | 7438.7 | 667.6
18 | 5948 | 8152.5 | 7050.2 | 4758.4 | 7435 | 6522 | 10190.6 | 7728.3 | 5608.6 | 339.4 | 7813.1 | 339.4 | 7526.2 | 202.1
18.25 | 6322.3 | 8582.6 | 7452.4 | 5057.8 | 7902.9 | 6866 | 10728.2 | 8292.9 | 5651.6 | 670.7 | 7911.8 | 670.7 | 7622.2 | 670.7
18.5 | 6453.3 | 8769.3 | 7611.3 | 5162.7 | 8066.7 | 7015.5 | 10961.7 | 8477.3 | 5710.7 | 742.7 | 8026.6 | 742.7 | 7734.6 | 742.7
18.75 | 6462.8 | 8835 | 7648.9 | 5170.3 | 8078.5 | 7068 | 11043.7 | 8542.9 | 5803.4 | 659.4 | 8175.6 | 659.4 | 7883.5 | 659.4
19 | 6490.7 | 8919.2 | 7705 | 5192.6 | 8113.4 | 7135.4 | 11149 | 8624.5 | 5836.7 | 654 | 8265.2 | 654 | 7970.6 | 654
19.25 | 6125.4 | 8610.1 | 7367.7 | 4900.3 | 7656.7 | 6888.1 | 10762.6 | 8212.5 | 5858.5 | 266.9 | 8343.2 | 266.9 | 8045.2 | 167.3
19.5 | 6120.3 | 8661 | 7390.7 | 4896.2 | 7650.4 | 6928.8 | 10826.3 | 8266.2 | 5866.4 | 253.9 | 8407.2 | 253.9 | 8105.4 | 160.9
19.75 | 6157.9 | 8754.4 | 7456.2 | 4926.3 | 7697.4 | 7003.5 | 10943 | 8350.3 | 5889 | 268.9 | 8485.5 | 268.9 | 8181.1 | 169.2
20 | 6151.5 | 8803.6 | 7477.5 | 4921.2 | 7689.3 | 7042.8 | 11004.5 | 8386.4 | 5866.8 | 284.6 | 8518.9 | 284.6 | 8208.7 | 177.7
20.25 | 6148.5 | 8855.7 | 7502.1 | 4918.8 | 7685.6 | 7084.6 | 11069.7 | 8436.9 | 5868.1 | 280.3 | 8575.4 | 280.3 | 8261 | 175.9
20.5 | 6117.9 | 8880 | 7498.9 | 4894.3 | 7647.4 | 7104 | 11100 | 8460.1 | 5846.6 | 271.3 | 8608.7 | 271.3 | 8288.6 | 171.5
20.75 | 6656.9 | 9473.6 | 8065.3 | 5325.6 | 8321.2 | 7578.9 | 11842 | 9150.2 | 5917.4 | 739.5 | 8734.1 | 739.5 | 8410.7 | 739.5
21 | 6195 | 9066.6 | 7630.8 | 4956 | 7743.7 | 7253.2 | 11333.2 | 8639.2 | 5923.3 | 271.7 | 8794.9 | 271.7 | 8466.8 | 172.4
21.25 | 6197.9 | 9124 | 7661 | 4958.3 | 7747.4 | 7299.2 | 11405 | 8688.6 | 5918 | 279.9 | 8844.1 | 279.9 | 8511.5 | 177.1
21.5 | 6721.8 | 9702.2 | 8212 | 5377.4 | 8402.3 | 7761.7 | 12127.7 | 9365.1 | 5945.2 | 776.6 | 8925.6 | 776.6 | 8588.5 | 776.6
21.75 | 6863.1 | 9898.3 | 8380.7 | 5490.5 | 8578.9 | 7918.6 | 12372.8 | 9560.6 | 6084.2 | 778.9 | 9119.4 | 778.9 | 8781.8 | 778.9
22 | 6461.8 | 9552.6 | 8007.2 | 5169.5 | 8077.3 | 7642.1 | 11940.7 | 9103.3 | 6164.8 | 297.1 | 9255.5 | 297.1 | 8916 | 187.3
22.25 | 6495.3 | 9641.8 | 8068.5 | 5196.3 | 8119.2 | 7713.4 | 12052.2 | 9192.8 | 6204.2 | 291.1 | 9350.6 | 291.1 | 9008.3 | 184.5
22.5 | 7095.5 | 10297.6 | 8696.6 | 5676.4 | 8869.4 | 8238.1 | 12872 | 9951.8 | 6277.3 | 818.3 | 9479.4 | 818.3 | 9133.6 | 818.3
22.75 | 7514.5 | 10773.1 | 9143.8 | 6011.6 | 9393.2 | 8618.5 | 13466.4 | 10421.8 | 6427.4 | 1087.1 | 9686 | 1087.1 | 9334.7 | 1087.1
23 | 7484.7 | 10802 | 9143.3 | 5987.8 | 9355.9 | 8641.6 | 13502.5 | 10450.7 | 6678.7 | 806 | 9995.9 | 806 | 9644.6 | 806
23.25 | 7128.8 | 10506.1 | 8817.5 | 5703.1 | 8911 | 8404.9 | 13132.7 | 10043 | 6824.1 | 304.7 | 10201.5 | 304.7 | 9849.9 | 193.1
23.5 | 7796.4 | 11234.5 | 9515.5 | 6237.1 | 9745.5 | 8987.6 | 14043.1 | 10879.5 | 6979.1 | 817.4 | 10417.1 | 817.4 | 10062.2 | 817.4
23.75 | 7924.8 | 11424.6 | 9674.7 | 6339.8 | 9906 | 9139.7 | 14280.7 | 11067 | 7060.2 | 864.6 | 10559.9 | 864.6 | 10202.4 | 864.6
24 | 8238.1 | 11800.2 | 10019.2 | 6590.5 | 10297.7 | 9440.2 | 14750.2 | 11439.4 | 7163.7 | 1074.4 | 10725.8 | 1074.4 | 10364.9 | 1074.4
24.25 | 9688.4 | 13313.5 | 11501 | 7750.8 | 12110.6 | 10650.8 | 16641.9 | 11550.8 | 7238.1 | 2450.3 | 10863.2 | 2450.3 | 10445.5 | 1105.3
24.5 | 8698.1 | 12388.3 | 10543.2 | 6958.4 | 10872.6 | 9910.7 | 15485.4 | 11934 | 7487.9 | 1210.2 | 11178.1 | 1210.2 | 10723.8 | 1210.2
24.75 | 8981.2 | 12739.9 | 10860.5 | 7185 | 11226.5 | 10191.9 | 15924.8 | 11675.5 | 7750.3 | 1230.9 | 11508.9 | 1230.9 | 11050.5 | 625
25 | 9640.5 | 13469.6 | 11555 | 7712.4 | 12050.6 | 10775.7 | 16837 | 12017.3 | 7847.3 | 1793.1 | 11676.5 | 1793.1 | 11160.6 | 856.7
25.25 | 8897.2 | 12798.7 | 10848 | 7117.7 | 11121.5 | 10239 | 15998.4 | 12253.8 | 8098.1 | 799 | 11999.7 | 799 | 11454.8 | 799
25.5 | 8504.7 | 12480.7 | 10492.7 | 6803.8 | 10630.9 | 9984.6 | 15600.9 | 11826.4 | 8201.9 | 302.8 | 12177.9 | 302.8 | 11631.1 | 195.3
25.75 | 9106.7 | 13156.8 | 11131.8 | 7285.3 | 11383.3 | 10525.5 | 16446.1 | 12605.2 | 8255.4 | 851.3 | 12305.5 | 851.3 | 11753.9 | 851.3
26 | 8949.8 | 13074.9 | 11012.3 | 7159.8 | 11187.2 | 10459.9 | 16343.6 | 12265.7 | 8348 | 601.8 | 12473.1 | 601.8 | 11918.4 | 347.2
26.25 | 9775.4 | 13976.1 | 11875.8 | 7820.3 | 12219.3 | 11180.9 | 17470.1 | 13414 | 8529 | 1246.4 | 12729.7 | 1246.4 | 12167.6 | 1246.4
26.5 | 9073.3 | 13351 | 11212.2 | 7258.7 | 11341.7 | 10680.8 | 16688.7 | 12630.3 | 8665.9 | 407.5 | 12943.5 | 407.5 | 12378.6 | 251.7
26.75 | 9989.7 | 14344.6 | 12167.1 | 7991.8 | 12487.1 | 11475.7 | 17930.7 | 13772.9 | 8734.7 | 1255 | 13089.6 | 1255 | 12517.9 | 1255
27 | 9261.2 | 13694.3 | 11477.7 | 7409 | 11576.5 | 10955.4 | 17117.9 | 12984 | 8890.1 | 371.1 | 13323.1 | 371.1 | 12750.3 | 233.6
27.25 | 9190.3 | 13701.5 | 11445.9 | 7352.2 | 11487.8 | 10961.2 | 17126.9 | 12999.7 | 8853.7 | 336.6 | 13364.9 | 336.6 | 12784 | 215.7
27.5 | 9209.7 | 13798.5 | 11504.1 | 7367.7 | 11512.1 | 11038.8 | 17248.1 | 13063.8 | 8821.1 | 388.5 | 13409.9 | 388.5 | 12820.3 | 243.5
27.75 | 9792.1 | 14458.1 | 12125.1 | 7833.7 | 12240.1 | 11566.5 | 18072.6 | 13864.6 | 8898.9 | 893.2 | 13564.9 | 893.2 | 12971.4 | 893.2
28 | 9956.8 | 14700.7 | 12328.7 | 7965.4 | 12446 | 11760.5 | 18375.8 | 14107.1 | 9029.5 | 927.3 | 13773.3 | 927.3 | 13179.8 | 927.3
28.25 | 10073.6 | 14895.7 | 12484.6 | 8058.9 | 12592 | 11916.5 | 18619.6 | 14298.9 | 9125 | 948.6 | 13947.1 | 948.6 | 13350.3 | 948.6
28.5 | 11424.4 | 16325.6 | 13875 | 9139.5 | 14280.5 | 13060.4 | 20406.9 | 14587.5 | 9280.2 | 2144.2 | 14181.4 | 2144.2 | 13570.4 | 1017.1
28.75 | 26211.6 | 31208.1 | 28709.9 | 20969.3 | 32764.5 | 24966.5 | 39010.1 | 19847.4 | 10387.2 | 15824.5 | 15383.6 | 15824.5 | 14458.4 | 5389
29 | 33844.1 | 38982.1 | 36413.1 | 27075.3 | 42305.1 | 31185.6 | 48727.6 | 22028.7 | 11570.6 | 22273.5 | 16708.5 | 22273.5 | 14850.4 | 7178.3
29.25 | 32860.3 | 38189.2 | 35524.8 | 26288.3 | 41075.4 | 30551.4 | 47736.5 | 21858 | 12606.2 | 20254.2 | 17935.1 | 20254.2 | 15214.4 | 6643.6
29.5 | 34072 | 39639 | 36855.5 | 27257.6 | 42589.9 | 31711.2 | 49548.7 | 22288.7 | 13746.3 | 20325.6 | 19313.4 | 20325.6 | 15613.5 | 6675.2
29.75 | 44364 | 50215.1 | 47289.5 | 35491.2 | 55455 | 40172.1 | 62768.8 | 25109.6 | 14927.4 | 29436.6 | 20778.5 | 29436.6 | 16004.7 | 9105
30 | 45992.6 | 52177.8 | 49085.2 | 36794.1 | 57490.8 | 41742.2 | 65222.2 | 25600.7 | 15341 | 30651.6 | 21526.1 | 30651.6 | 16169.6 | 9431.1
30.25 | 42601.9 | 49112.8 | 45857.4 | 34081.6 | 53252.4 | 39290.3 | 61391 | 24819.3 | 15015.3 | 27586.7 | 21526.1 | 27586.7 | 16169.6 | 8649.7
30.5 | 39288.7 | 46111.7 | 42700.2 | 31430.9 | 49110.8 | 36889.4 | 57639.7 | 24037.9 | 14703.1 | 24585.6 | 21526.1 | 24585.6 | 16169.6 | 7868.3
30.75 | 36056 | 43178.3 | 39617.2 | 28844.8 | 45070 | 34542.7 | 53972.9 | 23256.6 | 14403.8 | 21652.2 | 21526.1 | 21652.2 | 16169.6 | 7087
31 | 32908.1 | 40317.3 | 36612.7 | 26326.5 | 41135.1 | 32253.9 | 50396.7 | 22475.2 | 14116.9 | 18791.2 | 21526.1 | 18791.2 | 16169.6 | 6305.6
31.25 | 29850 | 37534.5 | 33692.3 | 23880 | 37312.5 | 30027.6 | 46918.2 | 21693.8 | 13841.6 | 16008.4 | 21526.1 | 16008.4 | 16169.6 | 5524.2
31.5 | 26888.6 | 34837.2 | 30862.9 | 21510.9 | 33610.7 | 27869.8 | 43546.5 | 20912.5 | 13577.5 | 13311.1 | 21526.1 | 13311.1 | 16169.6 | 4742.9
31.75 | 24032.9 | 32235 | 28134 | 19226.3 | 30041.1 | 25788 | 40293.8 | 20131.1 | 13324 | 10708.9 | 21526.1 | 10708.9 | 16169.6 | 3961.5
32 | 21295.4 | 29741 | 25518.2 | 17036.3 | 26619.3 | 23792.8 | 37176.2 | 19349.7 | 13080.6 | 8214.9 | 21526.1 | 8214.9 | 16169.6 | 3180.1
32.25 | 18694.8 | 27374.2 | 23034.5 | 14955.8 | 23368.5 | 21899.3 | 34217.7 | 18568.4 | 12846.8 | 5848 | 21526.1 | 5848 | 16169.6 | 2398.8
32.5 | 16261 | 25165 | 20713 | 13008.8 | 20326.2 | 20132 | 31456.2 | 17787 | 12622.1 | 3638.9 | 21526.1 | 3638.9 | 16169.6 | 1617.4
32.75 | 14052.2 | 23172.1 | 18612.1 | 11241.7 | 17565.2 | 18537.7 | 28965.1 | 17005.6 | 12406.2 | 1645.9 | 21526.1 | 1645.9 | 16169.6 | 836
33 | 19399.4 | 34081.9 | 26740.7 | 15519.6 | 24249.3 | 27265.5 | 42602.4 | 14284 | 19337.2 | 62.3 | 34019.7 | 62.3 | 12425.2 | 1858.8
33.25 | 26077.4 | 41241.8 | 33659.6 | 20862 | 32596.8 | 32993.4 | 51552.2 | 21756.3 | 19518.5 | 6558.9 | 34682.8 | 6558.9 | 19103 | 2653.2
33.5 | 24934 | 40571.8 | 32752.9 | 19947.2 | 31167.5 | 32457.5 | 50714.8 | 21561.7 | 19577 | 5357 | 35214.8 | 5357 | 19316.9 | 2244.8
33.75 | 26572.2 | 42672.3 | 34622.2 | 21257.7 | 33215.2 | 34137.9 | 53340.4 | 22309.8 | 19661.4 | 6910.8 | 35761.6 | 6910.8 | 19530.1 | 2779.7
34 | 27606.2 | 44160.2 | 35883.2 | 22084.9 | 34507.7 | 35328.2 | 55200.3 | 22841.9 | 19784.5 | 7821.7 | 36338.6 | 7821.7 | 19755.4 | 3086.6
34.25 | 25155.8 | 42155.6 | 33655.7 | 20124.7 | 31444.8 | 33724.4 | 52694.4 | 22197.6 | 19833.3 | 5322.5 | 36833 | 5322.5 | 19954.8 | 2242.9
34.5 | 28647.8 | 46083.1 | 37365.4 | 22918.2 | 35809.7 | 36866.5 | 57603.8 | 23558.9 | 19925.5 | 8722.3 | 37360.7 | 8722.3 | 20168.9 | 3390
34.75 | 26005.7 | 43871.9 | 34938.8 | 20804.6 | 32507.1 | 35097.5 | 54839.9 | 22851.8 | 20100 | 5905.7 | 37966.2 | 5905.7 | 20398.7 | 2453.1
35 | 29208.5 | 47500.9 | 38354.7 | 23366.8 | 36510.6 | 38000.7 | 59376.1 | 29517.4 | 20409.5 | 8799 | 38701.9 | 8799 | 20718.4 | 8799
35.25 | 25959.1 | 44689.5 | 35324.3 | 20767.3 | 32448.9 | 35751.6 | 55861.9 | 26706 | 22165.3 | 3793.7 | 40895.8 | 3793.7 | 22912.3 | 3793.7
35.5 | 30849 | 50032.1 | 40440.5 | 24679.2 | 38561.3 | 40025.6 | 62540.1 | 32048.6 | 24073.9 | 6775.1 | 43257 | 6775.1 | 25273.5 | 6775.1

## SRD WTG-04
Depth (m) | SRD AH-FF (kN) | SRD AH-NFF (kN) | SRD MEAN (kN) | SRD AH-FF-LB (kN) | SRD AH-FF-UB (kN) | SRD AH-NFF-LB (kN) | SRD AH-NFF-UB (kN) | Static Cap (kN) | Shaft AH-FF (kN) | Tip AH-FF (kN) | Shaft AH-NFF (kN) | Tip AH-NFF (kN) | Shaft SC (kN) | Tip SC (kN)
0.5 | 105 | 105.5 | 105.2 | 84 | 131.2 | 84.4 | 131.9 | 105.5 | 25.3 | 79.7 | 25.9 | 79.7 | 25.9 | 79.7
0.75 | 117.2 | 118.4 | 117.8 | 93.8 | 146.5 | 94.8 | 148.1 | 118.4 | 37.5 | 79.7 | 38.8 | 79.7 | 38.8 | 79.7
1 | 135.7 | 137.8 | 136.8 | 108.5 | 169.6 | 110.3 | 172.3 | 137.8 | 56 | 79.7 | 58.2 | 79.7 | 58.2 | 79.7
1.25 | 147.5 | 150.8 | 149.2 | 118 | 184.4 | 120.6 | 188.5 | 150.8 | 67.9 | 79.7 | 71.1 | 79.7 | 71.1 | 79.7
1.5 | 117.7 | 122.1 | 119.9 | 94.1 | 147.1 | 97.7 | 152.6 | 107.7 | 83.4 | 34.3 | 87.8 | 34.3 | 87.8 | 19.9
1.75 | 214.6 | 220.3 | 217.5 | 171.7 | 268.2 | 176.3 | 275.4 | 220.3 | 97.8 | 116.8 | 103.6 | 116.8 | 103.6 | 116.8
2 | 280.3 | 287.6 | 283.9 | 224.2 | 350.3 | 230.1 | 359.5 | 287.6 | 131.4 | 148.9 | 138.7 | 148.9 | 138.7 | 148.9
2.25 | 218.3 | 227.5 | 222.9 | 174.7 | 272.9 | 182 | 284.4 | 190.1 | 138.7 | 79.6 | 147.9 | 79.6 | 147.3 | 42.8
2.5 | 236.4 | 247.5 | 242 | 189.1 | 295.5 | 198 | 309.4 | 204.2 | 147.3 | 89.1 | 158.3 | 89.1 | 156.3 | 47.9
2.75 | 247.3 | 260.3 | 253.8 | 197.8 | 309.1 | 208.3 | 325.4 | 215.2 | 155.4 | 91.9 | 168.4 | 91.9 | 165.3 | 49.8
3 | 259.3 | 274.4 | 266.8 | 207.4 | 324.1 | 219.5 | 343 | 225.4 | 161.4 | 97.9 | 176.5 | 97.9 | 172.1 | 53.3
3.25 | 304 | 321.2 | 312.6 | 243.2 | 380 | 256.9 | 401.4 | 250 | 166.8 | 137.2 | 184 | 137.2 | 178.5 | 71.5
3.5 | 267.9 | 287.3 | 277.6 | 214.3 | 334.9 | 229.9 | 359.2 | 250.4 | 193.5 | 74.4 | 213 | 74.4 | 206.9 | 43.4
3.75 | 385.7 | 407.6 | 396.7 | 308.6 | 482.1 | 326.1 | 509.5 | 401.3 | 212.4 | 173.3 | 234.3 | 173.3 | 228 | 173.3
4 | 418.1 | 442.6 | 430.3 | 334.5 | 522.6 | 354.1 | 553.3 | 436.1 | 242 | 176.1 | 266.6 | 176.1 | 260.1 | 176.1
4.25 | 450.5 | 478 | 464.2 | 360.4 | 563.1 | 382.4 | 597.4 | 471.3 | 272.4 | 178.1 | 299.9 | 178.1 | 293.3 | 178.1
4.5 | 484 | 514.7 | 499.4 | 387.2 | 605 | 411.8 | 643.4 | 508.1 | 308.4 | 175.6 | 339.1 | 175.6 | 332.5 | 175.6
4.75 | 403.6 | 437.7 | 420.7 | 322.9 | 504.6 | 350.2 | 547.2 | 401.5 | 327.8 | 75.9 | 361.9 | 75.9 | 355.1 | 46.4
5 | 590 | 627.7 | 608.9 | 472 | 737.5 | 502.2 | 784.6 | 619.6 | 361.9 | 228.1 | 399.6 | 228.1 | 391.5 | 228.1
5.25 | 506.6 | 548.2 | 527.4 | 405.2 | 633.2 | 438.6 | 685.3 | 492.9 | 394.7 | 111.9 | 436.3 | 111.9 | 427.6 | 65.3
5.5 | 584.9 | 630.8 | 607.8 | 467.9 | 731.1 | 504.6 | 788.5 | 553 | 431.2 | 153.7 | 477.1 | 153.7 | 467.3 | 85.8
5.75 | 739.5 | 790.2 | 764.8 | 591.6 | 924.3 | 632.1 | 987.7 | 778.2 | 512.9 | 226.5 | 563.6 | 226.5 | 551.7 | 226.5
6 | 1192.2 | 1248.5 | 1220.4 | 953.8 | 1490.3 | 998.8 | 1560.6 | 1235.1 | 576.7 | 615.5 | 633 | 615.5 | 619.6 | 615.5
6.25 | 883.1 | 945.8 | 914.4 | 706.5 | 1103.8 | 756.6 | 1182.2 | 932.4 | 654.7 | 228.3 | 717.5 | 228.3 | 704.1 | 228.3
6.5 | 811.4 | 881 | 846.2 | 649.1 | 1014.3 | 704.8 | 1101.3 | 814.8 | 683.5 | 127.9 | 753.2 | 127.9 | 739.1 | 75.7
6.75 | 956.4 | 1033.2 | 994.8 | 765.1 | 1195.5 | 826.5 | 1291.5 | 1019.1 | 730.1 | 226.3 | 806.9 | 226.3 | 792.8 | 226.3
7 | 1012 | 1096.3 | 1054.2 | 809.6 | 1265.1 | 877 | 1370.4 | 1081.7 | 768.1 | 243.9 | 852.3 | 243.9 | 837.7 | 243.9
7.25 | 1020.3 | 1112.2 | 1066.3 | 816.2 | 1275.4 | 889.8 | 1390.3 | 1096.9 | 783.1 | 237.2 | 875.1 | 237.2 | 859.7 | 237.2
7.5 | 1107.4 | 1207.2 | 1157.3 | 885.9 | 1384.2 | 965.8 | 1509 | 1191.5 | 838.5 | 268.8 | 938.4 | 268.8 | 922.7 | 268.8
7.75 | 1153.4 | 1261.5 | 1207.5 | 922.7 | 1441.7 | 1009.2 | 1576.9 | 1245.2 | 872.3 | 281.1 | 980.5 | 281.1 | 964.2 | 281.1
8 | 1187.8 | 1304.6 | 1246.2 | 950.2 | 1484.8 | 1043.7 | 1630.7 | 1166.1 | 926.3 | 261.5 | 1043.1 | 261.5 | 1023.8 | 142.3
8.25 | 1216.3 | 1342.4 | 1279.4 | 973 | 1520.4 | 1073.9 | 1678 | 1237.1 | 1016.7 | 199.6 | 1142.8 | 199.6 | 1122.8 | 114.3
8.5 | 1429.4 | 1565.5 | 1497.4 | 1143.5 | 1786.7 | 1252.4 | 1956.9 | 1543.7 | 1093.6 | 335.8 | 1229.7 | 335.8 | 1207.9 | 335.8
8.75 | 1471.1 | 1618 | 1544.6 | 1176.9 | 1838.9 | 1294.4 | 2022.5 | 1595.4 | 1157.7 | 313.4 | 1304.6 | 313.4 | 1281.9 | 313.4
9 | 1563.1 | 1721.3 | 1642.2 | 1250.5 | 1953.9 | 1377.1 | 2151.7 | 1698.5 | 1228.2 | 334.9 | 1386.4 | 334.9 | 1363.6 | 334.9
9.25 | 1844.9 | 2014.8 | 1929.9 | 1475.9 | 2306.1 | 1611.9 | 2518.6 | 1987.9 | 1253.6 | 591.3 | 1423.6 | 591.3 | 1396.6 | 591.3
9.5 | 1711.2 | 1893.3 | 1802.2 | 1368.9 | 2139 | 1514.7 | 2366.6 | 1857.9 | 1331.9 | 379.3 | 1514.1 | 379.3 | 1478.6 | 379.3
9.75 | 1743 | 1938.3 | 1840.6 | 1394.4 | 2178.7 | 1550.6 | 2422.8 | 1900.3 | 1416 | 327 | 1611.3 | 327 | 1573.3 | 327
10 | 1950.3 | 2159.3 | 2054.8 | 1560.2 | 2437.9 | 1727.4 | 2699.1 | 2120.2 | 1488.7 | 461.6 | 1697.7 | 461.6 | 1658.5 | 461.6
10.25 | 1758.1 | 1981.4 | 1869.7 | 1406.5 | 2197.6 | 1585.1 | 2476.7 | 1862 | 1563.9 | 194.2 | 1787.2 | 194.2 | 1746.2 | 115.9
10.5 | 2485 | 2723.1 | 2604.1 | 1988 | 3106.2 | 2178.5 | 3403.9 | 2214.1 | 1614.9 | 870.1 | 1853 | 870.1 | 1808 | 406.1
10.75 | 2378.8 | 2632.6 | 2505.7 | 1903.1 | 2973.6 | 2106.1 | 3290.7 | 2260.1 | 1747.7 | 631.1 | 2001.5 | 631.1 | 1948.1 | 312
11 | 2652.5 | 2924.3 | 2788.4 | 2122 | 3315.6 | 2339.4 | 3655.4 | 2505.3 | 1956.2 | 696.3 | 2228 | 696.3 | 2165.3 | 340
11.25 | 3166.5 | 3459.3 | 3312.9 | 2533.2 | 3958.1 | 2767.5 | 4324.2 | 3390.9 | 2144.3 | 1022.1 | 2437.2 | 1022.1 | 2368.7 | 1022.1
11.5 | 3209.3 | 3525.2 | 3367.3 | 2567.4 | 4011.6 | 2820.2 | 4406.6 | 3447.3 | 2336.3 | 873 | 2652.2 | 873 | 2574.3 | 873
11.75 | 3365.1 | 3706.5 | 3535.8 | 2692.1 | 4206.4 | 2965.2 | 4633.2 | 3628.6 | 2500.5 | 864.6 | 2841.9 | 864.6 | 2763.9 | 864.6
12 | 3569.8 | 3938.6 | 3754.2 | 2855.8 | 4462.2 | 3150.9 | 4923.3 | 3859.2 | 2709.4 | 860.4 | 3078.3 | 860.4 | 2998.9 | 860.4
12.25 | 3544.7 | 3943.5 | 3744.1 | 2835.8 | 4430.9 | 3154.8 | 4929.3 | 3860.2 | 2896.4 | 648.3 | 3295.1 | 648.3 | 3211.9 | 648.3
12.5 | 3602.6 | 4033.3 | 3818 | 2882.1 | 4503.3 | 3226.7 | 5041.7 | 3656.2 | 3017.8 | 584.9 | 3448.5 | 584.9 | 3355.6 | 300.5
12.75 | 3851.9 | 4316 | 4083.9 | 3081.5 | 4814.9 | 3452.8 | 5395 | 4221 | 3176.9 | 675 | 3640.9 | 675 | 3546 | 675
13 | 4110.8 | 4609.3 | 4360.1 | 3288.6 | 5138.5 | 3687.5 | 5761.7 | 4508 | 3308.8 | 802 | 3807.4 | 802 | 3706 | 802
13.25 | 4303.9 | 4839 | 4571.4 | 3443.1 | 5379.9 | 3871.2 | 6048.7 | 4737.6 | 3517.8 | 786.1 | 4052.8 | 786.1 | 3951.5 | 786.1
13.5 | 4362.9 | 4936.4 | 4649.7 | 3490.4 | 5453.7 | 3949.1 | 6170.5 | 4835.1 | 3680 | 682.9 | 4253.5 | 682.9 | 4152.1 | 682.9
13.75 | 4423.7 | 5036.7 | 4730.2 | 3538.9 | 5529.6 | 4029.4 | 6295.9 | 4935.3 | 3789.2 | 634.5 | 4402.2 | 634.5 | 4300.8 | 634.5
14 | 4561.9 | 5215.3 | 4888.6 | 3649.5 | 5702.3 | 4172.3 | 6519.2 | 5113.3 | 3928.7 | 633.2 | 4582.2 | 633.2 | 4480.2 | 633.2
14.25 | 4653.9 | 5349.3 | 5001.6 | 3723.1 | 5817.4 | 4279.4 | 6686.6 | 5245.1 | 4065.3 | 588.6 | 4760.7 | 588.6 | 4656.5 | 588.6
14.5 | 4483.9 | 5222.2 | 4853.1 | 3587.1 | 5604.9 | 4177.8 | 6527.8 | 4985.7 | 4171.8 | 312.1 | 4910.1 | 312.1 | 4803.1 | 182.6
14.75 | 4802.2 | 5584.1 | 5193.1 | 3841.7 | 6002.7 | 4467.3 | 6980.1 | 5475.1 | 4220.6 | 581.6 | 5002.5 | 581.6 | 4893.5 | 581.6
15 | 4950.7 | 5776.4 | 5363.6 | 3960.6 | 6188.4 | 4621.1 | 7220.5 | 5664.3 | 4311.2 | 639.5 | 5136.9 | 639.5 | 5024.8 | 639.5
15.25 | 5055.4 | 5925.8 | 5490.6 | 4044.3 | 6319.3 | 4740.6 | 7407.2 | 5810.9 | 4413.5 | 642 | 5283.8 | 642 | 5168.9 | 642
15.5 | 5192 | 6107.5 | 5649.8 | 4153.6 | 6489.9 | 4886 | 7634.4 | 5989.7 | 4470.1 | 721.9 | 5385.7 | 721.9 | 5267.8 | 721.9
15.75 | 5051.9 | 6013.2 | 5532.5 | 4041.5 | 6314.8 | 4810.6 | 7516.5 | 5671.8 | 4561.2 | 490.7 | 5522.5 | 490.7 | 5401.8 | 270
16 | 5540.6 | 6548.8 | 6044.7 | 4432.5 | 6925.7 | 5239 | 8186 | 6423.2 | 4752.6 | 787.9 | 5760.8 | 787.9 | 5635.2 | 787.9
16.25 | 5571.6 | 6628.4 | 6100 | 4457.3 | 6964.5 | 5302.7 | 8285.5 | 6502.8 | 4890 | 681.6 | 5946.8 | 681.6 | 5821.2 | 681.6
16.5 | 5549.5 | 6655.7 | 6102.6 | 4439.6 | 6936.9 | 5324.6 | 8319.7 | 6529.7 | 4984.7 | 564.8 | 6090.9 | 564.8 | 5964.9 | 564.8
16.75 | 5676.9 | 6832.8 | 6254.8 | 4541.5 | 7096.1 | 5466.2 | 8541 | 6703.5 | 5022.9 | 654 | 6178.8 | 654 | 6049.5 | 654
17 | 5863.3 | 7069.3 | 6466.3 | 4690.6 | 7329.1 | 5655.4 | 8836.6 | 6939.5 | 5124.7 | 738.6 | 6330.7 | 738.6 | 6200.8 | 738.6
17.25 | 6085.6 | 7342.6 | 6714.1 | 4868.5 | 7607 | 5874.1 | 9178.2 | 7212.8 | 5278.2 | 807.4 | 6535.2 | 807.4 | 6405.4 | 807.4
17.5 | 6454.8 | 7764 | 7109.4 | 5163.9 | 8068.5 | 6211.2 | 9705 | 7634.2 | 5433.4 | 1021.5 | 6742.5 | 1021.5 | 6612.7 | 1021.5
17.75 | 6072.9 | 7435.9 | 6754.4 | 4858.3 | 7591.1 | 5948.7 | 9294.9 | 7108.5 | 5616.5 | 456.4 | 6979.5 | 456.4 | 6849.2 | 259.3
18 | 6614.3 | 8032.6 | 7323.4 | 5291.4 | 8267.8 | 6426.1 | 10040.7 | 7900.6 | 5820 | 794.3 | 7238.3 | 794.3 | 7106.3 | 794.3
18.25 | 7084.4 | 8560.1 | 7822.2 | 5667.5 | 8855.4 | 6848.1 | 10700.2 | 8428.2 | 6050.7 | 1033.7 | 7526.5 | 1033.7 | 7394.5 | 1033.7
18.5 | 7439.6 | 8975.3 | 8207.4 | 5951.7 | 9299.5 | 7180.2 | 11219.1 | 8843.3 | 6296.4 | 1143.2 | 7832.1 | 1143.2 | 7700.1 | 1143.2
18.75 | 7713.8 | 9311.4 | 8512.6 | 6171 | 9642.2 | 7449.1 | 11639.2 | 9174.5 | 6461.9 | 1251.8 | 8059.5 | 1251.8 | 7922.7 | 1251.8
19 | 7651.2 | 9313 | 8482.1 | 6120.9 | 9563.9 | 7450.4 | 11641.2 | 8705 | 6701 | 950.2 | 8362.8 | 950.2 | 8221.7 | 483.4
19.25 | 7809.8 | 9538.1 | 8673.9 | 6247.8 | 9762.2 | 7630.5 | 11922.6 | 9395.5 | 6901.9 | 907.9 | 8630.2 | 907.9 | 8487.6 | 907.9
19.5 | 7737.6 | 9533.3 | 8635.5 | 6190.1 | 9672 | 7626.7 | 11916.7 | 9384.5 | 6967.3 | 770.3 | 8763 | 770.3 | 8614.2 | 770.3
19.75 | 7880.4 | 9743.9 | 8812.1 | 6304.3 | 9850.4 | 7795.1 | 12179.8 | 9588.4 | 6992.2 | 888.2 | 8855.7 | 888.2 | 8700.2 | 888.2
20 | 7863.2 | 9794.4 | 8828.8 | 6290.6 | 9829 | 7835.5 | 12243 | 9634.8 | 7048.6 | 814.6 | 8979.8 | 814.6 | 8820.2 | 814.6
20.25 | 7332.5 | 9331.3 | 8331.9 | 5866 | 9165.6 | 7465 | 11664.1 | 9046.4 | 7021 | 311.5 | 9019.8 | 311.5 | 8853.4 | 192.9
20.5 | 7352.2 | 9418 | 8385.1 | 5881.8 | 9190.2 | 7534.4 | 11772.5 | 9102.3 | 6995.7 | 356.5 | 9061.5 | 356.5 | 8885.9 | 216.3
20.75 | 7313.5 | 9446 | 8379.7 | 5850.8 | 9141.9 | 7556.8 | 11807.5 | 9137.9 | 6986.9 | 326.6 | 9119.4 | 326.6 | 8936.4 | 201.5
21 | 7744.4 | 9943.1 | 8843.7 | 6195.5 | 9680.5 | 7954.5 | 12428.9 | 9753.6 | 6984.5 | 759.9 | 9183.2 | 759.9 | 8993.8 | 759.9
21.25 | 7286.4 | 9551.2 | 8418.8 | 5829.1 | 9108 | 7641 | 11939 | 9240.6 | 6979.7 | 306.7 | 9244.5 | 306.7 | 9048.6 | 192
21.5 | 7258.8 | 9589.1 | 8424 | 5807 | 9073.5 | 7671.3 | 11986.4 | 9271.6 | 6951.2 | 307.5 | 9281.6 | 307.5 | 9078.8 | 192.8
21.75 | 7223.1 | 9618.5 | 8420.8 | 5778.5 | 9028.9 | 7694.8 | 12023.2 | 9297.5 | 6920.8 | 302.3 | 9316.3 | 302.3 | 9107.1 | 190.4
22 | 7239.9 | 9699.9 | 8469.9 | 5791.9 | 9049.9 | 7759.9 | 12124.8 | 9351.2 | 6893.3 | 346.6 | 9353.2 | 346.6 | 9137.4 | 213.8
22.25 | 7167.7 | 9691.6 | 8429.7 | 5734.2 | 8959.6 | 7753.3 | 12114.6 | 9357.7 | 6865.7 | 302 | 9389.7 | 302 | 9166.7 | 191
22.5 | 7173.1 | 9760.6 | 8466.8 | 5738.5 | 8966.3 | 7808.4 | 12200.7 | 9405.4 | 6841.1 | 332 | 9428.6 | 332 | 9198.3 | 207.1
22.75 | 7132.7 | 9783.3 | 8458 | 5706.2 | 8915.9 | 7826.6 | 12229.1 | 9428.2 | 6816 | 316.7 | 9466.6 | 316.7 | 9228.7 | 199.5
23 | 7136.5 | 9849.6 | 8493 | 5709.2 | 8920.6 | 7879.7 | 12312 | 9474.6 | 6793.1 | 343.3 | 9506.3 | 343.3 | 9260.9 | 213.7
23.25 | 7051 | 9826.3 | 8438.7 | 5640.8 | 8813.8 | 7861 | 12282.8 | 9473.1 | 6766.4 | 284.7 | 9541.6 | 284.7 | 9289.9 | 183.2
23.5 | 7018.8 | 9855.6 | 8437.2 | 5615 | 8773.5 | 7884.5 | 12319.5 | 9500 | 6741 | 277.8 | 9577.9 | 277.8 | 9320.2 | 179.8
23.75 | 7051.8 | 9949.8 | 8500.8 | 5641.5 | 8814.8 | 7959.9 | 12437.3 | 9560.8 | 6717.6 | 334.3 | 9615.5 | 334.3 | 9350.7 | 210.2
24 | 6989 | 9947.7 | 8468.3 | 5591.2 | 8736.2 | 7958.1 | 12434.6 | 9571.4 | 6695.6 | 293.4 | 9654.3 | 293.4 | 9382.6 | 188.8
24.25 | 6973 | 9991.9 | 8482.4 | 5578.4 | 8716.2 | 7993.5 | 12489.8 | 9605.8 | 6670.6 | 302.4 | 9689.5 | 302.4 | 9411.8 | 194
24.5 | 7000.4 | 10079.1 | 8539.8 | 5600.3 | 8750.5 | 8063.3 | 12598.9 | 9663.9 | 6650.7 | 349.7 | 9729.4 | 349.7 | 9444.5 | 219.4
24.75 | 6940.7 | 10078.7 | 8509.7 | 5552.5 | 8675.8 | 8063 | 12598.4 | 9674.9 | 6631.1 | 309.5 | 9769.2 | 309.5 | 9476.4 | 198.5
25 | 6912.6 | 10109.6 | 8511.1 | 5530.1 | 8640.8 | 8087.7 | 12637 | 9703.3 | 6610.8 | 301.9 | 9807.8 | 301.9 | 9508.6 | 194.7
25.25 | 6896.9 | 10152.4 | 8524.6 | 5517.5 | 8621.1 | 8121.9 | 12690.4 | 9737.2 | 6588.7 | 308.2 | 9844.2 | 308.2 | 9538.7 | 198.5
25.5 | 6863.3 | 10176.9 | 8520.1 | 5490.7 | 8579.2 | 8141.5 | 12721.1 | 9762.2 | 6569.6 | 293.8 | 9883.1 | 293.8 | 9571.2 | 191
25.75 | 6837.3 | 10208.5 | 8522.9 | 5469.8 | 8546.6 | 8166.8 | 12760.6 | 9790.1 | 6547 | 290.3 | 9918.2 | 290.3 | 9600.7 | 189.4
26 | 6856.1 | 10284.5 | 8570.3 | 5484.9 | 8570.1 | 8227.6 | 12855.6 | 9843.1 | 6531 | 325.1 | 9959.4 | 325.1 | 9634.5 | 208.5
26.25 | 7422.9 | 10908.2 | 9165.5 | 5938.3 | 9278.6 | 8726.5 | 13635.2 | 10574.6 | 6540.6 | 882.3 | 10025.9 | 882.3 | 9692.3 | 882.3
26.5 | 6905.8 | 10448.2 | 8677 | 5524.7 | 8632.3 | 8358.6 | 13060.2 | 9995.4 | 6586 | 319.9 | 10128.3 | 319.9 | 9789 | 206.4
26.75 | 6868.8 | 10467.9 | 8668.3 | 5495 | 8586 | 8374.3 | 13084.9 | 10017.4 | 6568.6 | 300.1 | 10167.8 | 300.1 | 9821.3 | 196
27 | 7437.4 | 11093 | 9265.2 | 5950 | 9296.8 | 8874.4 | 13866.3 | 10739.2 | 6573.9 | 863.5 | 10229.5 | 863.5 | 9875.7 | 863.5
27.25 | 6898 | 10609.9 | 8753.9 | 5518.4 | 8622.5 | 8487.9 | 13262.4 | 10141.1 | 6583.9 | 314.1 | 10295.9 | 314.1 | 9936.8 | 204.2
27.5 | 6890.7 | 10658.6 | 8774.7 | 5512.5 | 8613.4 | 8526.9 | 13323.3 | 10179.8 | 6570.3 | 320.4 | 10338.3 | 320.4 | 9971.9 | 208
27.75 | 6911 | 10734.6 | 8822.8 | 5528.8 | 8638.8 | 8587.7 | 13418.2 | 10232.3 | 6554.8 | 356.2 | 10378.4 | 356.2 | 10004.8 | 227.5
28 | 6902.7 | 10781.6 | 8842.2 | 5522.2 | 8628.4 | 8625.3 | 13477.1 | 10282.4 | 6567.2 | 335.5 | 10446.1 | 335.5 | 10065.7 | 216.8
28.25 | 6972.7 | 10906.7 | 8939.7 | 5578.1 | 8715.8 | 8725.4 | 13633.4 | 10361 | 6557.9 | 414.7 | 10492 | 414.7 | 10102 | 259
28.5 | 6956.8 | 10945.8 | 8951.3 | 5565.5 | 8696 | 8756.6 | 13682.2 | 10395.2 | 6551.8 | 405 | 10540.8 | 405 | 10140.8 | 254.3
28.75 | 7340.4 | 11383.9 | 9362.1 | 5872.3 | 9175.5 | 9107.1 | 14229.9 | 10975.5 | 6552.7 | 787.7 | 10596.2 | 787.7 | 10187.8 | 787.7
29 | 10261.8 | 14359.9 | 12310.8 | 8209.4 | 12827.2 | 11487.9 | 17949.9 | 11854.2 | 6621.8 | 3639.9 | 10720 | 3639.9 | 10263.9 | 1590.2
29.25 | 9804 | 13960 | 11882 | 7843.2 | 12254.9 | 11168 | 17450 | 13412.9 | 6914.9 | 2889 | 11071 | 2889 | 10523.8 | 2889
29.5 | 9852.1 | 14070.9 | 11961.5 | 7881.6 | 12315.1 | 11256.7 | 17588.7 | 11954.2 | 7168.5 | 2683.6 | 11387.3 | 2683.6 | 10716.6 | 1237.6
29.75 | 11624.6 | 15910.6 | 13767.6 | 9299.7 | 14530.7 | 12728.4 | 19888.2 | 15098.7 | 7399.6 | 4225 | 11685.5 | 4225 | 10873.7 | 4225
30 | 12925.9 | 17286.9 | 15106.4 | 10340.7 | 16157.4 | 13829.5 | 21608.6 | 13379.3 | 7883.1 | 5042.8 | 12244.1 | 5042.8 | 11279 | 2100.3
30.25 | 9960.9 | 14403.2 | 12182 | 7968.7 | 12451.1 | 11522.5 | 18004 | 13327.9 | 8186.6 | 1774.3 | 12628.8 | 1774.3 | 11553.5 | 1774.3
30.5 | 8895 | 13423.1 | 11159 | 7116 | 11118.7 | 10738.5 | 16778.9 | 12204.6 | 8506.2 | 388.8 | 13034.3 | 388.8 | 11955.6 | 248.9
30.75 | 8810 | 13423.7 | 11116.8 | 7048 | 11012.4 | 10738.9 | 16779.6 | 12222.8 | 8473 | 337 | 13086.7 | 337 | 12001.6 | 221.3
31 | 8774.2 | 13472.5 | 11123.4 | 7019.3 | 10967.7 | 10778 | 16840.7 | 12262.7 | 8434.6 | 339.6 | 13132.9 | 339.6 | 12039.7 | 223
31.25 | 8740.8 | 13522.7 | 11131.8 | 6992.6 | 10926 | 10818.2 | 16903.4 | 12302.5 | 8393.8 | 346.9 | 13175.8 | 346.9 | 12075.2 | 227.3
31.5 | 8713.5 | 13578.2 | 11145.8 | 6970.8 | 10891.9 | 10862.5 | 16972.7 | 12346.2 | 8359.7 | 353.8 | 13224.3 | 353.8 | 12114.8 | 231.4
31.75 | 8690.8 | 13637.2 | 11164 | 6952.6 | 10863.5 | 10909.8 | 17046.5 | 12390.9 | 8323.2 | 367.5 | 13269.7 | 367.5 | 12151.8 | 239.1
32 | 8683.2 | 13710.6 | 11196.9 | 6946.5 | 10853.9 | 10968.5 | 17138.3 | 12470.8 | 8340.5 | 342.6 | 13368 | 342.6 | 12245 | 225.8
32.25 | 8658.3 | 13766 | 11212.2 | 6926.6 | 10822.8 | 11012.8 | 17207.6 | 12513.7 | 8304.4 | 353.8 | 13412.2 | 353.8 | 12281.4 | 232.3
32.5 | 8641.6 | 13828.8 | 11235.2 | 6913.3 | 10802 | 11063 | 17286 | 12561.7 | 8273.6 | 368 | 13460.8 | 368 | 12321.3 | 240.3
32.75 | 8617.5 | 13883.3 | 11250.4 | 6894 | 10771.9 | 11106.6 | 17354.1 | 12604.2 | 8241.9 | 375.6 | 13507.7 | 375.6 | 12359.5 | 244.7
33 | 8539 | 13882.4 | 11210.7 | 6831.2 | 10673.7 | 11106 | 17353.1 | 12617.3 | 8210.1 | 328.9 | 13553.6 | 328.9 | 12397.9 | 219.4
33.25 | 8587.9 | 14008.2 | 11298.1 | 6870.3 | 10734.9 | 11206.6 | 17510.3 | 12698.7 | 8176.5 | 411.4 | 13596.9 | 411.4 | 12434 | 264.7
33.5 | 8579.9 | 14076.4 | 11328.1 | 6863.9 | 10724.9 | 11261.1 | 17595.5 | 12750.1 | 8161.5 | 418.4 | 13658 | 418.4 | 12481.2 | 268.8
33.75 | 8711.7 | 14283.6 | 11497.6 | 6969.3 | 10889.6 | 11426.9 | 17854.5 | 12872.6 | 8138.5 | 573.2 | 13710.4 | 573.2 | 12522.7 | 349.9
34 | 10874.9 | 16522.1 | 13698.5 | 8699.9 | 13593.6 | 13217.7 | 20652.6 | 15314.6 | 8262.6 | 2612.3 | 13909.8 | 2612.3 | 12702.3 | 2612.3
34.25 | 10623.5 | 16350.7 | 13487.1 | 8498.8 | 13279.4 | 13080.6 | 20438.4 | 15143.2 | 8917.8 | 1705.8 | 14644.9 | 1705.8 | 13437.4 | 1705.8
34.5 | 10894.2 | 16705.8 | 13800 | 8715.3 | 13617.7 | 13364.7 | 20882.3 | 15481.8 | 9063.1 | 1831.1 | 14874.7 | 1831.1 | 13650.7 | 1831.1
34.75 | 10869.6 | 16767.1 | 13818.4 | 8695.7 | 13587 | 13413.7 | 20958.9 | 15543.1 | 9381.3 | 1488.3 | 15278.8 | 1488.3 | 14054.8 | 1488.3
35 | 10565.7 | 16551 | 13558.4 | 8452.5 | 13207.1 | 13240.8 | 20688.8 | 14890.2 | 9587.8 | 977.9 | 15573.1 | 977.9 | 14340.6 | 549.5
35.25 | 15023.2 | 21098.2 | 18060.7 | 12018.6 | 18779 | 16878.5 | 26372.7 | 16717.1 | 9775.8 | 5247.5 | 15850.7 | 5247.5 | 14485.4 | 2231.7
35.5 | 18302.4 | 24473.9 | 21388.2 | 14641.9 | 22878 | 19579.1 | 30592.4 | 17909.4 | 10191.1 | 8111.3 | 16362.6 | 8111.3 | 14696.8 | 3212.6
35.75 | 30578.2 | 36867 | 33722.6 | 24462.6 | 38222.7 | 29493.6 | 46083.8 | 21705.9 | 11151.7 | 19426.5 | 17440.5 | 19426.5 | 15044.3 | 6661.7
36 | 44760.1 | 51211.7 | 47985.9 | 35808 | 55950.1 | 40969.4 | 64014.7 | 25615.1 | 12143.3 | 32616.7 | 18595 | 32616.7 | 15341.1 | 10274
36.25 | 34289.6 | 40915.9 | 37602.7 | 27431.6 | 42861.9 | 32732.7 | 51144.9 | 22841 | 11968.7 | 22320.9 | 18595 | 22320.9 | 15341.1 | 7499.9
36.5 | 24602.2 | 31398.1 | 28000.2 | 19681.7 | 30752.7 | 25118.5 | 39247.7 | 20066.9 | 11799 | 12803.1 | 18595 | 12803.1 | 15341.1 | 4725.9
36.75 | 16057.8 | 23018.5 | 19538.1 | 12846.2 | 20072.2 | 18414.8 | 28773.1 | 17292.9 | 11634.3 | 4423.5 | 18595 | 4423.5 | 15341.1 | 1951.8
37 | 27021.8 | 34867.3 | 30944.6 | 21617.5 | 33777.3 | 27893.8 | 43584.1 | 20770.7 | 15733.7 | 11288.2 | 23579.1 | 11288.2 | 16504.1 | 4266.6
37.25 | 23889.6 | 32065.5 | 27977.6 | 19111.7 | 29862 | 25652.4 | 40081.9 | 19879.1 | 16334 | 7555.6 | 24509.9 | 7555.6 | 16821.4 | 3057.6
37.5 | 31811.2 | 40339.3 | 36075.2 | 25449 | 39764 | 32271.4 | 50424.1 | 32608.1 | 18751.6 | 13059.6 | 27279.7 | 13059.6 | 19548.5 | 13059.6
37.75 | 29586.9 | 38522.4 | 34054.6 | 23669.5 | 36983.6 | 30817.9 | 48153 | 30704.3 | 21391.2 | 8195.7 | 30326.7 | 8195.7 | 22508.6 | 8195.7
38 | 37243.3 | 46656.5 | 41949.9 | 29794.6 | 46554.1 | 37325.2 | 58320.6 | 30533 | 24222.2 | 13021.1 | 33635.4 | 13021.1 | 25701.7 | 4831.3
38.25 | 32133.5 | 42049 | 37091.2 | 25706.8 | 40166.9 | 33639.2 | 52561.2 | 29077.2 | 24567.5 | 7566 | 34482.9 | 7566 | 26000.1 | 3077.1
38.5 | 30034.3 | 40450.8 | 35242.6 | 24027.4 | 37542.9 | 32360.7 | 50563.5 | 28558.7 | 24627.7 | 5406.6 | 35044.2 | 5406.6 | 26230.1 | 2328.5
38.75 | 27383.3 | 38293.7 | 32838.5 | 21906.6 | 34229.1 | 30635 | 47867.1 | 27776.6 | 24505.6 | 2877.6 | 35416.1 | 2877.6 | 26398.2 | 1378.4
39 | 27411.9 | 38805 | 33108.5 | 21929.5 | 34264.9 | 31044 | 48506.3 | 29693.7 | 24429.4 | 2982.5 | 35822.5 | 2982.5 | 26711.2 | 2982.5
39.25 | 26187.3 | 38053.8 | 32120.6 | 20949.8 | 32734.1 | 30443.1 | 47567.3 | 28869 | 24672.7 | 1514.6 | 36539.3 | 1514.6 | 27354.5 | 1514.6
39.5 | 25930 | 38262.6 | 32096.3 | 20744 | 32412.5 | 30610.1 | 47828.3 | 29075.1 | 24728.4 | 1201.6 | 37061 | 1201.6 | 27873.5 | 1201.6
39.75 | 26898.6 | 39684.6 | 33291.6 | 21518.9 | 33623.3 | 31747.7 | 49605.8 | 30481.2 | 24587.1 | 2311.5 | 37373.1 | 2311.5 | 28169.7 | 2311.5
40 | 27081.4 | 40311.7 | 33696.5 | 21665.1 | 33851.7 | 32249.4 | 50389.7 | 31089.1 | 24746.1 | 2335.3 | 37976.4 | 2335.3 | 28753.8 | 2335.3
40.25 | 28034.9 | 41702.5 | 34868.7 | 22427.9 | 35043.6 | 33362 | 52128.2 | 30680 | 24799.7 | 3235.1 | 38467.4 | 3235.1 | 29150.3 | 1529.7
40.5 | 30397.2 | 44496.4 | 37446.8 | 24317.8 | 37996.5 | 35597.1 | 55620.5 | 31756.5 | 24895 | 5502.2 | 38994.2 | 5502.2 | 29372.3 | 2384.2
40.75 | 35210.5 | 49740 | 42475.3 | 28168.4 | 44013.1 | 39792 | 62175 | 33584.3 | 25076 | 10134.5 | 39605.5 | 10134.5 | 29613.1 | 3971.2
41 | 31485.9 | 46449.1 | 38967.5 | 25188.7 | 39357.4 | 37159.2 | 58061.3 | 32574.9 | 25282 | 6203.9 | 40245.1 | 6203.9 | 29933.6 | 2641.4
41.25 | 50564.5 | 65970.4 | 58267.5 | 40451.6 | 63205.7 | 52776.3 | 82463 | 38604.3 | 26059.4 | 24505.2 | 41465.2 | 24505.2 | 30295.8 | 8308.5

## SRD WTG-05
Depth (m) | SRD AH-FF (kN) | SRD AH-NFF (kN) | SRD MEAN (kN) | SRD AH-FF-LB (kN) | SRD AH-FF-UB (kN) | SRD AH-NFF-LB (kN) | SRD AH-NFF-UB (kN) | Static Cap (kN) | Shaft AH-FF (kN) | Tip AH-FF (kN) | Shaft AH-NFF (kN) | Tip AH-NFF (kN) | Shaft SC (kN) | Tip SC (kN)
0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.25 | 100.7 | 100.7 | 100.7 | 80.6 | 125.9 | 80.6 | 125.9 | 45.6 | 2 | 98.7 | 2.1 | 98.7 | 1.9 | 43.7
1.5 | 599.7 | 600.2 | 600 | 479.8 | 749.6 | 480.2 | 750.3 | 595.4 | 52.5 | 547.2 | 53.1 | 547.2 | 48.2 | 547.2
1.75 | 671.9 | 676 | 674 | 537.5 | 839.9 | 540.8 | 845 | 670.3 | 169.8 | 502.1 | 173.8 | 502.1 | 168.1 | 502.1
2 | 797.3 | 807.8 | 802.5 | 637.8 | 996.6 | 646.3 | 1009.8 | 800 | 257.8 | 539.5 | 268.4 | 539.5 | 260.5 | 539.5
2.25 | 868.3 | 887.3 | 877.8 | 694.6 | 1085.4 | 709.9 | 1109.2 | 878.8 | 359.6 | 508.7 | 378.6 | 508.7 | 370.1 | 508.7
2.5 | 1202 | 1231.6 | 1216.8 | 961.6 | 1502.5 | 985.2 | 1539.4 | 705.9 | 422.1 | 780 | 451.6 | 780 | 421.2 | 284.8
2.75 | 1418.2 | 1461.3 | 1439.8 | 1134.6 | 1772.8 | 1169.1 | 1826.7 | 1417.1 | 528.9 | 889.3 | 572 | 889.3 | 527.8 | 889.3
3 | 1706 | 1766.6 | 1736.3 | 1364.8 | 2132.5 | 1413.3 | 2208.2 | 1084.9 | 710.7 | 995.3 | 771.3 | 995.3 | 723.2 | 361.7
3.25 | 1353.7 | 1434.8 | 1394.3 | 1082.9 | 1692.1 | 1147.9 | 1793.5 | 1078.5 | 837.3 | 516.4 | 918.4 | 516.4 | 865.9 | 212.6
3.5 | 1621.8 | 1726.2 | 1674 | 1297.5 | 2027.3 | 1380.9 | 2157.7 | 1261.2 | 942.4 | 679.5 | 1046.7 | 679.5 | 990.2 | 271
3.75 | 2064.7 | 2194 | 2129.4 | 1651.8 | 2580.9 | 1755.2 | 2742.5 | 1424.2 | 1001.9 | 1062.8 | 1131.2 | 1062.8 | 1025.2 | 399
4 | 1867.7 | 2024.8 | 1946.2 | 1494.1 | 2334.6 | 1619.9 | 2531 | 1470.9 | 1136.3 | 731.3 | 1293.5 | 731.3 | 1175.2 | 295.8
4.25 | 1765.2 | 1952.1 | 1858.7 | 1412.2 | 2206.5 | 1561.7 | 2440.2 | 1515.5 | 1220.2 | 545.1 | 1407.1 | 545.1 | 1281.4 | 234.1
4.5 | 2209.1 | 2427.3 | 2318.2 | 1767.3 | 2761.4 | 1941.9 | 3034.2 | 1765.8 | 1326.2 | 882.9 | 1544.4 | 882.9 | 1412.3 | 353.6
4.75 | 2283.4 | 2534.6 | 2409 | 1826.7 | 2854.2 | 2027.7 | 3168.3 | 2397.6 | 1467.4 | 816 | 1718.6 | 816 | 1581.6 | 816
5 | 3486.2 | 3774.6 | 3630.4 | 2789 | 4357.8 | 3019.7 | 4718.3 | 3582.7 | 1641.5 | 1844.7 | 1929.9 | 1844.7 | 1738 | 1844.7
5.25 | 3211.9 | 3544 | 3377.9 | 2569.5 | 4014.8 | 2835.2 | 4430 | 3341 | 1888.1 | 1323.8 | 2220.2 | 1323.8 | 2017.2 | 1323.8
5.5 | 3179.8 | 3561.9 | 3370.9 | 2543.8 | 3974.7 | 2849.6 | 4452.4 | 3359 | 2234.8 | 945 | 2617 | 945 | 2414 | 945
5.75 | 3324.5 | 3761.2 | 3542.9 | 2659.6 | 4155.7 | 3008.9 | 4701.5 | 3008.2 | 2389.6 | 935 | 2826.2 | 935 | 2620.4 | 387.9
6 | 3337.7 | 3830.4 | 3584 | 2670.1 | 4172.1 | 3064.3 | 4788 | 3168.6 | 2553.4 | 784.2 | 3046.2 | 784.2 | 2831.1 | 337.5
6.25 | 3706.9 | 4258.3 | 3982.6 | 2965.5 | 4633.6 | 3406.6 | 5322.8 | 4040.5 | 2755.1 | 951.8 | 3306.5 | 951.8 | 3088.7 | 951.8
6.5 | 3504.1 | 4117.2 | 3810.6 | 2803.3 | 4380.1 | 3293.7 | 5146.5 | 3899.4 | 2971.9 | 532.2 | 3584.9 | 532.2 | 3367.2 | 532.2
6.75 | 4212.1 | 4888.7 | 4550.4 | 3369.7 | 5265.2 | 3910.9 | 6110.9 | 4670.9 | 3128.2 | 1083.9 | 3804.8 | 1083.9 | 3587 | 1083.9
7 | 4365.6 | 5108.5 | 4737.1 | 3492.5 | 5457 | 4086.8 | 6385.6 | 4890.8 | 3367.7 | 997.9 | 4110.6 | 997.9 | 3892.8 | 997.9
7.25 | 4527.5 | 5340.6 | 4934 | 3622 | 5659.4 | 4272.4 | 6675.7 | 5122.8 | 3625.7 | 901.8 | 4438.8 | 901.8 | 4221.1 | 901.8
7.5 | 4820.9 | 5708.2 | 5264.5 | 3856.7 | 6026.1 | 4566.6 | 7135.3 | 5487.8 | 3893.5 | 927.3 | 4780.9 | 927.3 | 4560.5 | 927.3
7.75 | 4827.6 | 5792.9 | 5310.3 | 3862.1 | 6034.5 | 4634.3 | 7241.1 | 5572.5 | 4122 | 705.6 | 5087.3 | 705.6 | 4866.9 | 705.6
8 | 5179.3 | 6225.1 | 5702.2 | 4143.4 | 6474.1 | 4980.1 | 7781.4 | 6004.7 | 4358.8 | 820.5 | 5404.6 | 820.5 | 5184.2 | 820.5
8.25 | 5735.9 | 6865.1 | 6300.5 | 4588.7 | 7169.9 | 5492.1 | 8581.4 | 6644.7 | 4573 | 1162.9 | 5702.2 | 1162.9 | 5481.8 | 1162.9
8.5 | 6319.1 | 7534.8 | 6926.9 | 5055.3 | 7898.8 | 6027.8 | 9418.5 | 6406.8 | 4800.8 | 1518.3 | 6016.5 | 1518.3 | 5784.8 | 622
8.75 | 5829.6 | 7134.4 | 6482 | 4663.7 | 7287.1 | 5707.5 | 8918 | 6894.6 | 5035.1 | 794.5 | 6339.9 | 794.5 | 6100.1 | 794.5
9 | 6180.3 | 7577.6 | 6879 | 4944.3 | 7725.4 | 6062.1 | 9472 | 7337.8 | 5298.7 | 881.6 | 6696 | 881.6 | 6456.2 | 881.6
9.25 | 6404.5 | 7896.6 | 7150.6 | 5123.6 | 8005.7 | 6317.3 | 9870.8 | 7131.4 | 5452.6 | 952 | 6944.7 | 952 | 6703.6 | 427.7
9.5 | 6271.7 | 7860.2 | 7065.9 | 5017.4 | 7839.6 | 6288.1 | 9825.2 | 7612.7 | 5685.2 | 586.5 | 7273.6 | 586.5 | 7026.2 | 586.5
9.75 | 6603.7 | 8289.8 | 7446.8 | 5283 | 8254.7 | 6631.8 | 10362.2 | 8041.3 | 5755.8 | 847.9 | 7441.9 | 847.9 | 7193.4 | 847.9
10 | 6510.1 | 8294.2 | 7402.2 | 5208.1 | 8137.7 | 6635.4 | 10367.8 | 8045.7 | 5895.1 | 615.1 | 7679.2 | 615.1 | 7430.6 | 615.1
10.25 | 6525.1 | 8407.5 | 7466.3 | 5220.1 | 8156.4 | 6726 | 10509.4 | 8156.9 | 5980.4 | 544.7 | 7862.9 | 544.7 | 7612.3 | 544.7
10.5 | 6660.4 | 8640.8 | 7650.6 | 5328.3 | 8325.5 | 6912.7 | 10801.1 | 8388.8 | 6019.5 | 640.9 | 8000 | 640.9 | 7747.9 | 640.9
10.75 | 6778.9 | 8857.3 | 7818.1 | 5423.1 | 8473.7 | 7085.8 | 11071.6 | 8605.2 | 6114.3 | 664.6 | 8192.7 | 664.6 | 7940.6 | 664.6
11 | 6503.2 | 8679.6 | 7591.4 | 5202.6 | 8129 | 6943.7 | 10849.5 | 8294.9 | 6202 | 301.3 | 8378.3 | 301.3 | 8125.9 | 168.9
11.25 | 6953.8 | 9227.6 | 8090.7 | 5563.1 | 8692.3 | 7382 | 11534.5 | 8973.7 | 6223.4 | 730.5 | 8497.1 | 730.5 | 8243.3 | 730.5
11.5 | 6639.1 | 9009.9 | 7824.5 | 5311.3 | 8298.9 | 7207.9 | 11262.3 | 8596.1 | 6284.6 | 354.5 | 8655.4 | 354.5 | 8401.1 | 194.9
11.75 | 7006.2 | 9473.8 | 8240 | 5605 | 8757.7 | 7579.1 | 11842.3 | 9217.8 | 6408.6 | 597.6 | 8876.2 | 597.6 | 8620.2 | 597.6
12 | 7300 | 9864.9 | 8582.4 | 5840 | 9125 | 7891.9 | 12331.1 | 9608.9 | 6500.7 | 799.3 | 9065.7 | 799.3 | 8809.6 | 799.3
12.25 | 7285.6 | 9948.1 | 8616.9 | 5828.5 | 9107 | 7958.5 | 12435.1 | 9688.7 | 6595.4 | 690.2 | 9257.9 | 690.2 | 8998.5 | 690.2
12.5 | 7478 | 10238.3 | 8858.1 | 5982.4 | 9347.4 | 8190.6 | 12797.9 | 9977.2 | 6697.3 | 780.7 | 9457.6 | 780.7 | 9196.5 | 780.7
12.75 | 7783.1 | 10642 | 9212.6 | 6226.5 | 9728.9 | 8513.6 | 13302.5 | 10380.4 | 6854 | 929.1 | 9712.8 | 929.1 | 9451.3 | 929.1
13 | 7896.3 | 10854.4 | 9375.3 | 6317.1 | 9870.4 | 8683.5 | 13567.9 | 10591.1 | 6978.5 | 917.8 | 9936.5 | 917.8 | 9673.2 | 917.8
13.25 | 7709.5 | 10766.9 | 9238.2 | 6167.6 | 9636.9 | 8613.6 | 13458.7 | 10497.6 | 7069.8 | 639.7 | 10127.2 | 639.7 | 9857.9 | 639.7
13.5 | 7952.1 | 11109.1 | 9530.6 | 6361.7 | 9940.1 | 8887.3 | 13886.4 | 10837.7 | 7104.4 | 847.7 | 10261.5 | 847.7 | 9990.1 | 847.7
13.75 | 8628.3 | 11885.1 | 10256.7 | 6902.6 | 10785.4 | 9508.1 | 14856.4 | 11611.4 | 7255.6 | 1372.7 | 10512.5 | 1372.7 | 10238.8 | 1372.7
14 | 8300.3 | 11659.8 | 9980.1 | 6640.2 | 10375.4 | 9327.9 | 14574.8 | 11386.1 | 7559 | 741.3 | 10918.5 | 741.3 | 10644.8 | 741.3
14.25 | 8333 | 11796.4 | 10064.7 | 6666.4 | 10416.3 | 9437.1 | 14745.4 | 11522.7 | 7620.9 | 712.1 | 11084.2 | 712.1 | 10810.5 | 712.1
14.5 | 8257.2 | 11824 | 10040.6 | 6605.7 | 10321.5 | 9459.2 | 14780 | 11276.1 | 7683.9 | 573.3 | 11250.7 | 573.3 | 10973.3 | 302.8
14.75 | 8643.6 | 12314.7 | 10479.2 | 6914.9 | 10804.6 | 9851.8 | 15393.4 | 12036.6 | 7874.9 | 768.7 | 11546 | 768.7 | 11267.9 | 768.7
15 | 8801.6 | 12577.7 | 10689.6 | 7041.3 | 11002 | 10062.1 | 15722.1 | 12295.9 | 8034.1 | 767.6 | 11810.1 | 767.6 | 11528.3 | 767.6
15.25 | 9342.2 | 13223.9 | 11283.1 | 7473.7 | 11677.7 | 10579.2 | 16529.9 | 12939.9 | 8152.3 | 1189.8 | 12034.1 | 1189.8 | 11750.1 | 1189.8
15.5 | 9229.5 | 13218.6 | 11224 | 7383.6 | 11536.9 | 10574.9 | 16523.2 | 12934.6 | 8356 | 873.5 | 12345.1 | 873.5 | 12061.1 | 873.5
15.75 | 9366.7 | 13464.1 | 11415.4 | 7493.4 | 11708.4 | 10771.3 | 16830.1 | 13177.8 | 8522.9 | 843.8 | 12620.3 | 843.8 | 12333.9 | 843.8
16 | 9962.9 | 14169.7 | 12066.3 | 7970.3 | 12453.6 | 11335.8 | 17712.2 | 13877 | 8661.2 | 1301.6 | 12868.1 | 1301.6 | 12575.4 | 1301.6
16.25 | 10422.2 | 14741 | 12581.6 | 8337.7 | 13027.7 | 11792.8 | 18426.2 | 14448.2 | 8955.1 | 1467 | 13273.9 | 1467 | 12981.2 | 1467
16.5 | 10311.9 | 14745.7 | 12528.8 | 8249.5 | 12889.9 | 11796.6 | 18432.1 | 14452.9 | 9207.2 | 1104.7 | 13641 | 1104.7 | 13348.2 | 1104.7
16.75 | 10953.3 | 15504.1 | 13228.7 | 8762.6 | 13691.6 | 12403.2 | 19380.1 | 15211.3 | 9478.1 | 1475.2 | 14028.9 | 1475.2 | 13736.1 | 1475.2
17 | 11045.4 | 15716.7 | 13381 | 8836.3 | 13806.7 | 12573.3 | 19645.8 | 15420.5 | 9797.2 | 1248.2 | 14468.5 | 1248.2 | 14172.3 | 1248.2
17.25 | 11372.4 | 16167.6 | 13770 | 9097.9 | 14215.5 | 12934.1 | 20209.5 | 15871.4 | 10082.6 | 1289.8 | 14877.7 | 1289.8 | 14581.6 | 1289.8
17.5 | 11199.7 | 16121.4 | 13660.5 | 8959.7 | 13999.6 | 12897.1 | 20151.7 | 15825.2 | 10363.7 | 835.9 | 15285.5 | 835.9 | 14989.3 | 835.9
17.75 | 11604.3 | 16654.7 | 14129.5 | 9283.4 | 14505.4 | 13323.7 | 20818.3 | 16358.5 | 10548.7 | 1055.6 | 15599 | 1055.6 | 15302.9 | 1055.6
18 | 11721.5 | 16901.8 | 14311.6 | 9377.2 | 14651.8 | 13521.4 | 21127.2 | 16605.6 | 10735.3 | 986.2 | 15915.6 | 986.2 | 15619.5 | 986.2
18.25 | 11925.6 | 17236.7 | 14581.1 | 9540.5 | 14907 | 13789.3 | 21545.8 | 16940.5 | 10845.3 | 1080.3 | 16156.4 | 1080.3 | 15860.2 | 1080.3
18.5 | 11490.3 | 16932.3 | 14211.3 | 9192.3 | 14362.9 | 13545.8 | 21165.4 | 16388.3 | 10940.4 | 549.9 | 16382.4 | 549.9 | 16083.5 | 304.8
18.75 | 11831.7 | 17404.7 | 14618.2 | 9465.4 | 14789.6 | 13923.7 | 21755.8 | 17100.6 | 11053.5 | 778.2 | 16626.4 | 778.2 | 16322.4 | 778.2
19 | 11908.9 | 17612.8 | 14760.8 | 9527.1 | 14886.1 | 14090.2 | 22016 | 17307.5 | 11088.8 | 820.1 | 16792.7 | 820.1 | 16487.4 | 820.1
19.25 | 11919.3 | 17753.3 | 14836.3 | 9535.4 | 14899.1 | 14202.7 | 22191.7 | 17444.7 | 11108 | 811.2 | 16942.1 | 811.2 | 16633.5 | 811.2
19.5 | 11932.4 | 17895.8 | 14914.1 | 9545.9 | 14915.5 | 14316.7 | 22369.8 | 17583.4 | 11082.9 | 849.5 | 17046.3 | 849.5 | 16733.9 | 849.5
19.75 | 11876.9 | 17968.8 | 14922.9 | 9501.5 | 14846.1 | 14375.1 | 22461.1 | 17656.4 | 11141.2 | 735.7 | 17233.2 | 735.7 | 16920.7 | 735.7
20 | 11414 | 17633.7 | 14523.9 | 9131.2 | 14267.5 | 14107 | 22042.1 | 15520.2 | 11095.7 | 318.3 | 17315.4 | 318.3 | 8858.5 | 6661.7
20.25 | 11838.7 | 18184.6 | 15011.6 | 9471 | 14798.4 | 14547.7 | 22730.7 | 17862.8 | 11055.3 | 783.4 | 17401.2 | 783.4 | 17079.4 | 783.4
20.5 | 11906.9 | 18378.2 | 15142.6 | 9525.6 | 14883.7 | 14702.6 | 22972.7 | 18053.9 | 11098.6 | 808.3 | 17569.9 | 808.3 | 17245.6 | 808.3
20.75 | 12273.2 | 18869.6 | 15571.4 | 9818.6 | 15341.6 | 15095.7 | 23587 | 18545.4 | 11191.8 | 1081.4 | 17788.2 | 1081.4 | 17464 | 1081.4
21 | 12195.6 | 18917.5 | 15556.6 | 9756.5 | 15244.5 | 15134 | 23646.9 | 18587 | 11356.5 | 839.1 | 18078.4 | 839.1 | 17747.9 | 839.1
21.25 | 12231.2 | 19078.9 | 15655.1 | 9785 | 15289.1 | 15263.1 | 23848.6 | 18745.9 | 11381.1 | 850.2 | 18228.7 | 850.2 | 17895.7 | 850.2
21.5 | 11752.9 | 18725.6 | 15239.3 | 9402.3 | 14691.1 | 14980.5 | 23407 | 17039.2 | 11383.7 | 369.2 | 18356.4 | 369.2 | 9407.7 | 7631.5
21.75 | 12301 | 19398 | 15849.5 | 9840.8 | 15376.3 | 15518.4 | 24247.4 | 19054.9 | 11425.1 | 876 | 18522 | 876 | 18178.9 | 876
22 | 12329.6 | 19551 | 15940.3 | 9863.7 | 15412 | 15640.8 | 24438.7 | 19205.5 | 11534 | 795.6 | 18755.3 | 795.6 | 18409.9 | 795.6
22.25 | 11785.5 | 19130.6 | 15458 | 9428.4 | 14731.9 | 15304.5 | 23913.2 | 16672 | 11453.8 | 331.8 | 18798.8 | 331.8 | 9650.5 | 7021.5
22.5 | 12246.2 | 19713.7 | 15980 | 9797 | 15307.8 | 15771 | 24642.1 | 19358.4 | 11460.1 | 786.1 | 18927.6 | 786.1 | 18572.3 | 786.1
22.75 | 11859.6 | 19449.1 | 15654.4 | 9487.7 | 14824.6 | 15559.3 | 24311.4 | 16944 | 11523.3 | 336.4 | 19112.7 | 336.4 | 9814.8 | 7129.3
23 | 12401.9 | 20112.7 | 16257.3 | 9921.5 | 15502.4 | 16090.2 | 25140.9 | 19754.6 | 11563.3 | 838.6 | 19274.1 | 838.6 | 18915.9 | 838.6
23.25 | 12432 | 20263.8 | 16347.9 | 9945.6 | 15540 | 16211 | 25329.7 | 19901.1 | 11599.9 | 832.1 | 19431.7 | 832.1 | 19069 | 832.1
23.5 | 12435.9 | 20387.9 | 16411.9 | 9948.7 | 15544.8 | 16310.3 | 25484.9 | 20019.1 | 11574.2 | 861.7 | 19526.2 | 861.7 | 19157.4 | 861.7
23.75 | 12007.6 | 20079.6 | 16043.6 | 9606.1 | 15009.5 | 16063.7 | 25099.5 | 17259.4 | 11675.6 | 332 | 19747.6 | 332 | 10155.1 | 7104.2
24 | 12493.1 | 20684.5 | 16588.8 | 9994.5 | 15616.4 | 16547.6 | 25855.7 | 20312.4 | 11692.9 | 800.2 | 19884.4 | 800.2 | 19512.2 | 800.2
24.25 | 12463.8 | 20774.2 | 16619 | 9971.1 | 15579.8 | 16619.3 | 25967.7 | 20398.8 | 11682.9 | 780.9 | 19993.2 | 780.9 | 19617.8 | 780.9
24.5 | 11973 | 20401.1 | 16187.1 | 9578.4 | 14966.3 | 16320.9 | 25501.3 | 17743.5 | 11625.9 | 347.2 | 20053.9 | 347.2 | 10331.3 | 7412.1
24.75 | 12516.5 | 21061.3 | 16788.9 | 10013.2 | 15645.7 | 16849 | 26326.6 | 20678.2 | 11665.7 | 850.8 | 20210.5 | 850.8 | 19827.4 | 850.8
25 | 11945.1 | 20606 | 16275.5 | 9556.1 | 14931.4 | 16484.8 | 25757.5 | 17366.7 | 11627.5 | 317.5 | 20288.5 | 317.5 | 10462.6 | 6904.1
25.25 | 12020.3 | 20796.1 | 16408.2 | 9616.3 | 15025.4 | 16636.9 | 25995.1 | 19569.3 | 11581.1 | 439.3 | 20356.9 | 439.3 | 10506.2 | 9063.1
25.5 | 11911.8 | 20801.6 | 16356.7 | 9529.4 | 14889.7 | 16641.3 | 26002 | 17643.7 | 11586.4 | 325.4 | 20476.2 | 325.4 | 10574.1 | 7069.6
25.75 | 12442.4 | 21445.5 | 16944 | 9953.9 | 15553 | 17156.4 | 26806.9 | 21044.9 | 11622.5 | 819.8 | 20625.7 | 819.8 | 20225.1 | 819.8
26 | 11893.5 | 21009.2 | 16451.4 | 9514.8 | 14866.8 | 16807.4 | 26261.6 | 17801.6 | 11567.2 | 326.2 | 20683 | 326.2 | 10693.5 | 7108.1
26.25 | 11819 | 21046.1 | 16432.5 | 9455.2 | 14773.7 | 16836.9 | 26307.6 | 17808.4 | 11494.7 | 324.2 | 20721.9 | 324.2 | 10725.3 | 7083.1
26.5 | 11750.6 | 21087.8 | 16419.2 | 9400.5 | 14688.3 | 16870.2 | 26359.7 | 17867.2 | 11425.6 | 325 | 20762.8 | 325 | 10759.2 | 7108.1
26.75 | 12821.4 | 22267.5 | 17544.4 | 10257.1 | 16026.7 | 17814 | 27834.4 | 21835.1 | 11407.5 | 1413.9 | 20853.7 | 1413.9 | 20421.2 | 1413.9
27 | 13591.5 | 23148.2 | 18369.9 | 10873.2 | 16989.4 | 18518.5 | 28935.2 | 22715.7 | 11759.9 | 1831.6 | 21316.6 | 1831.6 | 20884.1 | 1831.6
27.25 | 14377.7 | 24047.8 | 19212.7 | 11502.2 | 17972.1 | 19238.2 | 30059.7 | 23599.4 | 12067.5 | 2310.2 | 21737.6 | 2310.2 | 21289.3 | 2310.2
27.5 | 13552.6 | 23340.8 | 18446.7 | 10842.1 | 16940.7 | 18672.6 | 29176 | 22892.4 | 12508 | 1044.5 | 22296.2 | 1044.5 | 21847.9 | 1044.5
27.75 | 13541.6 | 23450.2 | 18495.9 | 10833.2 | 16926.9 | 18760.1 | 29312.7 | 23001.8 | 12693.4 | 848.1 | 22602 | 848.1 | 22153.7 | 848.1
28 | 13620.2 | 23648.9 | 18634.6 | 10896.1 | 17025.2 | 18919.1 | 29561.2 | 23195.8 | 12687.4 | 932.8 | 22716.2 | 932.8 | 22263.1 | 932.8
28.25 | 13595.1 | 23743.4 | 18669.2 | 10876.1 | 16993.8 | 18994.7 | 29679.3 | 23287.8 | 12728.2 | 866.9 | 22876.5 | 866.9 | 22420.8 | 866.9
28.5 | 13581.5 | 23848.9 | 18715.2 | 10865.2 | 16976.8 | 19079.2 | 29811.2 | 23388.7 | 12735.1 | 846.3 | 23002.6 | 846.3 | 22542.4 | 846.3
28.75 | 13006.5 | 23392.2 | 18199.4 | 10405.2 | 16258.1 | 18713.8 | 29240.2 | 19145.1 | 12683.6 | 322.9 | 23069.2 | 322.9 | 11975.4 | 7169.7
29 | 12930.7 | 23433.2 | 18182 | 10344.5 | 16163.3 | 18746.6 | 29291.6 | 19172.6 | 12608.7 | 322 | 23111.3 | 322 | 12010.6 | 7162
29.25 | 12860.9 | 23479.1 | 18170 | 10288.7 | 16076.1 | 18783.3 | 29348.9 | 19332.5 | 12532.6 | 328.3 | 23150.8 | 328.3 | 12043.5 | 7289
29.5 | 12799.5 | 23532 | 18165.8 | 10239.6 | 15999.4 | 18825.6 | 29415 | 19523.6 | 12463.5 | 336 | 23196 | 336 | 12080.6 | 7442.9
29.75 | 13518.2 | 24364.2 | 18941.2 | 10814.6 | 16897.8 | 19491.4 | 30455.2 | 23873.7 | 12509 | 1009.2 | 23354.9 | 1009.2 | 22864.4 | 1009.2
30 | 15242.6 | 26202.1 | 20722.3 | 12194 | 19053.2 | 20961.6 | 32752.6 | 24267.4 | 12606.4 | 2636.1 | 23565.9 | 2636.1 | 23046 | 1221.4
30.25 | 14293.4 | 25369.5 | 19831.4 | 11434.7 | 17866.7 | 20295.6 | 31711.8 | 24832.1 | 13067.5 | 1225.8 | 24143.7 | 1225.8 | 23606.3 | 1225.8
30.5 | 15976.9 | 27173.2 | 21575 | 12781.5 | 19971.1 | 21738.5 | 33966.5 | 26606.7 | 13271.4 | 2705.5 | 24467.7 | 2705.5 | 23901.2 | 2705.5
30.75 | 15770.6 | 27092.5 | 21431.5 | 12616.4 | 19713.2 | 21674 | 33865.6 | 26501.5 | 13844.4 | 1926.2 | 25166.3 | 1926.2 | 24575.4 | 1926.2
31 | 15278.2 | 26731.9 | 21005.1 | 12222.6 | 19097.8 | 21385.5 | 33414.9 | 26141 | 14325.6 | 952.7 | 25779.3 | 952.7 | 25188.3 | 952.7
31.25 | 16777.6 | 28364.5 | 22571.1 | 13422.1 | 20972 | 22691.6 | 35455.7 | 27698.7 | 14469.2 | 2308.4 | 26056.2 | 2308.4 | 25390.3 | 2308.4
31.5 | 16543.2 | 28268.4 | 22405.8 | 13234.6 | 20679 | 22614.7 | 35335.5 | 26727.7 | 14869.3 | 1673.9 | 26594.5 | 1673.9 | 25884 | 843.7
31.75 | 15620.2 | 27486.4 | 21553.3 | 12496.2 | 19525.3 | 21989.1 | 34358 | 22563.1 | 15233.5 | 386.7 | 27099.7 | 386.7 | 14088.8 | 8474.3
32 | 16060.4 | 28068.6 | 22064.5 | 12848.3 | 20075.5 | 22454.9 | 35085.7 | 26980.8 | 15226.9 | 833.6 | 27235 | 833.6 | 26507.7 | 473.2
32.25 | 17425 | 29575.4 | 23500.2 | 13940 | 21781.3 | 23660.3 | 36969.3 | 27821.7 | 15429.2 | 1995.9 | 27579.6 | 1995.9 | 26840.9 | 980.8
32.5 | 17539.6 | 29833.6 | 23686.6 | 14031.7 | 21924.6 | 23866.8 | 37291.9 | 28125.9 | 15672.7 | 1866.9 | 27966.6 | 1866.9 | 27196.9 | 929
32.75 | 19310.5 | 31750.2 | 25530.4 | 15448.4 | 24138.2 | 25400.2 | 39687.8 | 28928.5 | 15782.3 | 3528.3 | 28222 | 3528.3 | 27347.2 | 1581.3
33 | 18188.7 | 30776.6 | 24482.7 | 14551 | 22735.9 | 24621.3 | 38470.8 | 28583.4 | 15887.4 | 2301.3 | 28475.3 | 2301.3 | 27474.2 | 1109.2
33.25 | 19226.4 | 31964.3 | 25595.3 | 15381.1 | 24033 | 25571.4 | 39955.4 | 29277.8 | 16148.3 | 3078.1 | 28886.2 | 3078.1 | 27862.6 | 1415.2
33.5 | 27485.5 | 40382.2 | 33933.9 | 21988.4 | 34356.8 | 32305.8 | 50477.8 | 32151.8 | 16694 | 10791.4 | 29590.8 | 10791.4 | 28120 | 4031.8
33.75 | 29881.3 | 42958.5 | 36419.9 | 23905 | 37351.6 | 34366.8 | 53698.1 | 32978.7 | 17393.3 | 12488 | 30470.5 | 12488 | 28418.1 | 4560.6
34 | 22792.7 | 36070.4 | 29431.5 | 18234.1 | 28490.8 | 28856.3 | 45087.9 | 30781.1 | 17780.7 | 5012 | 31058.4 | 5012 | 28646.8 | 2134.4
34.25 | 22677.7 | 36161.6 | 29419.6 | 18142.1 | 28347.1 | 28929.2 | 45202 | 30845.6 | 17989.2 | 4688.5 | 31473.1 | 4688.5 | 28823.7 | 2021.9
34.5 | 24255 | 37949.6 | 31102.3 | 19404 | 30318.7 | 30359.7 | 47437 | 31510.5 | 18248.2 | 6006.8 | 31942.8 | 6006.8 | 29021.3 | 2489.3
34.75 | 25091.6 | 39003.2 | 32047.4 | 20073.3 | 31364.5 | 31202.6 | 48754 | 31907.7 | 18507.3 | 6584.3 | 32418.9 | 6584.3 | 29216.7 | 2691.1
35 | 38257 | 52398.6 | 45327.8 | 30605.6 | 47821.2 | 41918.9 | 65498.3 | 36063.2 | 19262.3 | 18994.6 | 33404 | 18994.6 | 29546.7 | 6516.4
35.25 | 30817.3 | 45221.3 | 38019.3 | 24653.8 | 38521.6 | 36177.1 | 56526.7 | 33959.9 | 19974 | 10843.3 | 34378.1 | 10843.3 | 29869.6 | 4090.3
35.5 | 33663.4 | 48352.4 | 41007.9 | 26930.7 | 42079.3 | 38681.9 | 60440.5 | 34959.2 | 20767.8 | 12895.6 | 35456.7 | 12895.6 | 30226.3 | 4732.9
35.75 | 43568.5 | 58570.5 | 51069.5 | 34854.8 | 54460.6 | 46856.4 | 73213.2 | 37965.8 | 21419.7 | 22148.8 | 36421.8 | 22148.8 | 30527.3 | 7438.5
36 | 40325.7 | 55647 | 47986.3 | 32260.6 | 50407.1 | 44517.6 | 69558.7 | 37145.1 | 21100.5 | 19225.2 | 36421.8 | 19225.2 | 30527.3 | 6617.9
36.25 | 37170.3 | 52802 | 44986.2 | 29736.3 | 46462.9 | 42241.6 | 66002.5 | 36324.5 | 20790.1 | 16380.2 | 36421.8 | 16380.2 | 30527.3 | 5797.2
36.5 | 34109.7 | 50043.2 | 42076.5 | 27287.8 | 42637.1 | 40034.6 | 62554 | 35503.9 | 20488.3 | 13621.4 | 36421.8 | 13621.4 | 30527.3 | 4976.6
36.75 | 31153.4 | 47380.6 | 39267 | 24922.7 | 38941.8 | 37904.5 | 59225.7 | 34683.2 | 20194.7 | 10958.8 | 36421.8 | 10958.8 | 30527.3 | 4156
37 | 28314.8 | 44827.6 | 36571.2 | 22651.8 | 35393.5 | 35862.1 | 56034.5 | 33862.6 | 19909 | 8405.8 | 36421.8 | 8405.8 | 30527.3 | 3335.4
37.25 | 25613.2 | 42403.9 | 34008.5 | 20490.5 | 32016.4 | 33923.1 | 53004.9 | 33042 | 19631 | 5982.1 | 36421.8 | 5982.1 | 30527.3 | 2514.7
37.5 | 23079.7 | 40141 | 31610.4 | 18463.8 | 28849.7 | 32112.8 | 50176.3 | 32221.4 | 19360.5 | 3719.3 | 36421.8 | 3719.3 | 30527.3 | 1694.1
37.75 | 20774.8 | 38099.4 | 29437.1 | 16619.8 | 25968.4 | 30479.5 | 47624.2 | 31400.7 | 19097.1 | 1677.6 | 36421.8 | 1677.6 | 30527.3 | 873.5
38 | 24014.8 | 43638.4 | 33826.6 | 19211.9 | 30018.5 | 34910.7 | 54548 | 21436.8 | 23957 | 57.8 | 43580.6 | 57.8 | 19639.6 | 1797.2
38.25 | 25197.5 | 45243.8 | 35220.7 | 20158 | 31496.9 | 36195.1 | 56554.8 | 34153.9 | 23818.1 | 1379.5 | 43864.4 | 1379.5 | 32774.5 | 1379.5
38.5 | 25905.1 | 46363.5 | 36134.3 | 20724.1 | 32381.4 | 37090.8 | 57954.4 | 35273.6 | 24048.6 | 1856.5 | 44507 | 1856.5 | 33417.1 | 1856.5
38.75 | 25741.4 | 46605.4 | 36173.4 | 20593.1 | 32176.8 | 37284.3 | 58256.8 | 35515.5 | 24416.7 | 1324.7 | 45280.7 | 1324.7 | 34190.8 | 1324.7
39 | 25946.7 | 47208.4 | 36577.5 | 20757.3 | 32433.4 | 37766.7 | 59010.5 | 36118.5 | 24591.2 | 1355.5 | 45852.9 | 1355.5 | 34763 | 1355.5
39.25 | 26383.5 | 48034.6 | 37209 | 21106.8 | 32979.4 | 38427.6 | 60043.2 | 36944.7 | 24731.4 | 1652.1 | 46382.4 | 1652.1 | 35292.5 | 1652.1
39.5 | 26742.8 | 48775.7 | 37759.2 | 21394.2 | 33428.5 | 39020.6 | 60969.6 | 37685.8 | 24963.7 | 1779.1 | 46996.6 | 1779.1 | 35906.7 | 1779.1
39.75 | 26833.1 | 49242.3 | 38037.7 | 21466.4 | 33541.3 | 39393.8 | 61552.9 | 38152.4 | 25339.1 | 1494 | 47748.3 | 1494 | 36658.4 | 1494
40 | 27165.3 | 49945.2 | 38555.2 | 21732.2 | 33956.6 | 39956.1 | 62431.5 | 38855.3 | 25579 | 1586.3 | 48358.9 | 1586.3 | 37269 | 1586.3
40.25 | 35098.4 | 58244.3 | 46671.4 | 28078.8 | 43873 | 46595.5 | 72805.4 | 41384.1 | 25859.6 | 9238.8 | 49005.5 | 9238.8 | 37725.7 | 3658.4
40.5 | 32490.4 | 56016.5 | 44253.4 | 25992.3 | 40613 | 44813.2 | 70020.6 | 44652.3 | 27871.8 | 4618.6 | 51397.9 | 4618.6 | 40033.7 | 4618.6
40.75 | 31734.8 | 55670.7 | 43702.8 | 25387.8 | 39668.5 | 44536.6 | 69588.4 | 44306.6 | 30031.5 | 1703.3 | 53967.5 | 1703.3 | 42603.3 | 1703.3
41 | 31965.4 | 56323.1 | 44144.3 | 25572.3 | 39956.8 | 45058.5 | 70403.9 | 44958.9 | 30633 | 1332.4 | 54990.7 | 1332.4 | 43626.6 | 1332.4
41.25 | 32141.9 | 56916.2 | 44529 | 25713.5 | 40177.3 | 45532.9 | 71145.2 | 45552 | 30828 | 1313.8 | 55602.3 | 1313.8 | 44238.2 | 1313.8
41.5 | 31928.5 | 57113.8 | 44521.2 | 25542.8 | 39910.7 | 45691 | 71392.2 | 45749.6 | 31041 | 887.5 | 56226.3 | 887.5 | 44862.1 | 887.5
41.75 | 32514.2 | 58104.6 | 45309.4 | 26011.4 | 40642.8 | 46483.7 | 72630.7 | 46740.4 | 31253.4 | 1260.9 | 56843.7 | 1260.9 | 45479.5 | 1260.9
42 | 32841.2 | 58831.3 | 45836.2 | 26272.9 | 41051.5 | 47065 | 73539.1 | 47467.1 | 31440.4 | 1400.7 | 57430.5 | 1400.7 | 46066.4 | 1400.7
42.25 | 32962.2 | 59346.9 | 46154.6 | 26369.8 | 41202.8 | 47477.5 | 74183.6 | 47982.7 | 31662.9 | 1299.4 | 58047.6 | 1299.4 | 46683.4 | 1299.4
42.5 | 33561.2 | 60336 | 46948.6 | 26848.9 | 41951.4 | 48268.8 | 75420 | 48971.8 | 31915.6 | 1645.6 | 58690.4 | 1645.6 | 47326.3 | 1645.6
42.75 | 33800.2 | 60961.8 | 47381 | 27040.1 | 42250.2 | 48769.4 | 76202.2 | 49596.9 | 32253.7 | 1546.5 | 59415.3 | 1546.5 | 48050.4 | 1546.5
43 | 34255.7 | 61802.5 | 48029.1 | 27404.6 | 42819.6 | 49442 | 77253.2 | 50437.6 | 32767.2 | 1488.5 | 60314 | 1488.5 | 48949.1 | 1488.5
43.25 | 34513.5 | 62444.1 | 48478.8 | 27610.8 | 43141.9 | 49955.3 | 78055.1 | 51079.2 | 33079.3 | 1434.2 | 61009.9 | 1434.2 | 49645 | 1434.2
43.5 | 34920.2 | 63231.6 | 49075.9 | 27936.2 | 43650.3 | 50585.3 | 79039.6 | 51866.7 | 33367.4 | 1552.8 | 61678.9 | 1552.8 | 50313.9 | 1552.8
43.75 | 35464.6 | 64153.8 | 49809.2 | 28371.7 | 44330.8 | 51323.1 | 80192.3 | 52787 | 33695.5 | 1769.1 | 62384.7 | 1769.1 | 51017.8 | 1769.1
44 | 35822.3 | 64889.7 | 50356 | 28657.9 | 44777.9 | 51911.8 | 81112.1 | 53522.8 | 34259.6 | 1562.8 | 63326.9 | 1562.8 | 51960.1 | 1562.8
44.25 | 36153.7 | 65598 | 50875.8 | 28922.9 | 45192.1 | 52478.4 | 81997.5 | 54231.1 | 34611.7 | 1541.9 | 64056 | 1541.9 | 52689.2 | 1541.9
44.5 | 36497.5 | 66317.7 | 51407.6 | 29198 | 45621.9 | 53054.2 | 82897.1 | 54950.8 | 35061.1 | 1436.5 | 64881.2 | 1436.5 | 53514.4 | 1436.5
44.75 | 37231.1 | 67425.9 | 52328.5 | 29784.8 | 46538.8 | 53940.7 | 84282.4 | 56059 | 35414.2 | 1816.9 | 65609 | 1816.9 | 54242.1 | 1816.9
45 | 37855.2 | 68425.9 | 53140.6 | 30284.2 | 47319 | 54740.8 | 85532.4 | 57059.1 | 36113.7 | 1741.5 | 66684.4 | 1741.5 | 55317.6 | 1741.5
45.25 | 38308.4 | 69256.8 | 53782.6 | 30646.7 | 47885.5 | 55405.4 | 86571 | 57889.9 | 36706.1 | 1602.4 | 67654.5 | 1602.4 | 56287.6 | 1602.4
45.5 | 39079.6 | 70406.9 | 54743.3 | 31263.7 | 48849.6 | 56325.6 | 88008.7 | 59040.1 | 37238.6 | 1841.1 | 68565.9 | 1841.1 | 57199 | 1841.1
45.75 | 39498.4 | 71206.4 | 55352.4 | 31598.7 | 49373 | 56965.1 | 89008 | 59839.5 | 37831.8 | 1666.6 | 69539.8 | 1666.6 | 58172.9 | 1666.6
46 | 40057.6 | 72147.9 | 56102.8 | 32046.1 | 50072.1 | 57718.4 | 90184.9 | 60781.1 | 38359.6 | 1698.1 | 70449.9 | 1698.1 | 59083 | 1698.1
46.25 | 40558.3 | 73031.8 | 56795.1 | 32446.7 | 50697.9 | 58425.4 | 91289.7 | 61664.9 | 38878.1 | 1680.2 | 71351.6 | 1680.2 | 59984.7 | 1680.2
46.5 | 41777.6 | 74636.4 | 58207 | 33422.1 | 52222 | 59709.1 | 93295.5 | 63269.5 | 39579 | 2198.6 | 72437.8 | 2198.6 | 61070.9 | 2198.6
46.75 | 42376.9 | 75626.1 | 59001.5 | 33901.5 | 52971.1 | 60500.9 | 94532.6 | 64259.2 | 40407.9 | 1968.9 | 73657.1 | 1968.9 | 62290.3 | 1968.9
47 | 43306.7 | 76951.5 | 60129.1 | 34645.4 | 54133.4 | 61561.2 | 96189.3 | 65584.6 | 41261.1 | 2045.7 | 74905.8 | 2045.7 | 63538.9 | 2045.7
47.25 | 43916.7 | 77962 | 60939.4 | 35133.4 | 54895.9 | 62369.6 | 97452.6 | 66595.2 | 41961.1 | 1955.6 | 76006.5 | 1955.6 | 64639.6 | 1955.6
47.5 | 45030.1 | 79479.9 | 62255 | 36024.1 | 56287.7 | 63583.9 | 99349.9 | 68111.2 | 42636 | 2394.1 | 77085.8 | 2394.1 | 65717.1 | 2394.1
47.75 | 45988 | 80848.1 | 63418 | 36790.4 | 57485 | 64678.4 | 101060.1 | 69479.4 | 43511 | 2477 | 78371.1 | 2477 | 67002.4 | 2477
48 | 46893 | 82170.7 | 64531.8 | 37514.4 | 58616.2 | 65736.5 | 102713.3 | 70802 | 44456.3 | 2436.7 | 79734 | 2436.7 | 68365.3 | 2436.7
48.25 | 47913.4 | 83615.9 | 65764.7 | 38330.7 | 59891.8 | 66892.7 | 104519.9 | 72247.3 | 45245.7 | 2667.7 | 80948.2 | 2667.7 | 69579.5 | 2667.7
48.5 | 48624.8 | 84760 | 66692.4 | 38899.8 | 60781 | 67808 | 105950.1 | 73391.4 | 46292.6 | 2332.1 | 82427.9 | 2332.1 | 71059.2 | 2332.1
48.75 | 49860.9 | 86438 | 68149.4 | 39888.7 | 62326.1 | 69150.4 | 108047.4 | 75069.3 | 47267.9 | 2593 | 83844.9 | 2593 | 72476.2 | 2593
49 | 50015.4 | 87043.3 | 68529.4 | 40012.4 | 62519.3 | 69634.7 | 108804.2 | 75674.7 | 48241.8 | 1773.7 | 85269.7 | 1773.7 | 73901 | 1773.7
49.25 | 50318.4 | 87800.7 | 69059.6 | 40254.7 | 62898 | 70240.6 | 109750.9 | 76432.1 | 48592.2 | 1726.1 | 86074.6 | 1726.1 | 74705.9 | 1726.1
49.5 | 50639.9 | 88577.2 | 69608.5 | 40511.9 | 63299.9 | 70861.7 | 110721.4 | 77208.5 | 48902 | 1737.9 | 86839.3 | 1737.9 | 75470.6 | 1737.9
49.75 | 51658.7 | 90050.1 | 70854.4 | 41326.9 | 64573.3 | 72040.1 | 112562.7 | 78676.6 | 49230.8 | 2427.9 | 87622.3 | 2427.9 | 76248.8 | 2427.9
50 | 53234.6 | 92086.1 | 72660.3 | 42587.7 | 66543.3 | 73668.8 | 115107.6 | 80712.6 | 50069.7 | 3164.9 | 88921.2 | 3164.9 | 77547.7 | 3164.9
50.25 | 54073.6 | 93394.7 | 73734.1 | 43258.9 | 67592 | 74715.7 | 116743.3 | 82021.2 | 51134.8 | 2938.8 | 90455.9 | 2938.8 | 79082.4 | 2938.8
50.5 | 57510.2 | 97319.8 | 77415 | 46008.1 | 71887.7 | 77855.8 | 121649.7 | 85946.3 | 53495.3 | 4014.8 | 93304.9 | 4014.8 | 81931.4 | 4014.8
50.75 | 60090.4 | 100422.7 | 80256.5 | 48072.3 | 75113 | 80338.1 | 125528.4 | 89049.2 | 55623.7 | 4466.7 | 95956 | 4466.7 | 84582.5 | 4466.7
51 | 60579.6 | 101464.1 | 81021.8 | 48463.7 | 75724.5 | 81171.3 | 126830.1 | 90090.6 | 57677.6 | 2901.9 | 98562.2 | 2901.9 | 87188.7 | 2901.9
51.25 | 61117 | 102570.3 | 81843.7 | 48893.6 | 76396.3 | 82056.2 | 128212.9 | 91196.8 | 58745.5 | 2371.5 | 100198.8 | 2371.5 | 88825.3 | 2371.5
51.5 | 61493.6 | 103522.2 | 82507.9 | 49194.9 | 76867 | 82817.7 | 129402.7 | 92148.7 | 59471 | 2022.6 | 101499.6 | 2022.6 | 90126.1 | 2022.6
51.75 | 62801.2 | 105411.9 | 84106.6 | 50241 | 78501.5 | 84329.5 | 131764.8 | 94038.4 | 60442.2 | 2359.1 | 103052.8 | 2359.1 | 91679.3 | 2359.1
52 | 63969.4 | 107170.1 | 85569.7 | 51175.5 | 79961.8 | 85736.1 | 133962.6 | 95796.6 | 61338.1 | 2631.3 | 104538.8 | 2631.3 | 93165.3 | 2631.3
52.25 | 65992.4 | 109795 | 87893.7 | 52793.9 | 82490.5 | 87836 | 137243.7 | 98421.5 | 62863.9 | 3128.4 | 106666.5 | 3128.4 | 95293.1 | 3128.4
52.5 | 67091.6 | 111518.5 | 89305 | 53673.3 | 83864.5 | 89214.8 | 139398.1 | 100145 | 64351.7 | 2739.9 | 108778.6 | 2739.9 | 97405.1 | 2739.9
52.75 | 68901.1 | 113963.6 | 91432.3 | 55120.9 | 86126.4 | 91170.9 | 142454.5 | 102590.1 | 65552.5 | 3348.6 | 110615 | 3348.6 | 99241.5 | 3348.6
53 | 71766.7 | 117483.3 | 94625 | 57413.4 | 89708.4 | 93986.7 | 146854.2 | 106109.8 | 67436.5 | 4330.3 | 113153.1 | 4330.3 | 101779.6 | 4330.3
53.25 | 74336.5 | 120735.7 | 97536.1 | 59469.2 | 92920.6 | 96588.6 | 150919.6 | 109362.2 | 69321.7 | 5014.8 | 115720.9 | 5014.8 | 104347.4 | 5014.8
53.5 | 77600.8 | 124714.3 | 101157.5 | 62080.6 | 97001 | 99771.4 | 155892.9 | 113340.8 | 71893.3 | 5707.5 | 119006.8 | 5707.5 | 107633.3 | 5707.5
53.75 | 79614.1 | 127481.5 | 103547.8 | 63691.3 | 99517.7 | 101985.2 | 159351.9 | 116108 | 74748.2 | 4865.9 | 122615.6 | 4865.9 | 111242.1 | 4865.9
54 | 92356.6 | 141029.1 | 116692.8 | 73885.3 | 115445.8 | 112823.2 | 176286.3 | 129655.6 | 77303.9 | 15052.7 | 125976.3 | 15052.7 | 114602.8 | 15052.7
54.25 | 85905.7 | 135460.6 | 110683.2 | 68724.5 | 107382.1 | 108368.5 | 169325.8 | 121397.1 | 80904.5 | 5001.2 | 130459.4 | 5001.2 | 119085.9 | 2311.1
54.5 | 83126.9 | 133586.6 | 108356.7 | 66501.5 | 103908.6 | 106869.3 | 166983.2 | 117113.2 | 79999.7 | 3127.2 | 130459.4 | 3127.2 | 63921.8 | 53191.5
54.75 | 80541.2 | 131892 | 106216.6 | 64433 | 100676.5 | 105513.6 | 164865.1 | 91695.1 | 79108.6 | 1432.6 | 130459.4 | 1432.6 | 63921.8 | 27773.4
55 | 91371.2 | 144579.4 | 117975.3 | 73097 | 114214 | 115663.5 | 180724.3 | 73463.1 | 91297.1 | 74.1 | 144505.3 | 74.1 | 71107.8 | 2355.3
55.25 | 110273.4 | 164628.4 | 137450.9 | 88218.7 | 137841.7 | 131702.7 | 205785.5 | 153095.2 | 91238.2 | 19035.2 | 145593.2 | 19035.2 | 134060 | 19035.2

## SRD WTG-06
Depth (m) | SRD AH-FF (kN) | SRD AH-NFF (kN) | SRD MEAN (kN) | SRD AH-FF-LB (kN) | SRD AH-FF-UB (kN) | SRD AH-NFF-LB (kN) | SRD AH-NFF-UB (kN) | Static Cap (kN) | Shaft AH-FF (kN) | Tip AH-FF (kN) | Shaft AH-NFF (kN) | Tip AH-NFF (kN) | Shaft SC (kN) | Tip SC (kN)
0.5 | 66.9 | 67 | 67 | 53.5 | 83.6 | 53.6 | 83.8 | 30.6 | 4.6 | 62.3 | 4.7 | 62.3 | 3.3 | 27.3
0.75 | 64.5 | 64.8 | 64.6 | 51.6 | 80.6 | 51.8 | 80.9 | 32.6 | 7.1 | 57.4 | 7.3 | 57.4 | 5.4 | 27.3
1 | 65.2 | 65.6 | 65.4 | 52.1 | 81.5 | 52.5 | 82 | 36.1 | 10.9 | 54.2 | 11.4 | 54.2 | 8.8 | 27.3
1.25 | 65.4 | 66.1 | 65.7 | 52.3 | 81.7 | 52.9 | 82.6 | 38.6 | 13.5 | 51.9 | 14.2 | 51.9 | 11.3 | 27.3
1.5 | 69.1 | 70.1 | 69.6 | 55.3 | 86.4 | 56.1 | 87.7 | 43.1 | 17.6 | 51.6 | 18.6 | 51.6 | 15.2 | 27.8
1.75 | 178.5 | 179.8 | 179.1 | 142.8 | 223.1 | 143.8 | 224.7 | 91.4 | 22.6 | 155.9 | 23.9 | 155.9 | 19.6 | 71.7
2 | 3555 | 3557.5 | 3556.2 | 2844 | 4443.8 | 2846 | 4446.8 | 1020.6 | 84.4 | 3470.7 | 86.8 | 3470.7 | 44.4 | 976.2
2.25 | 5892 | 5902.5 | 5897.2 | 4713.6 | 7365 | 4722 | 7378.1 | 1596.6 | 240.5 | 5651.5 | 251 | 5651.5 | 96 | 1500.6
2.5 | 6169.3 | 6200.5 | 6184.9 | 4935.4 | 7711.6 | 4960.4 | 7750.6 | 1712.1 | 448.9 | 5720.4 | 480.1 | 5720.4 | 164.6 | 1547.5
2.75 | 2036.3 | 2099 | 2067.6 | 1629 | 2545.3 | 1679.2 | 2623.8 | 1697.7 | 640.1 | 1396.2 | 702.8 | 1396.2 | 301.5 | 1396.2
3 | 1756.5 | 1859.7 | 1808.1 | 1405.2 | 2195.6 | 1487.7 | 2324.6 | 1458.4 | 942.3 | 814.2 | 1045.5 | 814.2 | 644.2 | 814.2
3.25 | 2798 | 2945 | 2871.5 | 2238.4 | 3497.5 | 2356 | 3681.2 | 2476.1 | 1029.6 | 1768.4 | 1176.6 | 1768.4 | 707.7 | 1768.4
3.5 | 2688.3 | 2884.8 | 2786.6 | 2150.7 | 3360.4 | 2307.9 | 3606 | 2375.9 | 1241.4 | 1446.9 | 1437.9 | 1446.9 | 929 | 1446.9
3.75 | 2049.8 | 2299.2 | 2174.5 | 1639.9 | 2562.3 | 1839.4 | 2874 | 1755.7 | 1388.9 | 661 | 1638.2 | 661 | 1094.7 | 661
4 | 2039.8 | 2343.6 | 2191.7 | 1631.8 | 2549.7 | 1874.8 | 2929.4 | 1792.8 | 1496.2 | 543.5 | 1800 | 543.5 | 1249.3 | 543.5
4.25 | 2393.6 | 2751.7 | 2572.6 | 1914.9 | 2992 | 2201.3 | 3439.6 | 1711 | 1594.7 | 798.9 | 1952.8 | 798.9 | 1382.6 | 328.5
4.5 | 2460.1 | 2873.7 | 2666.9 | 1968.1 | 3075.1 | 2299 | 3592.2 | 2300.8 | 1817 | 643.1 | 2230.6 | 643.1 | 1657.7 | 643.1
4.75 | 2615.9 | 3086.6 | 2851.3 | 2092.7 | 3269.9 | 2469.3 | 3858.3 | 2472.9 | 1951.3 | 664.6 | 2422 | 664.6 | 1808.3 | 664.6
5 | 2740.5 | 3271.3 | 3005.9 | 2192.4 | 3425.6 | 2617.1 | 4089.2 | 2652.7 | 2165.7 | 574.8 | 2696.6 | 574.8 | 2077.9 | 574.8
5.25 | 2883.3 | 3474.9 | 3179.1 | 2306.6 | 3604.1 | 2780 | 4343.7 | 2508.9 | 2266.7 | 616.6 | 2858.3 | 616.6 | 2235.1 | 273.9
5.5 | 2964.7 | 3616.9 | 3290.8 | 2371.8 | 3705.9 | 2893.5 | 4521.1 | 2991.6 | 2390.4 | 574.3 | 3042.6 | 574.3 | 2417.3 | 574.3
5.75 | 3465.1 | 4178.1 | 3821.6 | 2772.1 | 4331.4 | 3342.5 | 5222.7 | 3552.8 | 2514.5 | 950.6 | 3227.5 | 950.6 | 2602.2 | 950.6
6 | 3444.5 | 4219.3 | 3831.9 | 2755.6 | 4305.7 | 3375.4 | 5274.1 | 3583.9 | 2639.9 | 804.7 | 3414.6 | 804.7 | 2779.3 | 804.7
6.25 | 3522.5 | 4360.2 | 3941.3 | 2818 | 4403.1 | 3488.2 | 5450.3 | 3700.1 | 2789.3 | 733.2 | 3627 | 733.2 | 2967 | 733.2
6.5 | 3759.2 | 4662.4 | 4210.8 | 3007.4 | 4699 | 3729.9 | 5828 | 4002.4 | 3029.2 | 730 | 3932.4 | 730 | 3272.3 | 730
6.75 | 4053.3 | 5023.3 | 4538.3 | 3242.6 | 5066.6 | 4018.6 | 6279.1 | 3849.6 | 3156.3 | 897 | 4126.3 | 897 | 3459.6 | 390
7 | 3783.3 | 4820.8 | 4302 | 3026.6 | 4729.1 | 3856.6 | 6026 | 4150.8 | 3313.5 | 469.8 | 4351 | 469.8 | 3681.1 | 469.8
7.25 | 4042.3 | 5146.9 | 4594.6 | 3233.8 | 5052.8 | 4117.5 | 6433.6 | 4473.2 | 3334 | 708.3 | 4438.6 | 708.3 | 3764.9 | 708.3
7.5 | 3927.5 | 5098.8 | 4513.2 | 3142 | 4909.4 | 4079.1 | 6373.5 | 4425.1 | 3441 | 486.5 | 4612.3 | 486.5 | 3938.6 | 486.5
7.75 | 3729.6 | 4967.1 | 4348.3 | 2983.7 | 4662 | 3973.7 | 6208.9 | 4181.1 | 3484.7 | 244.9 | 4722.2 | 244.9 | 4045.9 | 135.2
8 | 4320.7 | 5623.7 | 4972.2 | 3456.6 | 5400.9 | 4498.9 | 7029.6 | 4944.2 | 3560.4 | 760.3 | 4863.4 | 760.3 | 4183.8 | 760.3
8.25 | 4189.5 | 5558.9 | 4874.2 | 3351.6 | 5236.9 | 4447.1 | 6948.6 | 4629.6 | 3695.1 | 494.4 | 5064.4 | 494.4 | 4384.3 | 245.3
8.5 | 4004.1 | 5439.9 | 4722 | 3203.3 | 5005.1 | 4351.9 | 6799.8 | 4641.2 | 3745.6 | 258.5 | 5181.4 | 258.5 | 4497.6 | 143.6
8.75 | 4356 | 5857.3 | 5106.6 | 3484.8 | 5445 | 4685.8 | 7321.6 | 5168.3 | 3742.6 | 613.5 | 5243.8 | 613.5 | 4554.9 | 613.5
9 | 4393.2 | 5959.6 | 5176.4 | 3514.6 | 5491.5 | 4767.7 | 7449.5 | 5270.3 | 3837.9 | 555.3 | 5404.3 | 555.3 | 4715 | 555.3
9.25 | 4499 | 6130.1 | 5314.5 | 3599.2 | 5623.7 | 4904.1 | 7662.6 | 5438.3 | 3866.5 | 632.5 | 5497.6 | 632.5 | 4805.8 | 632.5
9.5 | 4145.8 | 5841.2 | 4993.5 | 3316.7 | 5182.3 | 4673 | 7301.5 | 5060.9 | 3933.3 | 212.6 | 5628.6 | 212.6 | 4936.6 | 124.2
9.75 | 4188.9 | 5947.5 | 5068.2 | 3351.1 | 5236.1 | 4758 | 7434.4 | 5119 | 3893 | 295.9 | 5651.6 | 295.9 | 4954.6 | 164.3
10 | 4173.9 | 5994.8 | 5084.3 | 3339.1 | 5217.3 | 4795.8 | 7493.5 | 5193.1 | 3934.1 | 239.7 | 5755.1 | 239.7 | 5054.6 | 138.5
10.25 | 4158.8 | 6041.2 | 5100 | 3327 | 5198.5 | 4832.9 | 7551.5 | 5223.1 | 3896.8 | 261.9 | 5779.3 | 261.9 | 5073.4 | 149.7
10.5 | 4298.6 | 6241.4 | 5270 | 3438.9 | 5373.2 | 4993.2 | 7801.8 | 5345.1 | 3907 | 391.5 | 5849.9 | 391.5 | 5135 | 210.1
10.75 | 4550.7 | 6553.9 | 5552.3 | 3640.6 | 5688.4 | 5243.1 | 8192.4 | 5836.8 | 3973.9 | 576.8 | 5977.1 | 576.8 | 5260 | 576.8
11 | 4239.1 | 6302 | 5270.5 | 3391.3 | 5298.8 | 5041.6 | 7877.5 | 5482.8 | 3999.6 | 239.4 | 6062.5 | 239.4 | 5342.2 | 140.5
11.25 | 4269.6 | 6391.4 | 5330.5 | 3415.7 | 5337 | 5113.1 | 7989.3 | 5534 | 3966.3 | 303.3 | 6088.1 | 303.3 | 5362.2 | 171.8
11.5 | 5101.8 | 7281.9 | 6191.9 | 4081.5 | 6377.3 | 5825.5 | 9102.3 | 6550.9 | 4052.3 | 1049.5 | 6232.3 | 1049.5 | 5501.4 | 1049.5
11.75 | 4586.6 | 6826.4 | 5706.5 | 3669.3 | 5733.3 | 5461.1 | 8533 | 5923.6 | 4207.1 | 379.5 | 6446.9 | 379.5 | 5715.1 | 208.5
12 | 4954.4 | 7254.2 | 6104.3 | 3963.5 | 6193 | 5803.4 | 9067.7 | 6517.7 | 4291.4 | 663 | 6591.2 | 663 | 5854.7 | 663
12.25 | 5027 | 7386.6 | 6206.8 | 4021.6 | 6283.7 | 5909.3 | 9233.3 | 6642.9 | 4282.5 | 744.5 | 6642.1 | 744.5 | 5898.5 | 744.5
12.5 | 5114.6 | 7533.8 | 6324.2 | 4091.7 | 6393.2 | 6027 | 9417.3 | 6787.2 | 4365.1 | 749.5 | 6784.3 | 749.5 | 6037.7 | 749.5
12.75 | 5349.3 | 7828.3 | 6588.8 | 4279.4 | 6686.6 | 6262.7 | 9785.4 | 7078.4 | 4440.8 | 908.6 | 6919.8 | 908.6 | 6169.9 | 908.6
13 | 5201.8 | 7740.7 | 6471.2 | 4161.4 | 6502.2 | 6192.5 | 9675.8 | 6986.4 | 4494.8 | 706.9 | 7033.7 | 706.9 | 6279.5 | 706.9
13.25 | 5294.7 | 7893.3 | 6594 | 4235.7 | 6618.3 | 6314.7 | 9866.7 | 7134.5 | 4550.6 | 744 | 7149.3 | 744 | 6390.5 | 744
13.5 | 5211.4 | 7870.1 | 6540.7 | 4169.1 | 6514.3 | 6296 | 9837.6 | 6836.6 | 4642.9 | 568.5 | 7301.5 | 568.5 | 6537.8 | 298.8
13.75 | 5792.2 | 8511.8 | 7152 | 4633.8 | 7240.3 | 6809.4 | 10639.8 | 7746.9 | 4841.3 | 950.9 | 7560.9 | 950.9 | 6796.1 | 950.9
14 | 5854.4 | 8637 | 7245.7 | 4683.5 | 7318 | 6909.6 | 10796.2 | 7872.1 | 5049.3 | 805.1 | 7831.8 | 805.1 | 7067 | 805.1
14.25 | 5566.6 | 8413.4 | 6990 | 4453.3 | 6958.3 | 6730.7 | 10516.8 | 7446.6 | 5122.8 | 443.9 | 7969.5 | 443.9 | 7201.3 | 245.3
14.5 | 5682.6 | 8593.9 | 7138.3 | 4546.1 | 7103.2 | 6875.1 | 10742.4 | 7635.4 | 5255.6 | 427 | 8166.9 | 427 | 7397.2 | 238.2
14.75 | 6703.6 | 9680.2 | 8191.9 | 5362.8 | 8379.4 | 7744.2 | 12100.3 | 8907.2 | 5419.4 | 1284.2 | 8396 | 1284.2 | 7623.1 | 1284.2
15 | 6592.7 | 9637.1 | 8114.9 | 5274.1 | 8240.9 | 7709.7 | 12046.4 | 8854.6 | 5647.7 | 945 | 8692.1 | 945 | 7909.6 | 945
15.25 | 6714.1 | 9827.9 | 8271 | 5371.3 | 8392.7 | 7862.3 | 12284.8 | 9044 | 5767.6 | 946.6 | 8881.3 | 946.6 | 8097.4 | 946.6
15.5 | 6662.7 | 9846.7 | 8254.7 | 5330.2 | 8328.4 | 7877.3 | 12308.3 | 9061.5 | 5921.4 | 741.3 | 9105.3 | 741.3 | 8320.2 | 741.3
15.75 | 6742.7 | 9997.5 | 8370.1 | 5394.2 | 8428.4 | 7998 | 12496.8 | 8862.5 | 6030.4 | 712.4 | 9285.1 | 712.4 | 8492.6 | 369.9
16 | 6555.2 | 9881.8 | 8218.5 | 5244.1 | 8193.9 | 7905.4 | 12352.2 | 8910.9 | 6152.2 | 403 | 9478.8 | 403 | 8680.2 | 230.7
16.25 | 6528.9 | 9927.5 | 8228.2 | 5223.1 | 8161.1 | 7942 | 12409.3 | 8961 | 6145.9 | 383 | 9544.5 | 383 | 8739.3 | 221.7
16.5 | 7168 | 10638.1 | 8903.1 | 5734.4 | 8960 | 8510.5 | 13297.6 | 9828 | 6203.1 | 964.9 | 9673.2 | 964.9 | 8863.1 | 964.9
16.75 | 7097.5 | 10639.4 | 8868.4 | 5678 | 8871.9 | 8511.5 | 13299.2 | 9824 | 6267 | 830.5 | 9808.9 | 830.5 | 8993.5 | 830.5
17 | 6602.5 | 10216.3 | 8409.4 | 5282 | 8253.1 | 8173.1 | 12770.4 | 9290.9 | 6323.7 | 278.8 | 9937.6 | 278.8 | 9119.4 | 171.4
17.25 | 6711.5 | 10396.5 | 8554 | 5369.2 | 8389.3 | 8317.2 | 12995.7 | 9390.4 | 6288.6 | 422.8 | 9973.7 | 422.8 | 9147.2 | 243.1
17.5 | 6667.7 | 10423.4 | 8545.5 | 5334.2 | 8334.6 | 8338.7 | 13029.2 | 9448.1 | 6318.9 | 348.8 | 10074.5 | 348.8 | 9240.5 | 207.6
17.75 | 6996.8 | 10822.7 | 8909.7 | 5597.4 | 8746 | 8658.1 | 13528.3 | 9983.7 | 6317.4 | 679.3 | 10143.3 | 679.3 | 9304.4 | 679.3
18 | 6617 | 10512.6 | 8564.8 | 5293.6 | 8271.2 | 8410.1 | 13140.7 | 9540.8 | 6295.6 | 321.4 | 10191.2 | 321.4 | 9346 | 194.8
18.25 | 6530.6 | 10495 | 8512.8 | 5224.5 | 8163.2 | 8396 | 13118.8 | 9541.7 | 6259.7 | 270.8 | 10224.2 | 270.8 | 9372.4 | 169.3
18.5 | 6527.7 | 10560.2 | 8543.9 | 5222.1 | 8159.6 | 8448.1 | 13200.2 | 9586.1 | 6229.3 | 298.4 | 10261.8 | 298.4 | 9402.1 | 184
18.75 | 7014.8 | 11114.5 | 9064.6 | 5611.8 | 8768.4 | 8891.6 | 13893.1 | 10248.8 | 6212.8 | 802 | 10312.5 | 802 | 9446.9 | 802
19 | 6540.7 | 10707.3 | 8624 | 5232.5 | 8175.8 | 8565.8 | 13384.1 | 9705.7 | 6209.6 | 331.1 | 10376.2 | 331.1 | 9504.2 | 201.5
19.25 | 6699.8 | 10932.7 | 8816.3 | 5359.8 | 8374.7 | 8746.2 | 13665.9 | 9863.4 | 6247 | 452.8 | 10479.9 | 452.8 | 9601.3 | 262.2
19.5 | 7141.8 | 11441 | 9291.4 | 5713.5 | 8927.3 | 9152.8 | 14301.2 | 10554.6 | 6305.5 | 836.4 | 10604.6 | 836.4 | 9718.2 | 836.4
19.75 | 7513.1 | 11879 | 9696.1 | 6010.5 | 9391.4 | 9503.2 | 14848.8 | 10437 | 6417.1 | 1096 | 10783 | 1096 | 9887 | 550
20 | 6955.8 | 11389.8 | 9172.8 | 5564.7 | 8694.8 | 9111.8 | 14237.2 | 10337.4 | 6584.4 | 371.4 | 11018.3 | 371.4 | 10113.7 | 223.7
20.25 | 7012 | 11514.4 | 9263.2 | 5609.6 | 8765 | 9211.5 | 14393 | 10460.4 | 6644.7 | 367.4 | 11147.1 | 367.4 | 10238.3 | 222.1
20.5 | 7535.4 | 12106.4 | 9820.9 | 6028.4 | 9419.3 | 9685.1 | 15133 | 11190.8 | 6701.3 | 834.1 | 11272.3 | 834.1 | 10356.7 | 834.1
20.75 | 7051.4 | 11691.3 | 9371.4 | 5641.1 | 8814.2 | 9353.1 | 14614.2 | 10689 | 6806.2 | 245.1 | 11446.2 | 245.1 | 10529.8 | 159.2
21 | 7175.1 | 11884 | 9529.6 | 5740.1 | 8968.8 | 9507.2 | 14855 | 10839.2 | 6848.2 | 326.9 | 11557.1 | 326.9 | 10636.5 | 202.8
21.25 | 7685.3 | 12462.8 | 10074 | 6148.2 | 9606.6 | 9970.2 | 15578.5 | 11534 | 6818.1 | 867.1 | 11595.6 | 867.1 | 10666.8 | 867.1
21.5 | 7178.8 | 12024.4 | 9601.6 | 5743 | 8973.5 | 9619.5 | 15030.5 | 10956.1 | 6829.7 | 349.1 | 11675.3 | 349.1 | 10741.1 | 215
21.75 | 7106.8 | 12019.9 | 9563.3 | 5685.4 | 8883.5 | 9615.9 | 15024.9 | 10964.6 | 6801 | 305.8 | 11714.1 | 305.8 | 10771.7 | 192.9
22 | 7259.2 | 12239.6 | 9749.4 | 5807.3 | 9074 | 9791.7 | 15299.5 | 11162.1 | 6909.9 | 349.2 | 11890.3 | 349.2 | 10946.3 | 215.9
22.25 | 7233.8 | 12281.5 | 9757.6 | 5787 | 9042.2 | 9825.2 | 15351.8 | 11195 | 6882.4 | 351.4 | 11930.1 | 351.4 | 10977.6 | 217.4
22.5 | 7184.2 | 12298.6 | 9741.4 | 5747.4 | 8980.3 | 9838.9 | 15373.2 | 11215.9 | 6856.8 | 327.4 | 11971.2 | 327.4 | 11010.5 | 205.4
22.75 | 7163.7 | 12344 | 9753.9 | 5731 | 8954.6 | 9875.2 | 15430.1 | 11250.7 | 6828.7 | 335 | 12009.1 | 335 | 11041 | 209.7
23 | 7699.2 | 12945 | 10322.1 | 6159.3 | 9623.9 | 10356 | 16181.3 | 11974.1 | 6883.2 | 816 | 12129 | 816 | 11158.1 | 816
23.25 | 7891.2 | 13202.5 | 10546.8 | 6313 | 9864 | 10562 | 16503.1 | 12222.9 | 6864.8 | 1026.4 | 12176 | 1026.4 | 11196.4 | 1026.4
23.5 | 7218.8 | 12595.2 | 9907 | 5775 | 9023.5 | 10076.1 | 15744 | 11488.6 | 6891.6 | 327.2 | 12268 | 327.2 | 11281.9 | 206.7
23.75 | 7198.3 | 12639.3 | 9918.8 | 5758.7 | 8997.9 | 10111.4 | 15799.1 | 11523 | 6865.9 | 332.4 | 12306.9 | 332.4 | 11313.2 | 209.8
24 | 7956 | 13461 | 10708.5 | 6364.8 | 9945 | 10768.8 | 16826.2 | 12456 | 6858.5 | 1097.5 | 12363.5 | 1097.5 | 11358.5 | 1097.5
24.25 | 7267.1 | 12836.3 | 10051.7 | 5813.7 | 9083.9 | 10269.1 | 16045.4 | 11831.8 | 6921.4 | 345.8 | 12490.6 | 345.8 | 11486.1 | 345.8
24.5 | 7041.1 | 12674 | 9857.6 | 5632.9 | 8801.4 | 10139.2 | 15842.5 | 10049.3 | 6902.9 | 138.2 | 12535.8 | 138.2 | 6597.3 | 3452.1
24.75 | 7210.3 | 12906.3 | 10058.3 | 5768.3 | 9012.9 | 10325 | 16132.8 | 11773.6 | 6872.1 | 338.3 | 12568 | 338.3 | 11559.2 | 214.4
25 | 7210.3 | 12968.7 | 10089.5 | 5768.3 | 9012.9 | 10375 | 16210.9 | 11824.6 | 6864.1 | 346.3 | 12622.5 | 346.3 | 11605.7 | 218.9
25.25 | 7750 | 13570.4 | 10660.2 | 6200 | 9687.5 | 10856.3 | 16963 | 12545 | 6850.3 | 899.7 | 12670.7 | 899.7 | 11645.3 | 899.7
25.5 | 7203.3 | 13085.5 | 10144.4 | 5762.6 | 9004.1 | 10468.4 | 16356.9 | 11939.3 | 6881 | 322.4 | 12763.2 | 322.4 | 11732.3 | 206.9
25.75 | 7186.8 | 13130.4 | 10158.6 | 5749.5 | 8983.6 | 10504.3 | 16413 | 11974.6 | 6858.7 | 328.2 | 12802.2 | 328.2 | 11764.3 | 210.4
26 | 7161.1 | 13165.4 | 10163.3 | 5728.9 | 8951.4 | 10532.3 | 16456.8 | 12005.8 | 6841 | 320.1 | 12845.4 | 320.1 | 11799.4 | 206.4
26.25 | 7147.3 | 13211.9 | 10179.6 | 5717.8 | 8934.1 | 10569.5 | 16514.8 | 12042.1 | 6819.8 | 327.5 | 12884.4 | 327.5 | 11831.4 | 210.7
26.5 | 7141.7 | 13266.1 | 10203.9 | 5713.4 | 8927.1 | 10612.8 | 16582.6 | 12083.6 | 6803.2 | 338.5 | 12927.6 | 338.5 | 11866.7 | 216.9
26.75 | 7736.4 | 13920 | 10828.2 | 6189.1 | 9670.5 | 11136 | 17400 | 12849.9 | 6788.5 | 947.9 | 12972.1 | 947.9 | 11901.9 | 947.9
27 | 7212.9 | 13455.8 | 10334.4 | 5770.3 | 9016.1 | 10764.7 | 16819.8 | 12261.3 | 6875.7 | 337.2 | 13118.6 | 337.2 | 12044.4 | 216.9
27.25 | 7195.4 | 13497.5 | 10346.5 | 5756.3 | 8994.3 | 10798 | 16871.9 | 12295.4 | 6857.5 | 338 | 13159.5 | 338 | 12077.8 | 217.6
27.5 | 7199.1 | 13559.8 | 10379.5 | 5759.3 | 8998.9 | 10847.9 | 16949.8 | 12341.7 | 6844.3 | 354.8 | 13205.1 | 354.8 | 12114.7 | 227
27.75 | 7173.9 | 13592.8 | 10383.3 | 5739.1 | 8967.3 | 10874.2 | 16991 | 12371.2 | 6827.7 | 346.2 | 13246.6 | 346.2 | 12148.5 | 222.7
28 | 7179.9 | 13656.6 | 10418.2 | 5743.9 | 8974.9 | 10925.3 | 17070.8 | 12429.7 | 6836.7 | 343.2 | 13313.4 | 343.2 | 12208.3 | 221.4
28.25 | 7842.9 | 14377.3 | 11110.1 | 6274.4 | 9803.7 | 11501.8 | 17971.6 | 13263.3 | 6907 | 935.9 | 13441.4 | 935.9 | 12327.4 | 935.9
28.5 | 7254.7 | 13847 | 10550.8 | 5803.7 | 9068.4 | 11077.6 | 17308.7 | 12607.1 | 6918.6 | 336.1 | 13510.9 | 336.1 | 12388.8 | 218.3
28.75 | 7258.2 | 13908 | 10583.1 | 5806.6 | 9072.8 | 11126.4 | 17385 | 12652 | 6903.6 | 354.7 | 13553.3 | 354.7 | 12423.4 | 228.6
29 | 7930 | 14636.8 | 11283.4 | 6344 | 9912.4 | 11709.4 | 18296 | 13498.3 | 6928.4 | 1001.6 | 13635.3 | 1001.6 | 12496.7 | 1001.6
29.25 | 8779.6 | 15543.7 | 12161.7 | 7023.7 | 10974.5 | 12435 | 19429.7 | 13486.9 | 6990.7 | 1788.9 | 13754.8 | 1788.9 | 12603.8 | 883.1
29.5 | 9475.3 | 16298.3 | 12886.8 | 7580.3 | 11844.2 | 13038.7 | 20372.9 | 15096.5 | 7302.1 | 2173.3 | 14125 | 2173.3 | 12923.2 | 2173.3
29.75 | 8815.9 | 15702.3 | 12259.1 | 7052.7 | 11019.9 | 12561.8 | 19627.9 | 14419 | 7607 | 1208.8 | 14493.5 | 1208.8 | 13210.2 | 1208.8
30 | 9016.2 | 15969.4 | 12492.8 | 7213 | 11270.3 | 12775.5 | 19961.8 | 14101.7 | 7793.3 | 1222.9 | 14746.5 | 1222.9 | 13455.6 | 646.1
30.25 | 8321 | 15341.6 | 11831.3 | 6656.8 | 10401.3 | 12273.3 | 19177 | 13889.4 | 7926.7 | 394.3 | 14947.3 | 394.3 | 13637.5 | 251.9
30.5 | 8644.3 | 15732.4 | 12188.4 | 6915.4 | 10805.3 | 12586 | 19665.5 | 14108.9 | 7927.9 | 716.3 | 15016.1 | 716.3 | 13694 | 414.9
30.75 | 9347.5 | 16503.6 | 12925.5 | 7478 | 11684.4 | 13202.9 | 20629.5 | 15171.7 | 8056.5 | 1291 | 15212.6 | 1291 | 13880.7 | 1291
31 | 9594.8 | 16820.2 | 13207.5 | 7675.9 | 11993.5 | 13456.2 | 21025.3 | 15479.8 | 8329.4 | 1265.4 | 15554.8 | 1265.4 | 14214.4 | 1265.4
31.25 | 9679.6 | 16976.5 | 13328.1 | 7743.7 | 12099.5 | 13581.2 | 21220.7 | 15627.2 | 8605.4 | 1074.2 | 15902.3 | 1074.2 | 14553 | 1074.2
31.5 | 9134.1 | 16504.4 | 12819.3 | 7307.3 | 11417.7 | 13203.5 | 20630.5 | 15021.5 | 8760.6 | 373.6 | 16130.8 | 373.6 | 14779 | 242.5
31.75 | 9090.2 | 16533.5 | 12811.9 | 7272.2 | 11362.8 | 13226.8 | 20666.9 | 15050.1 | 8734.7 | 355.5 | 16178.1 | 355.5 | 14817.1 | 233
32 | 9725.5 | 17241.4 | 13483.4 | 7780.4 | 12156.9 | 13793.1 | 21551.7 | 15871.4 | 8754.7 | 970.8 | 16270.6 | 970.8 | 14900.7 | 970.8
32.25 | 10809.1 | 18398.3 | 14603.7 | 8647.3 | 13511.4 | 14718.6 | 22997.8 | 17001 | 8971.4 | 1837.7 | 16560.6 | 1837.7 | 15163.3 | 1837.7
32.5 | 12419.3 | 20085.6 | 16252.4 | 9935.4 | 15524.1 | 16068.5 | 25107 | 16996.1 | 9371.2 | 3048.1 | 17037.4 | 3048.1 | 15594.2 | 1401.9
32.75 | 13039.2 | 20787.4 | 16913.3 | 10431.4 | 16299 | 16629.9 | 25984.3 | 19164.6 | 9656.9 | 3382.3 | 17405.1 | 3382.3 | 15782.2 | 3382.3
33 | 12510.3 | 20349 | 16429.6 | 10008.2 | 15637.8 | 16279.2 | 25436.2 | 18726.1 | 10406.2 | 2104 | 18244.9 | 2104 | 16622.1 | 2104
33.25 | 11563.2 | 19497.4 | 15530.3 | 9250.6 | 14454 | 15597.9 | 24371.7 | 17525.9 | 10743.5 | 819.7 | 18677.7 | 819.7 | 17054.8 | 471.1
33.5 | 11960.6 | 19992.3 | 15976.4 | 9568.5 | 14950.7 | 15993.8 | 24990.3 | 17909.5 | 10961.3 | 999.2 | 18993 | 999.2 | 17353.2 | 556.3
33.75 | 12119.1 | 20250.1 | 16184.6 | 9695.3 | 15148.9 | 16200.1 | 25312.6 | 18186.9 | 11169.4 | 949.7 | 19300.4 | 949.7 | 17653 | 533.9
34 | 12571.7 | 20803.9 | 16687.8 | 10057.4 | 15714.6 | 16643.1 | 26004.9 | 19149.9 | 11495.5 | 1076.2 | 19727.7 | 1076.2 | 18073.6 | 1076.2
34.25 | 13976.1 | 22311.5 | 18143.8 | 11180.9 | 17470.1 | 17849.2 | 27889.3 | 19416.7 | 11624.4 | 2351.7 | 19959.8 | 2351.7 | 18277.1 | 1139.5
34.5 | 14804.6 | 23246 | 19025.3 | 11843.7 | 18505.7 | 18596.8 | 29057.5 | 21540.8 | 12127.6 | 2677 | 20569 | 2677 | 18863.8 | 2677
34.75 | 18291.8 | 26844.6 | 22568.2 | 14633.4 | 22864.7 | 21475.7 | 33555.7 | 21619.8 | 12415.6 | 5876.2 | 20968.4 | 5876.2 | 19169.2 | 2450.6
35 | 22595.3 | 31267.6 | 26931.4 | 18076.2 | 28244.1 | 25014.1 | 39084.5 | 23131.5 | 12882 | 9713.2 | 21554.3 | 9713.2 | 19400.8 | 3730.7
35.25 | 27253.7 | 36062.9 | 31658.3 | 21803 | 34067.2 | 28850.3 | 45078.7 | 24660.8 | 13568.8 | 13684.9 | 22378 | 13684.9 | 19689.3 | 4971.6

## SRD WTG-07
Depth (m) | SRD AH-FF (kN) | SRD AH-NFF (kN) | SRD MEAN (kN) | SRD AH-FF-LB (kN) | SRD AH-FF-UB (kN) | SRD AH-NFF-LB (kN) | SRD AH-NFF-UB (kN) | Static Cap (kN) | Shaft AH-FF (kN) | Tip AH-FF (kN) | Shaft AH-NFF (kN) | Tip AH-NFF (kN) | Shaft SC (kN) | Tip SC (kN)
0.5 | 105 | 105.5 | 105.2 | 84 | 131.2 | 84.4 | 131.9 | 105.5 | 25.3 | 79.7 | 25.9 | 79.7 | 25.9 | 79.7
0.75 | 117.2 | 118.4 | 117.8 | 93.8 | 146.5 | 94.8 | 148.1 | 118.4 | 37.5 | 79.7 | 38.8 | 79.7 | 38.8 | 79.7
1 | 90.8 | 92.9 | 91.9 | 72.6 | 113.5 | 74.4 | 116.2 | 75.3 | 53.3 | 37.5 | 55.5 | 37.5 | 55.4 | 19.9
1.25 | 155.9 | 159.1 | 157.5 | 124.7 | 194.8 | 127.3 | 198.9 | 159.1 | 72.1 | 83.7 | 75.4 | 83.7 | 75.4 | 83.7
1.5 | 175.6 | 180.2 | 177.9 | 140.5 | 219.5 | 144.1 | 225.2 | 180.1 | 93.3 | 82.4 | 97.8 | 82.4 | 97.8 | 82.4
1.75 | 197.3 | 203.4 | 200.3 | 157.9 | 246.7 | 162.7 | 254.2 | 203.3 | 112.5 | 84.9 | 118.5 | 84.9 | 118.5 | 84.9
2 | 218.7 | 226.4 | 222.6 | 175 | 273.4 | 181.2 | 283.1 | 226.4 | 133.2 | 85.5 | 140.9 | 85.5 | 140.9 | 85.5
2.25 | 238.3 | 247.8 | 243 | 190.6 | 297.8 | 198.2 | 309.8 | 247.8 | 152.1 | 86.2 | 161.6 | 86.2 | 161.6 | 86.2
2.5 | 259.4 | 270.9 | 265.1 | 207.5 | 324.2 | 216.7 | 338.6 | 270.9 | 172.5 | 86.9 | 184 | 86.9 | 184 | 86.9
2.75 | 280.2 | 293.9 | 287 | 224.2 | 350.3 | 235.1 | 367.3 | 293.8 | 191 | 89.2 | 204.7 | 89.2 | 204.7 | 89.2
3 | 301.6 | 317.6 | 309.6 | 241.3 | 377.1 | 254 | 397 | 317.5 | 212.5 | 89.2 | 228.4 | 89.2 | 228.4 | 89.2
3.25 | 325.1 | 343.4 | 334.3 | 260.1 | 406.4 | 274.7 | 429.3 | 301.9 | 232 | 93.2 | 250.3 | 93.2 | 250.3 | 51.6
3.5 | 351.4 | 372.4 | 361.9 | 281.2 | 439.3 | 297.9 | 465.5 | 327.2 | 253.6 | 97.8 | 274.5 | 97.8 | 272.7 | 54.4
3.75 | 382.8 | 406.5 | 394.7 | 306.3 | 478.5 | 325.2 | 508.2 | 350.4 | 265.4 | 117.5 | 289.1 | 117.5 | 286.3 | 64.1
4 | 750.8 | 777.4 | 764.1 | 600.6 | 938.5 | 621.9 | 971.7 | 504.2 | 276.4 | 474.5 | 302.9 | 474.5 | 296.7 | 207.5
4.25 | 438.6 | 468.4 | 453.5 | 350.8 | 548.2 | 374.7 | 585.5 | 404.8 | 320.8 | 117.8 | 350.7 | 117.8 | 339.1 | 65.7
4.5 | 471.4 | 504.9 | 488.2 | 377.1 | 589.2 | 404 | 631.2 | 438.6 | 349.1 | 122.3 | 382.6 | 122.3 | 370.2 | 68.5
4.75 | 614.6 | 652.1 | 633.3 | 491.6 | 768.2 | 521.7 | 815.2 | 639.3 | 384.6 | 229.9 | 422.2 | 229.9 | 409.4 | 229.9
5 | 629.6 | 671.5 | 650.5 | 503.7 | 787 | 537.2 | 839.4 | 658.4 | 427.3 | 202.3 | 469.2 | 202.3 | 456.1 | 202.3
5.25 | 956.1 | 1002.8 | 979.4 | 764.9 | 1195.1 | 802.2 | 1253.5 | 988.7 | 467.8 | 488.3 | 514.4 | 488.3 | 500.3 | 488.3
5.5 | 988.3 | 1040.6 | 1014.4 | 790.7 | 1235.4 | 832.4 | 1300.7 | 788.1 | 548.2 | 440.2 | 600.4 | 440.2 | 582.1 | 206
5.75 | 949.8 | 1008.8 | 979.3 | 759.9 | 1187.3 | 807.1 | 1261 | 990 | 669 | 280.8 | 728 | 280.8 | 709.2 | 280.8
6 | 1031 | 1098.1 | 1064.5 | 824.8 | 1288.7 | 878.5 | 1372.6 | 1079.3 | 772.1 | 258.9 | 839.2 | 258.9 | 820.4 | 258.9
6.25 | 1117.7 | 1193.8 | 1155.7 | 894.1 | 1397.1 | 955 | 1492.2 | 1174.5 | 866.2 | 251.4 | 942.4 | 251.4 | 923.1 | 251.4
6.5 | 1487.2 | 1573.1 | 1530.2 | 1189.8 | 1859 | 1258.5 | 1966.4 | 1550.5 | 921.5 | 565.7 | 1007.4 | 565.7 | 984.7 | 565.7
6.75 | 1432 | 1528.9 | 1480.4 | 1145.6 | 1790 | 1223.1 | 1911.1 | 1310.1 | 1045.2 | 386.8 | 1142.1 | 386.8 | 1118.5 | 191.6
7 | 2030.1 | 2139.4 | 2084.8 | 1624.1 | 2537.7 | 1711.6 | 2674.3 | 2114.1 | 1176.6 | 853.6 | 1285.9 | 853.6 | 1260.5 | 853.6
7.25 | 1865.3 | 1988.9 | 1927.1 | 1492.2 | 2331.6 | 1591.1 | 2486.1 | 1955.7 | 1274 | 591.3 | 1397.6 | 591.3 | 1364.4 | 591.3
7.5 | 2261.1 | 2400.6 | 2330.9 | 1808.9 | 2826.4 | 1920.5 | 3000.7 | 2344 | 1390.8 | 870.3 | 1530.3 | 870.3 | 1473.7 | 870.3
7.75 | 2320.4 | 2478.1 | 2399.2 | 1856.3 | 2900.5 | 1982.5 | 3097.6 | 2408.8 | 1541.8 | 778.7 | 1699.4 | 778.7 | 1630.1 | 778.7
8 | 2202.6 | 2381.2 | 2291.9 | 1762.1 | 2753.2 | 1905 | 2976.5 | 2311.9 | 1760.9 | 441.7 | 1939.5 | 441.7 | 1870.2 | 441.7
8.25 | 2324 | 2525.7 | 2424.9 | 1859.2 | 2905.1 | 2020.6 | 3157.2 | 2456.5 | 1897.3 | 426.8 | 2099 | 426.8 | 2029.7 | 426.8
8.5 | 2429.3 | 2655 | 2542.1 | 1943.4 | 3036.6 | 2124 | 3318.7 | 2585.7 | 2012.9 | 416.4 | 2238.6 | 416.4 | 2169.4 | 416.4
8.75 | 2610.3 | 2861.1 | 2735.7 | 2088.2 | 3262.8 | 2288.8 | 3576.3 | 2789.9 | 2118.3 | 492 | 2369.1 | 492 | 2298 | 492
9 | 2623.3 | 2900.3 | 2761.8 | 2098.7 | 3279.2 | 2320.2 | 3625.4 | 2829.2 | 2212.4 | 410.9 | 2489.4 | 410.9 | 2418.2 | 410.9
9.25 | 3012.7 | 3316.4 | 3164.5 | 2410.2 | 3765.9 | 2653.1 | 4145.5 | 3244.4 | 2274.1 | 738.6 | 2577.8 | 738.6 | 2505.8 | 738.6
9.5 | 3111.2 | 3442.5 | 3276.9 | 2489 | 3889 | 2754 | 4303.1 | 3370.1 | 2416.9 | 694.3 | 2748.3 | 694.3 | 2675.9 | 694.3
9.75 | 2994.9 | 3355.2 | 3175 | 2395.9 | 3743.6 | 2684.2 | 4194 | 3282.8 | 2550 | 444.9 | 2910.3 | 444.9 | 2837.9 | 444.9
10 | 3085.7 | 3476 | 3280.8 | 2468.5 | 3857.1 | 2780.8 | 4345 | 3403.2 | 2628.6 | 457.1 | 3018.9 | 457.1 | 2946.1 | 457.1
10.25 | 3364.1 | 3785.1 | 3574.6 | 2691.3 | 4205.2 | 3028.1 | 4731.3 | 3709.1 | 2737.1 | 627 | 3158 | 627 | 3082.1 | 627
10.5 | 3366 | 3819 | 3592.5 | 2692.8 | 4207.5 | 3055.2 | 4773.7 | 3743 | 2881.8 | 484.3 | 3334.7 | 484.3 | 3258.8 | 484.3
10.75 | 3430.2 | 3916.2 | 3673.2 | 2744.2 | 4287.8 | 3133 | 4895.2 | 3840.2 | 2968.6 | 461.6 | 3454.6 | 461.6 | 3378.6 | 461.6
11 | 3473.9 | 3993.4 | 3733.7 | 2779.2 | 4342.4 | 3194.7 | 4991.8 | 3917.5 | 3051.2 | 422.7 | 3570.7 | 422.7 | 3494.8 | 422.7
11.25 | 3740.2 | 4293.7 | 4017 | 2992.2 | 4675.3 | 3435 | 5367.1 | 4216 | 3122.7 | 617.5 | 3676.2 | 617.5 | 3598.5 | 617.5
11.5 | 3986.5 | 4574.9 | 4280.7 | 3189.2 | 4983.1 | 3659.9 | 5718.6 | 4497.2 | 3271 | 715.5 | 3859.4 | 715.5 | 3781.7 | 715.5
11.75 | 4183 | 4807.4 | 4495.2 | 3346.4 | 5228.7 | 3846 | 6009.3 | 4727.1 | 3361.1 | 821.9 | 3985.6 | 821.9 | 3905.2 | 821.9
12 | 4298.5 | 4960.2 | 4629.3 | 3438.8 | 5373.1 | 3968.1 | 6200.2 | 4446.9 | 3482.4 | 816.1 | 4144.1 | 816.1 | 4052.9 | 394
12.25 | 4756.2 | 5457 | 5106.6 | 3804.9 | 5945.2 | 4365.6 | 6821.2 | 5355.4 | 3721.4 | 1034.8 | 4422.2 | 1034.8 | 4320.5 | 1034.8
12.5 | 4746 | 5489.1 | 5117.5 | 3796.8 | 5932.5 | 4391.2 | 6861.3 | 5387.4 | 3947.2 | 798.8 | 4690.3 | 798.8 | 4588.6 | 798.8
12.75 | 5307.6 | 6095.7 | 5701.7 | 4246.1 | 6634.5 | 4876.6 | 7619.7 | 5387.4 | 4182.5 | 1125.1 | 4970.7 | 1125.1 | 4867.3 | 520.2
13 | 4690.5 | 5526.6 | 5108.5 | 3752.4 | 5863.1 | 4421.3 | 6908.2 | 5282 | 4373.5 | 317 | 5209.6 | 317 | 5100.4 | 181.6
13.25 | 5051 | 5935.9 | 5493.4 | 4040.8 | 6313.7 | 4748.7 | 7419.9 | 5825.1 | 4444.8 | 606.2 | 5329.7 | 606.2 | 5218.8 | 606.2
13.5 | 4903.7 | 5838 | 5370.8 | 3922.9 | 6129.6 | 4670.4 | 7297.5 | 5556.4 | 4521.7 | 382 | 5456 | 382 | 5342.9 | 213.5
13.75 | 5299.5 | 6283.9 | 5791.7 | 4239.6 | 6624.4 | 5027.1 | 7854.8 | 6166.7 | 4643.3 | 656.2 | 5627.6 | 656.2 | 5510.5 | 656.2
14 | 5383.2 | 6418.7 | 5900.9 | 4306.5 | 6728.9 | 5134.9 | 8023.3 | 6298.6 | 4783.9 | 599.2 | 5819.4 | 599.2 | 5699.4 | 599.2
14.25 | 5119.9 | 6207.5 | 5663.7 | 4095.9 | 6399.9 | 4966 | 7759.4 | 5951.1 | 4802.2 | 317.7 | 5889.8 | 317.7 | 5766.3 | 184.8
14.5 | 5617.3 | 6757 | 6187.2 | 4493.8 | 7021.6 | 5405.6 | 8446.3 | 6631.9 | 4883.2 | 734.1 | 6023 | 734.1 | 5897.8 | 734.1
14.75 | 5870.8 | 7063.6 | 6467.2 | 4696.7 | 7338.5 | 5650.8 | 8829.5 | 6933 | 4977.4 | 893.4 | 6170.2 | 893.4 | 6039.6 | 893.4
15 | 5485.4 | 6732.2 | 6108.8 | 4388.3 | 6856.8 | 5385.8 | 8415.3 | 6432.8 | 5105.4 | 380 | 6352.2 | 380 | 6216.4 | 216.4
15.25 | 6613.9 | 7915.5 | 7264.7 | 5291.1 | 8267.4 | 6332.4 | 9894.4 | 7772.5 | 5200.3 | 1413.6 | 6501.9 | 1413.6 | 6358.9 | 1413.6
15.5 | 6063.1 | 7421.5 | 6742.3 | 4850.5 | 7578.8 | 5937.2 | 9276.8 | 6970.6 | 5425.2 | 637.9 | 6783.6 | 637.9 | 6635.5 | 335.1
15.75 | 6174.9 | 7591.5 | 6883.2 | 4939.9 | 7718.7 | 6073.2 | 9489.3 | 7439.8 | 5562.8 | 612.1 | 6979.3 | 612.1 | 6827.7 | 612.1
16 | 5859.5 | 7334.8 | 6597.2 | 4687.6 | 7324.3 | 5867.9 | 9168.5 | 7067.9 | 5576 | 283.5 | 7051.3 | 283.5 | 6896.5 | 171.4
16.25 | 6258.7 | 7792.8 | 7025.8 | 5007 | 7823.4 | 6234.3 | 9741 | 7349.6 | 5645.4 | 613.3 | 7179.5 | 613.3 | 7022.7 | 326.9
16.5 | 6642 | 8236 | 7439 | 5313.6 | 8302.6 | 6588.8 | 10295 | 8074.2 | 5859.5 | 782.5 | 7453.5 | 782.5 | 7291.7 | 782.5
16.75 | 6966.4 | 8622.4 | 7794.4 | 5573.1 | 8708 | 6897.9 | 10778 | 8456.9 | 6044 | 922.4 | 7700 | 922.4 | 7534.6 | 922.4
17 | 7013.9 | 8734.4 | 7874.1 | 5611.1 | 8767.4 | 6987.5 | 10918 | 8568.9 | 6278.9 | 735 | 7999.4 | 735 | 7833.9 | 735
17.25 | 7235.5 | 9021.5 | 8128.5 | 5788.4 | 9044.4 | 7217.2 | 11276.9 | 8849.2 | 6372.7 | 862.8 | 8158.7 | 862.8 | 7986.3 | 862.8
17.5 | 7085.3 | 8937.8 | 8011.5 | 5668.2 | 8856.6 | 7150.2 | 11172.2 | 8477.2 | 6469 | 616.3 | 8321.5 | 616.3 | 8144.8 | 332.4
17.75 | 8010.6 | 9930.4 | 8970.5 | 6408.5 | 10013.3 | 7944.3 | 12412.9 | 9743.7 | 6591.1 | 1419.5 | 8510.8 | 1419.5 | 8324.2 | 1419.5
18 | 7031.1 | 9019.5 | 8025.3 | 5624.9 | 8788.9 | 7215.6 | 11274.4 | 8722.1 | 6746.9 | 284.2 | 8735.3 | 284.2 | 8546.8 | 175.3
18.25 | 7910.3 | 9967.9 | 8939.1 | 6328.2 | 9887.9 | 7974.3 | 12459.8 | 9773.6 | 6833.2 | 1077.1 | 8890.7 | 1077.1 | 8696.4 | 1077.1
18.5 | 7368.6 | 9496.2 | 8432.4 | 5894.9 | 9210.7 | 7596.9 | 11870.2 | 9102.8 | 6908.4 | 460.1 | 9036 | 460.1 | 8839.7 | 263.1
18.75 | 7272.3 | 9470.1 | 8371.2 | 5817.8 | 9090.3 | 7576.1 | 11837.6 | 9153.1 | 6965.8 | 306.4 | 9163.7 | 306.4 | 8965.2 | 187.9
19 | 7619.1 | 9886.8 | 8753 | 6095.3 | 9523.9 | 7909.5 | 12358.6 | 9682.5 | 6957.5 | 661.7 | 9225.2 | 661.7 | 9020.8 | 661.7
19.25 | 7298.8 | 9636.3 | 8467.6 | 5839.1 | 9123.5 | 7709 | 12045.4 | 9303.6 | 6976.9 | 321.9 | 9314.4 | 321.9 | 9106.9 | 196.6
19.5 | 7877.2 | 10284.2 | 9080.7 | 6301.8 | 9846.5 | 8227.4 | 12855.3 | 10071.1 | 7007.4 | 869.9 | 9414.4 | 869.9 | 9201.3 | 869.9
19.75 | 7841.3 | 10318.2 | 9079.8 | 6273.1 | 9801.7 | 8254.5 | 12897.7 | 10102.1 | 7074.9 | 766.4 | 9551.7 | 766.4 | 9335.6 | 766.4
20 | 7425.7 | 9972.6 | 8699.1 | 5940.6 | 9282.1 | 7978 | 12465.7 | 9640.7 | 7125.6 | 300.1 | 9672.4 | 300.1 | 9454 | 186.7
20.25 | 7865.9 | 10482.4 | 9174.1 | 6292.7 | 9832.3 | 8385.9 | 13103 | 10259.3 | 7130.9 | 735 | 9747.4 | 735 | 9524.3 | 735
20.5 | 7596.7 | 10282.7 | 8939.7 | 6077.4 | 9495.9 | 8226.2 | 12853.4 | 10056.2 | 7130.6 | 466.2 | 9816.6 | 466.2 | 9590 | 466.2
20.75 | 7401.2 | 10156.2 | 8778.7 | 5920.9 | 9251.5 | 8125 | 12695.3 | 9827.6 | 7129.5 | 271.7 | 9884.5 | 271.7 | 9654.7 | 172.9
21 | 7394.5 | 10218 | 8806.3 | 5915.6 | 9243.1 | 8174.4 | 12772.6 | 9871 | 7096.4 | 298.1 | 9920 | 298.1 | 9683.9 | 187.1
21.25 | 7333 | 10224.6 | 8778.8 | 5866.4 | 9166.3 | 8179.7 | 12780.8 | 9898.3 | 7086.5 | 246.5 | 9978.1 | 246.5 | 9738.3 | 160
21.5 | 7545.8 | 10504.8 | 9025.3 | 6036.6 | 9432.2 | 8403.9 | 13131 | 10052.7 | 7058.1 | 487.7 | 10017.1 | 487.7 | 9769.5 | 283.2
21.75 | 7391 | 10417.7 | 8904.3 | 5912.8 | 9238.8 | 8334.1 | 13022.1 | 10080 | 7139.5 | 251.5 | 10166.2 | 251.5 | 9916.6 | 163.4
22 | 7369.6 | 10463.6 | 8916.6 | 5895.7 | 9212 | 8370.9 | 13079.5 | 10115.3 | 7106.8 | 262.8 | 10200.8 | 262.8 | 9945.5 | 169.8
22.25 | 7400 | 10560.7 | 8980.4 | 5920 | 9250 | 8448.6 | 13200.9 | 10177 | 7072.5 | 327.5 | 10233.2 | 327.5 | 9972.6 | 204.4
22.5 | 7363.6 | 10590.7 | 8977.1 | 5890.9 | 9204.5 | 8472.6 | 13238.4 | 10221.2 | 7085.2 | 278.4 | 10312.3 | 278.4 | 10042.3 | 178.9
22.75 | 7405.4 | 10698.7 | 9052 | 5924.3 | 9256.7 | 8558.9 | 13373.4 | 10324.5 | 7121.7 | 283.7 | 10415 | 283.7 | 10142.5 | 182
23 | 7379.3 | 10738.5 | 9058.9 | 5903.4 | 9224.1 | 8590.8 | 13423.1 | 10356.9 | 7091.5 | 287.8 | 10450.7 | 287.8 | 10172.4 | 184.5
23.25 | 7358.6 | 10783.2 | 9070.9 | 5886.9 | 9198.3 | 8626.5 | 13479 | 10391.2 | 7059.7 | 298.9 | 10484.3 | 298.9 | 10200.4 | 190.8
23.5 | 7330.8 | 10820.1 | 9075.4 | 5864.6 | 9163.5 | 8656.1 | 13525.1 | 10422.3 | 7031.8 | 299 | 10521.1 | 299 | 10231.1 | 191.2
23.75 | 7806.9 | 11360.6 | 9583.8 | 6245.5 | 9758.6 | 9088.5 | 14200.8 | 11066.6 | 7070.6 | 736.3 | 10624.3 | 736.3 | 10330.3 | 736.3
24 | 7327 | 10945.1 | 9136.1 | 5861.6 | 9158.8 | 8756.1 | 13681.4 | 10552.9 | 7057.8 | 269.2 | 10675.9 | 269.2 | 10377.1 | 175.8
24.25 | 7307.8 | 10989.7 | 9148.7 | 5846.2 | 9134.7 | 8791.7 | 13737.1 | 10587.4 | 7027.8 | 280 | 10709.7 | 280 | 10405.5 | 182
24.5 | 7275.6 | 11020.8 | 9148.2 | 5820.5 | 9094.5 | 8816.6 | 13776 | 10615.6 | 7000.9 | 274.7 | 10746.1 | 274.7 | 10436.1 | 179.4
24.75 | 7229.3 | 11037.2 | 9133.3 | 5783.5 | 9036.6 | 8829.8 | 13796.5 | 10634.8 | 6970.2 | 259.1 | 10778.1 | 259.1 | 10463.6 | 171.2
25 | 7193.1 | 11063.2 | 9128.1 | 5754.5 | 8991.3 | 8850.5 | 13829 | 10660 | 6942.5 | 250.6 | 10812.6 | 250.6 | 10493.3 | 166.8
25.25 | 7170.3 | 11102 | 9136.2 | 5736.2 | 8962.9 | 8881.6 | 13877.5 | 10691.7 | 6912.4 | 257.9 | 10844.2 | 257.9 | 10520.6 | 171.1
25.5 | 7152.7 | 11145.6 | 9149.1 | 5722.2 | 8940.9 | 8916.4 | 13932 | 10726.8 | 6886.3 | 266.4 | 10879.2 | 266.4 | 10550.7 | 176.1
25.75 | 7091 | 11144.5 | 9117.7 | 5672.8 | 8863.8 | 8915.6 | 13930.6 | 10736.3 | 6857.1 | 233.9 | 10910.6 | 233.9 | 10578 | 158.2
26 | 7086.1 | 11199.7 | 9142.9 | 5668.9 | 8857.7 | 8959.8 | 13999.6 | 10778 | 6830.2 | 255.9 | 10943.8 | 255.9 | 10607.2 | 170.8
26.25 | 7053.6 | 11226.7 | 9140.2 | 5642.9 | 8817 | 8981.4 | 14033.4 | 10803.3 | 6803.3 | 250.3 | 10976.4 | 250.3 | 10635.3 | 168
26.5 | 7061.2 | 11293.4 | 9177.3 | 5649 | 8826.5 | 9034.7 | 14116.7 | 10851.6 | 6780.7 | 280.5 | 11012.9 | 280.5 | 10666.6 | 185
26.75 | 7045.5 | 11336.3 | 9190.9 | 5636.4 | 8806.8 | 9069 | 14170.3 | 10885.8 | 6756.7 | 288.8 | 11047.4 | 288.8 | 10696 | 189.9
27 | 7044.6 | 11393.5 | 9219.1 | 5635.7 | 8805.7 | 9114.8 | 14241.9 | 10929 | 6737.5 | 307.1 | 11086.4 | 307.1 | 10728.8 | 200.2
27.25 | 7659.5 | 12066.2 | 9862.9 | 6127.6 | 9574.4 | 9653 | 15082.8 | 11702 | 6757.3 | 902.2 | 11164 | 902.2 | 10799.8 | 902.2
27.5 | 8157.6 | 12622.4 | 10390 | 6526.1 | 10197 | 10098 | 15778.1 | 12255.8 | 6897.2 | 1260.4 | 11362 | 1260.4 | 10995.3 | 1260.4
27.75 | 8068.6 | 12592.9 | 10330.7 | 6454.9 | 10085.7 | 10074.3 | 15741.2 | 12223 | 7050 | 1018.5 | 11574.4 | 1018.5 | 11204.5 | 1018.5
28 | 7375.8 | 11960.2 | 9668 | 5900.6 | 9219.8 | 9568.2 | 14950.3 | 11489.2 | 7090.1 | 285.7 | 11674.5 | 285.7 | 11299.6 | 189.6
28.25 | 7415.8 | 12060 | 9737.9 | 5932.7 | 9269.8 | 9648 | 15075 | 11555 | 7068.5 | 347.3 | 11712.6 | 347.3 | 11331.5 | 223.5
28.5 | 7428.5 | 12132 | 9780.2 | 5942.8 | 9285.6 | 9705.6 | 15164.9 | 11617.4 | 7075.3 | 353.2 | 11778.7 | 353.2 | 11390.4 | 227
28.75 | 8032.8 | 12795.5 | 10414.1 | 6426.3 | 10041 | 10236.4 | 15994.3 | 12402.8 | 7121.5 | 911.3 | 11884.2 | 911.3 | 11491.5 | 911.3
29 | 8216.9 | 13039.3 | 10628.1 | 6573.5 | 10271.1 | 10431.4 | 16299.1 | 12646.6 | 7272.3 | 944.5 | 12094.7 | 944.5 | 11702.1 | 944.5
29.25 | 8378.7 | 13261.7 | 10820.2 | 6703 | 10473.4 | 10609.4 | 16577.1 | 12869.1 | 7420.1 | 958.6 | 12303.2 | 958.6 | 11910.5 | 958.6
29.5 | 8485.8 | 13430.4 | 10958.1 | 6788.6 | 10607.2 | 10744.3 | 16788 | 13037.8 | 7614.1 | 871.7 | 12558.7 | 871.7 | 12166.1 | 871.7
29.75 | 8579.6 | 13586.9 | 11083.3 | 6863.7 | 10724.5 | 10869.6 | 16983.7 | 13194.3 | 7751.8 | 827.8 | 12759.2 | 827.8 | 12366.5 | 827.8
30 | 8085.7 | 13156.1 | 10620.9 | 6468.6 | 10107.1 | 10524.9 | 16445.1 | 12654.8 | 7775.9 | 309.9 | 12846.2 | 309.9 | 12449.6 | 205.2
30.25 | 8094.1 | 13227.1 | 10660.6 | 6475.3 | 10117.6 | 10581.7 | 16533.9 | 12705.7 | 7755.9 | 338.2 | 12888.9 | 338.2 | 12484.6 | 221.1
30.5 | 8084.8 | 13280 | 10682.4 | 6467.8 | 10106 | 10624 | 16600 | 12747.7 | 7740.1 | 344.7 | 12935.3 | 344.7 | 12522.7 | 224.9
30.75 | 8046.2 | 13303.3 | 10674.8 | 6437 | 10057.8 | 10642.6 | 16629.1 | 12772.5 | 7720.9 | 325.3 | 12978 | 325.3 | 12557.9 | 214.6
31 | 8041.2 | 13359.7 | 10700.5 | 6433 | 10051.6 | 10687.8 | 16699.7 | 12816.5 | 7704.9 | 336.3 | 13023.4 | 336.3 | 12595.6 | 221
31.25 | 7978.9 | 13358.4 | 10668.6 | 6383.1 | 9973.6 | 10686.7 | 16698 | 12827.6 | 7682.6 | 296.3 | 13062.1 | 296.3 | 12628.5 | 199.1
31.5 | 8874.7 | 14315 | 11594.9 | 7099.8 | 11093.4 | 11452 | 17893.7 | 13875.4 | 7751.9 | 1122.8 | 13192.1 | 1122.8 | 12752.5 | 1122.8
31.75 | 10357.3 | 15860.1 | 13108.7 | 8285.9 | 12946.7 | 12688.1 | 19825.1 | 14185.5 | 8026.1 | 2331.3 | 13528.8 | 2331.3 | 13071.7 | 1113.7
32 | 12790 | 18359 | 15574.5 | 10232 | 15987.5 | 14687.2 | 22948.7 | 15153.3 | 8284.2 | 4505.8 | 13853.2 | 4505.8 | 13221.5 | 1931.7
32.25 | 20603.6 | 26248.5 | 23426 | 16482.9 | 25754.5 | 20998.8 | 32810.6 | 17760.1 | 8822.8 | 11780.8 | 14467.7 | 11780.8 | 13450 | 4310
32.5 | 15532.9 | 21274.2 | 18403.6 | 12426.4 | 19416.2 | 17019.4 | 26592.8 | 16200.1 | 9469.3 | 6063.7 | 15210.5 | 6063.7 | 13718.1 | 2482.1
32.75 | 21247.4 | 27097.9 | 24172.7 | 16997.9 | 26559.2 | 21678.4 | 33872.4 | 18117.2 | 9929.9 | 11317.5 | 15780.4 | 11317.5 | 13935.7 | 4181.6
33 | 35788.1 | 41774.8 | 38781.5 | 28630.5 | 44735.1 | 33419.9 | 52218.5 | 22347.5 | 11098.8 | 24689.3 | 17085.6 | 24689.3 | 14324.6 | 8022.8
33.25 | 30379.9 | 36556 | 33468 | 24303.9 | 37974.9 | 29244.8 | 45695.1 | 20911 | 12302 | 18077.9 | 18478.2 | 18077.9 | 14713.5 | 6197.4
33.5 | 38875.7 | 45285 | 42080.4 | 31100.6 | 48594.7 | 36228 | 56606.3 | 23356.1 | 13445.3 | 25430.4 | 19854.6 | 25430.4 | 15107.3 | 8248.8
33.75 | 18680.4 | 25364.5 | 22022.4 | 14944.3 | 23350.4 | 20291.6 | 31705.6 | 17364.2 | 14230.4 | 4450 | 20914.5 | 4450 | 15431.3 | 1933
34 | 16150.5 | 23117.7 | 19634.1 | 12920.4 | 20188.2 | 18494.2 | 28897.2 | 17604.9 | 14853.9 | 1296.6 | 21821.1 | 1296.6 | 16308.2 | 1296.6
34.25 | 15244.1 | 22489.2 | 18866.7 | 12195.3 | 19055.2 | 17991.3 | 28111.5 | 16755.2 | 14694.4 | 549.8 | 21939.4 | 549.8 | 16416 | 339.2
34.5 | 15766.7 | 23280.3 | 19523.5 | 12613.4 | 19708.4 | 18624.3 | 29100.4 | 17745 | 14545.2 | 1221.5 | 22058.8 | 1221.5 | 16523.5 | 1221.5
34.75 | 15787.7 | 23562 | 19674.9 | 12630.2 | 19734.7 | 18849.6 | 29452.5 | 18026.7 | 14556.3 | 1231.5 | 22330.6 | 1231.5 | 16795.3 | 1231.5
35 | 15816.9 | 23845 | 19831 | 12653.5 | 19771.1 | 19076 | 29806.3 | 18309.7 | 14590 | 1226.9 | 22618.1 | 1226.9 | 17082.8 | 1226.9
35.25 | 15088.6 | 23363.8 | 19226.2 | 12070.9 | 18860.7 | 18691 | 29204.7 | 17637.2 | 14579.3 | 509.3 | 22854.4 | 509.3 | 17317.4 | 319.8
35.5 | 22221.5 | 30739.6 | 26480.6 | 17777.2 | 27776.9 | 24591.7 | 38424.5 | 20497.1 | 14739.6 | 7482 | 23257.6 | 7482 | 17491 | 3006.1
35.75 | 23236.5 | 32005.3 | 27620.9 | 18589.2 | 29045.6 | 25604.2 | 40006.6 | 20944.5 | 15223.4 | 8013.1 | 23992.2 | 8013.1 | 17757.2 | 3187.3

## SRD WTG-08
Depth (m) | SRD AH-FF (kN) | SRD AH-NFF (kN) | SRD MEAN (kN) | SRD AH-FF-LB (kN) | SRD AH-FF-UB (kN) | SRD AH-NFF-LB (kN) | SRD AH-NFF-UB (kN) | Static Cap (kN) | Shaft AH-FF (kN) | Tip AH-FF (kN) | Shaft AH-NFF (kN) | Tip AH-NFF (kN) | Shaft SC (kN) | Tip SC (kN)
0.5 | 64.3 | 64.4 | 64.3 | 51.4 | 80.3 | 51.5 | 80.5 | 29.6 | 4.5 | 59.8 | 4.6 | 59.8 | 3.2 | 26.4
0.75 | 62 | 62.2 | 62.1 | 49.6 | 77.5 | 49.8 | 77.8 | 31.6 | 6.8 | 55.2 | 7.1 | 55.2 | 5.3 | 26.4
1 | 62.7 | 63.1 | 62.9 | 50.1 | 78.3 | 50.5 | 78.9 | 35 | 10.6 | 52.1 | 11 | 52.1 | 8.6 | 26.4
1.25 | 62.9 | 63.5 | 63.2 | 50.3 | 78.6 | 50.8 | 79.4 | 37.4 | 13.1 | 49.8 | 13.7 | 49.8 | 11 | 26.4
1.5 | 65 | 66 | 65.5 | 52 | 81.3 | 52.8 | 82.4 | 41.3 | 17 | 48 | 17.9 | 48 | 14.9 | 26.4
1.75 | 86.2 | 87.4 | 86.8 | 69 | 107.7 | 69.9 | 109.3 | 53.4 | 20.3 | 65.9 | 21.5 | 65.9 | 18.2 | 35.2
2 | 89.6 | 91.2 | 90.4 | 71.7 | 112 | 72.9 | 113.9 | 58.1 | 25.1 | 64.5 | 26.6 | 64.5 | 22.8 | 35.3
2.25 | 93.3 | 95.3 | 94.3 | 74.7 | 116.7 | 76.2 | 119.1 | 62.8 | 29.4 | 63.9 | 31.4 | 63.9 | 27.1 | 35.7
2.5 | 99.5 | 101.9 | 100.7 | 79.6 | 124.4 | 81.5 | 127.4 | 68.9 | 34.3 | 65.2 | 36.7 | 65.2 | 32 | 36.9
2.75 | 103.8 | 106.7 | 105.2 | 83 | 129.7 | 85.3 | 133.3 | 74 | 39 | 64.8 | 41.9 | 64.8 | 36.8 | 37.3
3 | 234.2 | 237.6 | 235.9 | 187.4 | 292.8 | 190.1 | 297 | 135.2 | 46.4 | 187.9 | 49.8 | 187.9 | 43.4 | 91.8
3.25 | 857.4 | 861.5 | 859.5 | 685.9 | 1071.7 | 689.2 | 1076.9 | 364.4 | 64.9 | 792.4 | 69.1 | 792.4 | 55.7 | 308.7
3.5 | 1188 | 1193.8 | 1190.9 | 950.4 | 1485.1 | 955 | 1492.2 | 484.3 | 114.4 | 1073.7 | 120.1 | 1073.7 | 81.3 | 403
3.75 | 991.3 | 1000.2 | 995.7 | 793 | 1239.1 | 800.1 | 1250.2 | 933.2 | 165.8 | 825.5 | 174.7 | 825.5 | 107.7 | 825.5
4 | 1055.7 | 1069.4 | 1062.5 | 844.6 | 1319.7 | 855.5 | 1336.7 | 487.2 | 239.1 | 816.6 | 252.8 | 816.6 | 158.5 | 328.7
4.25 | 853.4 | 873 | 863.2 | 682.7 | 1066.8 | 698.4 | 1091.3 | 467.2 | 314 | 539.4 | 333.6 | 539.4 | 232.2 | 235.1
4.5 | 2068.4 | 2094.9 | 2081.7 | 1654.7 | 2585.5 | 1675.9 | 2618.6 | 879.2 | 352.8 | 1715.6 | 379.3 | 1715.6 | 256.5 | 622.7
4.75 | 1049.9 | 1084.8 | 1067.3 | 839.9 | 1312.3 | 867.9 | 1356 | 607.8 | 454.8 | 595.1 | 489.8 | 595.1 | 347.7 | 260.1
5 | 2059.5 | 2105.2 | 2082.4 | 1647.6 | 2574.4 | 1684.2 | 2631.5 | 969.4 | 542 | 1517.5 | 587.7 | 1517.5 | 396.5 | 573
5.25 | 1250 | 1308.7 | 1279.4 | 1000 | 1562.5 | 1047 | 1635.9 | 1081.9 | 598.1 | 651.9 | 656.8 | 651.9 | 430 | 651.9
5.5 | 1487.6 | 1560.2 | 1523.9 | 1190.1 | 1859.5 | 1248.2 | 1950.3 | 857.6 | 667.8 | 819.8 | 740.4 | 819.8 | 508.9 | 348.7
5.75 | 1866.6 | 1953.9 | 1910.2 | 1493.2 | 2333.2 | 1563.1 | 2442.4 | 1007.7 | 729.2 | 1137.4 | 816.5 | 1137.4 | 545.9 | 461.9
6 | 1295.9 | 1399.5 | 1347.7 | 1036.7 | 1619.9 | 1119.6 | 1749.3 | 1116.4 | 812.1 | 483.8 | 915.7 | 483.8 | 632.6 | 483.8
6.25 | 1801.6 | 1922.2 | 1861.9 | 1441.3 | 2252 | 1537.8 | 2402.8 | 1088.1 | 872.5 | 929.1 | 993.1 | 929.1 | 692.3 | 395.8
6.5 | 1437.3 | 1575.9 | 1506.6 | 1149.8 | 1796.6 | 1260.7 | 1969.9 | 1268.6 | 986.9 | 450.3 | 1125.6 | 450.3 | 818.2 | 450.3
6.75 | 1572.5 | 1730 | 1651.2 | 1258 | 1965.7 | 1384 | 2162.4 | 1416.9 | 1009.3 | 563.2 | 1166.7 | 563.2 | 853.7 | 563.2
7 | 2185.3 | 2361.7 | 2273.5 | 1748.3 | 2731.7 | 1889.3 | 2952.1 | 1390 | 1062.6 | 1122.7 | 1239 | 1122.7 | 917.8 | 472.2
7.25 | 1607.7 | 1803.6 | 1705.7 | 1286.2 | 2009.7 | 1442.9 | 2254.5 | 1470.4 | 1134.1 | 473.6 | 1330 | 473.6 | 996.8 | 473.6
7.5 | 2084.2 | 2300.4 | 2192.3 | 1667.3 | 2605.2 | 1840.3 | 2875.4 | 1471 | 1201.1 | 883.1 | 1417.3 | 883.1 | 1080 | 391
7.75 | 1766.6 | 2003.4 | 1885 | 1413.3 | 2208.2 | 1602.7 | 2504.2 | 1397.7 | 1259.3 | 507.3 | 1496.1 | 507.3 | 1150 | 247.7
8 | 2363.9 | 2622.2 | 2493 | 1891.1 | 2954.8 | 2097.7 | 3277.7 | 1707.8 | 1366.7 | 997.2 | 1625 | 997.2 | 1270.4 | 437.4
8.25 | 1695.2 | 1975.9 | 1835.6 | 1356.2 | 2119.1 | 1580.7 | 2469.9 | 1480 | 1410.5 | 284.8 | 1691.1 | 284.8 | 1325.3 | 154.7
8.5 | 1915.7 | 2219 | 2067.3 | 1532.6 | 2394.6 | 1775.2 | 2773.7 | 1617.1 | 1451.3 | 464.4 | 1754.5 | 464.4 | 1383.3 | 233.8
8.75 | 4249.4 | 4576.4 | 4412.9 | 3399.5 | 5311.7 | 3661.1 | 5720.5 | 2471.7 | 1573.3 | 2676.1 | 1900.3 | 2676.1 | 1460.3 | 1011.4
9 | 2397 | 2752.9 | 2575 | 1917.6 | 2996.3 | 2202.3 | 3441.2 | 2061.7 | 1919.4 | 477.6 | 2275.3 | 477.6 | 1820.1 | 241.7
9.25 | 3669.2 | 4056.9 | 3863 | 2935.3 | 4586.5 | 3245.5 | 5071.1 | 2582.5 | 1997.1 | 1672.1 | 2384.8 | 1672.1 | 1892.6 | 690
9.5 | 3127 | 3548.7 | 3337.9 | 2501.6 | 3908.8 | 2839 | 4435.9 | 3023.2 | 2230 | 897 | 2651.7 | 897 | 2126.2 | 897
9.75 | 3163.1 | 3622.8 | 3392.9 | 2530.4 | 3953.8 | 2898.3 | 4528.5 | 3040.9 | 2422.4 | 740.6 | 2882.2 | 740.6 | 2300.2 | 740.6
10 | 3241.1 | 3741.9 | 3491.5 | 2592.9 | 4051.4 | 2993.6 | 4677.4 | 2816.2 | 2580.2 | 660.9 | 3081.1 | 660.9 | 2493.6 | 322.6
10.25 | 2881.5 | 3423.9 | 3152.7 | 2305.2 | 3601.8 | 2739.1 | 4279.8 | 2742.5 | 2671.6 | 209.8 | 3214 | 209.8 | 2618 | 124.5
10.5 | 2885.4 | 3469.4 | 3177.4 | 2308.3 | 3606.7 | 2775.6 | 4336.8 | 2775.4 | 2657.6 | 227.8 | 3241.7 | 227.8 | 2641.6 | 133.8
10.75 | 3317.3 | 3942.4 | 3629.9 | 2653.8 | 4146.6 | 3153.9 | 4928 | 3338.8 | 2678.5 | 638.8 | 3303.6 | 638.8 | 2700 | 638.8
11 | 3343.4 | 4009.3 | 3676.4 | 2674.8 | 4179.3 | 3207.5 | 5011.6 | 3398.5 | 2685.4 | 658 | 3351.3 | 658 | 2740.4 | 658
11.25 | 3607.9 | 4314.3 | 3961.1 | 2886.3 | 4509.9 | 3451.5 | 5392.9 | 3685.3 | 2710.7 | 897.2 | 3417.1 | 897.2 | 2788.1 | 897.2
11.5 | 3347.1 | 4094.7 | 3720.9 | 2677.7 | 4183.9 | 3275.7 | 5118.3 | 3459.7 | 2824.4 | 522.7 | 3571.9 | 522.7 | 2936.9 | 522.7
11.75 | 3248.1 | 4036.9 | 3642.5 | 2598.5 | 4060.1 | 3229.6 | 5046.2 | 3216 | 2847.1 | 401 | 3636 | 401 | 2997.5 | 218.5
12 | 3431.5 | 4261.7 | 3846.6 | 2745.2 | 4289.4 | 3409.3 | 5327.1 | 3613.6 | 2942.3 | 489.2 | 3772.4 | 489.2 | 3124.4 | 489.2
12.25 | 3470.4 | 4341.9 | 3906.1 | 2776.3 | 4337.9 | 3473.5 | 5427.4 | 3690.1 | 2946 | 524.3 | 3817.6 | 524.3 | 3165.7 | 524.3
12.5 | 3626.3 | 4539.1 | 4082.7 | 2901 | 4532.9 | 3631.3 | 5673.9 | 3877.9 | 3037.5 | 588.8 | 3950.3 | 588.8 | 3289.1 | 588.8
12.75 | 3353.3 | 4308.2 | 3830.8 | 2682.7 | 4191.7 | 3446.6 | 5385.2 | 3547.2 | 3107.9 | 245.4 | 4062.8 | 245.4 | 3400.1 | 147.1
13 | 3358.2 | 4355.1 | 3856.7 | 2686.6 | 4197.8 | 3484.1 | 5443.9 | 3609.6 | 3152.9 | 205.3 | 4149.8 | 205.3 | 3482.4 | 127.2
13.25 | 3337 | 4375.5 | 3856.2 | 2669.6 | 4171.2 | 3500.4 | 5469.4 | 3627.9 | 3134.7 | 202.2 | 4173.2 | 202.2 | 3501.9 | 126
13.5 | 3317.5 | 4397 | 3857.2 | 2654 | 4146.8 | 3517.6 | 5496.3 | 3647.2 | 3116.5 | 201 | 4196.1 | 201 | 3521.5 | 125.7
13.75 | 3632.6 | 4752.6 | 4192.6 | 2906 | 4540.7 | 3802.1 | 5940.7 | 4071.6 | 3108.5 | 524.1 | 4228.5 | 524.1 | 3547.5 | 524.1
14 | 3313 | 4473.2 | 3893.1 | 2650.4 | 4141.3 | 3578.6 | 5591.5 | 3724.5 | 3130.4 | 182.6 | 4290.6 | 182.6 | 3607.7 | 116.8
14.25 | 3537.6 | 4737.5 | 4137.6 | 2830.1 | 4422 | 3790 | 5921.9 | 3863.6 | 3114.6 | 423 | 4314.5 | 423 | 3627.7 | 235.8
14.5 | 3548.3 | 4787.8 | 4168.1 | 2838.7 | 4435.4 | 3830.2 | 5984.7 | 3941 | 3192.3 | 356.1 | 4431.7 | 356.1 | 3736.1 | 204.9
14.75 | 3454.3 | 4733.2 | 4093.8 | 2763.4 | 4317.9 | 3786.6 | 5916.5 | 3928.2 | 3189.4 | 264.8 | 4468.4 | 264.8 | 3767.6 | 160.6
15 | 3592.4 | 4910.5 | 4251.5 | 2874 | 4490.6 | 3928.4 | 6138.2 | 4024.6 | 3180.8 | 411.7 | 4498.9 | 411.7 | 3792.1 | 232.5
15.25 | 3802.5 | 5159.4 | 4480.9 | 3042 | 4753.1 | 4127.5 | 6449.2 | 4446.3 | 3217 | 585.4 | 4574 | 585.4 | 3860.9 | 585.4
15.5 | 3590.7 | 4986.5 | 4288.6 | 2872.6 | 4488.4 | 3989.2 | 6233.1 | 4117.2 | 3233.5 | 357.2 | 4629.2 | 357.2 | 3909.4 | 207.7
15.75 | 3894.4 | 5328.7 | 4611.5 | 3115.5 | 4867.9 | 4263 | 6660.9 | 4307.1 | 3277.2 | 617.2 | 4711.5 | 617.2 | 3978.6 | 328.5
16 | 3702.8 | 5176.6 | 4439.7 | 2962.2 | 4628.5 | 4141.2 | 6470.7 | 4322 | 3408.8 | 294 | 4882.6 | 294 | 4144.5 | 177.5
16.25 | 3890.3 | 5404 | 4647.2 | 3112.3 | 4862.9 | 4323.2 | 6755 | 4479.1 | 3466.3 | 424 | 4980 | 424 | 4237.6 | 241.5
16.5 | 4302.8 | 5856.5 | 5079.6 | 3442.2 | 5378.5 | 4685.2 | 7320.6 | 4733.3 | 3537.6 | 765.2 | 5091.3 | 765.2 | 4337.3 | 396
16.75 | 4439.2 | 6033.6 | 5236.4 | 3551.4 | 5549 | 4826.9 | 7542 | 4896.5 | 3665.5 | 773.7 | 5259.9 | 773.7 | 4495.8 | 400.7
17 | 4201.3 | 5837.2 | 5019.2 | 3361 | 5251.6 | 4669.7 | 7296.5 | 4863.8 | 3749.6 | 451.6 | 5385.5 | 451.6 | 4607.3 | 256.5
17.25 | 4565 | 6243.1 | 5404.1 | 3652 | 5706.3 | 4994.5 | 7803.9 | 5457.2 | 3839.8 | 725.3 | 5517.8 | 725.3 | 4731.9 | 725.3
17.5 | 4252.1 | 5972.9 | 5112.5 | 3401.6 | 5315.1 | 4778.3 | 7466.1 | 5041.5 | 3905.7 | 346.4 | 5626.5 | 346.4 | 4834.9 | 206.6
17.75 | 4713.9 | 6477.6 | 5595.7 | 3771.1 | 5892.4 | 5182.1 | 8097 | 5679.3 | 3981.7 | 732.3 | 5745.3 | 732.3 | 4947 | 732.3
18 | 4333.9 | 6140.7 | 5237.3 | 3467.1 | 5417.4 | 4912.6 | 7675.9 | 5209.9 | 4009 | 324.8 | 5815.9 | 324.8 | 5013.2 | 196.8
18.25 | 4233.9 | 6083.6 | 5158.7 | 3387.1 | 5292.4 | 4866.9 | 7604.5 | 5190 | 3999.5 | 234.4 | 5849.2 | 234.4 | 5039.7 | 150.3
18.5 | 4416.2 | 6308.4 | 5362.3 | 3532.9 | 5520.2 | 5046.7 | 7885.5 | 5337.9 | 4041.2 | 375 | 5933.4 | 375 | 5115.1 | 222.8
18.75 | 4785.6 | 6720.5 | 5753.1 | 3828.5 | 5982 | 5376.4 | 8400.6 | 5896.9 | 4055.6 | 730 | 5990.5 | 730 | 5166.9 | 730
19 | 4368.9 | 6346.3 | 5357.6 | 3495.2 | 5461.2 | 5077 | 7932.9 | 5408.8 | 4082.9 | 286 | 6060.3 | 286 | 5230.3 | 178.5
19.25 | 4425.2 | 6444.9 | 5435 | 3540.1 | 5531.5 | 5155.9 | 8056.1 | 5495.1 | 4131.6 | 293.5 | 6151.4 | 293.5 | 5312.3 | 182.8
19.5 | 4847.1 | 6909.3 | 5878.2 | 3877.7 | 6058.9 | 5527.5 | 8636.7 | 6062.5 | 4174.1 | 673 | 6236.3 | 673 | 5389.5 | 673
19.75 | 4500 | 6604.8 | 5552.4 | 3600 | 5625 | 5283.9 | 8256 | 5654.9 | 4232 | 268 | 6336.8 | 268 | 5484.7 | 170.2
20 | 4522.4 | 6669.9 | 5596.1 | 3617.9 | 5653 | 5335.9 | 8337.4 | 5715.4 | 4254.7 | 267.7 | 6402.2 | 267.7 | 5545 | 170.4
20.25 | 4843.3 | 7033.3 | 5938.3 | 3874.7 | 6054.1 | 5626.6 | 8791.6 | 5906.1 | 4253.3 | 590 | 6443.3 | 590 | 5576.1 | 329.9
20.5 | 4609.3 | 6841.8 | 5725.6 | 3687.5 | 5761.7 | 5473.4 | 8552.2 | 5864.3 | 4328.3 | 281 | 6560.7 | 281 | 5686.1 | 178.2
20.75 | 4567.1 | 6842.1 | 5704.6 | 3653.6 | 5708.8 | 5473.7 | 8552.6 | 5880.3 | 4329.2 | 237.9 | 6604.2 | 237.9 | 5724.9 | 155.4
21 | 4585.7 | 6903 | 5744.4 | 3668.6 | 5732.2 | 5522.4 | 8628.7 | 5923.5 | 4320.3 | 265.5 | 6637.5 | 265.5 | 5752.9 | 170.6
21.25 | 4572 | 6931.1 | 5751.5 | 3657.6 | 5715 | 5544.9 | 8663.8 | 5948.4 | 4309.3 | 262.8 | 6668.3 | 262.8 | 5778.9 | 169.5
21.5 | 4533.4 | 6933.9 | 5733.6 | 3626.7 | 5666.7 | 5547.1 | 8667.3 | 5960.4 | 4303 | 230.4 | 6703.5 | 230.4 | 5808.2 | 152.2
21.75 | 4594.7 | 7036.3 | 5815.5 | 3675.8 | 5743.4 | 5629 | 8795.4 | 6025.4 | 4294 | 300.7 | 6735.6 | 300.7 | 5835.1 | 190.4
22 | 4635.7 | 7118.1 | 5876.9 | 3708.6 | 5794.7 | 5694.5 | 8897.7 | 6079.9 | 4296.1 | 339.7 | 6778.4 | 339.7 | 5868.8 | 211.1
22.25 | 4530.8 | 7053.7 | 5792.2 | 3624.6 | 5663.5 | 5642.9 | 8817.1 | 6055.9 | 4289.2 | 241.5 | 6812.2 | 241.5 | 5896.7 | 159.2
22.5 | 4578.1 | 7141.2 | 5859.7 | 3662.5 | 5722.6 | 5713 | 8926.5 | 6114.1 | 4284.2 | 293.9 | 6847.3 | 293.9 | 5926.3 | 187.8
22.75 | 4554.9 | 7157.8 | 5856.4 | 3643.9 | 5693.6 | 5726.3 | 8947.3 | 6133.2 | 4276 | 278.9 | 6878.9 | 278.9 | 5953.1 | 180.1
23 | 4540.3 | 7182.8 | 5861.5 | 3632.2 | 5675.3 | 5746.2 | 8978.5 | 6157.8 | 4273.1 | 267.2 | 6915.6 | 267.2 | 5983.7 | 174.1
23.25 | 4530.9 | 7212.6 | 5871.7 | 3624.7 | 5663.6 | 5770.1 | 9015.7 | 6184 | 4263.3 | 267.6 | 6945 | 267.6 | 6009.3 | 174.6
23.5 | 4602 | 7322.6 | 5962.3 | 3681.6 | 5752.5 | 5858.1 | 9153.3 | 6254.2 | 4262 | 340 | 6982.6 | 340 | 6040.6 | 213.6
23.75 | 4514.1 | 7273.3 | 5893.7 | 3611.2 | 5642.6 | 5818.6 | 9091.6 | 6238.4 | 4257.3 | 256.7 | 7016.5 | 256.7 | 6069.1 | 169.3
24 | 4499.8 | 7297.4 | 5898.6 | 3599.9 | 5624.8 | 5837.9 | 9121.7 | 6262.3 | 4250.3 | 249.6 | 7047.8 | 249.6 | 6096.7 | 165.6
24.25 | 4488.8 | 7324.3 | 5906.5 | 3591 | 5610.9 | 5859.4 | 9155.3 | 6287.3 | 4246.5 | 242.2 | 7082.1 | 242.2 | 6125.4 | 161.9
24.5 | 4523.4 | 7396.6 | 5960 | 3618.7 | 5654.2 | 5917.3 | 9245.8 | 6338.1 | 4243.8 | 279.6 | 7117 | 279.6 | 6155.4 | 182.7
24.75 | 4539.7 | 7450.4 | 5995.1 | 3631.8 | 5674.7 | 5960.3 | 9313 | 6377.9 | 4241.7 | 298 | 7152.4 | 298 | 6184.9 | 193
25 | 4488.1 | 7436 | 5962 | 3590.5 | 5610.1 | 5948.8 | 9295 | 6381.3 | 4239.5 | 248.6 | 7187.4 | 248.6 | 6215.1 | 166.2
25.25 | 4486.8 | 7471.6 | 5979.2 | 3589.4 | 5608.5 | 5977.2 | 9339.4 | 6411.1 | 4233.3 | 253.4 | 7218.1 | 253.4 | 6241.9 | 169.2
25.5 | 4484.6 | 7506 | 5995.3 | 3587.7 | 5605.8 | 6004.8 | 9382.5 | 6441.4 | 4232.8 | 251.8 | 7254.2 | 251.8 | 6272.8 | 168.6
25.75 | 4550.6 | 7608.4 | 6079.5 | 3640.5 | 5688.3 | 6086.7 | 9510.5 | 6508.1 | 4231.6 | 319 | 7289.4 | 319 | 6302.5 | 205.6
26 | 4503.2 | 7597.2 | 6050.2 | 3602.6 | 5629 | 6077.7 | 9496.5 | 6513.8 | 4234.7 | 268.5 | 7328.6 | 268.5 | 6335.4 | 178.4
26.25 | 4495.6 | 7625.5 | 6060.5 | 3596.5 | 5619.5 | 6100.4 | 9531.8 | 6539.9 | 4230.8 | 264.8 | 7360.7 | 264.8 | 6363.3 | 176.6
26.5 | 4513.9 | 7679.4 | 6096.6 | 3611.1 | 5642.3 | 6143.5 | 9599.3 | 6581.4 | 4233.5 | 280.4 | 7399 | 280.4 | 6395.8 | 185.6
26.75 | 4461.8 | 7662.8 | 6062.3 | 3569.4 | 5577.2 | 6130.2 | 9578.5 | 6582.5 | 4232.1 | 229.7 | 7433.1 | 229.7 | 6425.1 | 157.4
27 | 4502.7 | 7739 | 6120.9 | 3602.2 | 5628.4 | 6191.2 | 9673.7 | 6636.7 | 4234.6 | 268.2 | 7470.8 | 268.2 | 6457.3 | 179.3
27.25 | 4520.2 | 7791.5 | 6155.9 | 3616.2 | 5650.3 | 6233.2 | 9739.4 | 6676.6 | 4233.8 | 286.4 | 7505.1 | 286.4 | 6486.8 | 189.7
27.5 | 4667.6 | 7973.6 | 6320.6 | 3734.1 | 5834.5 | 6378.9 | 9967.1 | 6786.5 | 4240.9 | 426.6 | 7547 | 426.6 | 6521.7 | 264.9
27.75 | 5823.5 | 9164.4 | 7494 | 4658.8 | 7279.4 | 7331.5 | 11455.5 | 8124.5 | 4297 | 1526.5 | 7637.8 | 1526.5 | 6598 | 1526.5
28 | 6399.7 | 9777.9 | 8088.8 | 5119.7 | 7999.6 | 7822.3 | 12222.3 | 8738 | 4752.7 | 1646.9 | 8130.9 | 1646.9 | 7091.1 | 1646.9
28.25 | 6980 | 10401.4 | 8690.7 | 5584 | 8725 | 8321.1 | 13001.7 | 9361.5 | 5314 | 1665.9 | 8735.5 | 1665.9 | 7695.6 | 1665.9
28.5 | 7672.5 | 11143.6 | 9408.1 | 6138 | 9590.6 | 8914.9 | 13929.5 | 10103.7 | 5925.1 | 1747.4 | 9396.2 | 1747.4 | 8356.3 | 1747.4
28.75 | 8308.2 | 11835.8 | 10072 | 6646.5 | 10385.2 | 9468.6 | 14794.7 | 10795.9 | 6540 | 1768.2 | 10067.5 | 1768.2 | 9027.7 | 1768.2
29 | 8862.5 | 12454.3 | 10658.4 | 7090 | 11078.1 | 9963.4 | 15567.9 | 11414.4 | 7252.6 | 1609.8 | 10844.5 | 1609.8 | 9804.6 | 1609.8
29.25 | 9074.6 | 12737.5 | 10906 | 7259.7 | 11343.2 | 10190 | 15921.9 | 11697.6 | 7785.6 | 1288.9 | 11448.6 | 1288.9 | 10408.7 | 1288.9
29.5 | 9114.8 | 12853.1 | 10984 | 7291.9 | 11393.5 | 10282.5 | 16066.4 | 11813.3 | 8162.6 | 952.2 | 11900.9 | 952.2 | 10861 | 952.2
29.75 | 8555.7 | 12371 | 10463.3 | 6844.6 | 10694.7 | 9896.8 | 15463.7 | 11229.2 | 8255 | 300.7 | 12070.2 | 300.7 | 11028.7 | 200.5
30 | 9054.3 | 12946.2 | 11000.3 | 7243.5 | 11317.9 | 10357 | 16182.8 | 11901.9 | 8293.6 | 760.8 | 12185.4 | 760.8 | 11141.1 | 760.8
30.25 | 8560.8 | 12529.2 | 10545 | 6848.7 | 10701.1 | 10023.3 | 15661.4 | 11388.9 | 8277 | 283.9 | 12245.3 | 283.9 | 11197.2 | 191.6
30.5 | 8520.4 | 12564.4 | 10542.4 | 6816.3 | 10650.5 | 10051.5 | 15705.5 | 11420.9 | 8240.1 | 280.3 | 12284.1 | 280.3 | 11231 | 189.9
30.75 | 8498.3 | 12617.4 | 10557.9 | 6798.7 | 10622.9 | 10093.9 | 15771.8 | 11462.1 | 8202 | 296.3 | 12321.1 | 296.3 | 11262.9 | 199.1
31 | 8469.1 | 12662.6 | 10565.9 | 6775.3 | 10586.4 | 10130.1 | 15828.3 | 11503.2 | 8176.1 | 293 | 12369.6 | 293 | 11305.6 | 197.6
31.25 | 8452.4 | 12719.7 | 10586 | 6761.9 | 10565.5 | 10175.7 | 15899.6 | 11546.7 | 8140.4 | 312 | 12407.7 | 312 | 11338.3 | 208.4
31.5 | 8428.7 | 12769.1 | 10598.9 | 6743 | 10535.9 | 10215.3 | 15961.4 | 11587.1 | 8111.1 | 317.6 | 12451.5 | 317.6 | 11375.3 | 211.8
31.75 | 8373.4 | 12786.3 | 10579.9 | 6698.7 | 10466.8 | 10229.1 | 15982.9 | 11608.6 | 8078.5 | 295 | 12491.4 | 295 | 11409.2 | 199.4
32 | 8515.1 | 13000 | 10757.5 | 6812.1 | 10643.9 | 10400 | 16250 | 11742.6 | 8063.7 | 451.4 | 12548.6 | 451.4 | 11457.9 | 284.7
32.25 | 9452.1 | 14008.7 | 11730.4 | 7561.7 | 11815.1 | 11206.9 | 17510.8 | 12908.2 | 8152.5 | 1299.6 | 12709.1 | 1299.6 | 11608.6 | 1299.6
32.5 | 9544.9 | 14174.7 | 11859.8 | 7635.9 | 11931.2 | 11339.8 | 17718.4 | 13074.3 | 8392.2 | 1152.7 | 13022 | 1152.7 | 11921.5 | 1152.7
32.75 | 10091.2 | 14795.3 | 12443.2 | 8072.9 | 12614 | 11836.3 | 18494.1 | 13685.8 | 8555.8 | 1535.4 | 13259.9 | 1535.4 | 12150.4 | 1535.4
33 | 10489.8 | 15271.6 | 12880.7 | 8391.8 | 13112.2 | 12217.3 | 19089.5 | 14162 | 9018.5 | 1471.3 | 13800.2 | 1471.3 | 12690.7 | 1471.3
33.25 | 11078.6 | 15941.2 | 13509.9 | 8862.9 | 13848.3 | 12752.9 | 19926.4 | 14826.5 | 9264.2 | 1814.4 | 14126.8 | 1814.4 | 13012.1 | 1814.4
33.5 | 11390.8 | 16336 | 13863.4 | 9112.6 | 14238.5 | 13068.8 | 20420 | 14188.5 | 9433.9 | 1956.9 | 14379.1 | 1956.9 | 13214.5 | 973.9
33.75 | 13936.3 | 18967.7 | 16452 | 11149.1 | 17420.4 | 15174.2 | 23709.7 | 17766.4 | 10003.2 | 3933.1 | 15034.6 | 3933.1 | 13833.2 | 3933.1
34 | 12782.6 | 17910.4 | 15346.5 | 10226.1 | 15978.3 | 14328.3 | 22388 | 16646.4 | 10785.8 | 1996.8 | 15913.6 | 1996.8 | 14649.6 | 1996.8
34.25 | 24289.8 | 29526.1 | 26908 | 19431.9 | 30362.3 | 23620.9 | 36907.6 | 19809.5 | 11344.2 | 12945.6 | 16580.5 | 12945.6 | 15088.2 | 4721.3
34.5 | 22083.2 | 27452.7 | 24767.9 | 17666.5 | 27604 | 21962.2 | 34315.9 | 25262.2 | 12321.1 | 9762.1 | 17690.6 | 9762.1 | 15500.1 | 9762.1
34.75 | 16861.3 | 22391.1 | 19626.2 | 13489 | 21076.6 | 17912.9 | 27988.9 | 18292.1 | 13395.8 | 3465.5 | 18925.6 | 3465.5 | 16713.4 | 1578.6
35 | 23855.7 | 29566.3 | 26711 | 19084.6 | 29819.7 | 23653.1 | 36957.9 | 27288.4 | 14943.6 | 8912.2 | 20654.2 | 8912.2 | 18376.2 | 8912.2
35.25 | 28734.4 | 34680.1 | 31707.3 | 22987.5 | 35918 | 27744.1 | 43350.1 | 25238.7 | 17373.2 | 11361.2 | 23318.9 | 11361.2 | 20981.5 | 4257.2
35.5 | 32118.9 | 38340.7 | 35229.8 | 25695.1 | 40148.6 | 30672.6 | 47925.9 | 35709 | 18677.8 | 13441.1 | 24899.6 | 13441.1 | 22267.9 | 13441.1
35.75 | 24278.1 | 30827.9 | 27553 | 19422.5 | 30347.6 | 24662.3 | 38534.9 | 28196.2 | 20924.9 | 3353.1 | 27474.8 | 3353.1 | 24843.1 | 3353.1
36 | 52482.6 | 59405.4 | 55944 | 41986.1 | 65603.2 | 47524.3 | 74256.8 | 36001.2 | 22765.2 | 29717.3 | 29688.1 | 29717.3 | 26476.4 | 9524.8

## SRD WTG-09
Depth (m) | SRD AH-FF (kN) | SRD AH-NFF (kN) | SRD MEAN (kN) | SRD AH-FF-LB (kN) | SRD AH-FF-UB (kN) | SRD AH-NFF-LB (kN) | SRD AH-NFF-UB (kN) | Static Cap (kN) | Shaft AH-FF (kN) | Tip AH-FF (kN) | Shaft AH-NFF (kN) | Tip AH-NFF (kN) | Shaft SC (kN) | Tip SC (kN)
0.5 | 58.6 | 58.9 | 58.7 | 46.9 | 73.3 | 47.1 | 73.6 | 58.9 | 17 | 41.6 | 17.2 | 41.6 | 17.2 | 41.6
0.75 | 66.9 | 67.5 | 67.2 | 53.5 | 83.6 | 54 | 84.4 | 67.5 | 25.2 | 41.6 | 25.9 | 41.6 | 25.9 | 41.6
1 | 79.3 | 80.4 | 79.9 | 63.5 | 99.2 | 64.3 | 100.5 | 80.4 | 37.7 | 41.6 | 38.8 | 41.6 | 38.8 | 41.6
1.25 | 65.5 | 67.1 | 66.3 | 52.4 | 81.8 | 53.7 | 83.9 | 59.9 | 46.4 | 19.1 | 48 | 19.1 | 48.1 | 11.8
1.5 | 120.9 | 123.1 | 122 | 96.7 | 151.1 | 98.5 | 153.9 | 123.2 | 58.4 | 62.5 | 60.7 | 62.5 | 60.8 | 62.5
1.75 | 149 | 152.1 | 150.5 | 119.2 | 186.2 | 121.6 | 190.1 | 152.2 | 89.9 | 59.1 | 93 | 59.1 | 93.1 | 59.1
2 | 177.1 | 181.3 | 179.2 | 141.7 | 221.3 | 145 | 226.6 | 181.4 | 124.6 | 52.5 | 128.8 | 52.5 | 128.9 | 52.5
2.25 | 221.5 | 227.2 | 224.3 | 177.2 | 276.9 | 181.7 | 283.9 | 227.3 | 155.9 | 65.6 | 161.5 | 65.6 | 161.6 | 65.6
2.5 | 259.9 | 267.2 | 263.6 | 207.9 | 324.9 | 213.8 | 334 | 267.3 | 190.7 | 69.2 | 197.9 | 69.2 | 198.1 | 69.2
2.75 | 301.2 | 310.4 | 305.8 | 240.9 | 376.5 | 248.3 | 388 | 310.5 | 224.9 | 76.3 | 234.2 | 76.3 | 234.3 | 76.3
3 | 361 | 372.6 | 366.8 | 288.8 | 451.3 | 298.1 | 465.7 | 372.7 | 273.7 | 87.3 | 285.2 | 87.3 | 285.3 | 87.3
3.25 | 395.4 | 409.7 | 402.5 | 316.3 | 494.2 | 327.7 | 512.1 | 409.8 | 316.6 | 78.7 | 330.9 | 78.7 | 331 | 78.7
3.5 | 458.1 | 475.4 | 466.7 | 366.5 | 572.6 | 380.3 | 594.3 | 475.5 | 356.2 | 101.8 | 373.6 | 101.8 | 373.7 | 101.8
3.75 | 500.1 | 520.8 | 510.5 | 400.1 | 625.2 | 416.7 | 651.1 | 521 | 394.9 | 105.2 | 415.6 | 105.2 | 415.7 | 105.2
4 | 581.4 | 605.8 | 593.6 | 465.1 | 726.8 | 484.6 | 757.3 | 605.9 | 443.4 | 138 | 467.8 | 138 | 467.9 | 138
4.25 | 643.4 | 671.9 | 657.7 | 514.7 | 804.2 | 537.5 | 839.9 | 672 | 492.7 | 150.7 | 521.2 | 150.7 | 521.3 | 150.7
4.5 | 721.1 | 754.2 | 737.6 | 576.9 | 901.4 | 603.3 | 942.7 | 754.3 | 540.5 | 180.6 | 573.6 | 180.6 | 573.7 | 180.6
4.75 | 763.5 | 801.5 | 782.5 | 610.8 | 954.3 | 641.2 | 1001.9 | 801.6 | 588.6 | 174.9 | 626.6 | 174.9 | 626.7 | 174.9
5 | 720.2 | 763.6 | 741.9 | 576.1 | 900.2 | 610.9 | 954.5 | 763.7 | 639.6 | 80.6 | 683.1 | 80.6 | 683.2 | 80.6
5.25 | 2069.2 | 2118.6 | 2093.9 | 1655.4 | 2586.6 | 1694.9 | 2648.2 | 1255.5 | 688.8 | 1380.5 | 738.1 | 1380.5 | 726.2 | 529.3
5.5 | 4630.4 | 4687.5 | 4658.9 | 3704.3 | 5787.9 | 3750 | 5859.4 | 2026.9 | 791.1 | 3839.2 | 848.3 | 3839.2 | 774.1 | 1252.7
5.75 | 4311.2 | 4381.7 | 4346.5 | 3449 | 5389 | 3505.4 | 5477.2 | 2049.8 | 1017.5 | 3293.7 | 1088 | 3293.7 | 937.5 | 1112.2
6 | 6594.6 | 6687.7 | 6641.1 | 5275.7 | 8243.2 | 5350.2 | 8359.6 | 2705.6 | 1246.5 | 5348 | 1339.6 | 5348 | 1025.3 | 1680.3
6.25 | 5534.4 | 5660.4 | 5597.4 | 4427.5 | 6917.9 | 4528.3 | 7075.5 | 2461.2 | 1464.8 | 4069.6 | 1590.8 | 4069.6 | 1111.8 | 1349.3
6.5 | 2938.7 | 3104.5 | 3021.6 | 2351 | 3673.4 | 2483.6 | 3880.6 | 1738.4 | 1604.9 | 1333.8 | 1770.7 | 1333.8 | 1201.8 | 536.5
6.75 | 2598.3 | 2806.1 | 2702.2 | 2078.6 | 3247.9 | 2244.9 | 3507.6 | 2204.3 | 1689.3 | 909 | 1897.1 | 909 | 1295.3 | 909
7 | 2358.5 | 2609.1 | 2483.8 | 1886.8 | 2948.1 | 2087.3 | 3261.4 | 1996.8 | 1838.9 | 519.6 | 2089.5 | 519.6 | 1477.2 | 519.6
7.25 | 6839 | 7133.2 | 6986.1 | 5471.2 | 8548.8 | 5706.5 | 8916.5 | 3181.6 | 1937.6 | 4901.4 | 2231.8 | 4901.4 | 1563.6 | 1618
7.5 | 5129.6 | 5474.1 | 5301.8 | 4103.7 | 6412 | 4379.3 | 6842.6 | 2734.4 | 2156.2 | 2973.4 | 2500.7 | 2973.4 | 1660.5 | 1073.9
7.75 | 7081.4 | 7481.9 | 7281.6 | 5665.1 | 8851.7 | 5985.5 | 9352.3 | 3343.4 | 2305.6 | 4775.8 | 2706 | 4775.8 | 1739.5 | 1603.9
8 | 9693.2 | 10158.1 | 9925.7 | 7754.6 | 12116.6 | 8126.4 | 12697.6 | 4104.7 | 2586.6 | 7106.6 | 3051.4 | 7106.6 | 1856.9 | 2247.7
8.25 | 10365.8 | 10907.9 | 10636.9 | 8292.6 | 12957.3 | 8726.3 | 13634.9 | 4340.1 | 2873.2 | 7492.6 | 3415.3 | 7492.6 | 1976.9 | 2363.2
8.5 | 11632.9 | 12266.5 | 11949.7 | 9306.3 | 14541.2 | 9813.2 | 15333.1 | 4735.5 | 3227.2 | 8405.7 | 3860.8 | 8405.7 | 2119.5 | 2616
8.75 | 11331.4 | 12071.2 | 11701.3 | 9065.1 | 14164.3 | 9656.9 | 15089 | 4724 | 3522.6 | 7808.9 | 4262.3 | 7808.9 | 2249.9 | 2474.1
9 | 10939.1 | 11798 | 11368.6 | 8751.3 | 13673.9 | 9438.4 | 14747.5 | 4690.4 | 3835.7 | 7103.4 | 4694.6 | 7103.4 | 2391.5 | 2298.9
9.25 | 8642.6 | 9630.2 | 9136.4 | 6914.1 | 10803.3 | 7704.2 | 12037.8 | 4117.6 | 4017.7 | 4625 | 5005.2 | 4625 | 2501.7 | 1615.9
9.5 | 9746.6 | 10866.9 | 10306.8 | 7797.3 | 12183.3 | 8693.5 | 13583.7 | 4506.3 | 4194.7 | 5552 | 5315 | 5552 | 2615.3 | 1891
9.75 | 11395.3 | 12654 | 12024.7 | 9116.2 | 14244.1 | 10123.2 | 15817.6 | 5039.1 | 4405.1 | 6990.2 | 5663.9 | 6990.2 | 2736.6 | 2302.5
10 | 8570.6 | 9975.2 | 9272.9 | 6856.5 | 10713.3 | 7980.1 | 12469 | 4356.1 | 4638.8 | 3931.8 | 6043.4 | 3931.8 | 2923.9 | 1432.2
10.25 | 8011.9 | 9564.8 | 8788.3 | 6409.5 | 10014.9 | 7651.8 | 11956 | 4256.1 | 4718.4 | 3293.4 | 6271.4 | 3293.4 | 3014.9 | 1241.2
10.5 | 8325.9 | 10027.1 | 9176.5 | 6660.7 | 10407.3 | 8021.6 | 12533.8 | 6630.8 | 4830.1 | 3495.7 | 6531.3 | 3495.7 | 3135.1 | 3495.7
10.75 | 8776.9 | 10629 | 9702.9 | 7021.5 | 10971.1 | 8503.2 | 13286.2 | 4861.1 | 5091.3 | 3685.7 | 6943.3 | 3685.7 | 3486.2 | 1374.9
11 | 12589.5 | 14596.4 | 13593 | 10071.6 | 15736.9 | 11677.1 | 18245.5 | 6053.8 | 5338.6 | 7250.9 | 7345.5 | 7250.9 | 3626.9 | 2426.9
11.25 | 14975.3 | 17146.5 | 16060.9 | 11980.3 | 18719.2 | 13717.2 | 21433.1 | 6789.4 | 5620.4 | 9354.9 | 7791.6 | 9354.9 | 3775.7 | 3013.7
11.5 | 10960.8 | 13306.3 | 12133.6 | 8768.7 | 13701.1 | 10645 | 16632.8 | 5746.7 | 5850.5 | 5110.4 | 8195.9 | 5110.4 | 3918.5 | 1828.2
11.75 | 8356.1 | 10879.3 | 9617.7 | 6684.9 | 10445.1 | 8703.5 | 13599.2 | 5171.3 | 6080.4 | 2275.7 | 8603.7 | 2275.7 | 4236.2 | 935.1
12 | 6624.1 | 9323.9 | 7974 | 5299.3 | 8280.1 | 7459.1 | 11654.9 | 4918.9 | 6175.6 | 448.5 | 8875.4 | 448.5 | 4470.4 | 448.5
12.25 | 8512.5 | 11384.7 | 9948.6 | 6810 | 10640.6 | 9107.7 | 14230.9 | 5593 | 6210.4 | 2302 | 9082.7 | 2302 | 4642.4 | 950.6
12.5 | 7616.8 | 10657.5 | 9137.1 | 6093.4 | 9520.9 | 8526 | 13321.9 | 5353 | 6227.3 | 1389.5 | 9268.1 | 1389.5 | 4726.6 | 626.4
12.75 | 6842.2 | 10049 | 8445.6 | 5473.8 | 8552.8 | 8039.2 | 12561.2 | 5505.4 | 6454.6 | 387.6 | 9661.3 | 387.6 | 5117.7 | 387.6
13 | 6969.7 | 10338.1 | 8653.9 | 5575.8 | 8712.1 | 8270.5 | 12922.6 | 5793.8 | 6462.8 | 506.9 | 9831.2 | 506.9 | 5287 | 506.9
13.25 | 6790.1 | 10314.5 | 8552.3 | 5432.1 | 8487.6 | 8251.6 | 12893.2 | 5770.3 | 6419.7 | 370.4 | 9944.1 | 370.4 | 5399.9 | 370.4
13.5 | 6769.7 | 10444.6 | 8607.1 | 5415.7 | 8462.1 | 8355.7 | 13055.7 | 5895.5 | 6388.2 | 381.5 | 10063.1 | 381.5 | 5514 | 381.5
13.75 | 6741 | 10561.3 | 8651.2 | 5392.8 | 8426.2 | 8449.1 | 13201.6 | 6012.2 | 6340 | 401 | 10160.3 | 401 | 5611.2 | 401
14 | 6677.1 | 10637.6 | 8657.3 | 5341.7 | 8346.4 | 8510.1 | 13297 | 6088.2 | 6288.3 | 388.8 | 10248.8 | 388.8 | 5699.4 | 388.8
14.25 | 6681.6 | 10777.2 | 8729.4 | 5345.3 | 8352 | 8621.8 | 13471.5 | 6227.1 | 6254.1 | 427.5 | 10349.8 | 427.5 | 5799.7 | 427.5
14.5 | 6627.6 | 10853.8 | 8740.7 | 5302.1 | 8284.5 | 8683.1 | 13567.3 | 6303.6 | 6212.1 | 415.5 | 10438.4 | 415.5 | 5888.1 | 415.5
14.75 | 6639.6 | 10991.9 | 8815.7 | 5311.6 | 8299.4 | 8793.5 | 13739.9 | 6441.2 | 6188.8 | 450.8 | 10541.1 | 450.8 | 5990.4 | 450.8
15 | 6685.8 | 11160.3 | 8923.1 | 5348.7 | 8357.3 | 8928.2 | 13950.4 | 6609.6 | 6183.9 | 501.9 | 10658.4 | 501.9 | 6107.7 | 501.9
15.25 | 6630.3 | 11223.3 | 8926.8 | 5304.3 | 8287.9 | 8978.6 | 14029.1 | 6672.6 | 6227.1 | 403.2 | 10820 | 403.2 | 6269.3 | 403.2
15.5 | 6624 | 11331.8 | 8977.9 | 5299.2 | 8280 | 9065.5 | 14164.8 | 6780.7 | 6181.4 | 442.6 | 10889.2 | 442.6 | 6338 | 442.6
15.75 | 6642.5 | 11461.3 | 9051.9 | 5314 | 8303.1 | 9169.1 | 14326.7 | 6909.4 | 6132 | 510.5 | 10950.8 | 510.5 | 6398.9 | 510.5
16 | 6387.6 | 11313.9 | 8850.7 | 5110.1 | 7984.5 | 9051.1 | 14142.3 | 6761.7 | 6130.5 | 257.1 | 11056.8 | 257.1 | 6504.6 | 257.1
16.25 | 6793.3 | 11823.7 | 9308.5 | 5434.6 | 8491.6 | 9459 | 14779.7 | 7270 | 6100.8 | 692.4 | 11131.3 | 692.4 | 6577.5 | 692.4
16.5 | 6486 | 11617.6 | 9051.8 | 5188.8 | 8107.5 | 9294.1 | 14522.1 | 6916.5 | 6129.1 | 356.9 | 11260.8 | 356.9 | 6705.7 | 210.8
16.75 | 6785.6 | 12015.6 | 9400.6 | 5428.5 | 8482 | 9612.5 | 15019.5 | 7457.1 | 6156.1 | 629.5 | 11386.1 | 629.5 | 6827.5 | 629.5
17 | 6729.9 | 12056.5 | 9393.2 | 5383.9 | 8412.4 | 9645.2 | 15070.7 | 7498 | 6273.3 | 456.7 | 11599.9 | 456.7 | 7041.3 | 456.7
17.25 | 6915.9 | 12337.4 | 9626.7 | 5532.7 | 8644.9 | 9870 | 15421.8 | 7778.9 | 6362.4 | 553.5 | 11783.9 | 553.5 | 7225.4 | 553.5
17.5 | 7179.4 | 12693.9 | 9936.6 | 5743.5 | 8974.3 | 10155.1 | 15867.3 | 8130.3 | 6382.4 | 797 | 11896.9 | 797 | 7333.3 | 797
17.75 | 6964.8 | 12570.3 | 9767.5 | 5571.8 | 8705.9 | 10056.2 | 15712.8 | 8002.2 | 6493.6 | 471.1 | 12099.1 | 471.1 | 7531.1 | 471.1
18 | 7224.3 | 12919.3 | 10071.8 | 5779.5 | 9030.4 | 10335.4 | 16149.1 | 8349.2 | 6496.1 | 728.2 | 12191.1 | 728.2 | 7621 | 728.2
18.25 | 7473.7 | 13256.2 | 10364.9 | 5979 | 9342.2 | 10604.9 | 16570.2 | 8683.6 | 6555.7 | 918.1 | 12338.1 | 918.1 | 7765.5 | 918.1
18.5 | 7308.4 | 13177.5 | 10242.9 | 5846.7 | 9135.5 | 10542 | 16471.8 | 8591.2 | 6795.7 | 512.8 | 12664.7 | 512.8 | 8078.4 | 512.8
18.75 | 7092.8 | 13048.5 | 10070.7 | 5674.3 | 8866.1 | 10438.8 | 16310.7 | 8365.6 | 6832.2 | 260.7 | 12787.9 | 260.7 | 8200 | 165.6
19 | 7513.1 | 13553.5 | 10533.3 | 6010.5 | 9391.4 | 10842.8 | 16941.9 | 8964.6 | 6870 | 643.1 | 12910.4 | 643.1 | 8321.5 | 643.1
19.25 | 7884.3 | 14008 | 10946.1 | 6307.4 | 9855.3 | 11206.4 | 17510 | 9415.6 | 6947.9 | 936.4 | 13071.6 | 936.4 | 8479.2 | 936.4
19.5 | 7578.5 | 13784.8 | 10681.6 | 6062.8 | 9473.1 | 11027.9 | 17231.1 | 9190.8 | 7080.6 | 497.8 | 13287 | 497.8 | 8692.9 | 497.8
19.75 | 7390.7 | 13678.6 | 10534.7 | 5912.6 | 9238.4 | 10942.9 | 17098.3 | 8964.3 | 7077.1 | 313.6 | 13365 | 313.6 | 8769.5 | 194.8
20 | 7970.2 | 14338 | 11154.1 | 6376.1 | 9962.7 | 11470.4 | 17922.5 | 9334.2 | 7129.4 | 840.8 | 13497.2 | 840.8 | 8890.2 | 444
20.25 | 7835.1 | 14282.2 | 11058.6 | 6268.1 | 9793.9 | 11425.8 | 17852.7 | 9672.1 | 7270.5 | 564.6 | 13717.6 | 564.6 | 9107.5 | 564.6
20.5 | 7872.6 | 14398.3 | 11135.5 | 6298.1 | 9840.8 | 11518.7 | 17997.9 | 9787.9 | 7318.7 | 554 | 13844.4 | 554 | 9233.9 | 554
20.75 | 7667.1 | 14270 | 10968.5 | 6133.7 | 9583.9 | 11416 | 17837.5 | 9511.6 | 7295.2 | 371.9 | 13898 | 371.9 | 9285.2 | 226.3
21 | 7617.8 | 14296.6 | 10957.2 | 6094.2 | 9522.2 | 11437.2 | 17870.7 | 9594.5 | 7369.1 | 248.7 | 14047.9 | 248.7 | 9432.4 | 162.1
21.25 | 7944.6 | 14698.3 | 11321.4 | 6355.7 | 9930.7 | 11758.6 | 18372.9 | 10081 | 7408.7 | 535.9 | 14162.4 | 535.9 | 9545.1 | 535.9
21.5 | 7576.2 | 14403.7 | 10990 | 6061 | 9470.3 | 11523 | 18004.6 | 9726.6 | 7389.9 | 186.3 | 14217.4 | 186.3 | 9598.7 | 128
21.75 | 7585.2 | 14484.9 | 11035 | 6068.2 | 9481.5 | 11587.9 | 18106.1 | 9780.8 | 7341 | 244.2 | 14240.7 | 244.2 | 9620.2 | 160.6
22 | 8142.6 | 15113.1 | 11627.9 | 6514 | 10178.2 | 12090.5 | 18891.4 | 10487.6 | 7435.2 | 707.4 | 14405.8 | 707.4 | 9780.2 | 707.4
22.25 | 7807.3 | 14848.5 | 11327.9 | 6245.8 | 9759.1 | 11878.8 | 18560.6 | 10090.9 | 7465.5 | 341.8 | 14506.7 | 341.8 | 9877.6 | 213.3
22.5 | 8366.8 | 15477.8 | 11922.3 | 6693.4 | 10458.4 | 12382.3 | 19347.3 | 10840 | 7512.7 | 854 | 14623.8 | 854 | 9986 | 854
22.75 | 7892.9 | 15073.4 | 11483.1 | 6314.3 | 9866.1 | 12058.7 | 18841.8 | 10337.5 | 7614.9 | 278 | 14795.4 | 278 | 10157.2 | 180.2
23 | 7875.4 | 15124.6 | 11500 | 6300.3 | 9844.2 | 12099.7 | 18905.8 | 10406.3 | 7641.9 | 233.5 | 14891.1 | 233.5 | 10250.2 | 156.1
23.25 | 8245.7 | 15562.7 | 11904.2 | 6596.6 | 10307.1 | 12450.2 | 19453.4 | 10919.7 | 7654 | 591.7 | 14971 | 591.7 | 10328 | 591.7
23.5 | 7947.4 | 15331.5 | 11639.5 | 6358 | 9934.3 | 12265.2 | 19164.4 | 10597.5 | 7685.7 | 261.7 | 15069.8 | 261.7 | 10425.2 | 172.3
23.75 | 7906.5 | 15356.8 | 11631.6 | 6325.2 | 9883.1 | 12285.4 | 19196 | 10648.5 | 7704.4 | 202.1 | 15154.7 | 202.1 | 10509.3 | 139.2
24 | 8428.5 | 15944 | 12186.3 | 6742.8 | 10535.7 | 12755.2 | 19930 | 11297 | 7716.6 | 711.9 | 15232.1 | 711.9 | 10585.1 | 711.9
24.25 | 8404 | 15984.1 | 12194.1 | 6723.2 | 10505.1 | 12787.3 | 19980.1 | 11333.3 | 7715.5 | 688.6 | 15295.5 | 688.6 | 10644.7 | 688.6
24.5 | 8281.8 | 15925.5 | 12103.7 | 6625.4 | 10352.2 | 12740.4 | 19906.9 | 11271.6 | 7746.4 | 535.4 | 15390.1 | 535.4 | 10736.2 | 535.4
24.75 | 7974.3 | 15681 | 11827.6 | 6379.4 | 9967.9 | 12544.8 | 19601.2 | 10940.7 | 7720.6 | 253.7 | 15427.3 | 253.7 | 10771.4 | 169.3
25 | 8316.4 | 16085.2 | 12200.8 | 6653.1 | 10395.5 | 12868.2 | 20106.5 | 11428 | 7768.8 | 547.6 | 15537.6 | 547.6 | 10880.4 | 547.6
25.25 | 7981.2 | 15811.5 | 11896.4 | 6385 | 9976.5 | 12649.2 | 19764.4 | 11078.9 | 7750.8 | 230.4 | 15581.1 | 230.4 | 10922.1 | 156.8
25.5 | 8000.1 | 15891.1 | 11945.6 | 6400.1 | 10000.2 | 12712.9 | 19863.9 | 11166.3 | 7792 | 208.1 | 15683 | 208.1 | 11022 | 144.3
25.75 | 8400.6 | 16351.8 | 12376.2 | 6720.4 | 10500.7 | 13081.4 | 20439.7 | 11688.8 | 7788.2 | 612.3 | 15739.4 | 612.3 | 11076.5 | 612.3
26 | 8399.2 | 16409.9 | 12404.5 | 6719.3 | 10499 | 13127.9 | 20512.4 | 11744.8 | 7829.8 | 569.3 | 15840.6 | 569.3 | 11175.5 | 569.3
26.25 | 8452.5 | 16522.5 | 12487.5 | 6762 | 10565.6 | 13218 | 20653.1 | 11855.6 | 7909.4 | 543.1 | 15979.4 | 543.1 | 11312.5 | 543.1
26.5 | 8572.7 | 16701.7 | 12637.2 | 6858.1 | 10715.8 | 13361.3 | 20877.1 | 12030.9 | 7909.6 | 663 | 16038.6 | 663 | 11367.9 | 663
26.75 | 8118.7 | 16306 | 12212.3 | 6494.9 | 10148.3 | 13044.8 | 20382.5 | 11565.8 | 7899.2 | 219.5 | 16086.5 | 219.5 | 11413.8 | 152
27 | 8503.6 | 16748.5 | 12626.1 | 6802.9 | 10629.5 | 13398.8 | 20935.7 | 12073.4 | 7893.1 | 610.5 | 16138 | 610.5 | 11462.9 | 610.5
27.25 | 8569.5 | 16871.5 | 12720.5 | 6855.6 | 10711.8 | 13497.2 | 21089.3 | 12194 | 7897.2 | 672.3 | 16199.2 | 672.3 | 11521.7 | 672.3
27.5 | 8723.1 | 17082 | 12902.5 | 6978.5 | 10903.8 | 13665.6 | 21352.5 | 12404.6 | 8032.4 | 690.6 | 16391.4 | 690.6 | 11713.9 | 690.6
27.75 | 8771.9 | 17188.2 | 12980 | 7017.5 | 10964.9 | 13750.5 | 21485.2 | 12510.7 | 8173.8 | 598.1 | 16590.1 | 598.1 | 11912.7 | 598.1
28 | 8964.5 | 17438.5 | 13201.5 | 7171.6 | 11205.7 | 13950.8 | 21798.2 | 12761.1 | 8299.7 | 664.8 | 16773.7 | 664.8 | 12096.3 | 664.8
28.25 | 9128.5 | 17660.5 | 13394.5 | 7302.8 | 11410.6 | 14128.4 | 22075.6 | 12983 | 8433.1 | 695.4 | 16965.1 | 695.4 | 12287.6 | 695.4
28.5 | 9307.6 | 17898.1 | 13602.8 | 7446 | 11634.4 | 14318.5 | 22372.6 | 13220.7 | 8573 | 734.5 | 17163.6 | 734.5 | 12486.1 | 734.5
28.75 | 9445.8 | 18095.4 | 13770.6 | 7556.7 | 11807.3 | 14476.3 | 22619.3 | 13418 | 8731.4 | 714.4 | 17381 | 714.4 | 12703.6 | 714.4
29 | 9602.6 | 18312 | 13957.3 | 7682.1 | 12003.3 | 14649.6 | 22890 | 13634.6 | 8902 | 700.6 | 17611.4 | 700.6 | 12934 | 700.6
29.25 | 9735.6 | 18505.5 | 14120.5 | 7788.5 | 12169.5 | 14804.4 | 23131.9 | 13828 | 9058.8 | 676.8 | 17828.7 | 676.8 | 13151.2 | 676.8
29.5 | 9869 | 18699.9 | 14284.5 | 7895.2 | 12336.3 | 14959.9 | 23374.9 | 14022.5 | 9182.5 | 686.6 | 18013.3 | 686.6 | 13335.9 | 686.6
29.75 | 10262.6 | 19155.1 | 14708.8 | 8210.1 | 12828.3 | 15324.1 | 23943.8 | 14477.6 | 9376.9 | 885.7 | 18269.4 | 885.7 | 13591.9 | 885.7
30 | 10481.4 | 19437 | 14959.2 | 8385.1 | 13101.8 | 15549.6 | 24296.3 | 14759.6 | 9662.3 | 819.2 | 18617.9 | 819.2 | 13940.4 | 819.2
30.25 | 10682.7 | 19702.9 | 15192.8 | 8546.2 | 13353.4 | 15762.4 | 24628.7 | 15025.5 | 9836.8 | 845.9 | 18857.1 | 845.9 | 14179.6 | 845.9
30.5 | 10860.6 | 19946.5 | 15403.5 | 8688.4 | 13575.7 | 15957.2 | 24933.1 | 15269 | 10015.1 | 845.4 | 19101 | 845.4 | 14423.6 | 845.4
30.75 | 11984.4 | 21136.7 | 16560.5 | 9587.5 | 14980.5 | 16909.3 | 26420.9 | 16453.7 | 10096.5 | 1887.9 | 19248.8 | 1887.9 | 14565.7 | 1887.9
31 | 11800.1 | 21020.4 | 16410.2 | 9440.1 | 14750.1 | 16816.3 | 26275.5 | 16334.3 | 10473.1 | 1327 | 19693.5 | 1327 | 15007.4 | 1327
31.25 | 11694.3 | 20985.9 | 16340.1 | 9355.4 | 14617.9 | 16788.7 | 26232.3 | 16299.8 | 10798.9 | 895.4 | 20090.4 | 895.4 | 15404.3 | 895.4
31.5 | 12162.5 | 21526.8 | 16844.6 | 9730 | 15203.1 | 17221.4 | 26908.5 | 16839.6 | 10987.6 | 1174.9 | 20351.9 | 1174.9 | 15664.7 | 1174.9
31.75 | 12613.6 | 22052.1 | 17332.9 | 10090.9 | 15767 | 17641.7 | 27565.1 | 17364.9 | 11250.7 | 1362.9 | 20689.2 | 1362.9 | 16001.9 | 1362.9
32 | 12954 | 22469.7 | 17711.9 | 10363.2 | 16192.5 | 17975.8 | 28087.2 | 17782.5 | 11682.3 | 1271.7 | 21198 | 1271.7 | 16510.8 | 1271.7
32.25 | 14346.4 | 23943.4 | 19144.9 | 11477.1 | 17933 | 19154.7 | 29929.2 | 18113 | 12132 | 2214.4 | 21728.9 | 2214.4 | 17037.9 | 1075.1
32.5 | 15790.3 | 25473.7 | 20632 | 12632.2 | 19737.8 | 20379 | 31842.2 | 20713.4 | 12515.9 | 3274.4 | 22199.3 | 3274.4 | 17439 | 3274.4
32.75 | 17101.7 | 26880.2 | 21991 | 13681.4 | 21377.1 | 21504.2 | 33600.3 | 22051.8 | 12980.7 | 4120.9 | 22759.3 | 4120.9 | 17930.9 | 4120.9
33 | 16784.2 | 26665.3 | 21724.7 | 13427.3 | 20980.2 | 21332.2 | 33331.6 | 21833 | 13770.5 | 3013.7 | 23651.6 | 3013.7 | 18819.3 | 3013.7
33.25 | 14821.6 | 24812.3 | 19816.9 | 11857.3 | 18527 | 19849.8 | 31015.3 | 19702.1 | 14143.6 | 677.9 | 24134.3 | 677.9 | 19299 | 403
33.5 | 19901.6 | 30003.2 | 24952.4 | 15921.3 | 24877 | 24002.5 | 37503.9 | 21819.2 | 14303.7 | 5597.8 | 24405.3 | 5597.8 | 19475.3 | 2343.9
33.75 | 22959.9 | 33179.2 | 28069.6 | 18367.9 | 28699.9 | 26543.4 | 41474 | 28017.6 | 14763.3 | 8196.6 | 24982.6 | 8196.6 | 19821 | 8196.6
34 | 21088.7 | 31439 | 26263.9 | 16871 | 26360.9 | 25151.2 | 39298.8 | 22627.7 | 15250.5 | 5838.3 | 25600.8 | 5838.3 | 20193.3 | 2434.4
34.25 | 17783.8 | 28273.3 | 23028.6 | 14227.1 | 22229.8 | 22618.7 | 35341.7 | 21473.6 | 15536.4 | 2247.4 | 26025.9 | 2247.4 | 20373.3 | 1100.3
34.5 | 20021.5 | 30654.7 | 25338.1 | 16017.2 | 25026.8 | 24523.7 | 38318.3 | 22418 | 15759.1 | 4262.3 | 26392.3 | 4262.3 | 20539.7 | 1878.3
34.75 | 19682.3 | 30464.1 | 25073.2 | 15745.8 | 24602.9 | 24371.3 | 38080.1 | 22433.7 | 15971.5 | 3710.8 | 26753.3 | 3710.8 | 20758 | 1675.7
35 | 23223.3 | 34159.1 | 28691.2 | 18578.6 | 29029.1 | 27327.2 | 42698.8 | 23782 | 16318.3 | 6905 | 27254.1 | 6905 | 20966.5 | 2815.5
35.25 | 22345.8 | 33445.3 | 27895.6 | 17876.7 | 27932.3 | 26756.3 | 41806.7 | 23568.7 | 16681.2 | 5664.6 | 27780.7 | 5664.6 | 21178.2 | 2390.5
35.5 | 22250.7 | 33523.2 | 27887 | 17800.6 | 27813.4 | 26818.6 | 41904.1 | 23996.8 | 17350.1 | 4900.6 | 28622.6 | 4900.6 | 21875.5 | 2121.3
35.75 | 19395.8 | 30850.8 | 25123.3 | 15516.6 | 24244.7 | 24680.7 | 38563.5 | 24041.8 | 17983.7 | 1412 | 29438.8 | 1412 | 22629.8 | 1412
36 | 21018.6 | 32665.3 | 26841.9 | 16814.8 | 26273.2 | 26132.3 | 40831.6 | 25694.2 | 19497.9 | 1520.7 | 31144.7 | 1520.7 | 24173.6 | 1520.7
36.25 | 25798.1 | 37663.3 | 31730.7 | 20638.5 | 32247.6 | 30130.6 | 47079.1 | 30664.7 | 20895.3 | 4902.8 | 32760.5 | 4902.8 | 25761.9 | 4902.8
36.5 | 27551.6 | 39642.6 | 33597.1 | 22041.2 | 34439.4 | 31714.1 | 49553.3 | 28770.4 | 21275.1 | 6276.4 | 33366.2 | 6276.4 | 26150.4 | 2620
36.75 | 27247.7 | 39571.3 | 33409.5 | 21798.2 | 34059.7 | 31657 | 49464.1 | 28779.2 | 21543.5 | 5704.3 | 33867 | 5704.3 | 26356.7 | 2422.5
37 | 36560.9 | 49125.5 | 42843.2 | 29248.7 | 45701.1 | 39300.4 | 61406.9 | 41202.1 | 22077.5 | 14483.4 | 34642.1 | 14483.4 | 26718.7 | 14483.4
37.25 | 28449.1 | 41289.5 | 34869.3 | 22759.3 | 35561.3 | 33031.6 | 51611.9 | 30539.3 | 23604.4 | 4844.6 | 36444.9 | 4844.6 | 28419.6 | 2119.6
37.5 | 30577.2 | 43707.4 | 37142.3 | 24461.8 | 38221.6 | 34965.9 | 54634.2 | 35573.7 | 24189.1 | 6388.1 | 37319.2 | 6388.1 | 29185.5 | 6388.1
37.75 | 31969.3 | 45396.9 | 38683.1 | 25575.4 | 39961.6 | 36317.6 | 56746.2 | 37034.1 | 24350.8 | 7618.5 | 37778.5 | 7618.5 | 29415.6 | 7618.5
38 | 34435.2 | 48175.1 | 41305.2 | 27548.2 | 43044 | 38540.1 | 60218.9 | 34245.7 | 25507 | 8928.2 | 39246.9 | 8928.2 | 30704.8 | 3541
38.25 | 43634.8 | 57710.5 | 50672.6 | 34907.8 | 54543.4 | 46168.4 | 72138.1 | 37878.6 | 26554.8 | 17080 | 40630.6 | 17080 | 31791.3 | 6087.3

## SRD WTG-10
Depth (m) | SRD AH-FF (kN) | SRD AH-NFF (kN) | SRD MEAN (kN) | SRD AH-FF-LB (kN) | SRD AH-FF-UB (kN) | SRD AH-NFF-LB (kN) | SRD AH-NFF-UB (kN) | Static Cap (kN) | Shaft AH-FF (kN) | Tip AH-FF (kN) | Shaft AH-NFF (kN) | Tip AH-NFF (kN) | Shaft SC (kN) | Tip SC (kN)
0.5 | 69.2 | 69.3 | 69.3 | 55.4 | 86.5 | 55.5 | 86.7 | 31.4 | 4.7 | 64.5 | 4.9 | 64.5 | 3.4 | 28.1
0.75 | 66.7 | 67 | 66.8 | 53.4 | 83.4 | 53.6 | 83.7 | 33.5 | 7.3 | 59.4 | 7.5 | 59.4 | 5.5 | 28.1
1 | 67.8 | 68.3 | 68.1 | 54.3 | 84.8 | 54.6 | 85.4 | 37 | 11.3 | 56.6 | 11.7 | 56.6 | 9 | 28.1
1.25 | 70.3 | 71 | 70.6 | 56.2 | 87.8 | 56.8 | 88.7 | 40.8 | 14.5 | 55.7 | 15.3 | 55.7 | 12 | 28.7
1.5 | 72 | 73 | 72.5 | 57.6 | 89.9 | 58.4 | 91.2 | 44.3 | 18.2 | 53.8 | 19.2 | 53.8 | 15.6 | 28.7
1.75 | 3514.5 | 3515.9 | 3515.2 | 2811.6 | 4393.1 | 2812.8 | 4394.9 | 977.3 | 36.8 | 3477.7 | 38.2 | 3477.7 | 24.4 | 952.9
2 | 11284.3 | 11294.2 | 11289.3 | 9027.5 | 14105.4 | 9035.4 | 14117.7 | 2651 | 260.8 | 11023.5 | 270.7 | 11023.5 | 89.4 | 2561.6
2.25 | 1975.7 | 2016.1 | 1995.9 | 1580.6 | 2469.6 | 1612.9 | 2520.1 | 655.5 | 454.6 | 1521.1 | 495 | 1521.1 | 152.1 | 503.4
2.5 | 1023.7 | 1100.1 | 1061.9 | 819 | 1279.7 | 880.1 | 1375.1 | 750.1 | 672.5 | 351.2 | 748.9 | 351.2 | 398.9 | 351.2
2.75 | 871.1 | 984.4 | 927.8 | 696.9 | 1088.9 | 787.5 | 1230.5 | 546.6 | 702.3 | 168.8 | 815.6 | 168.8 | 463.4 | 83.2
3 | 1335.8 | 1483.5 | 1409.7 | 1068.6 | 1669.7 | 1186.8 | 1854.4 | 736.2 | 709.3 | 626.5 | 857 | 626.5 | 484.3 | 252
3.25 | 815.1 | 995.3 | 905.2 | 652.1 | 1018.8 | 796.2 | 1244.1 | 560.1 | 688.2 | 126.9 | 868.4 | 126.9 | 492.7 | 67.4
3.5 | 989.7 | 1200.2 | 1095 | 791.8 | 1237.2 | 960.2 | 1500.3 | 822 | 720 | 269.7 | 930.5 | 269.7 | 552.3 | 269.7
3.75 | 809.5 | 1048.5 | 929 | 647.6 | 1011.8 | 838.8 | 1310.6 | 621.9 | 702.5 | 107 | 941.5 | 107 | 562 | 59.9
4 | 790.1 | 1055.6 | 922.8 | 632 | 987.6 | 844.5 | 1319.5 | 629.5 | 685.3 | 104.7 | 950.9 | 104.7 | 570.1 | 59.4
4.25 | 780.4 | 1070.6 | 925.5 | 624.3 | 975.4 | 856.5 | 1338.2 | 640.7 | 669.7 | 110.7 | 959.9 | 110.7 | 577.9 | 62.8
4.5 | 787.7 | 1101 | 944.4 | 630.2 | 984.7 | 880.8 | 1376.2 | 659.5 | 656.9 | 130.9 | 970.1 | 130.9 | 586.7 | 72.9
4.75 | 758.5 | 1093.3 | 925.9 | 606.8 | 948.1 | 874.6 | 1366.6 | 660.3 | 645.3 | 113.2 | 980.1 | 113.2 | 595.2 | 65.1
5 | 765 | 1119.8 | 942.4 | 612 | 956.2 | 895.9 | 1399.8 | 677.8 | 636.2 | 128.8 | 991.1 | 128.8 | 604.7 | 73.1
5.25 | 742.1 | 1115.9 | 929 | 593.7 | 927.7 | 892.7 | 1394.9 | 680.4 | 627.7 | 114.4 | 1001.5 | 114.4 | 613.7 | 66.8
5.5 | 742.8 | 1134.4 | 938.6 | 594.2 | 928.5 | 907.5 | 1418 | 694.3 | 621.3 | 121.5 | 1012.9 | 121.5 | 623.5 | 70.7
5.75 | 737.2 | 1145.5 | 941.4 | 589.7 | 921.5 | 916.4 | 1431.9 | 704.3 | 615.2 | 122 | 1023.6 | 122 | 632.9 | 71.5
6 | 755.6 | 1179.9 | 967.8 | 604.5 | 944.6 | 943.9 | 1474.8 | 726.2 | 611.9 | 143.7 | 1036.1 | 143.7 | 643.7 | 82.5
6.25 | 732.1 | 1171.4 | 951.8 | 585.7 | 915.1 | 937.1 | 1464.2 | 727.1 | 609.4 | 122.7 | 1048.7 | 122.7 | 654.3 | 72.8
6.5 | 746.1 | 1199.7 | 972.9 | 596.9 | 932.6 | 959.7 | 1499.6 | 746.3 | 607.7 | 138.4 | 1061.2 | 138.4 | 665.3 | 81
6.75 | 739.1 | 1206.4 | 972.7 | 591.3 | 923.9 | 965.1 | 1507.9 | 759.4 | 615.7 | 123.4 | 1082.9 | 123.4 | 685.3 | 74.1
7 | 744.5 | 1224.8 | 984.6 | 595.6 | 930.6 | 979.8 | 1531 | 773.9 | 615.3 | 129.1 | 1095.7 | 129.1 | 696.5 | 77.4
7.25 | 747.9 | 1240.7 | 994.3 | 598.3 | 934.8 | 992.6 | 1550.9 | 787 | 615.4 | 132.4 | 1108.3 | 132.4 | 707.5 | 79.5
7.5 | 757.9 | 1262.8 | 1010.3 | 606.3 | 947.4 | 1010.2 | 1578.5 | 803.7 | 617 | 140.9 | 1121.9 | 140.9 | 719.5 | 84.2
7.75 | 755.5 | 1271.9 | 1013.7 | 604.4 | 944.4 | 1017.6 | 1589.9 | 813.6 | 618.5 | 137 | 1134.9 | 137 | 730.9 | 82.7
8 | 766.3 | 1293.9 | 1030.1 | 613.1 | 957.9 | 1035.1 | 1617.4 | 830.5 | 621.9 | 144.4 | 1149.4 | 144.4 | 743.6 | 86.9
8.25 | 756 | 1294.3 | 1025.2 | 604.8 | 945 | 1035.4 | 1617.9 | 836.2 | 625 | 131 | 1163.3 | 131 | 755.7 | 80.5
8.5 | 777.4 | 1326.1 | 1051.7 | 621.9 | 971.7 | 1060.9 | 1657.6 | 858.3 | 630 | 147.4 | 1178.7 | 147.4 | 769.1 | 89.3
8.75 | 792.5 | 1351.3 | 1071.9 | 634 | 990.6 | 1081 | 1689.1 | 876.8 | 634.2 | 158.3 | 1193 | 158.3 | 781.6 | 95.2
9 | 779.6 | 1348.2 | 1063.9 | 623.6 | 974.4 | 1078.6 | 1685.3 | 881.4 | 639.6 | 139.9 | 1208.3 | 139.9 | 795.1 | 86.3
9.25 | 782.7 | 1360.9 | 1071.8 | 626.1 | 978.4 | 1088.8 | 1701.2 | 893.6 | 644.1 | 138.6 | 1222.4 | 138.6 | 807.6 | 86
9.5 | 790.1 | 1377.7 | 1083.9 | 632 | 987.6 | 1102.1 | 1722.1 | 908.4 | 650.4 | 139.7 | 1238 | 139.7 | 821.4 | 87
9.75 | 796 | 1392.7 | 1094.4 | 636.8 | 995 | 1114.2 | 1740.9 | 922 | 655.6 | 140.4 | 1252.4 | 140.4 | 834.3 | 87.7
10 | 805.5 | 1411.1 | 1108.3 | 644.4 | 1006.8 | 1128.9 | 1763.9 | 937.9 | 662.5 | 143 | 1268.1 | 143 | 848.4 | 89.5
10.25 | 815.6 | 1430.1 | 1122.8 | 652.5 | 1019.5 | 1144 | 1787.6 | 953.7 | 668.6 | 147 | 1283 | 147 | 861.7 | 92
10.5 | 831.2 | 1454.2 | 1142.7 | 664.9 | 1038.9 | 1163.3 | 1817.7 | 972.8 | 676.8 | 154.3 | 1299.8 | 154.3 | 876.6 | 96.2
10.75 | 846.3 | 1477.8 | 1162.1 | 677.1 | 1057.9 | 1182.3 | 1847.3 | 991.3 | 684.5 | 161.8 | 1316.1 | 161.8 | 890.9 | 100.4
11 | 859.5 | 1499.4 | 1179.5 | 687.6 | 1074.4 | 1199.5 | 1874.3 | 1017.2 | 710.5 | 149 | 1350.4 | 149 | 923.1 | 94.1
11.25 | 872.8 | 1521.1 | 1196.9 | 698.2 | 1090.9 | 1216.8 | 1901.3 | 1034.9 | 718.4 | 154.3 | 1366.7 | 154.3 | 937.6 | 97.3
11.5 | 876.1 | 1532.7 | 1204.4 | 700.9 | 1095.1 | 1226.2 | 1915.9 | 1047.8 | 727.6 | 148.5 | 1384.2 | 148.5 | 953.2 | 94.6
11.75 | 902.2 | 1567 | 1234.6 | 721.8 | 1127.8 | 1253.6 | 1958.8 | 1072.2 | 735.8 | 166.4 | 1400.6 | 166.4 | 967.9 | 104.4
12 | 911 | 1583.9 | 1247.4 | 728.8 | 1138.7 | 1267.1 | 1979.8 | 1088.2 | 746.9 | 164.1 | 1419.8 | 164.1 | 984.7 | 103.5
12.25 | 1224.3 | 1905.3 | 1564.8 | 979.5 | 1530.4 | 1524.3 | 2381.7 | 1467.3 | 762 | 462.3 | 1443 | 462.3 | 1005 | 462.3
12.5 | 972.4 | 1661.7 | 1317 | 777.9 | 1215.5 | 1329.4 | 2077.1 | 1166.6 | 816.4 | 155.9 | 1505.8 | 155.9 | 1066.7 | 99.9
12.75 | 983.5 | 1681.2 | 1332.3 | 786.8 | 1229.3 | 1344.9 | 2101.5 | 1183.6 | 825.4 | 158.1 | 1523.1 | 158.1 | 1082.2 | 101.4
13 | 1006.4 | 1712.4 | 1359.4 | 805.1 | 1258 | 1370 | 2140.6 | 1207.5 | 836.2 | 170.2 | 1542.3 | 170.2 | 1099.3 | 108.2
13.25 | 1025.8 | 1740.2 | 1383 | 820.7 | 1282.3 | 1392.1 | 2175.2 | 1229.1 | 847 | 178.8 | 1561.4 | 178.8 | 1116.1 | 113.1
13.5 | 1024.4 | 1747 | 1385.7 | 819.5 | 1280.5 | 1397.6 | 2183.7 | 1240.3 | 858.9 | 165.5 | 1581.5 | 165.5 | 1133.9 | 106.4
13.75 | 1034.2 | 1765 | 1399.6 | 827.3 | 1292.7 | 1412 | 2206.3 | 1256.9 | 869.4 | 164.8 | 1600.2 | 164.8 | 1150.6 | 106.3
14 | 1083.7 | 1822.8 | 1453.2 | 866.9 | 1354.6 | 1458.2 | 2278.4 | 1295.1 | 881.6 | 202 | 1620.7 | 202 | 1168.8 | 126.4
14.25 | 1506.8 | 2254.2 | 1880.5 | 1205.5 | 1883.5 | 1803.4 | 2817.8 | 1799.1 | 925.7 | 581.1 | 1673.1 | 581.1 | 1218 | 581.1
14.5 | 1168.7 | 1924.9 | 1546.8 | 935 | 1460.9 | 1540 | 2406.2 | 1409.5 | 999.3 | 169.4 | 1755.6 | 169.4 | 1299.8 | 109.8
14.75 | 1604.8 | 2370.1 | 1987.5 | 1283.8 | 2006 | 1896.1 | 2962.6 | 1910.6 | 1048.1 | 556.7 | 1813.4 | 556.7 | 1354 | 556.7
15 | 1311.5 | 2086.3 | 1698.9 | 1049.2 | 1639.4 | 1669.1 | 2607.9 | 1534.7 | 1080 | 231.5 | 1854.8 | 231.5 | 1391.5 | 143.2
15.25 | 1359 | 2143.4 | 1751.2 | 1087.2 | 1698.8 | 1714.7 | 2679.2 | 1572.4 | 1097.2 | 261.8 | 1881.5 | 261.8 | 1413.3 | 159.1
15.5 | 1335.4 | 2129.4 | 1732.4 | 1068.3 | 1669.2 | 1703.5 | 2661.7 | 1574.3 | 1114.7 | 220.7 | 1908.7 | 220.7 | 1436 | 138.4
15.75 | 1374.2 | 2177.8 | 1776 | 1099.3 | 1717.7 | 1742.3 | 2722.3 | 1607.9 | 1130.9 | 243.2 | 1934.6 | 243.2 | 1457.5 | 150.5
16 | 1402.9 | 2216.4 | 1809.6 | 1122.3 | 1753.7 | 1773.1 | 2770.4 | 1637.2 | 1151 | 251.9 | 1964.5 | 251.9 | 1481.9 | 155.3
16.25 | 1410.4 | 2233.7 | 1822 | 1128.3 | 1763 | 1786.9 | 2792.1 | 1654.9 | 1168.8 | 241.6 | 1992.1 | 241.6 | 1504.5 | 150.4
16.5 | 1448.3 | 2281.6 | 1864.9 | 1158.7 | 1810.4 | 1825.2 | 2851.9 | 1689.2 | 1189.4 | 258.9 | 2022.7 | 258.9 | 1529.5 | 159.8
16.75 | 1466 | 2309.3 | 1887.6 | 1172.8 | 1832.5 | 1847.4 | 2886.6 | 1712.5 | 1206.9 | 259.1 | 2050.2 | 259.1 | 1552.2 | 160.3
17 | 1474.5 | 2327.9 | 1901.2 | 1179.6 | 1843.1 | 1862.3 | 2909.8 | 1731.7 | 1225.9 | 248.6 | 2079.3 | 248.6 | 1576.5 | 155.2
17.25 | 1495.6 | 2359.2 | 1927.4 | 1196.5 | 1869.5 | 1887.3 | 2949 | 1756.9 | 1243.6 | 252 | 2107.2 | 252 | 1599.6 | 157.4
17.5 | 1521.3 | 2395.2 | 1958.3 | 1217 | 1901.6 | 1916.2 | 2994 | 1785.5 | 1263.7 | 257.6 | 2137.6 | 257.6 | 1624.8 | 160.7
17.75 | 1564.3 | 2448.6 | 2006.5 | 1251.4 | 1955.4 | 1958.9 | 3060.7 | 1822.3 | 1281.9 | 282.4 | 2166.2 | 282.4 | 1648.4 | 173.9
18 | 1552 | 2446.8 | 1999.4 | 1241.6 | 1940 | 1957.4 | 3058.5 | 1831.4 | 1303.4 | 248.5 | 2198.2 | 248.5 | 1674.7 | 156.7
18.25 | 1579.7 | 2485 | 2032.4 | 1263.7 | 1974.6 | 1988 | 3106.3 | 1860.7 | 1322.4 | 257.2 | 2227.8 | 257.2 | 1699 | 161.6
18.5 | 1616.8 | 2532.9 | 2074.8 | 1293.4 | 2021 | 2026.3 | 3166.1 | 1895.6 | 1342 | 274.8 | 2258 | 274.8 | 1724.4 | 171.2
18.75 | 1612.2 | 2539.1 | 2075.6 | 1289.8 | 2015.2 | 2031.2 | 3173.8 | 1908.2 | 1359.9 | 252.3 | 2286.8 | 252.3 | 1748.4 | 159.8
19 | 1624.5 | 2562.2 | 2093.4 | 1299.6 | 2030.6 | 2049.8 | 3202.8 | 1930.4 | 1380.2 | 244.3 | 2317.9 | 244.3 | 1774.5 | 155.9
19.25 | 1649.6 | 2598.3 | 2124 | 1319.7 | 2062 | 2078.7 | 3247.9 | 1958.7 | 1397.6 | 252 | 2346.3 | 252 | 1798.4 | 160.3
19.5 | 1666.9 | 2626.6 | 2146.8 | 1333.5 | 2083.6 | 2101.3 | 3283.3 | 1983.8 | 1418.3 | 248.6 | 2378.1 | 248.6 | 1825 | 158.9
19.75 | 1686.8 | 2657.6 | 2172.2 | 1349.4 | 2108.4 | 2126.1 | 3322.1 | 2009.6 | 1435.5 | 251.2 | 2406.4 | 251.2 | 1849 | 160.6
20 | 1723.8 | 2705.9 | 2214.9 | 1379.1 | 2154.8 | 2164.8 | 3382.4 | 2045.5 | 1456.3 | 267.5 | 2438.4 | 267.5 | 1875.9 | 169.6
20.25 | 1736.2 | 2729.6 | 2232.9 | 1388.9 | 2170.2 | 2183.7 | 3412 | 2067.6 | 1475 | 261.2 | 2468.4 | 261.2 | 1901 | 166.6
20.5 | 1746.8 | 2751.7 | 2249.3 | 1397.5 | 2183.6 | 2201.4 | 3439.6 | 2089.7 | 1495.5 | 251.4 | 2500.3 | 251.4 | 1928 | 161.7
20.75 | 1783.2 | 2799.5 | 2291.4 | 1426.5 | 2229 | 2239.6 | 3499.4 | 2124.8 | 1514.2 | 269 | 2530.6 | 269 | 1953.4 | 171.4
21 | 1803.5 | 2831.5 | 2317.5 | 1442.8 | 2254.4 | 2265.2 | 3539.4 | 2152.4 | 1536.3 | 267.2 | 2564.3 | 267.2 | 1981.5 | 170.8
21.25 | 1871.1 | 2910.8 | 2390.9 | 1496.8 | 2338.8 | 2328.6 | 3638.5 | 2204.1 | 1556.1 | 315 | 2595.8 | 315 | 2007.8 | 196.3
21.5 | 2095.7 | 3147.6 | 2621.7 | 1676.6 | 2619.7 | 2518.1 | 3934.5 | 2391.5 | 1692 | 403.7 | 2743.9 | 403.7 | 2149.6 | 241.9
21.75 | 2111.9 | 3177.2 | 2644.6 | 1689.5 | 2639.9 | 2541.8 | 3971.6 | 2463.4 | 1800.5 | 311.4 | 2865.8 | 311.4 | 2268.2 | 195.2
22 | 2105.2 | 3184.4 | 2644.8 | 1684.2 | 2631.5 | 2547.5 | 3980.5 | 2478.4 | 1824 | 281.2 | 2903.2 | 281.2 | 2298.7 | 179.7
22.25 | 2148.1 | 3241.3 | 2694.7 | 1718.5 | 2685.2 | 2593 | 4051.6 | 2518.8 | 1843.9 | 304.3 | 2937 | 304.3 | 2326.6 | 192.2
22.5 | 2276.2 | 3383.5 | 2829.9 | 1821 | 2845.3 | 2706.8 | 4229.4 | 2614.4 | 1886.7 | 389.5 | 2994 | 389.5 | 2377.8 | 236.6
22.75 | 2288.4 | 3410.5 | 2849.5 | 1830.7 | 2860.5 | 2728.4 | 4263.1 | 2688.4 | 2003.4 | 285 | 3125.5 | 285 | 2505.6 | 182.7
23 | 2329.8 | 3467.1 | 2898.5 | 1863.8 | 2912.3 | 2773.7 | 4333.9 | 2729.8 | 2025.6 | 304.2 | 3163 | 304.2 | 2536.6 | 193.3
23.25 | 2545.9 | 3698.8 | 3122.4 | 2036.7 | 3182.4 | 2959.1 | 4623.5 | 2898.7 | 2121.3 | 424.6 | 3274.2 | 424.6 | 2643.1 | 255.6
23.5 | 2565.1 | 3734.3 | 3149.7 | 2052.1 | 3206.4 | 2987.4 | 4667.9 | 2958.6 | 2202.6 | 362.5 | 3371.8 | 362.5 | 2734.1 | 224.5
23.75 | 2851.7 | 4037.9 | 3444.8 | 2281.3 | 3564.6 | 3230.3 | 5047.3 | 3154.1 | 2293.2 | 558.5 | 3479.4 | 558.5 | 2831.7 | 322.4
24 | 3012.3 | 4217.5 | 3614.9 | 2409.8 | 3765.4 | 3374 | 5271.8 | 3413.8 | 2625.5 | 386.8 | 3830.6 | 386.8 | 3176 | 237.8
24.25 | 3171.1 | 4397.1 | 3784.1 | 2536.9 | 3963.9 | 3517.7 | 5496.4 | 3516.4 | 2656.9 | 514.2 | 3882.9 | 514.2 | 3214.4 | 302
24.5 | 4056.7 | 5303.9 | 4680.3 | 3245.3 | 5070.8 | 4243.1 | 6629.8 | 3939.8 | 2735.3 | 1321.4 | 3982.5 | 1321.4 | 3275.4 | 664.4
24.75 | 3700.1 | 4970.6 | 4335.3 | 2960.1 | 4625.1 | 3976.5 | 6213.2 | 4230.5 | 2974.6 | 725.5 | 4245.1 | 725.5 | 3505.1 | 725.5
25 | 3336.1 | 4631.7 | 3983.9 | 2668.8 | 4170.1 | 3705.4 | 5789.6 | 3815.6 | 3104.4 | 231.7 | 4400 | 231.7 | 3659.3 | 156.3
25.25 | 3591.5 | 4912.5 | 4252 | 2873.2 | 4489.4 | 3930 | 6140.7 | 3974.6 | 3116.2 | 475.3 | 4437.3 | 475.3 | 3689.8 | 284.8
25.5 | 3739 | 5085.7 | 4412.3 | 2991.2 | 4673.7 | 4068.5 | 6357.1 | 4074.5 | 3171.8 | 567.1 | 4518.6 | 567.1 | 3743.9 | 330.6
25.75 | 3748.4 | 5121.3 | 4434.9 | 2998.7 | 4685.5 | 4097 | 6401.6 | 4106.2 | 3210.6 | 537.8 | 4583.5 | 537.8 | 3789.3 | 316.9
26 | 4592.4 | 5991.7 | 5292 | 3673.9 | 5740.4 | 4793.3 | 7489.6 | 4516.2 | 3253.8 | 1338.6 | 4653.1 | 1338.6 | 3837.6 | 678.6
26.25 | 5368.3 | 6795.2 | 6081.8 | 4294.7 | 6710.4 | 5436.1 | 8494 | 4866.4 | 3361.9 | 2006.4 | 4788.8 | 2006.4 | 3913.8 | 952.6
26.5 | 4463.4 | 5919.8 | 5191.6 | 3570.7 | 5579.3 | 4735.8 | 7399.7 | 4522.9 | 3487.4 | 976 | 4943.8 | 976 | 3999.5 | 523.4
26.75 | 4832.2 | 6319.7 | 5576 | 3865.8 | 6040.3 | 5055.7 | 7899.6 | 4743.3 | 3621.8 | 1210.4 | 5109.2 | 1210.4 | 4116 | 627.3
27 | 4782.7 | 6302.5 | 5542.6 | 3826.1 | 5978.3 | 5042 | 7878.1 | 4756.9 | 3693.3 | 1089.4 | 5213.1 | 1089.4 | 4181.3 | 575.6
27.25 | 6285.1 | 7838.3 | 7061.7 | 5028.1 | 7856.4 | 6270.6 | 9797.8 | 6766.1 | 3832.4 | 2452.7 | 5385.5 | 2452.7 | 4313.3 | 2452.7
27.5 | 6174.4 | 7764.9 | 6969.7 | 4939.6 | 7718.1 | 6211.9 | 9706.1 | 5554.2 | 4142.9 | 2031.5 | 5733.4 | 2031.5 | 4583.5 | 970.7
27.75 | 7890.4 | 9525.3 | 8707.9 | 6312.4 | 9863.1 | 7620.2 | 11906.6 | 6471 | 4624.3 | 3266.1 | 6259.1 | 3266.1 | 5026.8 | 1444.2
28 | 14486.7 | 16172.8 | 15329.8 | 11589.3 | 18108.4 | 12938.3 | 20216 | 8719.7 | 4999.8 | 9486.9 | 6686 | 9486.9 | 5201.6 | 3518.1
28.25 | 34565.8 | 36320.8 | 35443.3 | 27652.7 | 43207.3 | 29056.7 | 45401.1 | 14312.6 | 5304 | 29261.8 | 7059 | 29261.8 | 5304.2 | 9008.4
28.5 | 22895.7 | 24721.3 | 23808.5 | 18316.6 | 28619.7 | 19777 | 30901.6 | 11227.6 | 5233.5 | 17662.3 | 7059 | 17662.3 | 5304.2 | 5923.4
28.75 | 12457.4 | 14351.7 | 13404.5 | 9965.9 | 15571.8 | 11481.3 | 17939.6 | 8142.6 | 5164.7 | 7292.7 | 7059 | 7292.7 | 5304.2 | 2838.4
29 | 8422.5 | 11064.2 | 9743.3 | 6738 | 10528.1 | 8851.3 | 13830.2 | 6106.2 | 8352.5 | 70 | 10994.2 | 70 | 6047 | 59.2
29.25 | 8769 | 11634.1 | 10201.6 | 7015.2 | 10961.2 | 9307.3 | 14542.7 | 6433.2 | 8168 | 601 | 11033.1 | 601 | 6077.6 | 355.6
29.5 | 9066.5 | 12143.9 | 10605.2 | 7253.2 | 11333.1 | 9715.1 | 15179.9 | 6690.8 | 8027 | 1039.4 | 11104.5 | 1039.4 | 6128.6 | 562.2
29.75 | 9255.9 | 12535.6 | 10895.7 | 7404.7 | 11569.8 | 10028.4 | 15669.4 | 6897.6 | 7942.7 | 1313.2 | 11222.4 | 1313.2 | 6213.4 | 684.2
30 | 10247 | 13720.6 | 11983.8 | 8197.6 | 12808.7 | 10976.4 | 17150.7 | 7469.2 | 7995.5 | 2251.5 | 11469.1 | 2251.5 | 6395.4 | 1073.9
30.25 | 13263.8 | 16926.9 | 15095.3 | 10611 | 16579.7 | 13541.5 | 21158.7 | 8676.6 | 8163.2 | 5100.5 | 11826.4 | 5100.5 | 6550.4 | 2126.2
30.5 | 12865.7 | 16717.8 | 14791.8 | 10292.5 | 16082.1 | 13374.3 | 20897.3 | 8637.8 | 8388.8 | 4476.9 | 12241 | 4476.9 | 6727.4 | 1910.3
30.75 | 10762.7 | 14805.7 | 12784.2 | 8610.1 | 13453.3 | 11844.6 | 18507.2 | 9241 | 9174.8 | 1587.9 | 13217.9 | 1587.9 | 7653.1 | 1587.9
31 | 11086.3 | 15323.8 | 13205.1 | 8869.1 | 13857.9 | 12259.1 | 19154.8 | 9755.6 | 9590.6 | 1495.8 | 13828.1 | 1495.8 | 8259.9 | 1495.8
31.25 | 14403.6 | 18831.9 | 16617.8 | 11522.9 | 18004.6 | 15065.5 | 23539.9 | 13204.6 | 9818.6 | 4585.1 | 14246.8 | 4585.1 | 8619.6 | 4585.1
31.5 | 12618.9 | 17239.2 | 14929.1 | 10095.1 | 15773.6 | 13791.4 | 21549.1 | 11612 | 10441.5 | 2177.4 | 15061.9 | 2177.4 | 9434.6 | 2177.4
31.75 | 12401.6 | 17214.1 | 14807.8 | 9921.3 | 15502 | 13771.3 | 21517.6 | 10701.2 | 10658.2 | 1743.4 | 15470.7 | 1743.4 | 9824.6 | 876.6
32 | 22074 | 27081.2 | 24577.6 | 17659.2 | 27592.5 | 21664.9 | 33851.5 | 21365.4 | 11645.3 | 10428.8 | 16652.4 | 10428.8 | 10936.6 | 10428.8
32.25 | 24359 | 29582.9 | 26971 | 19487.2 | 30448.8 | 23666.4 | 36978.7 | 15803.1 | 12259.3 | 12099.7 | 17483.3 | 12099.7 | 11384.9 | 4418.2
32.5 | 48314.7 | 53778.9 | 51046.8 | 38651.8 | 60393.4 | 43023.1 | 67223.6 | 22481.7 | 13378.4 | 34936.3 | 18842.5 | 34936.3 | 11774.1 | 10707.7

## SRD WTG-11
Depth (m) | SRD AH-FF (kN) | SRD AH-NFF (kN) | SRD MEAN (kN) | SRD AH-FF-LB (kN) | SRD AH-FF-UB (kN) | SRD AH-NFF-LB (kN) | SRD AH-NFF-UB (kN) | Static Cap (kN) | Shaft AH-FF (kN) | Tip AH-FF (kN) | Shaft AH-NFF (kN) | Tip AH-NFF (kN) | Shaft SC (kN) | Tip SC (kN)
0.5 | 120.1 | 120.9 | 120.5 | 96.1 | 150.2 | 96.7 | 151.2 | 120.9 | 33.7 | 86.4 | 34.5 | 86.4 | 34.5 | 86.4
0.75 | 136.3 | 138.2 | 137.3 | 109.1 | 170.4 | 110.5 | 172.7 | 138.2 | 49.9 | 86.4 | 51.7 | 86.4 | 51.7 | 86.4
1 | 160.9 | 164 | 162.5 | 128.7 | 201.1 | 131.2 | 205 | 164 | 74.4 | 86.4 | 77.6 | 86.4 | 77.6 | 86.4
1.25 | 176.6 | 181.3 | 178.9 | 141.3 | 220.7 | 145 | 226.6 | 181.3 | 90.1 | 86.4 | 94.8 | 86.4 | 94.8 | 86.4
1.5 | 200.7 | 207.1 | 203.9 | 160.5 | 250.8 | 165.7 | 258.9 | 207.1 | 114.2 | 86.4 | 120.7 | 86.4 | 120.7 | 86.4
1.75 | 284.6 | 293 | 288.8 | 227.7 | 355.8 | 234.4 | 366.3 | 292.7 | 132.1 | 152.5 | 140.5 | 152.5 | 140.2 | 152.5
2 | 393.8 | 404.5 | 399.2 | 315.1 | 492.3 | 323.6 | 505.7 | 275 | 165 | 228.9 | 175.7 | 228.9 | 174 | 101
2.25 | 399.1 | 412.8 | 405.9 | 319.3 | 498.9 | 330.2 | 516 | 410.6 | 229.8 | 169.3 | 243.5 | 169.3 | 241.4 | 169.3
2.5 | 481.8 | 499.2 | 490.5 | 385.5 | 602.3 | 399.4 | 624 | 497.1 | 275.9 | 205.9 | 293.3 | 205.9 | 291.2 | 205.9
2.75 | 539.7 | 561.4 | 550.5 | 431.8 | 674.7 | 449.1 | 701.7 | 559.2 | 323.2 | 216.6 | 344.8 | 216.6 | 342.7 | 216.6
3 | 614 | 640.4 | 627.2 | 491.2 | 767.5 | 512.3 | 800.5 | 638.3 | 375.5 | 238.5 | 401.9 | 238.5 | 399.8 | 238.5
3.25 | 654.3 | 686.1 | 670.2 | 523.5 | 817.9 | 548.9 | 857.7 | 683.5 | 412.2 | 242.1 | 444 | 242.1 | 441.4 | 242.1
3.5 | 737.4 | 775.1 | 756.2 | 589.9 | 921.7 | 620 | 968.8 | 772.4 | 474.4 | 262.9 | 512.1 | 262.9 | 509.5 | 262.9
3.75 | 850.7 | 895 | 872.8 | 680.5 | 1063.3 | 716 | 1118.7 | 890.9 | 522.1 | 328.6 | 566.4 | 328.6 | 562.3 | 328.6
4 | 866.3 | 918.1 | 892.2 | 693.1 | 1082.9 | 734.5 | 1147.6 | 913.9 | 602 | 264.3 | 653.8 | 264.3 | 649.5 | 264.3
4.25 | 899.1 | 958.9 | 929 | 719.3 | 1123.9 | 767.1 | 1198.6 | 954.7 | 655.8 | 243.3 | 715.6 | 243.3 | 711.4 | 243.3
4.5 | 942.2 | 1010.4 | 976.3 | 753.8 | 1177.8 | 808.4 | 1263.1 | 1005.8 | 695.6 | 246.7 | 763.8 | 246.7 | 759.2 | 246.7
4.75 | 1026.9 | 1104 | 1065.5 | 821.5 | 1283.7 | 883.2 | 1380 | 1098.8 | 745 | 282 | 822.1 | 282 | 816.8 | 282
5 | 1105 | 1191.6 | 1148.3 | 884 | 1381.3 | 953.3 | 1489.5 | 1186.4 | 808.2 | 296.9 | 894.7 | 296.9 | 889.5 | 296.9
5.25 | 1209.9 | 1306.6 | 1258.3 | 968 | 1512.4 | 1045.3 | 1633.2 | 1301.4 | 874.1 | 335.8 | 970.8 | 335.8 | 965.5 | 335.8
5.5 | 1201.9 | 1309.3 | 1255.6 | 961.6 | 1502.4 | 1047.5 | 1636.7 | 1303.8 | 931.8 | 270.2 | 1039.1 | 270.2 | 1033.6 | 270.2
5.75 | 1166 | 1284.4 | 1225.2 | 932.8 | 1457.5 | 1027.5 | 1605.5 | 1181 | 958 | 208 | 1076.5 | 208 | 1069.5 | 111.6
6 | 1343 | 1472.9 | 1408 | 1074.4 | 1678.7 | 1178.3 | 1841.2 | 1465.4 | 1027.1 | 315.9 | 1157 | 315.9 | 1149.5 | 315.9
6.25 | 1456.2 | 1598.4 | 1527.3 | 1165 | 1820.3 | 1278.7 | 1998 | 1590.9 | 1099.4 | 356.9 | 1241.5 | 356.9 | 1234 | 356.9
6.5 | 1465.5 | 1620.6 | 1543 | 1172.4 | 1831.9 | 1296.4 | 2025.7 | 1612.8 | 1168.2 | 297.3 | 1323.2 | 297.3 | 1315.4 | 297.3
6.75 | 1518.1 | 1686.4 | 1602.3 | 1214.5 | 1897.6 | 1349.1 | 2108 | 1677.5 | 1200.8 | 317.3 | 1369.2 | 317.3 | 1360.3 | 317.3
7 | 1472.1 | 1654.2 | 1563.1 | 1177.7 | 1840.2 | 1323.3 | 2067.7 | 1645.1 | 1262.6 | 209.5 | 1444.6 | 209.5 | 1435.5 | 209.5
7.25 | 1794.2 | 1990.3 | 1892.3 | 1435.3 | 2242.7 | 1592.3 | 2487.9 | 1980.6 | 1321.9 | 472.3 | 1518.1 | 472.3 | 1508.3 | 472.3
7.5 | 1535.6 | 1746.6 | 1641.1 | 1228.5 | 1919.5 | 1397.3 | 2183.2 | 1681.3 | 1397.3 | 138.3 | 1608.3 | 138.3 | 1598.3 | 83
7.75 | 1760.9 | 1987.2 | 1874.1 | 1408.8 | 2201.2 | 1589.7 | 2484 | 1821.7 | 1436.1 | 324.9 | 1662.3 | 324.9 | 1651.6 | 170.2
8 | 1680 | 1921.8 | 1800.9 | 1344 | 2100 | 1537.4 | 2402.2 | 1822.7 | 1478.9 | 201.1 | 1720.6 | 201.1 | 1708 | 114.7
8.25 | 2052.9 | 2310.6 | 2181.7 | 1642.3 | 2566.1 | 1848.5 | 2888.2 | 2296.4 | 1560.9 | 492 | 1818.6 | 492 | 1804.4 | 492
8.5 | 1963.2 | 2238 | 2100.6 | 1570.5 | 2454 | 1790.4 | 2797.5 | 2086.6 | 1665.8 | 297.4 | 1940.6 | 297.4 | 1926.1 | 160.6
8.75 | 2346 | 2638.9 | 2492.5 | 1876.8 | 2932.5 | 2111.1 | 3298.6 | 2622.5 | 1758.4 | 587.7 | 2051.2 | 587.7 | 2034.8 | 587.7
9 | 2402.4 | 2714.3 | 2558.4 | 1922 | 3003.1 | 2171.5 | 3392.9 | 2697.7 | 1868 | 534.5 | 2179.9 | 534.5 | 2163.2 | 534.5
9.25 | 2564.3 | 2896.3 | 2730.3 | 2051.5 | 3205.4 | 2317.1 | 3620.4 | 2879.3 | 1974.2 | 590.2 | 2306.2 | 590.2 | 2289.2 | 590.2
9.5 | 2658.4 | 3011.9 | 2835.2 | 2126.7 | 3323 | 2409.5 | 3764.8 | 2994.9 | 2113.1 | 545.4 | 2466.5 | 545.4 | 2449.5 | 545.4
9.75 | 2899.4 | 3275.5 | 3087.5 | 2319.5 | 3624.2 | 2620.4 | 4094.4 | 3254.7 | 2225.3 | 674.1 | 2601.4 | 674.1 | 2580.6 | 674.1
10 | 3029.5 | 3430.6 | 3230.1 | 2423.6 | 3786.9 | 2744.5 | 4288.3 | 3409.8 | 2443 | 586.5 | 2844.1 | 586.5 | 2823.3 | 586.5
10.25 | 3139.9 | 3567.9 | 3353.9 | 2512 | 3924.9 | 2854.4 | 4459.9 | 3547.2 | 2579.6 | 560.3 | 3007.7 | 560.3 | 2986.9 | 560.3
10.5 | 3454.6 | 3911.1 | 3682.9 | 2763.7 | 4318.3 | 3128.9 | 4888.9 | 3890.3 | 2752.7 | 701.9 | 3209.2 | 701.9 | 3188.4 | 701.9
10.75 | 3963.8 | 4451 | 4207.4 | 3171 | 4954.7 | 3560.8 | 5563.7 | 4430.2 | 2963.3 | 1000.4 | 3450.5 | 1000.4 | 3429.8 | 1000.4
11 | 3855.2 | 4375.7 | 4115.5 | 3084.2 | 4819 | 3500.6 | 5469.7 | 4352.5 | 3124.7 | 730.5 | 3645.3 | 730.5 | 3622 | 730.5
11.25 | 4281.1 | 4836.9 | 4559 | 3424.9 | 5351.4 | 3869.5 | 6046.2 | 4809.7 | 3328.7 | 952.5 | 3884.5 | 952.5 | 3857.3 | 952.5
11.5 | 4442.3 | 5036.4 | 4739.4 | 3553.9 | 5552.9 | 4029.1 | 6295.5 | 5009.2 | 3586.9 | 855.4 | 4181 | 855.4 | 4153.8 | 855.4
11.75 | 4443.4 | 5077.5 | 4760.4 | 3554.7 | 5554.2 | 4062 | 6346.9 | 5049.3 | 3716.3 | 727.1 | 4350.4 | 727.1 | 4322.3 | 727.1
12 | 4730.4 | 5406 | 5068.2 | 3784.4 | 5913 | 4324.8 | 6757.5 | 5376.9 | 3886.8 | 843.6 | 4562.4 | 843.6 | 4533.3 | 843.6
12.25 | 4754.9 | 5474.3 | 5114.6 | 3803.9 | 5943.6 | 4379.4 | 6842.9 | 5445.1 | 4111.8 | 643.1 | 4831.2 | 643.1 | 4802 | 643.1
12.5 | 4844.8 | 5609.7 | 5227.2 | 3875.8 | 6056 | 4487.7 | 7012.1 | 5580.5 | 4237.4 | 607.4 | 5002.3 | 607.4 | 4973.2 | 607.4
12.75 | 4948.7 | 5760 | 5354.3 | 3958.9 | 6185.8 | 4608 | 7200 | 5730.8 | 4357.1 | 591.5 | 5168.5 | 591.5 | 5139.3 | 591.5
13 | 5073.5 | 5932.5 | 5503 | 4058.8 | 6341.9 | 4746 | 7415.6 | 5903.3 | 4489.7 | 583.8 | 5348.6 | 583.8 | 5319.5 | 583.8
13.25 | 5194.6 | 6102.2 | 5648.4 | 4155.7 | 6493.2 | 4881.8 | 7627.8 | 6073.1 | 4615.9 | 578.6 | 5523.6 | 578.6 | 5494.5 | 578.6
13.5 | 5398.1 | 6355.2 | 5876.7 | 4318.5 | 6747.6 | 5084.2 | 7944 | 6324.7 | 4696.1 | 701.9 | 5653.3 | 701.9 | 5622.7 | 701.9
13.75 | 5147.2 | 6154.5 | 5650.9 | 4117.7 | 6434 | 4923.6 | 7693.2 | 5970.4 | 4794.6 | 352.6 | 5802 | 352.6 | 5769.8 | 200.6
14 | 5563.4 | 6621.4 | 6092.4 | 4450.7 | 6954.3 | 5297.1 | 8276.7 | 6585 | 4850.6 | 712.8 | 5908.6 | 712.8 | 5872.2 | 712.8
14.25 | 5614 | 6723.3 | 6168.6 | 4491.2 | 7017.5 | 5378.6 | 8404.1 | 6686.8 | 4973.1 | 640.9 | 6082.4 | 640.9 | 6046 | 640.9
14.5 | 5627.3 | 6788.6 | 6207.9 | 4501.8 | 7034.1 | 5430.9 | 8485.8 | 6751.2 | 5051.1 | 576.1 | 6212.5 | 576.1 | 6175.1 | 576.1
14.75 | 5720.6 | 6934.5 | 6327.6 | 4576.5 | 7150.8 | 5547.6 | 8668.1 | 6897.1 | 5123.2 | 597.4 | 6337.1 | 597.4 | 6299.7 | 597.4
15 | 5744.6 | 7011.2 | 6377.9 | 4595.7 | 7180.7 | 5609 | 8764 | 6973.8 | 5200.6 | 544 | 6467.2 | 544 | 6429.8 | 544
15.25 | 5822.6 | 7142.3 | 6482.5 | 4658.1 | 7278.3 | 5713.8 | 8927.9 | 7103.7 | 5244.9 | 577.7 | 6564.6 | 577.7 | 6526 | 577.7
15.5 | 5981.5 | 7354.6 | 6668 | 4785.2 | 7476.9 | 5883.7 | 9193.2 | 7316 | 5340.6 | 640.9 | 6713.7 | 640.9 | 6675.1 | 640.9
15.75 | 6087.7 | 7514.6 | 6801.2 | 4870.1 | 7609.6 | 6011.7 | 9393.3 | 7475 | 5402.9 | 684.8 | 6829.9 | 684.8 | 6790.3 | 684.8
16 | 6152.6 | 7633.9 | 6893.2 | 4922 | 7690.7 | 6107.1 | 9542.3 | 7594.3 | 5516.2 | 636.3 | 6997.5 | 636.3 | 6958 | 636.3
16.25 | 6218.3 | 7754.6 | 6986.4 | 4974.6 | 7772.8 | 6203.7 | 9693.2 | 7422.9 | 5595.9 | 622.4 | 7132.2 | 622.4 | 7091.6 | 331.3
16.5 | 6391.8 | 7983.7 | 7187.8 | 5113.4 | 7989.7 | 6387 | 9979.7 | 7936.9 | 5735.5 | 656.2 | 7327.5 | 656.2 | 7280.7 | 656.2
16.75 | 6127.5 | 7775.9 | 6951.7 | 4902 | 7659.3 | 6220.7 | 9719.9 | 7592.6 | 5794.4 | 333.1 | 7442.8 | 333.1 | 7394.8 | 197.8
17 | 6556.6 | 8261.8 | 7409.2 | 5245.3 | 8195.8 | 6609.4 | 10327.2 | 8211.5 | 5861.5 | 695.2 | 7566.6 | 695.2 | 7516.3 | 695.2
17.25 | 6569.2 | 8331.5 | 7450.4 | 5255.4 | 8211.5 | 6665.2 | 10414.4 | 8281.2 | 5943.3 | 625.9 | 7705.6 | 625.9 | 7655.3 | 625.9
17.5 | 6225.4 | 8045.1 | 7135.3 | 4980.3 | 7781.8 | 6436.1 | 10056.3 | 7887.5 | 5952.8 | 272.6 | 7772.5 | 272.6 | 7718.9 | 168.6
17.75 | 6583.7 | 8460.2 | 7522 | 5267 | 8229.6 | 6768.2 | 10575.3 | 8401.6 | 5924.8 | 659 | 7801.3 | 659 | 7742.7 | 659
18 | 6244.3 | 8177.6 | 7211 | 4995.4 | 7805.3 | 6542.1 | 10222 | 8019.8 | 5982.4 | 261.9 | 7915.7 | 261.9 | 7855.9 | 163.8
18.25 | 6296 | 8286.2 | 7291.1 | 5036.8 | 7870 | 6628.9 | 10357.7 | 8124.5 | 6029.6 | 266.4 | 8019.8 | 266.4 | 7958 | 166.5
18.5 | 6726.4 | 8773.4 | 7749.9 | 5381.1 | 8408 | 7018.7 | 10966.8 | 8707.8 | 6065.6 | 660.8 | 8112.7 | 660.8 | 8047 | 660.8
18.75 | 6783.3 | 8887.3 | 7835.3 | 5426.7 | 8479.2 | 7109.8 | 11109.1 | 8817.1 | 6059.9 | 723.4 | 8163.8 | 723.4 | 8093.6 | 723.4
19 | 6540.7 | 8701.6 | 7621.2 | 5232.6 | 8175.9 | 6961.3 | 10877 | 8630.1 | 6126.6 | 414.1 | 8287.5 | 414.1 | 8216 | 414.1
19.25 | 6910 | 9128.2 | 8019.1 | 5528 | 8637.5 | 7302.5 | 11410.2 | 9055.9 | 6225.3 | 684.8 | 8443.4 | 684.8 | 8371.1 | 684.8
19.5 | 6489.9 | 8765.6 | 7627.7 | 5191.9 | 8112.4 | 7012.5 | 10957 | 8592.1 | 6226.2 | 263.7 | 8501.9 | 263.7 | 8425.1 | 167
19.75 | 6971.2 | 9304.2 | 8137.7 | 5577 | 8714.1 | 7443.3 | 11630.2 | 9224.9 | 6257.5 | 713.7 | 8590.5 | 713.7 | 8511.2 | 713.7
20 | 6623.9 | 9014.4 | 7819.1 | 5299.1 | 8279.9 | 7211.5 | 11268 | 8818.9 | 6321.6 | 302.3 | 8712.1 | 302.3 | 8631 | 187.9
20.25 | 7150.5 | 9598.9 | 8374.7 | 5720.4 | 8938.1 | 7679.1 | 11998.7 | 9517.6 | 6442 | 708.5 | 8890.4 | 708.5 | 8809.1 | 708.5
20.5 | 7170.4 | 9677.3 | 8423.8 | 5736.3 | 8962.9 | 7741.8 | 12096.6 | 9593.1 | 6482 | 688.4 | 8988.9 | 688.4 | 8904.8 | 688.4
20.75 | 7266.2 | 9831.5 | 8548.9 | 5813 | 9082.8 | 7865.2 | 12289.4 | 9744.4 | 6510.4 | 755.8 | 9075.7 | 755.8 | 8988.6 | 755.8
21 | 7327.1 | 9951.2 | 8639.2 | 5861.7 | 9158.9 | 7961 | 12439 | 9864.1 | 6641.5 | 685.7 | 9265.6 | 685.7 | 9178.4 | 685.7
21.25 | 7466.1 | 10149.8 | 8808 | 5972.9 | 9332.7 | 8119.8 | 12687.2 | 10061.5 | 6739.5 | 726.6 | 9423.2 | 726.6 | 9334.9 | 726.6
21.5 | 9091.8 | 11835.3 | 10463.6 | 7273.5 | 11364.8 | 9468.2 | 14794.1 | 10450.2 | 6780.2 | 2311.6 | 9523.7 | 2311.6 | 9413.8 | 1036.4
21.75 | 10680.9 | 13495.8 | 12088.4 | 8544.7 | 13351.1 | 10796.7 | 16869.8 | 13373.8 | 8284 | 2396.9 | 11099 | 2396.9 | 10976.9 | 2396.9
22 | 13195.1 | 16111.4 | 14653.2 | 10556.1 | 16493.8 | 12889.1 | 20139.2 | 15989.4 | 10334.8 | 2860.3 | 13251.1 | 2860.3 | 13129.1 | 2860.3
22.25 | 13022.7 | 16086.8 | 14554.8 | 10418.1 | 16278.3 | 12869.5 | 20108.5 | 15964.8 | 12031.3 | 991.4 | 15095.5 | 991.4 | 14973.4 | 991.4
22.5 | 13233.3 | 16453.5 | 14843.4 | 10586.6 | 16541.6 | 13162.8 | 20566.9 | 16331.5 | 12275.6 | 957.7 | 15495.9 | 957.7 | 15373.9 | 957.7
22.75 | 13451.7 | 16828.7 | 15140.2 | 10761.3 | 16814.6 | 13462.9 | 21035.9 | 16706.6 | 12377.7 | 1074 | 15754.7 | 1074 | 15632.7 | 1074
23 | 14146.9 | 17680.7 | 15913.8 | 11317.5 | 17683.6 | 14144.6 | 22100.9 | 17558.7 | 12576.9 | 1570 | 16110.7 | 1570 | 15988.7 | 1570
23.25 | 13831.9 | 17524.2 | 15678 | 11065.5 | 17289.9 | 14019.4 | 21905.2 | 17402.2 | 12842.8 | 989.1 | 16535.1 | 989.1 | 16413.1 | 989.1
23.5 | 15097.5 | 18948.8 | 17023.1 | 12078 | 18871.8 | 15159 | 23686 | 17613 | 12901.9 | 2195.5 | 16753.3 | 2195.5 | 16605 | 1008
23.75 | 18322 | 22334 | 20328 | 14657.6 | 22902.5 | 17867.2 | 27917.5 | 18833.4 | 13054.6 | 5267.5 | 17066.5 | 5267.5 | 16738.9 | 2094.5
24 | 18195.9 | 22374.7 | 20285.3 | 14556.7 | 22744.9 | 17899.7 | 27968.3 | 18881.7 | 13286.4 | 4909.5 | 17465.1 | 4909.5 | 16902.4 | 1979.3
24.25 | 18642.2 | 22994.5 | 20818.3 | 14913.7 | 23302.7 | 18395.6 | 28743.1 | 22351.2 | 13796.4 | 4845.8 | 18148.7 | 4845.8 | 17505.4 | 4845.8
24.5 | 21237.2 | 25781.6 | 23509.4 | 16989.7 | 26546.4 | 20625.3 | 32227 | 25138.3 | 14900.2 | 6337 | 19444.6 | 6337 | 18801.3 | 6337
24.75 | 18414.1 | 23174.4 | 20794.3 | 14731.3 | 23017.7 | 18539.6 | 28968 | 22531.1 | 16002.8 | 2411.3 | 20763.1 | 2411.3 | 20119.8 | 2411.3
25 | 22255.7 | 27246.5 | 24751.1 | 17804.6 | 27819.6 | 21797.2 | 34058.2 | 23108.7 | 16638.4 | 5617.3 | 21629.3 | 5617.3 | 20878 | 2230.6
25.25 | 31691.7 | 36921 | 34306.3 | 25353.4 | 39614.6 | 29536.8 | 46151.2 | 26252.7 | 17069 | 14622.7 | 22298.3 | 14622.7 | 21292.4 | 4960.3

## SRD WTG-12
Depth (m) | SRD AH-FF (kN) | SRD AH-NFF (kN) | SRD MEAN (kN) | SRD AH-FF-LB (kN) | SRD AH-FF-UB (kN) | SRD AH-NFF-LB (kN) | SRD AH-NFF-UB (kN) | Static Cap (kN) | Shaft AH-FF (kN) | Tip AH-FF (kN) | Shaft AH-NFF (kN) | Tip AH-NFF (kN) | Shaft SC (kN) | Tip SC (kN)
0.5 | 76.2 | 76.3 | 76.3 | 61 | 95.3 | 61.1 | 95.4 | 34 | 5.1 | 71.1 | 5.3 | 71.1 | 3.6 | 30.4
0.75 | 73.4 | 73.7 | 73.6 | 58.7 | 91.8 | 59 | 92.1 | 36.2 | 7.9 | 65.5 | 8.2 | 65.5 | 5.8 | 30.4
1 | 74.5 | 75.1 | 74.8 | 59.6 | 93.2 | 60.1 | 93.9 | 39.9 | 12.2 | 62.4 | 12.7 | 62.4 | 9.5 | 30.4
1.25 | 348.2 | 349 | 348.6 | 278.5 | 435.2 | 279.2 | 436.3 | 140.5 | 18 | 330.2 | 18.8 | 330.2 | 13.8 | 126.6
1.5 | 1139.7 | 1141.4 | 1140.6 | 911.8 | 1424.7 | 913.1 | 1426.7 | 383.2 | 50.9 | 1088.8 | 52.6 | 1088.8 | 29.5 | 353.7
1.75 | 2318.8 | 2323.2 | 2321 | 1855 | 2898.4 | 1858.6 | 2904 | 710.2 | 108.3 | 2210.4 | 112.8 | 2210.4 | 53.5 | 656.7
2 | 2755.2 | 2765.9 | 2760.5 | 2204.2 | 3444 | 2212.7 | 3457.3 | 847.7 | 174.8 | 2580.4 | 185.5 | 2580.4 | 82.2 | 765.5
2.25 | 1307.2 | 1327.8 | 1317.5 | 1045.8 | 1634 | 1062.2 | 1659.7 | 485.9 | 248.1 | 1059.1 | 268.6 | 1059.1 | 113.5 | 372.4
2.5 | 924.5 | 956.9 | 940.7 | 739.6 | 1155.6 | 765.5 | 1196.2 | 787.8 | 377.3 | 547.2 | 409.8 | 547.2 | 240.6 | 547.2
2.75 | 972.2 | 1019.5 | 995.9 | 777.8 | 1215.2 | 815.6 | 1274.4 | 568.5 | 494.4 | 477.8 | 541.8 | 477.8 | 370.1 | 198.3
3 | 1301.4 | 1365.5 | 1333.4 | 1041.1 | 1626.7 | 1092.4 | 1706.9 | 1188.9 | 614.8 | 686.6 | 678.9 | 686.6 | 502.3 | 686.6
3.25 | 1677.6 | 1761.4 | 1719.5 | 1342.1 | 2097.1 | 1409.1 | 2201.7 | 1580.8 | 741.9 | 935.7 | 825.7 | 935.7 | 645.1 | 935.7
3.5 | 1524.4 | 1629.7 | 1577.1 | 1219.5 | 1905.5 | 1303.8 | 2037.2 | 1445.9 | 889.9 | 634.5 | 995.2 | 634.5 | 811.4 | 634.5
3.75 | 1620.5 | 1750 | 1685.3 | 1296.4 | 2025.6 | 1400 | 2187.5 | 1566.2 | 1016.7 | 603.7 | 1146.3 | 603.7 | 962.4 | 603.7
4 | 1627.2 | 1782.5 | 1704.8 | 1301.8 | 2034 | 1426 | 2228.1 | 1596.6 | 1131.2 | 496 | 1286.5 | 496 | 1100.6 | 496
4.25 | 1726.8 | 1908.9 | 1817.9 | 1381.4 | 2158.5 | 1527.2 | 2386.2 | 1721.1 | 1206.1 | 520.7 | 1388.3 | 520.7 | 1200.4 | 520.7
4.5 | 1867 | 2077 | 1972 | 1493.6 | 2333.8 | 1661.6 | 2596.2 | 1887.8 | 1338 | 529.1 | 1547.9 | 529.1 | 1358.7 | 529.1
4.75 | 1960.2 | 2199.7 | 2079.9 | 1568.1 | 2450.2 | 1759.7 | 2749.6 | 2009.8 | 1443.5 | 516.6 | 1683.1 | 516.6 | 1493.2 | 516.6
5 | 2168.4 | 2438.1 | 2303.2 | 1734.7 | 2710.4 | 1950.5 | 3047.7 | 2246.5 | 1528 | 640.4 | 1797.7 | 640.4 | 1606.1 | 640.4
5.25 | 2343.1 | 2644.5 | 2493.8 | 1874.5 | 2928.9 | 2115.6 | 3305.7 | 2452.8 | 1663.6 | 679.5 | 1965 | 679.5 | 1773.3 | 679.5
5.5 | 2478.9 | 2813.4 | 2646.1 | 1983.1 | 3098.6 | 2250.7 | 3516.7 | 2619.8 | 1793.2 | 685.7 | 2127.7 | 685.7 | 1934.1 | 685.7
5.75 | 2173.6 | 2542.8 | 2358.2 | 1738.9 | 2717 | 2034.2 | 3178.5 | 2209.9 | 1890 | 283.6 | 2259.1 | 283.6 | 2064.8 | 145.1
6 | 2181.3 | 2585.3 | 2383.3 | 1745 | 2726.6 | 2068.3 | 3231.7 | 2262 | 1918.4 | 262.9 | 2322.4 | 262.9 | 2124.9 | 137.1
6.25 | 2583.1 | 3022.1 | 2802.6 | 2066.5 | 3228.9 | 2417.7 | 3777.6 | 2821 | 2000.4 | 582.7 | 2439.4 | 582.7 | 2238.3 | 582.7
6.5 | 2746.4 | 3221.5 | 2984 | 2197.1 | 3433 | 2577.2 | 4026.9 | 3020.4 | 2125.9 | 620.5 | 2601 | 620.5 | 2400 | 620.5
6.75 | 2457.2 | 2969.5 | 2713.3 | 1965.8 | 3071.5 | 2375.6 | 3711.8 | 2658 | 2217.2 | 240 | 2729.5 | 240 | 2528.4 | 129.6
7 | 2894 | 3443.6 | 3168.8 | 2315.2 | 3617.5 | 2754.9 | 4304.5 | 3237.4 | 2250 | 644 | 2799.6 | 644 | 2593.4 | 644
7.25 | 2966.7 | 3554.2 | 3260.5 | 2373.4 | 3708.4 | 2843.4 | 4442.8 | 3345.5 | 2344.2 | 622.5 | 2931.7 | 622.5 | 2723 | 622.5
7.5 | 3035.8 | 3662 | 3348.9 | 2428.6 | 3794.7 | 2929.6 | 4577.5 | 3452 | 2434.3 | 601.5 | 3060.5 | 601.5 | 2850.6 | 601.5
7.75 | 2995.9 | 3661.6 | 3328.7 | 2396.7 | 3744.9 | 2929.3 | 4577 | 3211.3 | 2525.4 | 470.5 | 3191 | 470.5 | 2979 | 232.4
8 | 3264 | 3970 | 3617 | 2611.2 | 4080 | 3176 | 4962.5 | 3756.3 | 2667 | 597 | 3373.1 | 597 | 3159.3 | 597
8.25 | 3548.7 | 4296.1 | 3922.4 | 2839 | 4435.9 | 3436.9 | 5370.2 | 4080.4 | 2750.8 | 797.9 | 3498.2 | 797.9 | 3282.5 | 797.9
8.5 | 3861.5 | 4651.5 | 4256.5 | 3089.2 | 4826.9 | 3721.2 | 5814.3 | 4435.8 | 2915.1 | 946.3 | 3705.1 | 946.3 | 3489.4 | 946.3
8.75 | 3762.9 | 4596.9 | 4179.9 | 3010.3 | 4703.6 | 3677.5 | 5746.2 | 4381.2 | 3038.7 | 724.1 | 3872.8 | 724.1 | 3657.1 | 724.1
9 | 3990.9 | 4870.2 | 4430.6 | 3192.7 | 4988.6 | 3896.2 | 6087.8 | 4654.5 | 3193.4 | 797.4 | 4072.8 | 797.4 | 3857.1 | 797.4
9.25 | 3773.4 | 4700 | 4236.7 | 3018.7 | 4716.7 | 3760 | 5875 | 4282.4 | 3354.1 | 419.2 | 4280.8 | 419.2 | 4065.1 | 217.4
9.5 | 4179.9 | 5155 | 4667.5 | 3343.9 | 5224.8 | 4124 | 6443.8 | 4935.5 | 3500.1 | 679.8 | 4475.3 | 679.8 | 4255.8 | 679.8
9.75 | 4374.3 | 5399.3 | 4886.8 | 3499.4 | 5467.8 | 4319.5 | 6749.2 | 5174.5 | 3575.7 | 798.6 | 4600.8 | 798.6 | 4376 | 798.6
10 | 4031.8 | 5107.6 | 4569.7 | 3225.5 | 5039.8 | 4086.1 | 6384.5 | 4711.6 | 3667.1 | 364.8 | 4742.9 | 364.8 | 4515.5 | 196.1
10.25 | 4297.2 | 5423.7 | 4860.4 | 3437.7 | 5371.5 | 4338.9 | 6779.6 | 4884.3 | 3694.7 | 602.5 | 4821.2 | 602.5 | 4585.2 | 299.1
10.5 | 4657.2 | 5835.3 | 5246.3 | 3725.8 | 5821.5 | 4668.3 | 7294.2 | 5597 | 3862 | 795.2 | 5040.1 | 795.2 | 4801.8 | 795.2
10.75 | 4729.9 | 5961 | 5345.5 | 3784 | 5912.4 | 4768.8 | 7451.2 | 5722.6 | 3984.8 | 745.2 | 5215.8 | 745.2 | 4977.4 | 745.2
11 | 4857.3 | 6142 | 5499.6 | 3885.8 | 6071.6 | 4913.6 | 7677.5 | 5901.2 | 4072.9 | 784.3 | 5357.7 | 784.3 | 5116.9 | 784.3
11.25 | 4392.1 | 5730.9 | 5061.5 | 3513.7 | 5490.2 | 4584.7 | 7163.6 | 5363.2 | 4106.4 | 285.8 | 5445.2 | 285.8 | 5200 | 163.2
11.5 | 4731 | 6123.4 | 5427.2 | 3784.8 | 5913.7 | 4898.7 | 7654.2 | 5872.6 | 4110 | 620.9 | 5502.5 | 620.9 | 5251.6 | 620.9
11.75 | 4811.4 | 6257 | 5534.2 | 3849.1 | 6014.2 | 5005.6 | 7821.3 | 5999.4 | 4107.4 | 704 | 5553.1 | 704 | 5295.4 | 704
12 | 4421.4 | 5920.3 | 5170.9 | 3537.1 | 5526.8 | 4736.2 | 7400.4 | 5539.7 | 4140.5 | 280.9 | 5639.4 | 280.9 | 5377.1 | 162.6
12.25 | 4402.2 | 5953.9 | 5178 | 3521.8 | 5502.8 | 4763.1 | 7442.3 | 5573.4 | 4129.6 | 272.6 | 5681.3 | 272.6 | 5414.3 | 159.1
12.5 | 4404.4 | 6008.2 | 5206.3 | 3523.5 | 5505.5 | 4806.5 | 7510.2 | 5613.2 | 4114.5 | 289.9 | 5718.3 | 289.9 | 5445.2 | 168
12.75 | 4822.2 | 6477.6 | 5649.9 | 3857.8 | 6027.7 | 5182.1 | 8097 | 6198.1 | 4118.4 | 703.8 | 5773.8 | 703.8 | 5494.3 | 703.8
13 | 4477.4 | 6184.4 | 5330.9 | 3581.9 | 5596.7 | 4947.5 | 7730.4 | 5776.4 | 4179.7 | 297.6 | 5886.7 | 297.6 | 5603.5 | 172.9
13.25 | 4545.9 | 6304.3 | 5425.1 | 3636.7 | 5682.3 | 5043.4 | 7880.3 | 5842.7 | 4158.1 | 387.8 | 5916.5 | 387.8 | 5626.4 | 216.2
13.5 | 4458.1 | 6267.8 | 5363 | 3566.5 | 5572.7 | 5014.2 | 7834.7 | 5871.7 | 4204.7 | 253.5 | 6014.3 | 253.5 | 5719.6 | 152.2
13.75 | 4478 | 6338.5 | 5408.3 | 3582.4 | 5597.5 | 5070.8 | 7923.1 | 5915.6 | 4184.2 | 293.9 | 6044.7 | 293.9 | 5743 | 172.7
14 | 4461.7 | 6372.5 | 5417.1 | 3569.4 | 5577.2 | 5098 | 7965.6 | 5942.2 | 4166.4 | 295.3 | 6077.2 | 295.3 | 5768.3 | 173.9
14.25 | 4478.5 | 6439 | 5458.8 | 3582.8 | 5598.1 | 5151.2 | 8048.8 | 5983.9 | 4148.1 | 330.4 | 6108.6 | 330.4 | 5792.4 | 191.5
14.5 | 4607.7 | 6617.4 | 5612.6 | 3686.1 | 5759.6 | 5293.9 | 8271.8 | 6078.4 | 4132.2 | 475.5 | 6142 | 475.5 | 5818.3 | 260.1
14.75 | 4523.1 | 6582.1 | 5552.6 | 3618.5 | 5653.9 | 5265.7 | 8227.6 | 6133 | 4224.2 | 298.9 | 6283.2 | 298.9 | 5955.8 | 177.2
15 | 4495.9 | 6604.1 | 5550 | 3596.7 | 5619.9 | 5283.3 | 8255.2 | 6154 | 4208 | 287.9 | 6316.2 | 287.9 | 5981.8 | 172.2
15.25 | 4481.6 | 6638.5 | 5560.1 | 3585.3 | 5602 | 5310.8 | 8298.2 | 6180.5 | 4190.6 | 291 | 6347.5 | 291 | 6006.2 | 174.2
15.5 | 4461.9 | 6667 | 5564.5 | 3569.5 | 5577.3 | 5333.6 | 8333.8 | 6204.8 | 4175.6 | 286.2 | 6380.8 | 286.2 | 6032.5 | 172.3
15.75 | 4480.1 | 6733 | 5606.6 | 3584.1 | 5600.2 | 5386.4 | 8416.3 | 6247.1 | 4159.1 | 321.1 | 6411.9 | 321.1 | 6056.9 | 190.1
16 | 4433.1 | 6733.1 | 5583.1 | 3546.5 | 5541.3 | 5386.5 | 8416.4 | 6257.5 | 4145.5 | 287.6 | 6445.6 | 287.6 | 6083.6 | 173.9
16.25 | 4433.8 | 6780.6 | 5607.2 | 3547.1 | 5542.3 | 5424.5 | 8475.8 | 6290.9 | 4131.4 | 302.4 | 6478.2 | 302.4 | 6109.1 | 181.8
16.5 | 4419.1 | 6812.2 | 5615.6 | 3535.3 | 5523.9 | 5449.7 | 8515.2 | 6317.1 | 4119.6 | 299.5 | 6512.7 | 299.5 | 6136.3 | 180.8
16.75 | 4407.3 | 6846.2 | 5626.8 | 3525.9 | 5509.2 | 5476.9 | 8557.7 | 6343.9 | 4106.1 | 301.3 | 6544.9 | 301.3 | 6161.8 | 182.2
17 | 4404.1 | 6888.3 | 5646.2 | 3523.3 | 5505.1 | 5510.6 | 8610.4 | 6375.7 | 4095.7 | 308.5 | 6579.8 | 308.5 | 6189.5 | 186.2
17.25 | 4394.5 | 6923.6 | 5659.1 | 3515.6 | 5493.1 | 5538.9 | 8654.5 | 6403.3 | 4083.4 | 311.2 | 6612.5 | 311.2 | 6215.3 | 188
17.5 | 4377.4 | 6951 | 5664.2 | 3501.9 | 5471.7 | 5560.8 | 8688.7 | 6427.8 | 4073.8 | 303.6 | 6647.4 | 303.6 | 6243.2 | 184.7
17.75 | 4366.7 | 6984.4 | 5675.5 | 3493.4 | 5458.4 | 5587.5 | 8730.4 | 6454.6 | 4062 | 304.7 | 6679.7 | 304.7 | 6268.9 | 185.7
18 | 4709.2 | 7370.6 | 6039.9 | 3767.4 | 5886.6 | 5896.5 | 9213.2 | 6650.3 | 4063.7 | 645.5 | 6725.1 | 645.5 | 6302.4 | 347.9
18.25 | 4391.7 | 7096.9 | 5744.3 | 3513.4 | 5489.7 | 5677.6 | 8871.2 | 6565.6 | 4121.6 | 270.2 | 6826.8 | 270.2 | 6396.9 | 168.8
18.5 | 4400.2 | 7149.1 | 5774.6 | 3520.1 | 5500.2 | 5719.2 | 8936.3 | 6603 | 4112.1 | 288.1 | 6861 | 288.1 | 6424.6 | 178.4
18.75 | 4423.5 | 7215.7 | 5819.6 | 3538.8 | 5529.4 | 5772.5 | 9019.6 | 6647.2 | 4103.1 | 320.4 | 6895.3 | 320.4 | 6451.8 | 195.4
19 | 4649.1 | 7484.2 | 6066.6 | 3719.2 | 5811.3 | 5987.3 | 9355.2 | 6790 | 4104.7 | 544.3 | 6939.9 | 544.3 | 6485.4 | 304.6
19.25 | 8542.3 | 11421.5 | 9981.9 | 6833.8 | 10677.9 | 9137.2 | 14276.9 | 8421.1 | 4332.5 | 4209.7 | 7211.8 | 4209.7 | 6742.2 | 1678.9
19.5 | 15267.3 | 18202.3 | 16734.8 | 12213.8 | 19084.1 | 14561.8 | 22752.8 | 10521.3 | 4905.3 | 10362 | 7840.3 | 10362 | 6955.6 | 3565.7
19.75 | 23172.8 | 26191.9 | 24682.3 | 18538.2 | 28965.9 | 20953.5 | 32739.9 | 12746.7 | 5727 | 17445.8 | 8746.2 | 17445.8 | 7228 | 5518.8
20 | 32627.4 | 35772.3 | 34199.8 | 26101.9 | 40784.2 | 28617.8 | 44715.4 | 15243.8 | 6750.7 | 25876.7 | 9895.6 | 25876.7 | 7558.6 | 7685.2

## SRD WTG-13
Depth (m) | SRD AH-FF (kN) | SRD AH-NFF (kN) | SRD MEAN (kN) | SRD AH-FF-LB (kN) | SRD AH-FF-UB (kN) | SRD AH-NFF-LB (kN) | SRD AH-NFF-UB (kN) | Static Cap (kN) | Shaft AH-FF (kN) | Tip AH-FF (kN) | Shaft AH-NFF (kN) | Tip AH-NFF (kN) | Shaft SC (kN) | Tip SC (kN)
0.5 | 165 | 167.2 | 166.1 | 132 | 206.3 | 133.8 | 209 | 167.2 | 92.6 | 72.4 | 94.8 | 72.4 | 94.8 | 72.4
0.75 | 209.5 | 214.7 | 212.1 | 167.6 | 261.9 | 171.7 | 268.3 | 214.7 | 137.1 | 72.4 | 142.2 | 72.4 | 142.2 | 72.4
1 | 276.9 | 285.8 | 281.3 | 221.5 | 346.1 | 228.6 | 357.2 | 285.8 | 204.5 | 72.4 | 213.4 | 72.4 | 213.4 | 72.4
1.25 | 319.9 | 333.2 | 326.5 | 255.9 | 399.8 | 266.5 | 416.5 | 333.2 | 247.5 | 72.4 | 260.8 | 72.4 | 260.8 | 72.4
1.5 | 385.9 | 404.3 | 395.1 | 308.7 | 482.4 | 323.4 | 505.4 | 404.3 | 313.5 | 72.4 | 331.9 | 72.4 | 331.9 | 72.4
1.75 | 443.5 | 467.5 | 455.5 | 354.8 | 554.4 | 374 | 584.4 | 467.5 | 365 | 78.5 | 389 | 78.5 | 389 | 78.5
2 | 3267.5 | 3298 | 3282.8 | 2614 | 4084.4 | 2638.4 | 4122.5 | 1262.3 | 433.8 | 2833.7 | 464.3 | 2833.7 | 435 | 827.3
2.25 | 1367.2 | 1410.8 | 1389 | 1093.8 | 1709 | 1128.7 | 1763.5 | 1370.9 | 729.5 | 637.7 | 773.1 | 637.7 | 733.2 | 637.7
2.5 | 1308.6 | 1372.9 | 1340.7 | 1046.9 | 1635.8 | 1098.3 | 1716.1 | 1332.9 | 919.8 | 388.8 | 984.1 | 388.8 | 944.2 | 388.8
2.75 | 1592.8 | 1680.7 | 1636.7 | 1274.3 | 1991 | 1344.5 | 2100.8 | 1640.7 | 1076.7 | 516.2 | 1164.5 | 516.2 | 1124.6 | 516.2
3 | 3620.5 | 3735.2 | 3677.8 | 2896.4 | 4525.6 | 2988.1 | 4668.9 | 2027.6 | 1208.9 | 2411.6 | 1323.5 | 2411.6 | 1253.4 | 774.1
3.25 | 3391.8 | 3538.3 | 3465.1 | 2713.4 | 4239.7 | 2830.7 | 4422.9 | 2141.9 | 1428.6 | 1963.2 | 1575.1 | 1963.2 | 1480.7 | 661.2
3.5 | 2174.8 | 2359 | 2266.9 | 1739.8 | 2718.5 | 1887.2 | 2948.7 | 2254.6 | 1716.8 | 458 | 1901 | 458 | 1796.6 | 458
3.75 | 2352.7 | 2579.1 | 2465.9 | 1882.2 | 2940.9 | 2063.3 | 3223.8 | 2474.7 | 1866.9 | 485.8 | 2093.2 | 485.8 | 1988.9 | 485.8
4 | 2434.7 | 2704.8 | 2569.8 | 1947.8 | 3043.4 | 2163.8 | 3381 | 2589.6 | 2000.7 | 434 | 2270.8 | 434 | 2155.6 | 434
4.25 | 2645.1 | 2961.4 | 2803.3 | 2116.1 | 3306.4 | 2369.1 | 3701.8 | 2839.3 | 2135.3 | 509.8 | 2451.6 | 509.8 | 2329.5 | 509.8
4.5 | 2954 | 3318.9 | 3136.5 | 2363.2 | 3692.5 | 2655.1 | 4148.6 | 3193 | 2278.8 | 675.2 | 2643.7 | 675.2 | 2517.7 | 675.2
4.75 | 3059.2 | 3474.8 | 3267 | 2447.4 | 3824 | 2779.8 | 4343.5 | 3348.8 | 2473.3 | 585.9 | 2888.9 | 585.9 | 2763 | 585.9
5 | 3051.1 | 3520.2 | 3285.7 | 2440.9 | 3813.9 | 2816.2 | 4400.3 | 3394.3 | 2624.3 | 426.8 | 3093.4 | 426.8 | 2967.5 | 426.8
5.25 | 3319 | 3842.4 | 3580.7 | 2655.2 | 4148.7 | 3073.9 | 4803 | 3716.4 | 2725.6 | 593.3 | 3249 | 593.3 | 3123.1 | 593.3
5.5 | 3351 | 3930 | 3640.5 | 2680.8 | 4188.8 | 3144 | 4912.5 | 3804.1 | 2858.6 | 492.4 | 3437.6 | 492.4 | 3311.7 | 492.4
5.75 | 3519.1 | 4154.6 | 3836.9 | 2815.3 | 4398.9 | 3323.7 | 5193.2 | 4025.2 | 2953.2 | 565.9 | 3588.6 | 565.9 | 3459.3 | 565.9
6 | 3812.1 | 4505.3 | 4158.7 | 3049.7 | 4765.1 | 3604.2 | 5631.6 | 4374.8 | 3081.2 | 730.9 | 3774.4 | 730.9 | 3643.9 | 730.9
6.25 | 3750.6 | 4502.5 | 4126.5 | 3000.5 | 4688.3 | 3602 | 5628.1 | 4372 | 3205.3 | 545.4 | 3957.1 | 545.4 | 3826.6 | 545.4
6.5 | 3872.4 | 4683.9 | 4278.2 | 3097.9 | 4840.5 | 3747.1 | 5854.9 | 4550.9 | 3342.4 | 530 | 4154 | 530 | 4020.9 | 530
6.75 | 3935.1 | 4807.4 | 4371.3 | 3148.1 | 4918.9 | 3846 | 6009.3 | 4674.4 | 3440.7 | 494.4 | 4313 | 494.4 | 4180 | 494.4
7 | 4158.1 | 5091.9 | 4625 | 3326.5 | 5197.6 | 4073.5 | 6364.9 | 4958.9 | 3564.3 | 593.8 | 4498.1 | 593.8 | 4365.1 | 593.8
7.25 | 4282.9 | 5279.3 | 4781.1 | 3426.3 | 5353.6 | 4223.4 | 6599.1 | 5146.2 | 3696.4 | 586.5 | 4692.7 | 586.5 | 4559.7 | 586.5
7.5 | 4506.9 | 5566.9 | 5036.9 | 3605.6 | 5633.7 | 4453.5 | 6958.6 | 5432.6 | 3829 | 678 | 4888.9 | 678 | 4754.7 | 678
7.75 | 4615.7 | 5740.2 | 5178 | 3692.5 | 5769.6 | 4592.2 | 7175.3 | 5605.1 | 3942 | 673.7 | 5066.6 | 673.7 | 4931.4 | 673.7
8 | 4871.1 | 6062 | 5466.6 | 3896.9 | 6088.9 | 4849.6 | 7577.5 | 5926.9 | 4147.4 | 723.7 | 5338.3 | 723.7 | 5203.2 | 723.7
8.25 | 4905.6 | 6164.8 | 5535.2 | 3924.5 | 6132 | 4931.9 | 7706 | 6029.7 | 4312.7 | 592.9 | 5572 | 592.9 | 5436.8 | 592.9
8.5 | 5148.1 | 6477.4 | 5812.7 | 4118.5 | 6435.1 | 5181.9 | 8096.7 | 6342.2 | 4477.8 | 670.3 | 5807.1 | 670.3 | 5671.9 | 670.3
8.75 | 5300.3 | 6701.3 | 6000.8 | 4240.3 | 6625.4 | 5361.1 | 8376.7 | 6566.2 | 4660.4 | 639.9 | 6061.4 | 639.9 | 5926.2 | 639.9
9 | 5565.4 | 7040.1 | 6302.7 | 4452.3 | 6956.7 | 5632.1 | 8800.2 | 6905 | 4843.9 | 721.4 | 6318.7 | 721.4 | 6183.6 | 721.4
9.25 | 6376.3 | 7926.7 | 7151.5 | 5101.1 | 7970.4 | 6341.3 | 9908.4 | 7791.5 | 5045.3 | 1331 | 6595.7 | 1331 | 6460.5 | 1331
9.5 | 6009.1 | 7637.7 | 6823.4 | 4807.3 | 7511.4 | 6110.2 | 9547.1 | 7500.5 | 5257.4 | 751.7 | 6886 | 751.7 | 6748.7 | 751.7
9.75 | 6204.7 | 7913.3 | 7059 | 4963.7 | 7755.8 | 6330.7 | 9891.7 | 7776.1 | 5403.6 | 801.1 | 7112.3 | 801.1 | 6975 | 801.1
10 | 6385.3 | 8176.3 | 7280.8 | 5108.3 | 7981.6 | 6541.1 | 10220.4 | 8039.1 | 5655.3 | 730 | 7446.3 | 730 | 7309.1 | 730
10.25 | 6596.6 | 8472.4 | 7534.5 | 5277.3 | 8245.8 | 6777.9 | 10590.5 | 8335.2 | 5848.5 | 748.1 | 7724.3 | 748.1 | 7587.1 | 748.1
10.5 | 6575.5 | 8537.9 | 7556.7 | 5260.4 | 8219.4 | 6830.3 | 10672.4 | 8400.7 | 6022.4 | 553.1 | 7984.9 | 553.1 | 7847.6 | 553.1
10.75 | 6882.9 | 8932.9 | 7907.9 | 5506.3 | 8603.6 | 7146.3 | 11166.1 | 8795.6 | 6128.2 | 754.7 | 8178.2 | 754.7 | 8040.9 | 754.7
11 | 7002.3 | 9141 | 8071.7 | 5601.9 | 8752.9 | 7312.8 | 11426.3 | 9000.8 | 6280.9 | 721.4 | 8419.6 | 721.4 | 8279.4 | 721.4
11.25 | 7081.9 | 9310.4 | 8196.2 | 5665.5 | 8852.4 | 7448.3 | 11638 | 9170.2 | 6446.7 | 635.2 | 8675.2 | 635.2 | 8535 | 635.2
11.5 | 7324.1 | 9644 | 8484.1 | 5859.3 | 9155.2 | 7715.2 | 12055 | 9130.8 | 6595 | 729.2 | 8914.8 | 729.2 | 8773.6 | 357.2
11.75 | 7387.1 | 9798.9 | 8593 | 5909.7 | 9233.9 | 7839.1 | 12248.6 | 9652.2 | 6725 | 662.1 | 9136.7 | 662.1 | 8990.1 | 662.1
12 | 7464.6 | 9969 | 8716.8 | 5971.7 | 9330.7 | 7975.2 | 12461.3 | 9822.4 | 6831.4 | 633.2 | 9335.9 | 633.2 | 9189.2 | 633.2
12.25 | 7505.6 | 10103.1 | 8804.3 | 6004.5 | 9382 | 8082.5 | 12628.9 | 9956.5 | 6926.3 | 579.3 | 9523.8 | 579.3 | 9377.2 | 579.3
12.5 | 7645.9 | 10336.9 | 8991.4 | 6116.7 | 9557.4 | 8269.5 | 12921.2 | 10190.3 | 7012.3 | 633.6 | 9703.3 | 633.6 | 9556.7 | 633.6
12.75 | 7637 | 10421.4 | 9029.2 | 6109.6 | 9546.3 | 8337.1 | 13026.7 | 10274.8 | 7058.2 | 578.8 | 9842.5 | 578.8 | 9695.9 | 578.8
13 | 7726.7 | 10604 | 9165.3 | 6181.3 | 9658.3 | 8483.2 | 13255 | 10454.7 | 7088.1 | 638.6 | 9965.4 | 638.6 | 9816.1 | 638.6
13.25 | 7775.4 | 10745.4 | 9260.4 | 6220.3 | 9719.2 | 8596.3 | 13431.7 | 10594.9 | 7140.9 | 634.5 | 10110.8 | 634.5 | 9960.4 | 634.5
13.5 | 7995.7 | 11058.2 | 9526.9 | 6396.6 | 9994.6 | 8846.6 | 13822.7 | 10905.5 | 7191 | 804.7 | 10253.5 | 804.7 | 10100.8 | 804.7
13.75 | 7899.1 | 11054.1 | 9476.6 | 6319.3 | 9873.9 | 8843.3 | 13817.6 | 10901.4 | 7279.7 | 619.4 | 10434.8 | 619.4 | 10282 | 619.4
14 | 8045.5 | 11293 | 9669.3 | 6436.4 | 10056.9 | 9034.4 | 14116.3 | 11137 | 7334.5 | 711 | 10582 | 711 | 10426 | 711
14.25 | 8308.1 | 11648.4 | 9978.2 | 6646.4 | 10385.1 | 9318.7 | 14560.4 | 11489.1 | 7439.1 | 868.9 | 10779.4 | 868.9 | 10620.1 | 868.9
14.5 | 8207.9 | 11642 | 9925 | 6566.3 | 10259.9 | 9313.6 | 14552.5 | 11482.7 | 7580.6 | 627.3 | 11014.7 | 627.3 | 10855.5 | 627.3
14.75 | 8259.2 | 11787.1 | 10023.2 | 6607.4 | 10324 | 9429.7 | 14733.9 | 11627.8 | 7626.7 | 632.5 | 11154.6 | 632.5 | 10995.3 | 632.5
15 | 8359.4 | 11980.8 | 10170.1 | 6687.5 | 10449.3 | 9584.7 | 14976 | 11817.6 | 7710.9 | 648.5 | 11332.3 | 648.5 | 11169 | 648.5
15.25 | 8400.3 | 12115.5 | 10257.9 | 6720.3 | 10500.4 | 9692.4 | 15144.4 | 11951.4 | 7751.1 | 649.2 | 11466.3 | 649.2 | 11302.1 | 649.2
15.5 | 8458.1 | 12266.8 | 10362.4 | 6766.5 | 10572.6 | 9813.4 | 15333.5 | 12102.6 | 7814.1 | 644 | 11622.8 | 644 | 11458.6 | 644
15.75 | 8557.6 | 12459.4 | 10508.5 | 6846.1 | 10697 | 9967.5 | 15574.3 | 12290.2 | 7825.3 | 732.3 | 11727.2 | 732.3 | 11557.9 | 732.3
16 | 8670.5 | 12665.3 | 10667.9 | 6936.4 | 10838.1 | 10132.3 | 15831.7 | 12495.4 | 7903.4 | 767.1 | 11898.2 | 767.1 | 11728.2 | 767.1
16.25 | 8667.7 | 12755.6 | 10711.6 | 6934.2 | 10834.6 | 10204.5 | 15944.5 | 12585.6 | 7973.9 | 693.8 | 12061.8 | 693.8 | 11891.8 | 693.8
16.5 | 8695.7 | 12876.7 | 10786.2 | 6956.6 | 10869.7 | 10301.4 | 16095.9 | 12706.7 | 8051.7 | 644 | 12232.7 | 644 | 12062.7 | 644
16.75 | 8805.3 | 13079.2 | 10942.2 | 7044.2 | 11006.6 | 10463.3 | 16348.9 | 12907.6 | 8092.9 | 712.4 | 12366.8 | 712.4 | 12195.3 | 712.4
17 | 19412.7 | 23782.4 | 21597.5 | 15530.2 | 24265.9 | 19025.9 | 29727.9 | 16013.9 | 8405.1 | 11007.6 | 12774.7 | 11007.6 | 12351.6 | 3662.4
17.25 | 49619.4 | 54176 | 51897.7 | 39695.5 | 62024.3 | 43340.8 | 67720 | 25074.2 | 10978.6 | 38640.8 | 15535.1 | 38640.8 | 14615.7 | 10458.5

## SRD WTG-14
Depth (m) | SRD AH-FF (kN) | SRD AH-NFF (kN) | SRD MEAN (kN) | SRD AH-FF-LB (kN) | SRD AH-FF-UB (kN) | SRD AH-NFF-LB (kN) | SRD AH-NFF-UB (kN) | Static Cap (kN) | Shaft AH-FF (kN) | Tip AH-FF (kN) | Shaft AH-NFF (kN) | Tip AH-NFF (kN) | Shaft SC (kN) | Tip SC (kN)
0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.75 | 90.3 | 90.5 | 90.4 | 72.3 | 112.9 | 72.4 | 113.1 | 90.5 | 23.8 | 66.5 | 23.9 | 66.5 | 23.9 | 66.5
2 | 212.5 | 213 | 212.8 | 170 | 265.6 | 170.4 | 266.3 | 213 | 56.8 | 155.7 | 57.3 | 155.7 | 57.3 | 155.7
2.25 | 267.4 | 268.8 | 268.1 | 213.9 | 334.3 | 215 | 336 | 268.8 | 99.5 | 167.9 | 100.9 | 167.9 | 100.9 | 167.9
2.5 | 311.3 | 314.1 | 312.7 | 249.1 | 389.2 | 251.3 | 392.7 | 314.1 | 145.7 | 165.6 | 148.5 | 165.6 | 148.5 | 165.6
2.75 | 366.2 | 371 | 368.6 | 293 | 457.8 | 296.8 | 463.7 | 371 | 188.2 | 178.1 | 192.9 | 178.1 | 192.9 | 178.1
3 | 418.5 | 425.7 | 422.1 | 334.8 | 523.1 | 340.6 | 532.1 | 425.7 | 236.1 | 182.4 | 243.3 | 182.4 | 243.3 | 182.4
3.25 | 468.4 | 478.6 | 473.5 | 374.7 | 585.5 | 382.9 | 598.2 | 478.6 | 280.1 | 188.3 | 290.3 | 188.3 | 290.3 | 188.3
3.5 | 519.7 | 533.3 | 526.5 | 415.7 | 649.6 | 426.6 | 666.6 | 533.3 | 327.3 | 192.3 | 340.9 | 192.3 | 340.9 | 192.3
3.75 | 577.6 | 595.2 | 586.4 | 462.1 | 722 | 476.1 | 743.9 | 595.2 | 371.5 | 206.1 | 389 | 206.1 | 389 | 206.1
4 | 637.2 | 659.1 | 648.1 | 509.7 | 796.4 | 527.3 | 823.9 | 659.1 | 423.5 | 213.6 | 445.5 | 213.6 | 445.5 | 213.6
4.25 | 694.7 | 721.5 | 708.1 | 555.7 | 868.3 | 577.2 | 901.9 | 721.5 | 473.6 | 221.1 | 500.4 | 221.1 | 500.4 | 221.1
4.5 | 750.5 | 782.7 | 766.6 | 600.4 | 938.1 | 626.2 | 978.4 | 782.7 | 524.2 | 226.3 | 556.5 | 226.3 | 556.5 | 226.3
4.75 | 805.5 | 843.6 | 824.5 | 644.4 | 1006.9 | 674.9 | 1054.5 | 843.6 | 573.3 | 232.2 | 611.4 | 232.2 | 611.4 | 232.2
5 | 918.1 | 962.5 | 940.3 | 734.4 | 1147.6 | 770 | 1203.1 | 962.1 | 622.1 | 296 | 666.5 | 296 | 666.1 | 296
5.25 | 940.3 | 991.6 | 965.9 | 752.2 | 1175.3 | 793.3 | 1239.5 | 991.2 | 684.8 | 255.5 | 736.1 | 255.5 | 735.7 | 255.5
5.5 | 972.4 | 1031.1 | 1001.8 | 777.9 | 1215.5 | 824.9 | 1288.9 | 1030.7 | 737.5 | 234.9 | 796.2 | 234.9 | 795.8 | 234.9
5.75 | 1038.9 | 1105.5 | 1072.2 | 831.1 | 1298.6 | 884.4 | 1381.8 | 1105.1 | 786.1 | 252.8 | 852.7 | 252.8 | 852.3 | 252.8
6 | 1092.4 | 1167.2 | 1129.8 | 873.9 | 1365.5 | 933.8 | 1459 | 1166.6 | 842.1 | 250.3 | 916.9 | 250.3 | 916.4 | 250.3
6.25 | 1230.5 | 1314.1 | 1272.3 | 984.4 | 1538.1 | 1051.3 | 1642.7 | 1310.9 | 915.3 | 315.2 | 998.9 | 315.2 | 995.7 | 315.2
6.5 | 1640.7 | 1734.6 | 1687.7 | 1312.6 | 2050.9 | 1387.7 | 2168.3 | 1710.1 | 1019.4 | 621.4 | 1113.2 | 621.4 | 1088.7 | 621.4
6.75 | 1747.7 | 1853.8 | 1800.7 | 1398.2 | 2184.6 | 1483 | 2317.2 | 1827.4 | 1153 | 594.7 | 1259.1 | 594.7 | 1232.7 | 594.7
7 | 1830.8 | 1950.4 | 1890.6 | 1464.7 | 2288.6 | 1560.3 | 2438 | 1921.6 | 1262.4 | 568.4 | 1381.9 | 568.4 | 1353.2 | 568.4
7.25 | 1918.3 | 2052.6 | 1985.5 | 1534.7 | 2397.9 | 1642.1 | 2565.7 | 2023.8 | 1394.3 | 524.1 | 1528.5 | 524.1 | 1499.8 | 524.1
7.5 | 1877 | 2027.3 | 1952.1 | 1501.6 | 2346.3 | 1621.8 | 2534.1 | 1998.5 | 1499.6 | 377.4 | 1649.8 | 377.4 | 1621.1 | 377.4
7.75 | 2250.9 | 2418 | 2334.5 | 1800.7 | 2813.7 | 1934.4 | 3022.5 | 2387.5 | 1582.2 | 668.7 | 1749.3 | 668.7 | 1718.8 | 668.7
8 | 2230.1 | 2415.5 | 2322.8 | 1784.1 | 2787.7 | 1932.4 | 3019.4 | 2385 | 1721.9 | 508.2 | 1907.3 | 508.2 | 1876.7 | 508.2
8.25 | 2255.8 | 2460.8 | 2358.3 | 1804.6 | 2819.7 | 1968.6 | 3076 | 2428.5 | 1842.8 | 413 | 2047.8 | 413 | 2015.5 | 413
8.5 | 2307.7 | 2533.5 | 2420.6 | 1846.1 | 2884.6 | 2026.8 | 3166.8 | 2501.2 | 1939.3 | 368.4 | 2165.1 | 368.4 | 2132.8 | 368.4
8.75 | 2404.4 | 2651.7 | 2528 | 1923.5 | 3005.5 | 2121.3 | 3314.6 | 2619 | 2011.3 | 393.1 | 2258.6 | 393.1 | 2225.9 | 393.1
9 | 2528.9 | 2798.3 | 2663.6 | 2023.2 | 3161.2 | 2238.7 | 3497.9 | 2764.3 | 2103.5 | 425.4 | 2372.9 | 425.4 | 2338.9 | 425.4
9.25 | 2555.7 | 2848.2 | 2701.9 | 2044.6 | 3194.6 | 2278.5 | 3560.2 | 2814 | 2183.9 | 371.8 | 2476.4 | 371.8 | 2442.2 | 371.8
9.5 | 2659.1 | 2975.1 | 2817.1 | 2127.3 | 3323.9 | 2380.1 | 3718.9 | 2940.9 | 2259.5 | 399.6 | 2575.5 | 399.6 | 2541.3 | 399.6
9.75 | 2808.3 | 3148.5 | 2978.4 | 2246.7 | 3510.4 | 2518.8 | 3935.6 | 3112.3 | 2346.5 | 461.9 | 2686.6 | 461.9 | 2650.4 | 461.9
10 | 2864.4 | 3229.8 | 3047.1 | 2291.5 | 3580.5 | 2583.9 | 4037.3 | 3193.6 | 2468.4 | 396 | 2833.8 | 396 | 2797.6 | 396
10.25 | 3059.3 | 3450.8 | 3255.1 | 2447.4 | 3824.1 | 2760.6 | 4313.5 | 3414.6 | 2548.8 | 510.5 | 2940.3 | 510.5 | 2904.1 | 510.5
10.5 | 2891.5 | 3309.9 | 3100.7 | 2313.2 | 3614.4 | 2647.9 | 4137.4 | 3171.4 | 2650.2 | 241.3 | 3068.6 | 241.3 | 3031.8 | 139.6
10.75 | 3258.1 | 3704.1 | 3481.1 | 2606.5 | 4072.6 | 2963.3 | 4630.1 | 3667.1 | 2750.7 | 507.3 | 3196.8 | 507.3 | 3159.7 | 507.3
11 | 3068 | 3542.5 | 3305.3 | 2454.4 | 3835 | 2834 | 4428.2 | 3403.5 | 2825.5 | 242.5 | 3300 | 242.5 | 3262.1 | 141.3
11.25 | 3346.6 | 3850.2 | 3598.4 | 2677.3 | 4183.3 | 3080.1 | 4812.7 | 3812.1 | 2925 | 421.6 | 3428.6 | 421.6 | 3390.5 | 421.6
11.5 | 3482.8 | 4016.2 | 3749.5 | 2786.3 | 4353.5 | 3212.9 | 5020.2 | 3976.5 | 3010.3 | 472.5 | 3543.7 | 472.5 | 3504 | 472.5
11.75 | 3577.4 | 4141.2 | 3859.3 | 2861.9 | 4471.8 | 3313 | 5176.5 | 4100 | 3101.5 | 475.9 | 3665.3 | 475.9 | 3624.1 | 475.9
12 | 3759 | 4354.2 | 4056.6 | 3007.2 | 4698.8 | 3483.3 | 5442.7 | 4310.6 | 3187.9 | 571.2 | 3783 | 571.2 | 3739.5 | 571.2
12.25 | 4427.9 | 5055.7 | 4741.8 | 3542.3 | 5534.9 | 4044.6 | 6319.6 | 5010.1 | 3358.7 | 1069.2 | 3986.5 | 1069.2 | 3940.9 | 1069.2
12.5 | 4167.8 | 4830.5 | 4499.2 | 3334.3 | 5209.8 | 3864.4 | 6038.1 | 4784.9 | 3578.1 | 589.7 | 4240.8 | 589.7 | 4195.2 | 589.7
12.75 | 4207.9 | 4906.7 | 4557.3 | 3366.3 | 5259.8 | 3925.4 | 6133.4 | 4861.1 | 3674.5 | 533.4 | 4373.3 | 533.4 | 4327.8 | 533.4
13 | 4011.6 | 4747.3 | 4379.4 | 3209.3 | 5014.5 | 3797.8 | 5934.1 | 4602.3 | 3765 | 246.6 | 4500.7 | 246.6 | 4454.9 | 147.4
13.25 | 4447.6 | 5221.2 | 4834.4 | 3558.1 | 5559.5 | 4177 | 6526.5 | 5167.8 | 3949.1 | 498.5 | 4722.7 | 498.5 | 4669.3 | 498.5
13.5 | 4408.4 | 5221.9 | 4815.1 | 3526.7 | 5510.5 | 4177.5 | 6527.3 | 5010 | 4051.1 | 357.3 | 4864.5 | 357.3 | 4807.9 | 202.1
13.75 | 4823.6 | 5677.8 | 5250.7 | 3858.8 | 6029.4 | 4542.3 | 7097.3 | 5620.8 | 4212.1 | 611.4 | 5066.4 | 611.4 | 5009.4 | 611.4
14 | 5320.2 | 6216.6 | 5768.4 | 4256.2 | 6650.3 | 4973.3 | 7770.7 | 6158.9 | 4343.6 | 976.7 | 5239.9 | 976.7 | 5182.2 | 976.7
14.25 | 5123.5 | 6063.6 | 5593.5 | 4098.8 | 6404.3 | 4850.8 | 7579.5 | 6005.8 | 4517.9 | 605.5 | 5458 | 605.5 | 5400.3 | 605.5
14.5 | 5193.6 | 6178.5 | 5686 | 4154.9 | 6492 | 4942.8 | 7723.1 | 6120.7 | 4619.3 | 574.3 | 5604.1 | 574.3 | 5546.4 | 574.3
14.75 | 5341.4 | 6371.6 | 5856.5 | 4273.1 | 6676.7 | 5097.3 | 7964.5 | 6313.9 | 4698.5 | 642.9 | 5728.7 | 642.9 | 5671 | 642.9
15 | 5370.4 | 6446.7 | 5908.6 | 4296.3 | 6713 | 5157.4 | 8058.4 | 6389 | 4806.5 | 563.9 | 5882.8 | 563.9 | 5825.1 | 563.9
15.25 | 5418.6 | 6541.5 | 5980 | 4334.9 | 6773.3 | 5233.2 | 8176.8 | 6483.3 | 4879.4 | 539.2 | 6002.2 | 539.2 | 5944 | 539.2
15.5 | 5524.3 | 6694.2 | 6109.3 | 4419.5 | 6905.4 | 5355.4 | 8367.8 | 6636 | 4963.6 | 560.7 | 6133.5 | 560.7 | 6075.3 | 560.7
15.75 | 5567.3 | 6784.4 | 6175.8 | 4453.8 | 6959.1 | 5427.5 | 8480.5 | 6719.1 | 4996.1 | 571.2 | 6213.2 | 571.2 | 6147.9 | 571.2
16 | 5980.1 | 7245.2 | 6612.6 | 4784.1 | 7475.1 | 5796.1 | 9056.4 | 7172.5 | 5134.2 | 845.9 | 6399.3 | 845.9 | 6326.6 | 845.9
16.25 | 6217.4 | 7532.2 | 6874.8 | 4973.9 | 7771.7 | 6025.8 | 9415.3 | 7457.2 | 5328.5 | 888.9 | 6643.4 | 888.9 | 6568.3 | 888.9
16.5 | 6644.5 | 8010.8 | 7327.7 | 5315.6 | 8305.7 | 6408.7 | 10013.6 | 7933.8 | 5505.4 | 1139.1 | 6871.7 | 1139.1 | 6794.7 | 1139.1
16.75 | 6417.1 | 7836.7 | 7126.9 | 5133.7 | 8021.4 | 6269.4 | 9795.9 | 7750.5 | 5678 | 739.1 | 7097.6 | 739.1 | 7011.4 | 739.1
17 | 6189 | 7663.6 | 6926.3 | 4951.2 | 7736.2 | 6130.9 | 9579.6 | 7412.2 | 5799.6 | 389.4 | 7274.2 | 389.4 | 7186.5 | 225.7
17.25 | 6433.5 | 7963.6 | 7198.5 | 5146.8 | 8041.8 | 6370.9 | 9954.5 | 7874.8 | 5880 | 553.5 | 7410.1 | 553.5 | 7321.3 | 553.5
17.5 | 6478 | 8063.9 | 7270.9 | 5182.4 | 8097.5 | 6451.1 | 10079.8 | 7970.5 | 5949 | 529.1 | 7534.8 | 529.1 | 7441.5 | 529.1
17.75 | 6556.2 | 8198.1 | 7377.2 | 5245 | 8195.3 | 6558.5 | 10247.7 | 8102.2 | 5994.1 | 562.1 | 7636 | 562.1 | 7540.1 | 562.1
18 | 6234.6 | 7932.7 | 7083.6 | 4987.7 | 7793.2 | 6346.2 | 9915.9 | 7761.2 | 6025 | 209.6 | 7723.1 | 209.6 | 7625.2 | 136
18.25 | 6254.9 | 8009.1 | 7132 | 5003.9 | 7818.7 | 6407.3 | 10011.4 | 7835.2 | 6044.6 | 210.4 | 7798.8 | 210.4 | 7698.5 | 136.7
18.5 | 6243.5 | 8053.5 | 7148.5 | 4994.8 | 7804.3 | 6442.8 | 10066.8 | 7870.1 | 6019.5 | 223.9 | 7829.6 | 223.9 | 7725.7 | 144.4
18.75 | 6272.1 | 8137.7 | 7204.9 | 5017.7 | 7840.1 | 6510.2 | 10172.1 | 7947 | 6035.4 | 236.7 | 7901 | 236.7 | 7795.4 | 151.6
19 | 6265.8 | 8186.6 | 7226.2 | 5012.6 | 7832.2 | 6549.3 | 10233.3 | 7982.8 | 6010.6 | 255.1 | 7931.5 | 255.1 | 7821.1 | 161.7
19.25 | 6772.3 | 8748.4 | 7760.3 | 5417.8 | 8465.3 | 6998.7 | 10935.4 | 8637.8 | 6098.8 | 673.4 | 8074.9 | 673.4 | 7964.4 | 673.4
19.5 | 6437 | 8468.9 | 7453 | 5149.6 | 8046.3 | 6775.1 | 10586.1 | 8258.1 | 6168.3 | 268.8 | 8200.1 | 268.8 | 8088.5 | 169.6
19.75 | 7970.8 | 10058.3 | 9014.6 | 6376.7 | 9963.5 | 8046.7 | 12572.9 | 9932.1 | 6178.6 | 1792.2 | 8266.1 | 1792.2 | 8139.9 | 1792.2
20 | 11853.9 | 14003.4 | 12928.7 | 9483.1 | 14817.4 | 11202.8 | 17504.3 | 13846.6 | 7159.8 | 4694.1 | 9309.3 | 4694.1 | 9152.4 | 4694.1

## SRD WTG-15
Depth (m) | SRD AH-FF (kN) | SRD AH-NFF (kN) | SRD MEAN (kN) | SRD AH-FF-LB (kN) | SRD AH-FF-UB (kN) | SRD AH-NFF-LB (kN) | SRD AH-NFF-UB (kN) | Static Cap (kN) | Shaft AH-FF (kN) | Tip AH-FF (kN) | Shaft AH-NFF (kN) | Tip AH-NFF (kN) | Shaft SC (kN) | Tip SC (kN)
0.5 | 63 | 63.1 | 63 | 50.4 | 78.7 | 50.5 | 78.8 | 29.1 | 4.4 | 58.6 | 4.5 | 58.6 | 3.2 | 25.9
0.75 | 60.7 | 61 | 60.9 | 48.6 | 75.9 | 48.8 | 76.2 | 31.1 | 6.7 | 54 | 7 | 54 | 5.2 | 25.9
1 | 61.4 | 61.8 | 61.6 | 49.1 | 76.8 | 49.5 | 77.3 | 34.4 | 10.4 | 51 | 10.8 | 51 | 8.5 | 25.9
1.25 | 61.6 | 62.3 | 62 | 49.3 | 77 | 49.8 | 77.9 | 36.8 | 12.9 | 48.8 | 13.5 | 48.8 | 10.9 | 25.9
1.5 | 63.8 | 64.7 | 64.2 | 51 | 79.7 | 51.7 | 80.8 | 40.6 | 16.7 | 47 | 17.6 | 47 | 14.7 | 25.9
1.75 | 64.8 | 66 | 65.4 | 51.9 | 81.1 | 52.8 | 82.5 | 43.3 | 19.2 | 45.6 | 20.4 | 45.6 | 17.4 | 25.9
2 | 70.5 | 72 | 71.3 | 56.4 | 88.2 | 57.6 | 90.1 | 48.9 | 23.3 | 47.3 | 24.8 | 47.3 | 21.6 | 27.3
2.25 | 87.2 | 89.1 | 88.2 | 69.8 | 109.1 | 71.3 | 111.4 | 59.5 | 27.1 | 60.1 | 29 | 60.1 | 25.6 | 33.9
2.5 | 91.5 | 93.8 | 92.7 | 73.2 | 114.4 | 75 | 117.3 | 64.7 | 31.9 | 59.6 | 34.2 | 59.6 | 30.4 | 34.3
2.75 | 96.7 | 99.4 | 98.1 | 77.4 | 120.9 | 79.6 | 124.3 | 70.2 | 36.3 | 60.4 | 39 | 60.4 | 35 | 35.2
3 | 104.8 | 108 | 106.4 | 83.9 | 131.1 | 86.4 | 135 | 77.4 | 41.3 | 63.6 | 44.5 | 63.6 | 40.1 | 37.2
3.25 | 117.7 | 121.4 | 119.6 | 94.2 | 147.1 | 97.1 | 151.8 | 86.9 | 46.6 | 71.1 | 50.3 | 71.1 | 45.5 | 41.4
3.5 | 147.8 | 152.1 | 149.9 | 118.2 | 184.7 | 121.7 | 190.1 | 105.2 | 53.6 | 94.2 | 57.9 | 94.2 | 52.3 | 53
3.75 | 200 | 204.9 | 202.4 | 160 | 249.9 | 163.9 | 256.1 | 133.3 | 61.6 | 138.4 | 66.5 | 138.4 | 59.6 | 73.8
4 | 169.3 | 175 | 172.1 | 135.4 | 211.6 | 140 | 218.7 | 124 | 70.1 | 99.1 | 75.8 | 99.1 | 67.6 | 56.5
4.25 | 181.2 | 187.7 | 184.5 | 145 | 226.5 | 150.2 | 234.7 | 134 | 77.9 | 103.3 | 84.4 | 103.3 | 75 | 59
4.5 | 193.4 | 200.9 | 197.2 | 154.8 | 241.8 | 160.7 | 251.1 | 144.8 | 87.9 | 105.6 | 95.3 | 105.6 | 84.2 | 60.6
4.75 | 200.5 | 208.9 | 204.7 | 160.4 | 250.6 | 167.1 | 261.1 | 152.8 | 95.6 | 104.8 | 104.1 | 104.8 | 91.9 | 60.8
5 | 209.7 | 219.3 | 214.5 | 167.8 | 262.2 | 175.4 | 274.1 | 162.2 | 104.4 | 105.3 | 114 | 105.3 | 100.7 | 61.6
5.25 | 225.8 | 236.5 | 231.1 | 180.6 | 282.2 | 189.2 | 295.6 | 174.9 | 112.8 | 113 | 123.5 | 113 | 109.1 | 65.8
5.5 | 238.8 | 250.8 | 244.8 | 191.1 | 298.5 | 200.6 | 313.5 | 186.6 | 122.8 | 116 | 134.8 | 116 | 118.8 | 67.8
5.75 | 245.4 | 258.6 | 252 | 196.3 | 306.7 | 206.9 | 323.3 | 195 | 131.8 | 113.6 | 145 | 113.6 | 127.9 | 67.1
6 | 255.2 | 269.9 | 262.5 | 204.1 | 319 | 215.9 | 337.3 | 205.3 | 141.4 | 113.8 | 156 | 113.8 | 137.7 | 67.7
6.25 | 264.9 | 281.1 | 273 | 211.9 | 331.2 | 224.9 | 351.4 | 215.5 | 150.3 | 114.6 | 166.5 | 114.6 | 146.9 | 68.5
6.5 | 274.9 | 292.6 | 283.8 | 219.9 | 343.7 | 234.1 | 365.8 | 226.2 | 160.6 | 114.3 | 178.4 | 114.3 | 157.4 | 68.8
6.75 | 323.9 | 343.3 | 333.6 | 259.1 | 404.9 | 274.6 | 429.1 | 256.3 | 173.1 | 150.8 | 192.5 | 150.8 | 169 | 87.2
7 | 321.7 | 342.8 | 332.2 | 257.3 | 402.1 | 274.3 | 428.5 | 261.7 | 185.6 | 136.1 | 206.7 | 136.1 | 181.2 | 80.6
7.25 | 327.1 | 350.2 | 338.7 | 261.7 | 408.9 | 280.2 | 437.7 | 270.7 | 198.7 | 128.4 | 221.8 | 128.4 | 193.5 | 77.2
7.5 | 329.8 | 354.9 | 342.4 | 263.9 | 412.3 | 283.9 | 443.7 | 278.5 | 209.5 | 120.3 | 234.6 | 120.3 | 204.9 | 73.5
7.75 | 341.2 | 368.4 | 354.8 | 272.9 | 426.5 | 294.7 | 460.5 | 290.4 | 219.7 | 121.4 | 246.9 | 121.4 | 215.9 | 74.5
8 | 370.3 | 399.7 | 385 | 296.2 | 462.8 | 319.7 | 499.6 | 311.8 | 231.2 | 139.1 | 260.6 | 139.1 | 228 | 83.8
8.25 | 362.5 | 394.2 | 378.4 | 290 | 453.2 | 315.3 | 492.7 | 314.2 | 241.6 | 120.9 | 273.2 | 120.9 | 239.2 | 75
8.5 | 383.8 | 417.8 | 400.8 | 307 | 479.7 | 334.2 | 522.2 | 331.9 | 252.6 | 131.2 | 286.6 | 131.2 | 251.3 | 80.7
8.75 | 401.1 | 437.6 | 419.4 | 320.9 | 501.4 | 350.1 | 547 | 347.6 | 264.4 | 136.7 | 300.9 | 136.7 | 263.7 | 83.9
9 | 723.4 | 762.4 | 742.9 | 578.7 | 904.3 | 609.9 | 953 | 503.2 | 278.5 | 444.9 | 317.5 | 444.9 | 277.8 | 225.4
9.25 | 1302.7 | 1344.5 | 1323.6 | 1042.2 | 1628.4 | 1075.6 | 1680.7 | 1293.3 | 316.6 | 986.2 | 358.4 | 986.2 | 307.2 | 986.2
9.5 | 999.5 | 1046.1 | 1022.8 | 799.6 | 1249.4 | 836.9 | 1307.6 | 988.6 | 546 | 453.5 | 592.6 | 453.5 | 535.1 | 453.5
9.75 | 853.3 | 906.4 | 879.8 | 682.6 | 1066.6 | 725.1 | 1133 | 729.2 | 594 | 259.3 | 647 | 259.3 | 583.4 | 145.8
10 | 843.2 | 903.1 | 873.1 | 674.6 | 1054 | 722.5 | 1128.8 | 737.6 | 613.7 | 229.5 | 673.5 | 229.5 | 605.3 | 132.3
10.25 | 1021.5 | 1088.4 | 1054.9 | 817.2 | 1276.9 | 870.7 | 1360.5 | 1018.5 | 647 | 374.5 | 713.9 | 374.5 | 643.9 | 374.5
10.5 | 869.8 | 943.8 | 906.8 | 695.8 | 1087.2 | 755.1 | 1179.8 | 788.2 | 665 | 204.8 | 739 | 204.8 | 666.9 | 121.3
10.75 | 886 | 967.3 | 926.7 | 708.8 | 1107.4 | 773.9 | 1209.2 | 816.6 | 693.2 | 192.8 | 774.6 | 192.8 | 700.8 | 115.8
11 | 897.2 | 986.1 | 941.6 | 717.8 | 1121.5 | 788.8 | 1232.6 | 835.2 | 709.9 | 187.3 | 798.8 | 187.3 | 721.7 | 113.5
11.25 | 889.6 | 986.1 | 937.8 | 711.7 | 1112 | 788.9 | 1232.6 | 852.6 | 740.7 | 148.9 | 837.2 | 148.9 | 758.5 | 94.1
11.5 | 941.5 | 1045.8 | 993.7 | 753.2 | 1176.9 | 836.6 | 1307.2 | 890.6 | 752.9 | 188.6 | 857.1 | 188.6 | 775.5 | 115.1
11.75 | 1048.8 | 1160.9 | 1104.8 | 839 | 1311 | 928.7 | 1451.1 | 954.3 | 763 | 285.8 | 875.1 | 285.8 | 791.1 | 163.3
12 | 1029.3 | 1149.3 | 1089.3 | 823.4 | 1286.6 | 919.4 | 1436.6 | 960.8 | 793.4 | 235.8 | 913.5 | 235.8 | 821.2 | 139.6
12.25 | 1004.6 | 1133 | 1068.8 | 803.7 | 1255.8 | 906.4 | 1416.2 | 974.5 | 832.9 | 171.8 | 961.2 | 171.8 | 866.9 | 107.6
12.5 | 1077.1 | 1213.9 | 1145.5 | 861.7 | 1346.3 | 971.1 | 1517.3 | 1023.6 | 846.6 | 230.4 | 983.4 | 230.4 | 885.6 | 137.9
12.75 | 2278.1 | 2423.9 | 2351 | 1822.5 | 2847.7 | 1939.1 | 3029.9 | 1537.8 | 917 | 1361.1 | 1062.8 | 1361.1 | 929.6 | 608.2
13 | 2221.6 | 2378.2 | 2299.9 | 1777.2 | 2776.9 | 1902.6 | 2972.8 | 2233.5 | 1120 | 1101.6 | 1276.7 | 1101.6 | 1131.9 | 1101.6
13.25 | 1972.9 | 2142.8 | 2057.8 | 1578.3 | 2466.1 | 1714.2 | 2678.4 | 1979.9 | 1270 | 702.9 | 1439.9 | 702.9 | 1277.1 | 702.9
13.5 | 1730.7 | 1915.7 | 1823.2 | 1384.6 | 2163.4 | 1532.6 | 2394.6 | 1594.5 | 1378.3 | 352.4 | 1563.3 | 352.4 | 1395.2 | 199.2
13.75 | 2510 | 2710.8 | 2610.4 | 2008 | 3137.5 | 2168.6 | 3388.4 | 1975.1 | 1450.9 | 1059.1 | 1651.6 | 1059.1 | 1475.1 | 500
14 | 2240.4 | 2457.7 | 2349.1 | 1792.3 | 2800.5 | 1966.2 | 3072.1 | 2268.9 | 1559.3 | 681.1 | 1776.6 | 681.1 | 1587.8 | 681.1
14.25 | 1958.4 | 2193 | 2075.7 | 1566.7 | 2447.9 | 1754.4 | 2741.3 | 1844.6 | 1599.6 | 358.7 | 1834.3 | 358.7 | 1640.4 | 204.1
14.5 | 2413.6 | 2665.8 | 2539.7 | 1930.8 | 3016.9 | 2132.6 | 3332.2 | 2456.7 | 1636 | 777.5 | 1888.3 | 777.5 | 1679.2 | 777.5
14.75 | 2790 | 3060.6 | 2925.3 | 2232 | 3487.5 | 2448.5 | 3825.7 | 2840.2 | 1724 | 1066 | 1994.5 | 1066 | 1774.1 | 1066
15 | 2140.6 | 2430.8 | 2285.7 | 1712.5 | 2675.8 | 1944.7 | 3038.5 | 2102.5 | 1874.3 | 266.3 | 2164.5 | 266.3 | 1941.8 | 160.7
15.25 | 2332.1 | 2642.4 | 2487.2 | 1865.7 | 2915.1 | 2113.9 | 3303 | 2214.2 | 1892.6 | 439.5 | 2202.9 | 439.5 | 1969.6 | 244.6
15.5 | 2247.9 | 2578.9 | 2413.4 | 1798.3 | 2809.9 | 2063.1 | 3223.6 | 2241.9 | 1989.2 | 258.7 | 2320.2 | 258.7 | 2084.2 | 157.7
15.75 | 2388.9 | 2740.8 | 2564.9 | 1911.1 | 2986.1 | 2192.6 | 3426 | 2331.1 | 2002.8 | 386.1 | 2354.7 | 386.1 | 2110.3 | 220.8
16 | 2546 | 2919.2 | 2732.6 | 2036.8 | 3182.5 | 2335.3 | 3649 | 2455.2 | 2068.5 | 477.5 | 2441.7 | 477.5 | 2190.9 | 264.3
16.25 | 2763.9 | 3158.7 | 2961.3 | 2211.1 | 3454.9 | 2527 | 3948.4 | 2596.9 | 2124.2 | 639.8 | 2519 | 639.8 | 2258.7 | 338.2
16.5 | 2901.7 | 3318.4 | 3110.1 | 2321.4 | 3627.1 | 2654.8 | 4148.1 | 3048.3 | 2146.8 | 754.9 | 2563.5 | 754.9 | 2293.4 | 754.9
16.75 | 2533.7 | 2972.7 | 2753.2 | 2027 | 3167.1 | 2378.2 | 3715.9 | 2561.5 | 2195.5 | 338.2 | 2634.5 | 338.2 | 2361.7 | 199.9
17 | 2546.9 | 3008.3 | 2777.6 | 2037.5 | 3183.6 | 2406.6 | 3760.3 | 2601.8 | 2233 | 313.9 | 2694.4 | 313.9 | 2413.5 | 188.3
17.25 | 2601.5 | 3085.6 | 2843.5 | 2081.2 | 3251.9 | 2468.4 | 3856.9 | 2675.9 | 2298.4 | 303.1 | 2782.4 | 303.1 | 2492.6 | 183.4
17.5 | 2841.3 | 3348.3 | 3094.8 | 2273 | 3551.6 | 2678.7 | 4185.4 | 2817 | 2317.6 | 523.7 | 2824.7 | 523.7 | 2527.1 | 289.9
17.75 | 3299.1 | 3829.6 | 3564.4 | 2639.3 | 4123.9 | 3063.7 | 4787 | 3523.7 | 2418.6 | 880.5 | 2949.1 | 880.5 | 2643.2 | 880.5
18 | 2952.6 | 3507.7 | 3230.1 | 2362.1 | 3690.8 | 2806.1 | 4384.6 | 3003.1 | 2507.8 | 444.8 | 3062.9 | 444.8 | 2748.8 | 254.2
18.25 | 3222.3 | 3802.5 | 3512.4 | 2577.9 | 4027.9 | 3042 | 4753.1 | 3483.1 | 2601.6 | 620.7 | 3181.8 | 620.7 | 2862.4 | 620.7
18.5 | 2873.5 | 3479.2 | 3176.4 | 2298.8 | 3591.9 | 2783.4 | 4349 | 3060.5 | 2615.7 | 257.8 | 3221.4 | 257.8 | 2898.4 | 162.1
18.75 | 2963.8 | 3594.9 | 3279.3 | 2371 | 3704.7 | 2875.9 | 4493.7 | 3129.5 | 2621 | 342.8 | 3252.2 | 342.8 | 2923.5 | 206
19 | 2883.8 | 3540.4 | 3212.1 | 2307 | 3604.7 | 2832.3 | 4425.5 | 3115.8 | 2635.7 | 248.1 | 3292.3 | 248.1 | 2958.1 | 157.7
19.25 | 3272.7 | 3954.7 | 3613.7 | 2618.2 | 4090.9 | 3163.7 | 4943.3 | 3327.9 | 2643.2 | 629.5 | 3325.1 | 629.5 | 2984.4 | 343.5
19.5 | 2979.6 | 3687.2 | 3333.4 | 2383.7 | 3724.5 | 2949.7 | 4609 | 3245.1 | 2720.7 | 258.9 | 3428.3 | 258.9 | 3080.9 | 164.2
19.75 | 3307.9 | 4041.2 | 3674.5 | 2646.3 | 4134.8 | 3233 | 5051.5 | 3688.9 | 2729.9 | 577.9 | 3463.3 | 577.9 | 3111 | 577.9
20 | 2967.3 | 3726.6 | 3346.9 | 2373.8 | 3709.1 | 2981.3 | 4658.2 | 3301.9 | 2760.6 | 206.7 | 3519.9 | 206.7 | 3165.2 | 136.7
20.25 | 3023.7 | 3808.9 | 3416.3 | 2419 | 3779.7 | 3047.1 | 4761.1 | 3355.6 | 2765.9 | 257.9 | 3551 | 257.9 | 3190.9 | 164.7
20.5 | 3035.2 | 3846 | 3440.6 | 2428.1 | 3794 | 3076.8 | 4807.6 | 3385.8 | 2773.6 | 261.6 | 3584.5 | 261.6 | 3218.8 | 167
20.75 | 3038.6 | 3875.1 | 3456.9 | 2430.9 | 3798.2 | 3100.1 | 4843.9 | 3410.9 | 2778.6 | 260 | 3615.2 | 260 | 3244.4 | 166.5
21 | 3022.6 | 3884.8 | 3453.7 | 2418.1 | 3778.3 | 3107.8 | 4855.9 | 3426.3 | 2786.3 | 236.4 | 3648.4 | 236.4 | 3272.2 | 154.1
21.25 | 3063.3 | 3951 | 3507.2 | 2450.7 | 3829.2 | 3160.8 | 4938.7 | 3471.5 | 2790.4 | 272.9 | 3678.1 | 272.9 | 3297.4 | 174.1
21.5 | 3330.8 | 4243.9 | 3787.3 | 2664.7 | 4163.5 | 3395.1 | 5304.8 | 3630 | 2801.1 | 529.7 | 3714.2 | 529.7 | 3326.9 | 303.1
21.75 | 3074.9 | 4013.3 | 3544.1 | 2459.9 | 3843.6 | 3210.7 | 5016.6 | 3525.2 | 2809.6 | 265.3 | 3748 | 265.3 | 3354.6 | 170.7
22 | 3074 | 4037.7 | 3555.8 | 2459.2 | 3842.4 | 3230.2 | 5047.1 | 3548.7 | 2813.8 | 260.1 | 3777.6 | 260.1 | 3380.4 | 168.2
22.25 | 3094.3 | 4083.2 | 3588.8 | 2475.4 | 3867.9 | 3266.6 | 5104 | 3583 | 2818.8 | 275.5 | 3807.7 | 275.5 | 3406.1 | 176.8
22.5 | 3116.5 | 4130.5 | 3623.5 | 2493.2 | 3895.6 | 3304.4 | 5163.1 | 3619.2 | 2829.5 | 287 | 3843.5 | 287 | 3435.9 | 183.3
22.75 | 3727 | 4766.3 | 4246.6 | 2981.6 | 4658.7 | 3813.1 | 5957.9 | 3961.5 | 2901.3 | 825.6 | 3940.7 | 825.6 | 3518.5 | 443
23 | 5613.9 | 6680.7 | 6147.3 | 4491.1 | 7017.4 | 5344.6 | 8350.9 | 4749.8 | 3083.3 | 2530.6 | 4150.1 | 2530.6 | 3620.7 | 1129.1
23.25 | 10027.7 | 11125.9 | 10576.8 | 8022.2 | 12534.6 | 8900.7 | 13907.3 | 6287.9 | 3319.9 | 6707.8 | 4418.1 | 6707.8 | 3738.5 | 2549.4
23.5 | 10135.2 | 11275.7 | 10705.5 | 8108.2 | 12669 | 9020.6 | 14094.6 | 6370.9 | 3800.6 | 6334.6 | 4941.1 | 6334.6 | 3935.1 | 2435.9
23.75 | 11516.7 | 12711.6 | 12114.2 | 9213.4 | 14395.9 | 10169.3 | 15889.5 | 6861.8 | 4201.3 | 7315.4 | 5396.2 | 7315.4 | 4109.4 | 2752.4
24 | 6885 | 8146.1 | 7515.6 | 5508 | 8606.3 | 6516.9 | 10182.7 | 5339.9 | 4564 | 2321 | 5825.1 | 2321 | 4280.3 | 1059.6
24.25 | 9355.6 | 10687.4 | 10021.5 | 7484.5 | 11694.6 | 8549.9 | 13359.2 | 9036.5 | 4700.2 | 4655.4 | 6031.9 | 4655.4 | 4381.1 | 4655.4
24.5 | 6562.3 | 7973.3 | 7267.8 | 5249.9 | 8202.9 | 6378.6 | 9966.6 | 6317.7 | 5543.6 | 1018.8 | 6954.5 | 1018.8 | 5299 | 1018.8
24.75 | 7231.9 | 8727.2 | 7979.6 | 5785.5 | 9039.8 | 6981.8 | 10909 | 7071.7 | 5943.8 | 1288 | 7439.2 | 1288 | 5783.7 | 1288
25 | 7513 | 9097 | 8305 | 6010.4 | 9391.3 | 7277.6 | 11371.3 | 7441.5 | 6474.4 | 1038.7 | 8058.4 | 1038.7 | 6402.9 | 1038.7
25.25 | 7525.3 | 9200.8 | 8363.1 | 6020.2 | 9406.6 | 7360.7 | 11501 | 7545.3 | 6741.9 | 783.4 | 8417.4 | 783.4 | 6761.9 | 783.4
25.5 | 7737.3 | 9504.4 | 8620.9 | 6189.9 | 9671.7 | 7603.5 | 11880.5 | 7845.9 | 6809.5 | 927.8 | 8576.6 | 927.8 | 6918.2 | 927.8
25.75 | 7417.6 | 9275.7 | 8346.6 | 5934.1 | 9272 | 7420.5 | 11594.6 | 7409.7 | 6931.5 | 486.1 | 8789.5 | 486.1 | 7118.2 | 291.5
26 | 7723.4 | 9671.9 | 8697.6 | 6178.7 | 9654.2 | 7737.5 | 12089.9 | 7615.3 | 6923.4 | 800 | 8872 | 800 | 7173.1 | 442.2
26.25 | 8925.2 | 10964.3 | 9944.7 | 7140.1 | 11156.5 | 8771.4 | 13705.3 | 9259.5 | 7143.4 | 1781.8 | 9182.5 | 1781.8 | 7477.7 | 1781.8
26.5 | 8295.8 | 10427.6 | 9361.7 | 6636.6 | 10369.7 | 8342.1 | 13034.5 | 8722.8 | 7433.6 | 862.2 | 9565.4 | 862.2 | 7860.7 | 862.2
26.75 | 7743.3 | 9967.9 | 8855.6 | 6194.7 | 9679.2 | 7974.3 | 12459.9 | 8160.7 | 7454.3 | 289 | 9678.9 | 289 | 7970.5 | 190.2
27 | 8619.3 | 10935.9 | 9777.6 | 6895.5 | 10774.2 | 8748.7 | 13669.8 | 9218.5 | 7625.5 | 993.9 | 9942 | 993.9 | 8224.6 | 993.9
27.25 | 10834.7 | 13245 | 12039.9 | 8667.8 | 13543.4 | 10596 | 16556.3 | 11468.4 | 7838.4 | 2996.3 | 10248.7 | 2996.3 | 8472.1 | 2996.3
27.5 | 9084 | 11592.4 | 10338.2 | 7267.2 | 11355 | 9273.9 | 14490.5 | 9411.6 | 8225.2 | 858.8 | 10733.6 | 858.8 | 8938 | 473.6
27.75 | 9308 | 11916 | 10612 | 7446.4 | 11635 | 9532.8 | 14895 | 10114.2 | 8426.3 | 881.6 | 11034.4 | 881.6 | 9232.5 | 881.6
28 | 10827.5 | 13536.1 | 12181.8 | 8662 | 13534.3 | 10828.9 | 16920.2 | 11696.9 | 8621.2 | 2206.3 | 11329.8 | 2206.3 | 9490.6 | 2206.3
28.25 | 9864.5 | 12675.9 | 11270.2 | 7891.6 | 12330.6 | 10140.7 | 15844.9 | 10836.7 | 8855.5 | 1009 | 11666.9 | 1009 | 9827.7 | 1009
28.5 | 9171.9 | 12085.7 | 10628.8 | 7337.5 | 11464.9 | 9668.6 | 15107.2 | 10112.1 | 8820.3 | 351.6 | 11734.1 | 351.6 | 9885.7 | 226.4
28.75 | 9198.4 | 12213.1 | 10705.8 | 7358.7 | 11498 | 9770.5 | 15266.4 | 10191.5 | 8757.5 | 440.9 | 11772.2 | 440.9 | 9917.7 | 273.8
29 | 14277.4 | 17395.1 | 15836.2 | 11421.9 | 17846.7 | 13916.1 | 21743.9 | 12235.7 | 9055.7 | 5221.6 | 12173.4 | 5221.6 | 10084.4 | 2151.3
29.25 | 12139.3 | 15371.3 | 13755.3 | 9711.5 | 15174.1 | 12297.1 | 19214.1 | 13226.1 | 9932.5 | 2206.8 | 13164.5 | 2206.8 | 11019.3 | 2206.8
29.5 | 20109.8 | 23471.5 | 21790.7 | 16087.9 | 25137.3 | 18777.2 | 29339.3 | 21277 | 10947.8 | 9162 | 14309.5 | 9162 | 12115 | 9162
29.75 | 17730.6 | 21251.3 | 19490.9 | 14184.5 | 22163.2 | 17001 | 26564.1 | 15580.7 | 12002.3 | 5728.3 | 15523 | 5728.3 | 13245.9 | 2334.8
30 | 16085.9 | 19778.5 | 17932.2 | 12868.7 | 20107.4 | 15822.8 | 24723.1 | 15095.5 | 12279.6 | 3806.3 | 15972.2 | 3806.3 | 13432 | 1663.6
30.25 | 14397.9 | 18265.1 | 16331.5 | 11518.3 | 17997.4 | 14612.1 | 22831.3 | 14546.7 | 12320.7 | 2077.2 | 16187.8 | 2077.2 | 13540.8 | 1005.9
30.5 | 15012.5 | 19054 | 17033.2 | 12010 | 18765.6 | 15243.2 | 23817.5 | 14885.7 | 12400.4 | 2612 | 16442 | 2612 | 13666.3 | 1219.5
30.75 | 15680.6 | 19897.6 | 17789.1 | 12544.5 | 19600.7 | 15918 | 24871.9 | 15235.4 | 12500 | 3180.6 | 16717 | 3180.6 | 13796.1 | 1439.3
31 | 14645.2 | 19038.5 | 16841.8 | 11716.1 | 18306.4 | 15230.8 | 23798.1 | 14928.9 | 12579.2 | 2066 | 16972.5 | 2066 | 13922.7 | 1006.2
31.25 | 16537 | 21106.7 | 18821.9 | 13229.6 | 20671.3 | 16885.4 | 26383.4 | 15749.2 | 12656.8 | 3880.3 | 17226.5 | 3880.3 | 14045.2 | 1704
31.5 | 15150.7 | 19898.6 | 17524.6 | 12120.6 | 18938.4 | 15918.8 | 24873.2 | 15319.7 | 12782.1 | 2368.6 | 17530 | 2368.6 | 14188.6 | 1131.1
31.75 | 16191.1 | 21117.6 | 18654.3 | 12952.9 | 20238.8 | 16894.1 | 26397 | 15819 | 12842.5 | 3348.6 | 17769.1 | 3348.6 | 14307.3 | 1511.8
32 | 15902.3 | 21008.4 | 18455.4 | 12721.9 | 19877.9 | 16806.8 | 26260.6 | 15809.2 | 12946.4 | 2955.9 | 18052.5 | 2955.9 | 14444.6 | 1364.6
32.25 | 16700.8 | 21987.3 | 19344.1 | 13360.7 | 20876 | 17589.9 | 27484.2 | 16209.2 | 13037.2 | 3663.6 | 18323.7 | 3663.6 | 14574.8 | 1634.4
32.5 | 16219.2 | 21688.5 | 18953.8 | 12975.3 | 20274 | 17350.8 | 27110.6 | 16125 | 13214.9 | 3004.3 | 18684.2 | 3004.3 | 14737.6 | 1387.4
32.75 | 19445.2 | 25100.5 | 22272.9 | 15556.2 | 24306.6 | 20080.4 | 31375.6 | 17386.9 | 13435.2 | 6010.1 | 19090.4 | 6010.1 | 14910.6 | 2476.3
33 | 17706.4 | 23552.8 | 20629.6 | 14165.1 | 22133 | 18842.3 | 29441.1 | 16875.4 | 13648.2 | 4058.2 | 19494.7 | 4058.2 | 15087.6 | 1787.8
33.25 | 19027.3 | 25068.4 | 22047.9 | 15221.9 | 23784.2 | 20054.7 | 31335.5 | 17452.5 | 13840.6 | 5186.8 | 19881.6 | 5186.8 | 15255.8 | 2196.6
33.5 | 17019.2 | 23258.2 | 20138.7 | 13615.4 | 21274 | 18606.6 | 29072.7 | 18475.7 | 14055.7 | 2963.5 | 20294.7 | 2963.5 | 15512.2 | 2963.5
33.75 | 17640 | 24082.8 | 20861.4 | 14112 | 22050 | 19266.2 | 30103.5 | 19300.3 | 14753 | 2887 | 21195.8 | 2887 | 16413.3 | 2887
34 | 17451.2 | 24099.9 | 20775.6 | 13961 | 21814 | 19279.9 | 30124.9 | 19247.5 | 14944.8 | 2506.4 | 21593.6 | 2506.4 | 16741.2 | 2506.4
34.25 | 16814.2 | 23670.9 | 20242.5 | 13451.3 | 21017.7 | 18936.7 | 29588.6 | 18092.3 | 15298.5 | 1515.6 | 22155.2 | 1515.6 | 17300.3 | 792
34.5 | 18848.3 | 25914.9 | 22381.6 | 15078.7 | 23560.4 | 20731.9 | 32393.6 | 21046.2 | 15772.6 | 3075.7 | 22839.1 | 3075.7 | 17970.5 | 3075.7
34.75 | 18956.2 | 26235.2 | 22595.7 | 15165 | 23695.3 | 20988.2 | 32794.1 | 21331.5 | 16052.9 | 2903.3 | 23332 | 2903.3 | 18428.2 | 2903.3
35 | 18330.2 | 25825.7 | 22078 | 14664.2 | 22912.8 | 20660.6 | 32282.2 | 20921.9 | 16618.1 | 1712.1 | 24113.6 | 1712.1 | 19209.8 | 1712.1
35.25 | 19089.7 | 26804.1 | 22946.9 | 15271.7 | 23862.1 | 21443.2 | 33505.1 | 21886.1 | 16849.6 | 2240 | 24564 | 2240 | 19646.1 | 2240
35.5 | 19126.7 | 27060.5 | 23093.6 | 15301.4 | 23908.4 | 21648.4 | 33825.7 | 22128.7 | 17119.5 | 2007.2 | 25053.4 | 2007.2 | 20121.5 | 2007.2
35.75 | 18969.5 | 27124.3 | 23046.9 | 15175.6 | 23711.9 | 21699.4 | 33905.3 | 22164.7 | 17430.7 | 1538.8 | 25585.5 | 1538.8 | 20625.9 | 1538.8
36 | 18630.4 | 27007.3 | 22818.8 | 14904.3 | 23288 | 21605.8 | 33759.1 | 21625.7 | 17663.5 | 966.9 | 26040.4 | 966.9 | 21076.6 | 549.1
36.25 | 21297.8 | 29896.5 | 25597.1 | 17038.2 | 26622.2 | 23917.2 | 37370.6 | 24914.3 | 17980.6 | 3317.2 | 26579.3 | 3317.2 | 21597.1 | 3317.2
36.5 | 20590.1 | 29418.1 | 25004.1 | 16472.1 | 25737.6 | 23534.5 | 36772.7 | 24435.9 | 18827.8 | 1762.3 | 27655.8 | 1762.3 | 22673.6 | 1762.3
36.75 | 24244 | 33307.9 | 28776 | 19395.2 | 30305.1 | 26646.3 | 41634.9 | 25270.5 | 19097.7 | 5146.3 | 28161.5 | 5146.3 | 23050.7 | 2219.8
37 | 22285.1 | 31588.3 | 26936.7 | 17828.1 | 27856.4 | 25270.7 | 39485.4 | 26397.8 | 19623 | 2662.1 | 28926.3 | 2662.1 | 23735.7 | 2662.1
37.25 | 23811.5 | 33359.7 | 28585.6 | 19049.2 | 29764.4 | 26687.8 | 41699.6 | 28162.9 | 20103.8 | 3707.7 | 29652 | 3707.7 | 24455.1 | 3707.7
37.5 | 26577.4 | 36376.6 | 31477 | 21261.9 | 33221.7 | 29101.2 | 45470.7 | 31142 | 20771.7 | 5805.7 | 30570.9 | 5805.7 | 25336.4 | 5805.7
37.75 | 26628.5 | 36687.1 | 31657.8 | 21302.8 | 33285.6 | 29349.7 | 45858.9 | 31294.3 | 21000.2 | 5628.3 | 31058.8 | 5628.3 | 25666.1 | 5628.3
38 | 27076.9 | 37400 | 32238.4 | 21661.5 | 33846.1 | 29920 | 46750 | 28444 | 21342.3 | 5734.6 | 31665.3 | 5734.6 | 26000.1 | 2443.9
38.25 | 25715.2 | 36307.3 | 31011.3 | 20572.2 | 32144 | 29045.9 | 45384.2 | 28082.1 | 21445.9 | 4269.3 | 32038.1 | 4269.3 | 26168.6 | 1913.5
38.5 | 25270.1 | 36132.5 | 30701.3 | 20216.1 | 31587.6 | 28906 | 45165.7 | 28051.2 | 21541.5 | 3728.6 | 32403.9 | 3728.6 | 26339.7 | 1711.4
38.75 | 26113.4 | 37247.9 | 31680.6 | 20890.7 | 32641.7 | 29798.3 | 46559.8 | 28500.1 | 21682.2 | 4431.1 | 32816.7 | 4431.1 | 26521.5 | 1978.7
39 | 25039.6 | 36448.7 | 30744.2 | 20031.7 | 31299.5 | 29158.9 | 45560.8 | 28379.7 | 21906.8 | 3132.8 | 33315.9 | 3132.8 | 26895.9 | 1483.9
39.25 | 27981.9 | 39667.8 | 33824.9 | 22385.5 | 34977.4 | 31734.2 | 49584.7 | 29611.1 | 22007.8 | 5974.2 | 33693.6 | 5974.2 | 27067 | 2544.2
39.5 | 27492.9 | 39458.2 | 33475.6 | 21994.4 | 34366.2 | 31566.6 | 49322.7 | 29578 | 22133.3 | 5359.7 | 34098.5 | 5359.7 | 27251.1 | 2326.9
39.75 | 26565.4 | 38812.3 | 32688.9 | 21252.3 | 33206.7 | 31049.9 | 48515.4 | 29374.2 | 22251.3 | 4314.1 | 34498.3 | 4314.1 | 27429.9 | 1944.3
40 | 28489 | 41019 | 34754 | 22791.2 | 35611.3 | 32815.2 | 51273.7 | 33784.2 | 22408.7 | 6080.4 | 34938.6 | 6080.4 | 27703.8 | 6080.4
40.25 | 28642.6 | 41458.2 | 35050.4 | 22914.1 | 35803.3 | 33166.5 | 51822.7 | 30516 | 22587.5 | 6055.1 | 35403 | 6055.1 | 27930.9 | 2585.1
40.5 | 27658.9 | 40765.4 | 34212.1 | 22127.1 | 34573.6 | 32612.3 | 50956.8 | 30297.9 | 22853.6 | 4805.3 | 35960.2 | 4805.3 | 28163.3 | 2134.6
40.75 | 25996.2 | 39396.6 | 32696.4 | 20796.9 | 32495.2 | 31517.2 | 49245.7 | 29806.2 | 22890 | 3106.2 | 36290.4 | 3106.2 | 28320.5 | 1485.6
41 | 26968.6 | 40662.7 | 33815.7 | 21574.9 | 33710.8 | 32530.2 | 50828.4 | 30331.2 | 22986.3 | 3982.3 | 36680.4 | 3982.3 | 28501.6 | 1829.5
41.25 | 27755.7 | 41744.3 | 34750 | 22204.5 | 34694.6 | 33395.4 | 52180.4 | 30830 | 23087.4 | 4668.3 | 37076 | 4668.3 | 28739 | 2091
41.5 | 29737.9 | 44022.7 | 36880.3 | 23790.4 | 37172.4 | 35218.1 | 55028.4 | 31697.8 | 23229.4 | 6508.5 | 37514.1 | 6508.5 | 28936.4 | 2761.4
41.75 | 27888 | 42472.2 | 35180.1 | 22310.4 | 34860 | 33977.8 | 53090.3 | 33761.1 | 23683.3 | 4204.7 | 38267.6 | 4204.7 | 29556.4 | 4204.7
42 | 28101.9 | 42991.5 | 35546.7 | 22481.5 | 35127.4 | 34393.2 | 53739.4 | 34240.8 | 24152.3 | 3949.6 | 39041.9 | 3949.6 | 30291.1 | 3949.6
42.25 | 28991.7 | 44191.1 | 36591.4 | 23193.4 | 36239.7 | 35352.9 | 55238.8 | 35440.4 | 24729.4 | 4262.4 | 39928.7 | 4262.4 | 31178 | 4262.4
42.5 | 28866.9 | 44382.9 | 36624.9 | 23093.5 | 36083.6 | 35506.3 | 55478.7 | 35583.4 | 25290.2 | 3576.7 | 40806.2 | 3576.7 | 32006.7 | 3576.7
42.75 | 28597.9 | 44434.5 | 36516.2 | 22878.3 | 35747.4 | 35547.6 | 55543.2 | 34064 | 25647.8 | 2950.2 | 41484.4 | 2950.2 | 32628.6 | 1435.5
43 | 28729.1 | 44888.3 | 36808.7 | 22983.3 | 35911.4 | 35910.6 | 56110.4 | 34586.8 | 26031.2 | 2697.9 | 42190.4 | 2697.9 | 33253 | 1333.7
43.25 | 29909.1 | 46394.3 | 38151.7 | 23927.3 | 37386.4 | 37115.4 | 57992.8 | 37388.4 | 26475.9 | 3433.3 | 42961 | 3433.3 | 33955.2 | 3433.3
43.5 | 30252.3 | 47068.2 | 38660.3 | 24201.8 | 37815.3 | 37654.6 | 58835.3 | 37925.2 | 26768.3 | 3483.9 | 43584.3 | 3483.9 | 34441.2 | 3483.9
43.75 | 29055.7 | 46205.7 | 37630.7 | 23244.6 | 36319.6 | 36964.6 | 57757.1 | 37062.7 | 27459.7 | 1596 | 44609.7 | 1596 | 35466.7 | 1596
44 | 29278.7 | 46764.6 | 38021.7 | 23423 | 36598.4 | 37411.7 | 58455.8 | 37599.2 | 27764.4 | 1514.3 | 45250.3 | 1514.3 | 36084.9 | 1514.3
44.25 | 29895.8 | 47720.6 | 38808.2 | 23916.6 | 37369.8 | 38176.4 | 59650.7 | 38555.1 | 28482.6 | 1413.2 | 46307.4 | 1413.2 | 37142 | 1413.2
44.5 | 32438 | 50603.2 | 41520.6 | 25950.4 | 40547.5 | 40482.6 | 63254.1 | 39365.1 | 28658.7 | 3779.3 | 46823.9 | 3779.3 | 37588.6 | 1776.5
44.75 | 30816.2 | 49323.9 | 40070 | 24652.9 | 38520.2 | 39459.1 | 61654.8 | 40058.3 | 29346.2 | 1470 | 47853.9 | 1470 | 38588.3 | 1470
45 | 30813.7 | 49664.6 | 40239.1 | 24651 | 38517.1 | 39731.7 | 62080.8 | 40392.6 | 29328.3 | 1485.4 | 48179.2 | 1485.4 | 38907.2 | 1485.4
45.25 | 40622.9 | 59814 | 50218.5 | 32498.3 | 50778.7 | 47851.2 | 74767.5 | 43640.7 | 29382.9 | 11240.1 | 48573.9 | 11240.1 | 39222.7 | 4418
45.5 | 58541.3 | 78080.5 | 68310.9 | 46833.1 | 73176.6 | 62464.4 | 97600.6 | 49095.5 | 29403.6 | 29137.7 | 48942.8 | 29137.7 | 39314 | 9781.5
45.75 | 48565.4 | 68447.8 | 58506.6 | 38852.3 | 60706.8 | 54758.2 | 85559.7 | 46321.7 | 29060.4 | 19505 | 48942.8 | 19505 | 39314 | 7007.7
46 | 39365.9 | 59585.1 | 49475.5 | 31492.7 | 49207.3 | 47668.1 | 74481.3 | 43547.9 | 28723.6 | 10642.3 | 48942.8 | 10642.3 | 39314 | 4233.9
46.25 | 31355.8 | 51905.6 | 41630.7 | 25084.6 | 39194.7 | 41524.5 | 64882 | 40774.1 | 28393 | 2962.8 | 48942.8 | 2962.8 | 39314 | 1460.1
46.5 | 37419.7 | 59209.7 | 48314.7 | 29935.8 | 46774.7 | 47367.7 | 74012.1 | 42584.6 | 32943.3 | 4476.4 | 54733.3 | 4476.4 | 40523.1 | 2061.5
46.75 | 35743.5 | 58029 | 46886.3 | 28594.8 | 44679.4 | 46423.2 | 72536.3 | 42140.3 | 32883.7 | 2859.9 | 55169.1 | 2859.9 | 40719.7 | 1420.6
47 | 35917.5 | 58690.6 | 47304 | 28734 | 44896.9 | 46952.5 | 73363.2 | 42441 | 32773.5 | 3143.9 | 55546.6 | 3143.9 | 40902.3 | 1538.8
47.25 | 36679.9 | 59931 | 48305.5 | 29343.9 | 45849.9 | 47944.8 | 74913.7 | 43060.8 | 32603.5 | 4076.5 | 55854.5 | 4076.5 | 41148.4 | 1912.4
47.5 | 39498.7 | 63219.7 | 51359.2 | 31599 | 49373.4 | 50575.8 | 79024.6 | 48333.2 | 32696 | 6802.7 | 56417 | 6802.7 | 41530.5 | 6802.7
47.75 | 46866.3 | 71057.4 | 58961.9 | 37493.1 | 58582.9 | 56845.9 | 88821.8 | 47169.2 | 33066.1 | 13800.2 | 57257.2 | 13800.2 | 41875.2 | 5293.9
48 | 49060.3 | 73736.9 | 61398.6 | 39248.3 | 61325.4 | 58989.5 | 92171.2 | 57760.9 | 34123 | 14937.3 | 58799.6 | 14937.3 | 42823.6 | 14937.3
48.25 | 47494.1 | 72695.8 | 60095 | 37995.3 | 59367.6 | 58156.7 | 90869.8 | 56719.8 | 36511.2 | 10982.9 | 61712.9 | 10982.9 | 45736.9 | 10982.9
48.5 | 48379.1 | 74152.6 | 61265.9 | 38703.3 | 60473.8 | 59322.1 | 92690.8 | 57779.1 | 38318.7 | 10060.4 | 64092.3 | 10060.4 | 47718.7 | 10060.4
48.75 | 51663.7 | 78044.8 | 64854.2 | 41331 | 64579.6 | 62435.8 | 97556 | 61671.2 | 40762.2 | 10901.5 | 67143.3 | 10901.5 | 50769.8 | 10901.5
49 | 55158.1 | 82187.7 | 68672.9 | 44126.5 | 68947.7 | 65750.2 | 102734.7 | 58156.5 | 42749.7 | 12408.5 | 69779.3 | 12408.5 | 53288.4 | 4868.2
49.25 | 48582.9 | 76283.7 | 62433.3 | 38866.3 | 60728.6 | 61026.9 | 95354.6 | 56137.3 | 42922.6 | 5660.3 | 70623.4 | 5660.3 | 53603.9 | 2533.5
49.5 | 51380.2 | 79749.4 | 65564.8 | 41104.1 | 64225.2 | 63799.5 | 99686.7 | 57561.2 | 42990.4 | 8389.8 | 71359.6 | 8389.8 | 54041.2 | 3520
49.75 | 63849.6 | 92893.9 | 78371.8 | 51079.7 | 79812 | 74315.1 | 116117.4 | 75453.5 | 44280.4 | 19569.2 | 73324.7 | 19569.2 | 55884.2 | 19569.2
50 | 71143.2 | 100910.2 | 86026.7 | 56914.6 | 88929 | 80728.1 | 126137.7 | 66392.5 | 45915.1 | 25228.1 | 75682.1 | 25228.1 | 57565.8 | 8826.7

## SRD WTG-16
Depth (m) | SRD AH-FF (kN) | SRD AH-NFF (kN) | SRD MEAN (kN) | SRD AH-FF-LB (kN) | SRD AH-FF-UB (kN) | SRD AH-NFF-LB (kN) | SRD AH-NFF-UB (kN) | Static Cap (kN) | Shaft AH-FF (kN) | Tip AH-FF (kN) | Shaft AH-NFF (kN) | Tip AH-NFF (kN) | Shaft SC (kN) | Tip SC (kN)
0.5 | 49.2 | 49.3 | 49.3 | 39.4 | 61.5 | 39.4 | 61.6 | 23.8 | 3.6 | 45.6 | 3.6 | 45.6 | 2.8 | 21
0.75 | 47.6 | 47.7 | 47.7 | 38.1 | 59.5 | 38.2 | 59.7 | 25.5 | 5.5 | 42.1 | 5.6 | 42.1 | 4.5 | 21
1 | 48.2 | 48.5 | 48.4 | 38.6 | 60.3 | 38.8 | 60.7 | 28.4 | 8.5 | 39.7 | 8.8 | 39.7 | 7.4 | 21
1.25 | 48.5 | 49 | 48.7 | 38.8 | 60.6 | 39.2 | 61.2 | 30.5 | 10.5 | 38 | 11 | 38 | 9.4 | 21
1.5 | 50.3 | 51 | 50.6 | 40.2 | 62.9 | 40.8 | 63.7 | 33.8 | 13.7 | 36.6 | 14.3 | 36.6 | 12.7 | 21
1.75 | 52.4 | 53.3 | 52.9 | 42 | 65.6 | 42.7 | 66.7 | 36.9 | 16.2 | 36.3 | 17.1 | 36.3 | 15.5 | 21.4
2 | 56 | 57.1 | 56.6 | 44.8 | 70 | 45.7 | 71.4 | 40.9 | 19.1 | 36.9 | 20.2 | 36.9 | 18.7 | 22.2
2.25 | 70.9 | 72.3 | 71.6 | 56.7 | 88.6 | 57.8 | 90.3 | 50.6 | 22.2 | 48.7 | 23.5 | 48.7 | 22.1 | 28.5
2.5 | 77.6 | 79.2 | 78.4 | 62 | 96.9 | 63.4 | 99 | 56.6 | 26.3 | 51.3 | 27.9 | 51.3 | 26.4 | 30.2
2.75 | 167 | 169 | 168 | 133.6 | 208.8 | 135.2 | 211.3 | 167.3 | 35.3 | 131.7 | 37.3 | 131.7 | 35.6 | 131.7
3 | 100.5 | 102.9 | 101.7 | 80.4 | 125.6 | 82.4 | 128.7 | 79.4 | 46 | 54.5 | 48.5 | 54.5 | 46.7 | 32.7
3.25 | 105.4 | 108.4 | 106.9 | 84.3 | 131.7 | 86.7 | 135.4 | 84.8 | 50.2 | 55.2 | 53.2 | 55.2 | 51.3 | 33.5
3.5 | 111 | 114.6 | 112.8 | 88.8 | 138.8 | 91.6 | 143.2 | 90.9 | 54.9 | 56.2 | 58.4 | 56.2 | 56.5 | 34.4
3.75 | 119.1 | 123.2 | 121.2 | 95.3 | 148.9 | 98.6 | 154 | 99.2 | 61.5 | 57.6 | 65.6 | 57.6 | 63.7 | 35.5
4 | 122.8 | 127.5 | 125.2 | 98.2 | 153.5 | 102 | 159.4 | 104.6 | 66.5 | 56.2 | 71.3 | 56.2 | 69.4 | 35.2
4.25 | 129.5 | 134.9 | 132.2 | 103.6 | 161.9 | 108 | 168.7 | 111.3 | 71 | 58.5 | 76.5 | 58.5 | 74.6 | 36.7
4.5 | 136.4 | 142.5 | 139.5 | 109.1 | 170.5 | 114 | 178.2 | 118.5 | 76.3 | 60.1 | 82.4 | 60.1 | 80.6 | 37.9
4.75 | 144.7 | 151.6 | 148.2 | 115.8 | 180.9 | 121.3 | 189.5 | 127.3 | 83.3 | 61.4 | 90.2 | 61.4 | 88.4 | 38.9
5 | 164.5 | 172.2 | 168.4 | 131.6 | 205.7 | 137.8 | 215.2 | 141.6 | 89.1 | 75.5 | 96.7 | 75.5 | 95 | 46.6
5.25 | 177.9 | 186.4 | 182.2 | 142.3 | 222.4 | 149.2 | 233.1 | 159.7 | 111.3 | 66.6 | 119.9 | 66.6 | 117.4 | 42.3
5.5 | 191.2 | 200.7 | 196 | 152.9 | 239 | 160.6 | 250.9 | 171 | 118.2 | 73 | 127.8 | 73 | 125 | 46
5.75 | 215.9 | 226.5 | 221.2 | 172.7 | 269.8 | 181.2 | 283.2 | 191.8 | 132.2 | 83.7 | 142.8 | 83.7 | 139.8 | 52
6 | 219.5 | 231.4 | 225.5 | 175.6 | 274.4 | 185.1 | 289.2 | 199.1 | 140.7 | 78.8 | 152.6 | 78.8 | 149.3 | 49.8
6.25 | 224.9 | 238 | 231.4 | 179.9 | 281.1 | 190.4 | 297.5 | 206.4 | 147.4 | 77.5 | 160.5 | 77.5 | 156.9 | 49.4
6.5 | 232.2 | 246.6 | 239.4 | 185.8 | 290.2 | 197.3 | 308.2 | 215.1 | 154.6 | 77.6 | 169 | 77.6 | 165.3 | 49.8
6.75 | 257.9 | 273.6 | 265.8 | 206.3 | 322.3 | 218.9 | 342 | 238.7 | 172.6 | 85.2 | 188.4 | 85.2 | 184.5 | 54.2
7 | 263.2 | 280.4 | 271.8 | 210.5 | 328.9 | 224.3 | 350.5 | 247.3 | 181.7 | 81.5 | 198.9 | 81.5 | 194.8 | 52.5
7.25 | 283.6 | 302.4 | 293 | 226.9 | 354.5 | 241.9 | 378 | 263.1 | 188.7 | 94.9 | 207.5 | 94.9 | 203.2 | 60
7.5 | 283.6 | 304 | 293.8 | 226.9 | 354.5 | 243.2 | 380 | 268.5 | 196.3 | 87.3 | 216.7 | 87.3 | 212.2 | 56.2
7.75 | 439.8 | 461.8 | 450.8 | 351.8 | 549.7 | 369.4 | 577.3 | 457.1 | 208.3 | 231.5 | 230.3 | 231.5 | 225.6 | 231.5
8 | 311.4 | 335.2 | 323.3 | 249.1 | 389.2 | 268.1 | 419 | 298.5 | 221.3 | 90.1 | 245 | 90.1 | 240.1 | 58.4
8.25 | 326.1 | 351.7 | 338.9 | 260.9 | 407.6 | 281.3 | 439.6 | 311.8 | 229 | 97 | 254.6 | 97 | 249.4 | 62.4
8.5 | 341.3 | 368.8 | 355.1 | 273 | 426.6 | 295 | 461 | 325.8 | 237.8 | 103.5 | 265.3 | 103.5 | 259.6 | 66.2
8.75 | 372.8 | 402.3 | 387.5 | 298.3 | 466 | 321.8 | 502.8 | 348.4 | 247.5 | 125.4 | 276.9 | 125.4 | 270.3 | 78
9 | 372.3 | 403.7 | 388 | 297.9 | 465.4 | 323 | 504.7 | 354.7 | 258.7 | 113.6 | 290.2 | 113.6 | 282.5 | 72.2
9.25 | 364.8 | 398.3 | 381.5 | 291.8 | 456 | 318.6 | 497.9 | 356.5 | 267.3 | 97.4 | 300.9 | 97.4 | 292.7 | 63.8
9.5 | 394.7 | 430.4 | 412.5 | 315.8 | 493.4 | 344.3 | 538 | 379.2 | 277.7 | 117 | 313.3 | 117 | 304.5 | 74.7
9.75 | 438.3 | 476.2 | 457.3 | 350.7 | 547.9 | 381 | 595.3 | 409.7 | 290.1 | 148.2 | 328 | 148.2 | 318.3 | 91.3
10 | 590.8 | 631.1 | 611 | 472.7 | 738.6 | 504.9 | 788.8 | 492 | 306.8 | 284.1 | 347 | 284.1 | 334.3 | 157.7
10.25 | 4052.1 | 4096.5 | 4074.3 | 3241.7 | 5065.1 | 3277.2 | 5120.6 | 1713.2 | 462.8 | 3589.2 | 507.2 | 3589.2 | 400.9 | 1312.2
10.5 | 5662.1 | 5717.8 | 5689.9 | 4529.7 | 7077.6 | 4574.2 | 7147.3 | 2225.3 | 730.7 | 4931.4 | 786.5 | 4931.4 | 506.8 | 1718.6
10.75 | 3978.1 | 4054 | 4016.1 | 3182.5 | 4972.7 | 3243.2 | 5067.5 | 1750.5 | 946 | 3032.1 | 1021.9 | 3032.1 | 599 | 1151.5
11 | 4344.7 | 4445.7 | 4395.2 | 3475.8 | 5430.9 | 3556.6 | 5557.1 | 1901.4 | 1116 | 3228.7 | 1217 | 3228.7 | 682.5 | 1218.9
11.25 | 3971.5 | 4101.9 | 4036.7 | 3177.2 | 4964.4 | 3281.5 | 5127.3 | 1816.2 | 1265.8 | 2705.7 | 1396.2 | 2705.7 | 759.6 | 1056.6
11.5 | 4653.2 | 4816.8 | 4735 | 3722.5 | 5816.5 | 3853.4 | 6021 | 2072.4 | 1425.7 | 3227.5 | 1589.3 | 3227.5 | 843.2 | 1229.2
11.75 | 4090 | 4290.8 | 4190.4 | 3272 | 5112.6 | 3432.6 | 5363.5 | 3452.9 | 1568.7 | 2521.3 | 1769.5 | 2521.3 | 931.6 | 2521.3
12 | 3989.7 | 4231.7 | 4110.7 | 3191.8 | 4987.1 | 3385.3 | 5289.6 | 3290.5 | 1786.1 | 2203.6 | 2028.1 | 2203.6 | 1086.9 | 2203.6
12.25 | 2637.8 | 2925.6 | 2781.7 | 2110.2 | 3297.2 | 2340.5 | 3657 | 1757.9 | 2156.6 | 481.2 | 2444.4 | 481.2 | 1503.2 | 254.6
12.5 | 2631.7 | 2966.9 | 2799.3 | 2105.4 | 3289.6 | 2373.5 | 3708.7 | 2023.2 | 2257.9 | 373.8 | 2593.1 | 373.8 | 1649.4 | 373.8
12.75 | 2679.8 | 3061.7 | 2870.8 | 2143.8 | 3349.7 | 2449.4 | 3827.2 | 2116.6 | 2252.3 | 427.5 | 2634.3 | 427.5 | 1689.2 | 427.5
13 | 2741.4 | 3169.4 | 2955.4 | 2193.1 | 3426.8 | 2535.5 | 3961.7 | 2223.7 | 2342.7 | 398.7 | 2770.6 | 398.7 | 1825 | 398.7
13.25 | 2645.4 | 3118.7 | 2882 | 2116.3 | 3306.7 | 2494.9 | 3898.4 | 2036.4 | 2331.3 | 314.1 | 2804.6 | 314.1 | 1855.6 | 180.9
13.5 | 2967.1 | 3485.3 | 3226.2 | 2373.7 | 3708.8 | 2788.2 | 4356.6 | 2535.4 | 2455.7 | 511.4 | 2973.8 | 511.4 | 2024 | 511.4
13.75 | 3130.8 | 3693.5 | 3412.1 | 2504.6 | 3913.5 | 2954.8 | 4616.9 | 2422.8 | 2487.5 | 643.2 | 3050.3 | 643.2 | 2092.1 | 330.7
14 | 5046.1 | 5653.9 | 5350 | 4036.9 | 6307.7 | 4523.1 | 7067.3 | 3233.3 | 2631.3 | 2414.8 | 3239.1 | 2414.8 | 2234.1 | 999.2
14.25 | 3456.8 | 4111.8 | 3784.3 | 2765.5 | 4321 | 3289.4 | 5139.7 | 3064.1 | 2815.1 | 641.8 | 3470 | 641.8 | 2422.3 | 641.8
14.5 | 3407.4 | 4111.9 | 3759.6 | 2725.9 | 4259.3 | 3289.5 | 5139.9 | 2872.6 | 2982.1 | 425.3 | 3686.6 | 425.3 | 2636.2 | 236.5
14.75 | 5367.5 | 6121.5 | 5744.5 | 4294 | 6709.4 | 4897.2 | 7651.9 | 3671.1 | 3043.5 | 2324 | 3797.5 | 2324 | 2694.3 | 976.8
15 | 5817.3 | 6624.5 | 6220.9 | 4653.8 | 7271.6 | 5299.6 | 8280.6 | 3867.3 | 3268 | 2549.3 | 4075.2 | 2549.3 | 2808.7 | 1058.6
15.25 | 5980.4 | 6844.5 | 6412.5 | 4784.4 | 7475.6 | 5475.6 | 8555.6 | 3967.6 | 3353.4 | 2627 | 4217.4 | 2627 | 2878.8 | 1088.7
15.5 | 6140.8 | 7063.5 | 6602.2 | 4912.7 | 7676 | 5650.8 | 8829.4 | 4069.6 | 3486 | 2654.8 | 4408.8 | 2654.8 | 2967.9 | 1101.7
15.75 | 6972.6 | 7957.3 | 7464.9 | 5578 | 8715.7 | 6365.9 | 9946.7 | 4397.9 | 3656.5 | 3316.1 | 4641.2 | 3316.1 | 3067.7 | 1330.2
16 | 6883.3 | 7935.2 | 7409.2 | 5506.6 | 8604.1 | 6348.1 | 9919 | 4416.6 | 3877.1 | 3006.2 | 4928.9 | 3006.2 | 3187 | 1229.5
16.25 | 6420 | 7543.2 | 6981.6 | 5136 | 8024.9 | 6034.6 | 9429 | 5714 | 4108 | 2312 | 5231.2 | 2312 | 3402 | 2312
16.5 | 5731.4 | 6932.7 | 6332 | 4585.1 | 7164.2 | 5546.2 | 8665.9 | 5103.6 | 4653.3 | 1078 | 5854.7 | 1078 | 4025.5 | 1078
16.75 | 5997.2 | 7280.1 | 6638.7 | 4797.8 | 7496.5 | 5824.1 | 9100.2 | 5442.3 | 4853.6 | 1143.7 | 6136.5 | 1143.7 | 4298.6 | 1143.7
17 | 7244.9 | 8611.2 | 7928 | 5795.9 | 9056.1 | 6888.9 | 10764 | 5536.5 | 5074.9 | 2170.1 | 6441.1 | 2170.1 | 4589.6 | 946.9
17.25 | 7349.7 | 8801 | 8075.4 | 5879.8 | 9187.2 | 7040.8 | 11001.3 | 6913.4 | 5407.7 | 1942 | 6859 | 1942 | 4971.4 | 1942
17.5 | 7503.4 | 9045.7 | 8274.6 | 6002.7 | 9379.2 | 7236.6 | 11307.2 | 7125.6 | 5750.6 | 1752.8 | 7292.9 | 1752.8 | 5372.7 | 1752.8
17.75 | 9442 | 11079.6 | 10260.8 | 7553.6 | 11802.5 | 8863.7 | 13849.5 | 9089.6 | 6049.5 | 3392.5 | 7687.1 | 3392.5 | 5697.1 | 3392.5
18 | 11563.4 | 13300.6 | 12432 | 9250.7 | 14454.3 | 10640.5 | 16625.7 | 7945.9 | 6278.6 | 5284.8 | 8015.8 | 5284.8 | 5937.5 | 2008.4
18.25 | 16023.1 | 17868 | 16945.5 | 12818.5 | 20028.8 | 14294.4 | 22335 | 9354.9 | 6665 | 9358.1 | 8509.9 | 9358.1 | 6112.8 | 3242.2
18.5 | 9515.6 | 11488.9 | 10502.2 | 7612.5 | 11894.5 | 9191.1 | 14361.1 | 8930.2 | 7802.6 | 1713 | 9775.9 | 1713 | 7217.2 | 1713
18.75 | 8938.9 | 11058.3 | 9998.6 | 7151.1 | 11173.6 | 8846.7 | 13822.9 | 8499.4 | 8261.3 | 677.5 | 10380.8 | 677.5 | 7821.9 | 677.5
19 | 9368.3 | 11633.1 | 10500.7 | 7494.7 | 11710.4 | 9306.4 | 14541.3 | 9074 | 8331.9 | 1036.4 | 10596.7 | 1036.4 | 8037.6 | 1036.4
19.25 | 9048.4 | 11456.2 | 10252.3 | 7238.7 | 11310.5 | 9165 | 14320.3 | 8897.2 | 8363 | 685.4 | 10770.8 | 685.4 | 8211.8 | 685.4
19.5 | 9499.9 | 12048.9 | 10774.4 | 7600 | 11874.9 | 9639.1 | 15061.1 | 9489.9 | 8474.8 | 1025.1 | 11023.8 | 1025.1 | 8464.8 | 1025.1
19.75 | 9435.9 | 12124.4 | 10780.1 | 7548.7 | 11794.9 | 9699.5 | 15155.5 | 9563 | 8535.3 | 900.6 | 11223.8 | 900.6 | 8662.4 | 900.6
20 | 8857.1 | 11683.8 | 10270.4 | 7085.7 | 11071.4 | 9347 | 14604.7 | 9045.4 | 8634.6 | 222.5 | 11461.3 | 222.5 | 8899.4 | 146
20.25 | 9396 | 12358.6 | 10877.3 | 7516.8 | 11745 | 9886.9 | 15448.2 | 9793.3 | 8579.8 | 816.2 | 11542.4 | 816.2 | 8977.1 | 816.2
20.5 | 9213.9 | 12309.8 | 10761.8 | 7371.1 | 11517.4 | 9847.8 | 15387.3 | 9736.9 | 8590.2 | 623.7 | 11686.2 | 623.7 | 9113.3 | 623.7
20.75 | 9434.6 | 12662.1 | 11048.4 | 7547.7 | 11793.3 | 10129.7 | 15827.6 | 10087.4 | 8605.1 | 829.6 | 11832.5 | 829.6 | 9257.8 | 829.6
21 | 9278.4 | 12635.3 | 10956.8 | 7422.7 | 11598 | 10108.2 | 15794.1 | 10056.9 | 8666.5 | 611.9 | 12023.4 | 611.9 | 9445 | 611.9
21.25 | 9263.4 | 12748 | 11005.7 | 7410.7 | 11579.3 | 10198.4 | 15934.9 | 10166 | 8650.2 | 613.2 | 12134.7 | 613.2 | 9552.8 | 613.2
21.5 | 9502.3 | 13112.6 | 11307.4 | 7601.8 | 11877.8 | 10490 | 16390.7 | 10528.4 | 8657.3 | 845 | 12267.6 | 845 | 9683.4 | 845
21.75 | 9306.1 | 13040.2 | 11173.1 | 7444.9 | 11632.6 | 10432.2 | 16300.3 | 10451.5 | 8669.3 | 636.8 | 12403.4 | 636.8 | 9814.7 | 636.8
22 | 8920.7 | 12777.1 | 10848.9 | 7136.6 | 11150.9 | 10221.7 | 15971.4 | 10117.9 | 8709.4 | 211.2 | 12565.9 | 211.2 | 9975.9 | 142
22.25 | 8924.2 | 12900.7 | 10912.4 | 7139.3 | 11155.2 | 10320.6 | 16125.9 | 10209 | 8646 | 278.2 | 12622.5 | 278.2 | 10030 | 178.9
22.5 | 9333.7 | 13428.2 | 11381 | 7467 | 11667.2 | 10742.6 | 16785.3 | 10833.1 | 8672.1 | 661.7 | 12766.5 | 661.7 | 10171.4 | 661.7
22.75 | 9374.1 | 13585.2 | 11479.6 | 7499.3 | 11717.6 | 10868.1 | 16981.5 | 10706.3 | 8744 | 630.1 | 12955.1 | 630.1 | 10351.3 | 355
23 | 9747.7 | 14074.8 | 11911.2 | 7798.2 | 12184.6 | 11259.8 | 17593.5 | 11459.5 | 8876.9 | 870.8 | 13204 | 870.8 | 10588.7 | 870.8
23.25 | 9751 | 14194 | 11972.5 | 7800.8 | 12188.8 | 11355.2 | 17742.6 | 11578.7 | 8978.2 | 772.8 | 13421.3 | 772.8 | 10805.9 | 772.8
23.5 | 9725.2 | 14282.8 | 12004 | 7780.1 | 12156.5 | 11426.3 | 17853.5 | 11663.6 | 8958 | 767.1 | 13515.7 | 767.1 | 10896.5 | 767.1
23.75 | 9197.7 | 13868.1 | 11532.9 | 7358.2 | 11497.1 | 11094.5 | 17335.2 | 11163 | 8948.1 | 249.6 | 13618.6 | 249.6 | 10997.7 | 165.2
24 | 9698.4 | 14479.7 | 12089.1 | 7758.7 | 12123 | 11583.8 | 18099.6 | 11855.2 | 8883.8 | 814.6 | 13665.1 | 814.6 | 11040.6 | 814.6
24.25 | 9233.8 | 14124.5 | 11679.1 | 7387.1 | 11542.3 | 11299.6 | 17655.6 | 11396.9 | 8942.1 | 291.7 | 13832.8 | 291.7 | 11208.1 | 188.8
24.5 | 9236.5 | 14235.2 | 11735.8 | 7389.2 | 11545.6 | 11388.2 | 17794 | 11507.3 | 8950.6 | 285.9 | 13949.3 | 285.9 | 11321.3 | 186
24.75 | 9540 | 14645.4 | 12092.7 | 7632 | 11925 | 11716.3 | 18306.7 | 12016.8 | 8961.8 | 578.2 | 14067.2 | 578.2 | 11438.6 | 578.2
25 | 9125.5 | 14336 | 11730.7 | 7300.4 | 11406.8 | 11468.8 | 17920 | 11634.2 | 8903.9 | 221.6 | 14114.4 | 221.6 | 11483.3 | 150.9
25.25 | 9036.2 | 14349.9 | 11693 | 7229 | 11295.2 | 11479.9 | 17937.3 | 11651.6 | 8828.2 | 208 | 14141.9 | 208 | 11508.1 | 143.4
25.5 | 9012.7 | 14427.7 | 11720.2 | 7210.2 | 11265.9 | 11542.2 | 18034.6 | 11706.1 | 8758.6 | 254.1 | 14173.6 | 254.1 | 11536.3 | 169.7
25.75 | 8883.4 | 14397.8 | 11640.6 | 7106.7 | 11104.2 | 11518.3 | 17997.3 | 11698.7 | 8687.5 | 195.9 | 14202 | 195.9 | 11561.8 | 136.8
26 | 8839.8 | 14451.9 | 11645.9 | 7071.9 | 11049.8 | 11561.5 | 18064.9 | 11739.9 | 8618.1 | 221.7 | 14230.2 | 221.7 | 11588 | 152
26.25 | 8766.9 | 14474.9 | 11620.9 | 7013.5 | 10958.6 | 11580 | 18093.7 | 11762.7 | 8550.6 | 216.3 | 14258.6 | 216.3 | 11613.6 | 149.1
26.5 | 8687.1 | 14489.4 | 11588.2 | 6949.7 | 10858.9 | 11591.5 | 18111.7 | 11781.3 | 8486 | 201.1 | 14288.3 | 201.1 | 11640.7 | 140.5
26.75 | 8641.5 | 14536.4 | 11588.9 | 6913.2 | 10801.9 | 11629.1 | 18170.4 | 11817.9 | 8420.7 | 220.8 | 14315.5 | 220.8 | 11665.7 | 152.2
27 | 8515.3 | 14501.2 | 11508.3 | 6812.3 | 10644.2 | 11600.9 | 18126.5 | 11083.3 | 8362.4 | 153 | 14348.2 | 153 | 7265.7 | 3817.7
27.25 | 8551.2 | 14626.6 | 11588.9 | 6840.9 | 10689 | 11701.2 | 18283.2 | 11897.8 | 8321.1 | 230.1 | 14396.5 | 230.1 | 11739.8 | 157.9
27.5 | 8484.7 | 14648.2 | 11566.4 | 6787.8 | 10605.9 | 11718.5 | 18310.2 | 11920.9 | 8265.1 | 219.6 | 14428.6 | 219.6 | 11768.7 | 152.2
27.75 | 8464.7 | 14714.8 | 11589.7 | 6771.8 | 10580.9 | 11771.8 | 18393.4 | 11969 | 8210.3 | 254.5 | 14460.3 | 254.5 | 11796.7 | 172.3
28 | 8418.3 | 14753.5 | 11585.9 | 6734.6 | 10522.9 | 11802.8 | 18441.9 | 12002.3 | 8160.9 | 257.4 | 14496.1 | 257.4 | 11828 | 174.2
28.25 | 8349.8 | 14768.9 | 11559.4 | 6679.8 | 10437.3 | 11815.1 | 18461.1 | 12030.6 | 8128.6 | 221.2 | 14547.7 | 221.2 | 11876.9 | 153.8
28.5 | 8329.2 | 14830.9 | 11580 | 6663.3 | 10411.4 | 11864.7 | 18538.6 | 12079.1 | 8084.4 | 244.8 | 14586.1 | 244.8 | 11911.5 | 167.6
28.75 | 8307.6 | 14890.7 | 11599.1 | 6646 | 10384.4 | 11912.5 | 18613.3 | 12127.7 | 8044.7 | 262.9 | 14627.8 | 262.9 | 11949.6 | 178.1
29 | 8284.5 | 14947.8 | 11616.2 | 6627.6 | 10355.7 | 11958.2 | 18684.7 | 12171.6 | 8001.8 | 282.8 | 14665 | 282.8 | 11982 | 189.5
29.25 | 8261.4 | 15003.7 | 11632.5 | 6609.2 | 10326.8 | 12002.9 | 18754.6 | 12213.9 | 7962.8 | 298.6 | 14705 | 298.6 | 12015.2 | 198.6
29.5 | 11142.9 | 17963.3 | 14553.1 | 8914.3 | 13928.6 | 14370.6 | 22454.1 | 15250.1 | 8104.7 | 3038.2 | 14925.2 | 3038.2 | 12211.9 | 3038.2
29.75 | 10406.9 | 17314.9 | 13860.9 | 8325.5 | 13008.6 | 13851.9 | 21643.7 | 14601.7 | 9090.8 | 1316.1 | 15998.8 | 1316.1 | 13285.6 | 1316.1
30 | 10514.2 | 17516.5 | 14015.4 | 8411.4 | 13142.8 | 14013.2 | 21895.7 | 14803.3 | 9436.2 | 1078 | 16438.5 | 1078 | 13725.3 | 1078
30.25 | 10406.5 | 17504.3 | 13955.4 | 8325.2 | 13008.1 | 14003.5 | 21880.4 | 14790.7 | 9572.6 | 833.9 | 16670.4 | 833.9 | 13956.8 | 833.9
30.5 | 9897.7 | 17090.5 | 13494.1 | 7918.2 | 12372.2 | 13672.4 | 21363.1 | 14253.6 | 9556.8 | 340.9 | 16749.6 | 340.9 | 14030.3 | 223.3
30.75 | 9883.2 | 17169.9 | 13526.5 | 7906.6 | 12354 | 13735.9 | 21462.3 | 14340.9 | 9565.5 | 317.7 | 16852.2 | 317.7 | 14130 | 210.9
31 | 9917.9 | 17297.6 | 13607.8 | 7934.3 | 12397.4 | 13838.1 | 21622.1 | 14463.9 | 9598 | 319.9 | 16977.8 | 319.9 | 14251.5 | 212.4
31.25 | 10503.3 | 17975.2 | 14239.3 | 8402.6 | 13129.1 | 14380.2 | 22469 | 15246 | 9608.8 | 894.5 | 17080.7 | 894.5 | 14351.5 | 894.5
31.5 | 10002.8 | 17566.4 | 13784.6 | 8002.2 | 12503.5 | 14053.1 | 21958 | 14720 | 9665.7 | 337.1 | 17229.3 | 337.1 | 14497.5 | 222.4
31.75 | 9988.1 | 17642.6 | 13815.4 | 7990.5 | 12485.1 | 14114.1 | 22053.3 | 14774.2 | 9621.1 | 367 | 17275.6 | 367 | 14535.1 | 239.1
32 | 9967.5 | 17711.7 | 13839.6 | 7974 | 12459.3 | 14169.4 | 22139.6 | 14825.4 | 9579.1 | 388.4 | 17323.4 | 388.4 | 14574.5 | 251
32.25 | 9847.8 | 17680.7 | 13764.2 | 7878.2 | 12309.7 | 14144.6 | 22100.9 | 14826.2 | 9546 | 301.7 | 17379 | 301.7 | 14622.6 | 203.6
32.5 | 9878.7 | 17799.3 | 13839 | 7903 | 12348.4 | 14239.5 | 22249.2 | 14910.3 | 9516.4 | 362.4 | 17437 | 362.4 | 14672.8 | 237.5
32.75 | 12023.4 | 20031.2 | 16027.3 | 9618.8 | 15029.3 | 16025 | 25039 | 17252.3 | 9658.9 | 2364.5 | 17666.7 | 2364.5 | 14887.8 | 2364.5
33 | 11929.2 | 20027.2 | 15978.2 | 9543.3 | 14911.4 | 16021.8 | 25034.1 | 16326.4 | 10118 | 1811.2 | 18216.1 | 1811.2 | 15416.3 | 910.1
33.25 | 10813 | 19005.5 | 14909.2 | 8650.4 | 13516.3 | 15204.4 | 23756.9 | 16115.4 | 10534.8 | 278.2 | 18727.3 | 278.2 | 15924.2 | 191.3
33.5 | 11541.3 | 19829.2 | 15685.3 | 9233 | 14426.6 | 15863.4 | 24786.6 | 17024.9 | 10650.6 | 890.7 | 18938.6 | 890.7 | 16134.2 | 890.7
33.75 | 11019.2 | 19402.7 | 15211 | 8815.4 | 13774 | 15522.1 | 24253.4 | 16483.3 | 10683 | 336.2 | 19066.4 | 336.2 | 16258.7 | 224.5
34 | 11228.4 | 19706.4 | 15467.4 | 8982.7 | 14035.5 | 15765.1 | 24633 | 16659.2 | 10643.7 | 584.7 | 19121.7 | 584.7 | 16302.7 | 356.5
34.25 | 11944 | 20517 | 16230.5 | 9555.2 | 14930 | 16413.6 | 25646.2 | 17644.2 | 10898.6 | 1045.5 | 19471.5 | 1045.5 | 16598.8 | 1045.5
34.5 | 12915.9 | 21586 | 17251 | 10332.7 | 16144.9 | 17268.8 | 26982.5 | 18699.5 | 11101.1 | 1814.8 | 19771.2 | 1814.8 | 16884.7 | 1814.8
34.75 | 12647.3 | 21416.6 | 17032 | 10117.8 | 15809.1 | 17133.3 | 26770.8 | 18528.1 | 11420.4 | 1226.9 | 20189.7 | 1226.9 | 17301.2 | 1226.9
35 | 12770.3 | 21641 | 17205.6 | 10216.2 | 15962.9 | 17312.8 | 27051.2 | 18752.5 | 11742.5 | 1027.8 | 20613.2 | 1027.8 | 17724.7 | 1027.8
35.25 | 17154.5 | 26128.1 | 21641.3 | 13723.6 | 21443.1 | 20902.5 | 32660.2 | 23192.4 | 11929 | 5225.5 | 20902.7 | 5225.5 | 17966.9 | 5225.5
35.5 | 17507.4 | 26590.2 | 22048.8 | 14005.9 | 21884.2 | 21272.2 | 33237.7 | 20765.1 | 12586.8 | 4920.6 | 21669.6 | 4920.6 | 18645.6 | 2119.4
35.75 | 17959.9 | 27161.6 | 22560.7 | 14367.9 | 22449.9 | 21729.3 | 33952 | 21003.8 | 12862.6 | 5097.3 | 22064.3 | 5097.3 | 18818.2 | 2185.7
36 | 22056.9 | 31386.3 | 26721.6 | 17645.5 | 27571.1 | 25109.1 | 39232.9 | 22478 | 13369 | 8687.9 | 22698.4 | 8687.9 | 19064.7 | 3413.3
36.25 | 15855.9 | 25327.1 | 20591.5 | 12684.8 | 19819.9 | 20261.7 | 31658.9 | 21515.1 | 14243.2 | 1612.8 | 23714.3 | 1612.8 | 19902.4 | 1612.8
36.5 | 17094.7 | 26720.1 | 21907.4 | 13675.7 | 21368.4 | 21376.1 | 33400.1 | 22908.1 | 14999.7 | 2095 | 24625.1 | 2095 | 20813.1 | 2095
36.75 | 19652.8 | 29435.4 | 24544.1 | 15722.2 | 24566 | 23548.3 | 36794.3 | 23222 | 15415.2 | 4237.6 | 25197.9 | 4237.6 | 21338.7 | 1883.3
37 | 20332.1 | 30279.2 | 25305.6 | 16265.6 | 25415.1 | 24223.3 | 37848.9 | 23565.3 | 15692.7 | 4639.3 | 25639.8 | 4639.3 | 21531.7 | 2033.7
37.25 | 17714.3 | 27831.6 | 22772.9 | 14171.4 | 22142.8 | 22265.3 | 34789.6 | 23634.5 | 16295.6 | 1418.6 | 26413 | 1418.6 | 22215.9 | 1418.6
37.5 | 18151.4 | 28443.9 | 23297.6 | 14521.1 | 22689.2 | 22755.1 | 35554.9 | 24220.6 | 16563.8 | 1587.6 | 26856.2 | 1587.6 | 22632.9 | 1587.6
37.75 | 18340.7 | 28810.8 | 23575.8 | 14672.6 | 22925.9 | 23048.6 | 36013.5 | 24580.9 | 16935.3 | 1405.5 | 27405.3 | 1405.5 | 23175.4 | 1405.5
38 | 18440 | 29088.4 | 23764.2 | 14752 | 23050 | 23270.7 | 36360.4 | 24858.5 | 17165.5 | 1274.5 | 27813.9 | 1274.5 | 23584.1 | 1274.5
38.25 | 18605.4 | 29431.3 | 24018.4 | 14884.3 | 23256.8 | 23545.1 | 36789.2 | 25192.9 | 17185 | 1420.4 | 28010.9 | 1420.4 | 23772.5 | 1420.4
38.5 | 18496.9 | 29499.8 | 23998.3 | 14797.5 | 23121.1 | 23599.8 | 36874.7 | 25261.3 | 17332.4 | 1164.5 | 28335.3 | 1164.5 | 24096.9 | 1164.5
38.75 | 17818 | 28996.6 | 23407.3 | 14254.4 | 22272.5 | 23197.3 | 36245.8 | 24567.7 | 17310.2 | 507.8 | 28488.8 | 507.8 | 24243.3 | 324.4
39 | 18755.7 | 30108.2 | 24432 | 15004.6 | 23444.7 | 24086.6 | 37635.3 | 25853.3 | 17320.2 | 1435.6 | 28672.6 | 1435.6 | 24417.7 | 1435.6
39.25 | 18683.2 | 30208.8 | 24446 | 14946.5 | 23354 | 24167.1 | 37761.1 | 25953.9 | 17429.1 | 1254.1 | 28954.7 | 1254.1 | 24699.9 | 1254.1
39.5 | 18704.2 | 30402.1 | 24553.1 | 14963.3 | 23380.2 | 24321.6 | 38002.6 | 26142.6 | 17463.2 | 1241 | 29161.1 | 1241 | 24901.6 | 1241
39.75 | 21449.5 | 33318.3 | 27383.9 | 17159.6 | 26811.9 | 26654.7 | 41647.9 | 26881.6 | 17492 | 3957.5 | 29360.8 | 3957.5 | 25078.6 | 1803
40 | 24655.8 | 36703.9 | 30679.8 | 19724.6 | 30819.7 | 29363.1 | 45879.9 | 32329.8 | 19120.7 | 5535 | 31168.9 | 5535 | 26794.8 | 5535
40.25 | 28493.2 | 40757.1 | 34625.2 | 22794.6 | 35616.5 | 32605.7 | 50946.4 | 31069 | 20062.6 | 8430.7 | 32326.4 | 8430.7 | 27674.5 | 3394.5
40.5 | 27048.7 | 39545.9 | 33297.3 | 21639 | 33810.9 | 31636.7 | 49432.3 | 30662.5 | 20806.3 | 6242.4 | 33303.5 | 6242.4 | 28016.6 | 2645.9
40.75 | 30036.4 | 42783.9 | 36410.2 | 24029.1 | 37545.5 | 34227.1 | 53479.9 | 31805.6 | 21203.3 | 8833.1 | 33950.8 | 8833.1 | 28267.8 | 3537.8
41 | 30709.3 | 43744.5 | 37226.9 | 24567.4 | 38386.6 | 34995.6 | 54680.6 | 38008.4 | 24649.3 | 6060 | 37684.5 | 6060 | 31948.4 | 6060
41.25 | 33461.8 | 46864.9 | 40163.4 | 26769.5 | 41827.3 | 37491.9 | 58581.1 | 41128.8 | 28022.3 | 5439.5 | 41425.4 | 5439.5 | 35689.3 | 5439.5
41.5 | 36243.1 | 50065.8 | 43154.5 | 28994.5 | 45303.9 | 40052.7 | 62582.3 | 44329.8 | 30905 | 5338.2 | 44727.7 | 5338.2 | 38991.6 | 5338.2
41.75 | 40040.5 | 54318.6 | 47179.6 | 32032.4 | 50050.7 | 43454.9 | 67898.3 | 48582.6 | 33193.7 | 6846.8 | 47471.8 | 6846.8 | 41735.7 | 6846.8
42 | 41766.4 | 56548.1 | 49157.3 | 33413.2 | 52208.1 | 45238.5 | 70685.1 | 50812 | 36802.6 | 4963.9 | 51584.2 | 4963.9 | 45848.2 | 4963.9
42.25 | 43341.2 | 58681.7 | 51011.4 | 34672.9 | 54176.4 | 46945.3 | 73352.1 | 52945.6 | 39373.4 | 3967.7 | 54713.9 | 3967.7 | 48977.8 | 3967.7
42.5 | 44932.3 | 60855.9 | 52894.1 | 35945.9 | 56165.4 | 48684.7 | 76069.9 | 55119.8 | 40988.6 | 3943.8 | 56912.1 | 3943.8 | 51176.1 | 3943.8
42.75 | 45420.4 | 61943.5 | 53682 | 36336.3 | 56775.4 | 49554.8 | 77429.4 | 56207.5 | 42319.5 | 3100.8 | 58842.7 | 3100.8 | 53106.7 | 3100.8
43 | 48042.6 | 65182.2 | 56612.4 | 38434.1 | 60053.2 | 52145.8 | 81477.8 | 59446.2 | 43883.9 | 4158.7 | 61023.5 | 4158.7 | 55287.4 | 4158.7
43.25 | 50615.3 | 68390.9 | 59503.1 | 40492.2 | 63269.1 | 54712.7 | 85488.7 | 62654.9 | 45720.2 | 4895.1 | 63495.9 | 4895.1 | 57759.8 | 4895.1
43.5 | 50200.6 | 68636.5 | 59418.5 | 40160.5 | 62750.7 | 54909.2 | 85795.7 | 62873.7 | 47060.1 | 3140.4 | 65496.1 | 3140.4 | 59733.3 | 3140.4
43.75 | 52353.1 | 71463.5 | 61908.3 | 41882.5 | 65441.4 | 57170.8 | 89329.4 | 65700.7 | 48418 | 3935.2 | 67528.4 | 3935.2 | 61765.6 | 3935.2
44 | 53844.4 | 73651.5 | 63747.9 | 43075.5 | 67305.5 | 58921.2 | 92064.3 | 67888.7 | 50121.5 | 3722.9 | 69928.6 | 3722.9 | 64165.8 | 3722.9
44.25 | 53936.6 | 74454.5 | 64195.5 | 43149.3 | 67420.8 | 59563.6 | 93068.1 | 68691.7 | 51199.6 | 2737 | 71717.5 | 2737 | 65954.7 | 2737
44.5 | 54211.5 | 75445.5 | 64828.5 | 43369.2 | 67764.3 | 60356.4 | 94306.9 | 69682.7 | 51811.4 | 2400 | 73045.5 | 2400 | 67282.7 | 2400
44.75 | 53835 | 75785 | 64810 | 43068 | 67293.7 | 60628 | 94731.3 | 70022.2 | 52226.3 | 1608.7 | 74176.3 | 1608.7 | 68413.5 | 1608.7
45 | 54161 | 76823.5 | 65492.2 | 43328.8 | 67701.3 | 61458.8 | 96029.3 | 71060.7 | 52282.8 | 1878.2 | 74945.3 | 1878.2 | 69182.5 | 1878.2
45.25 | 54257.8 | 77627.9 | 65942.8 | 43406.2 | 67822.2 | 62102.3 | 97034.9 | 71865.1 | 52444.3 | 1813.5 | 75814.4 | 1813.5 | 70051.6 | 1813.5
45.5 | 54561.9 | 78636 | 66599 | 43649.5 | 68202.4 | 62908.8 | 98295 | 72873.2 | 52700 | 1861.9 | 76774.1 | 1861.9 | 71011.3 | 1861.9
45.75 | 54987 | 79761.9 | 67374.4 | 43989.6 | 68733.8 | 63809.5 | 99702.3 | 73999 | 52944.3 | 2042.7 | 77719.1 | 2042.7 | 71956.3 | 2042.7
46 | 57525.9 | 83000.4 | 70263.2 | 46020.7 | 71907.3 | 66400.4 | 103750.6 | 77237.6 | 53435.9 | 4089.9 | 78910.5 | 4089.9 | 73147.7 | 4089.9
46.25 | 59493.6 | 85681.4 | 72587.5 | 47594.9 | 74367 | 68545.1 | 107101.7 | 79918.6 | 55278.1 | 4215.5 | 81465.8 | 4215.5 | 75703 | 4215.5
46.5 | 65411.7 | 92347.3 | 78879.5 | 52329.4 | 81764.7 | 73877.8 | 115434.1 | 86584.5 | 58257.8 | 7153.9 | 85193.4 | 7153.9 | 79430.6 | 7153.9
46.75 | 70757 | 98512.6 | 84634.8 | 56605.6 | 88446.2 | 78810 | 123140.7 | 92749.8 | 62111.6 | 8645.4 | 89867.2 | 8645.4 | 84104.4 | 8645.4
47 | 72703.9 | 101375.5 | 87039.7 | 58163.1 | 90879.8 | 81100.4 | 126719.4 | 95612.7 | 67510.1 | 5193.8 | 96181.7 | 5193.8 | 90418.9 | 5193.8
47.25 | 77188.6 | 106849.1 | 92018.8 | 61750.9 | 96485.7 | 85479.3 | 133561.4 | 101086.3 | 70546.5 | 6642 | 100207.1 | 6642 | 94444.3 | 6642
47.5 | 78689.9 | 109397.9 | 94043.9 | 62952 | 98362.4 | 87518.3 | 136747.4 | 103635.1 | 73855.5 | 4834.4 | 104563.5 | 4834.4 | 98800.7 | 4834.4
47.75 | 81734 | 113525.3 | 97629.6 | 65387.2 | 102167.5 | 90820.2 | 141906.6 | 107762.5 | 75853 | 5881 | 107644.2 | 5881 | 101881.4 | 5881
48 | 85673.4 | 118584.4 | 102128.9 | 68538.7 | 107091.7 | 94867.5 | 148230.4 | 112821.6 | 78789.2 | 6884.2 | 111700.2 | 6884.2 | 105937.4 | 6884.2
48.25 | 89144.9 | 123235.2 | 106190 | 71315.9 | 111431.1 | 98588.1 | 154044 | 117472.4 | 82404.9 | 6740 | 116495.1 | 6740 | 110732.3 | 6740
48.5 | 93017.8 | 128360.7 | 110689.3 | 74414.2 | 116272.3 | 102688.6 | 160450.9 | 122597.9 | 86603.9 | 6413.9 | 121946.8 | 6413.9 | 116184 | 6413.9
48.75 | 97260.4 | 133921.1 | 115590.7 | 77808.3 | 121575.5 | 107136.9 | 167401.3 | 128158.3 | 89563 | 7697.4 | 126223.6 | 7697.4 | 120460.8 | 7697.4
49 | 132183.8 | 170242.5 | 151213.1 | 105747 | 165229.7 | 136194 | 212803.1 | 164372.6 | 94033.7 | 38150 | 132092.4 | 38150 | 126222.6 | 38150

## SRD WTG-17
Depth (m) | SRD AH-FF (kN) | SRD AH-NFF (kN) | SRD MEAN (kN) | SRD AH-FF-LB (kN) | SRD AH-FF-UB (kN) | SRD AH-NFF-LB (kN) | SRD AH-NFF-UB (kN) | Static Cap (kN) | Shaft AH-FF (kN) | Tip AH-FF (kN) | Shaft AH-NFF (kN) | Tip AH-NFF (kN) | Shaft SC (kN) | Tip SC (kN)
0.5 | 78.6 | 78.7 | 78.6 | 62.9 | 98.2 | 63 | 98.4 | 34.9 | 5.3 | 73.3 | 5.4 | 73.3 | 3.6 | 31.2
0.75 | 75.7 | 76 | 75.8 | 60.5 | 94.6 | 60.8 | 95 | 37.1 | 8.1 | 67.6 | 8.4 | 67.6 | 5.9 | 31.2
1 | 76.3 | 76.9 | 76.6 | 61 | 95.4 | 61.5 | 96.1 | 40.9 | 12.5 | 63.8 | 13.1 | 63.8 | 9.7 | 31.2
1.25 | 76.5 | 77.3 | 76.9 | 61.2 | 95.6 | 61.8 | 96.6 | 43.6 | 15.4 | 61 | 16.3 | 61 | 12.4 | 31.2
1.5 | 697.9 | 699.1 | 698.5 | 558.3 | 872.3 | 559.3 | 873.9 | 257.5 | 29.2 | 668.7 | 30.4 | 668.7 | 20.8 | 236.7
1.75 | 3257.7 | 3260.9 | 3259.3 | 2606.2 | 4072.1 | 2608.7 | 4076.2 | 936.1 | 98 | 3159.8 | 101.2 | 3159.8 | 47.6 | 888.5
2 | 4142.5 | 4153.6 | 4148 | 3314 | 5178.1 | 3322.9 | 5192 | 1182.9 | 225.1 | 3917.4 | 236.2 | 3917.4 | 92.8 | 1090
2.25 | 3739.4 | 3766.1 | 3752.8 | 2991.6 | 4674.3 | 3012.9 | 4707.7 | 1127.6 | 352 | 3387.4 | 378.7 | 3387.4 | 140.1 | 987.5
2.5 | 2291.6 | 2340.3 | 2316 | 1833.3 | 2864.5 | 1872.2 | 2925.4 | 2019.4 | 470.9 | 1820.7 | 519.6 | 1820.7 | 198.7 | 1820.7
2.75 | 3472.3 | 3547.8 | 3510 | 2777.8 | 4340.4 | 2838.2 | 4434.7 | 1153.4 | 579.2 | 2893.1 | 654.7 | 2893.1 | 255.9 | 897.6
3 | 4526.9 | 4634.4 | 4580.7 | 3621.5 | 5658.7 | 3707.6 | 5793.1 | 1461.5 | 710.4 | 3816.5 | 818 | 3816.5 | 312.9 | 1148.6
3.25 | 2768.7 | 2913.7 | 2841.2 | 2214.9 | 3460.8 | 2331 | 3642.2 | 1088.8 | 867.7 | 1901 | 1012.7 | 1901 | 437.2 | 651.7
3.5 | 4992.5 | 5180.1 | 5086.3 | 3994 | 6240.7 | 4144.1 | 6475.2 | 1736.4 | 973.6 | 4018.9 | 1161.2 | 4018.9 | 504.5 | 1231.9
3.75 | 3294.9 | 3528.9 | 3411.9 | 2635.9 | 4118.6 | 2823.1 | 4411.1 | 2806.4 | 1137.2 | 2157.7 | 1371.2 | 2157.7 | 648.8 | 2157.7
4 | 2286.6 | 2571.2 | 2428.9 | 1829.2 | 2858.2 | 2056.9 | 3214 | 1168.9 | 1239.8 | 1046.8 | 1524.4 | 1046.8 | 758.3 | 410.6
4.25 | 3129.8 | 3465.1 | 3297.4 | 2503.9 | 3912.3 | 2772 | 4331.3 | 1464.5 | 1284.2 | 1845.6 | 1619.5 | 1845.6 | 799.1 | 665.4
4.5 | 2222.2 | 2608.5 | 2415.4 | 1777.8 | 2777.8 | 2086.8 | 3260.6 | 1753.6 | 1369.5 | 852.7 | 1755.8 | 852.7 | 900.9 | 852.7
4.75 | 1969.2 | 2407.2 | 2188.2 | 1575.4 | 2461.5 | 1925.8 | 3009 | 1258 | 1444 | 525.2 | 1882 | 525.2 | 1020.3 | 237.7
5 | 1843.8 | 2332 | 2087.9 | 1475 | 2304.7 | 1865.6 | 2915 | 1258.1 | 1455.8 | 388 | 1944 | 388 | 1072 | 186.1
5.25 | 1941.8 | 2478.5 | 2210.2 | 1553.4 | 2427.3 | 1982.8 | 3098.2 | 1342.3 | 1466 | 475.8 | 2002.7 | 475.8 | 1120.1 | 222.3
5.5 | 1938.9 | 2523.2 | 2231 | 1551.1 | 2423.6 | 2018.6 | 3154 | 1418 | 1523.8 | 415.1 | 2108.1 | 415.1 | 1218.2 | 199.8
5.75 | 2205.3 | 2836.5 | 2520.9 | 1764.3 | 2756.7 | 2269.2 | 3545.7 | 1596.6 | 1576.5 | 628.8 | 2207.8 | 628.8 | 1312.2 | 284.4
6 | 2001.5 | 2678.6 | 2340 | 1601.2 | 2501.8 | 2142.9 | 3348.3 | 1588.9 | 1627.3 | 374.1 | 2304.5 | 374.1 | 1403.1 | 185.8
6.25 | 2313 | 3035 | 2674 | 1850.4 | 2891.2 | 2428 | 3793.7 | 2125.8 | 1661.7 | 651.3 | 2383.7 | 651.3 | 1474.5 | 651.3
6.5 | 1988 | 2754 | 2371 | 1590.4 | 2485 | 2203.2 | 3442.4 | 1676.9 | 1657.6 | 330.4 | 2423.6 | 330.4 | 1507.3 | 169.6
6.75 | 2590.6 | 3398.9 | 2994.8 | 2072.5 | 3238.3 | 2719.2 | 4248.7 | 2472.3 | 1652.9 | 937.7 | 2461.2 | 937.7 | 1534.6 | 937.7
7 | 2155.4 | 3006 | 2580.7 | 1724.3 | 2694.3 | 2404.8 | 3757.5 | 1884 | 1766.1 | 389.3 | 2616.7 | 389.3 | 1687.3 | 196.8
7.25 | 2158.2 | 3050.6 | 2604.4 | 1726.6 | 2697.8 | 2440.5 | 3813.3 | 1944.8 | 1803.7 | 354.5 | 2696.1 | 354.5 | 1761.8 | 183
7.5 | 2163.2 | 3096.3 | 2629.8 | 1730.6 | 2704 | 2477 | 3870.4 | 1973.7 | 1792.7 | 370.5 | 2725.8 | 370.5 | 1782.8 | 190.9
7.75 | 2358.5 | 3331.2 | 2844.8 | 1886.8 | 2948.1 | 2664.9 | 4164 | 2092.3 | 1806.3 | 552.2 | 2779 | 552.2 | 1824.7 | 267.6
8 | 2234.7 | 3247 | 2740.8 | 1787.7 | 2793.3 | 2597.6 | 4058.8 | 2135.7 | 1908.9 | 325.7 | 2921.3 | 325.7 | 1962.5 | 173.2
8.25 | 2352.6 | 3404.1 | 2878.3 | 1882.1 | 2940.7 | 2723.2 | 4255.1 | 2217.8 | 1907.2 | 445.4 | 2958.6 | 445.4 | 1991.9 | 225.9
8.5 | 2266 | 3355.6 | 2810.8 | 1812.8 | 2832.5 | 2684.5 | 4194.5 | 2217.9 | 1920.2 | 345.8 | 3009.8 | 345.8 | 2034 | 183.9
8.75 | 2899.6 | 4026.5 | 3463 | 2319.7 | 3624.5 | 3221.2 | 5033.1 | 3042.3 | 1930.6 | 969 | 3057.5 | 969 | 2073.3 | 969
9 | 2512.1 | 3676.3 | 3094.2 | 2009.7 | 3140.2 | 2941.1 | 4595.4 | 2440.2 | 2014.7 | 497.4 | 3178.9 | 497.4 | 2189.1 | 251.2
9.25 | 2695.1 | 3896.1 | 3295.6 | 2156.1 | 3368.9 | 3116.9 | 4870.1 | 2548 | 2026.1 | 668.9 | 3227.2 | 668.9 | 2225 | 323
9.5 | 2596.8 | 3834.7 | 3215.8 | 2077.5 | 3246.1 | 3067.8 | 4793.4 | 2601.3 | 2135.1 | 461.8 | 3372.9 | 461.8 | 2363.1 | 238.2
9.75 | 4130.4 | 5405.3 | 4767.8 | 3304.3 | 5163 | 4324.2 | 6756.6 | 3217 | 2183.5 | 1946.9 | 3458.4 | 1946.9 | 2423.5 | 793.5
10 | 3466 | 4779.1 | 4122.5 | 2772.8 | 4332.5 | 3823.3 | 5973.8 | 3724.3 | 2364.9 | 1101.1 | 3678 | 1101.1 | 2623.2 | 1101.1
10.25 | 2844 | 4196.1 | 3520 | 2275.2 | 3555 | 3356.9 | 5245.1 | 2908.3 | 2376.3 | 467.7 | 3728.4 | 467.7 | 2664.5 | 243.7
10.5 | 2951.9 | 4342.7 | 3647.3 | 2361.6 | 3689.9 | 3474.2 | 5428.4 | 3040.2 | 2471.1 | 480.8 | 3861.9 | 480.8 | 2789.8 | 250.4
10.75 | 3865.1 | 5295.6 | 4580.3 | 3092.1 | 4831.4 | 4236.4 | 6619.4 | 4214.1 | 2642 | 1223.1 | 4072.5 | 1223.1 | 2991 | 1223.1
11 | 3479.2 | 4951.3 | 4215.2 | 2783.3 | 4349 | 3961 | 6189.1 | 3856.7 | 2746.9 | 732.3 | 4219 | 732.3 | 3124.5 | 732.3
11.25 | 3167.5 | 4681.4 | 3924.5 | 2534 | 3959.4 | 3745.2 | 5851.8 | 3407.5 | 2789.1 | 378.4 | 4303.1 | 378.4 | 3200.2 | 207.4
11.5 | 3657.6 | 5213.3 | 4435.4 | 2926.1 | 4572 | 4170.6 | 6516.6 | 4103.4 | 2863.8 | 793.8 | 4419.5 | 793.8 | 3309.6 | 793.8
11.75 | 3149.5 | 4746.9 | 3948.2 | 2519.6 | 3936.8 | 3797.5 | 5933.6 | 3529.1 | 2896.6 | 252.9 | 4493.9 | 252.9 | 3379.8 | 149.3
12 | 3161.6 | 4800 | 3980.8 | 2529.3 | 3952 | 3840 | 6000 | 3564.2 | 2885.2 | 276.5 | 4523.6 | 276.5 | 3402.9 | 161.3
12.25 | 3711.9 | 5390.6 | 4551.2 | 2969.5 | 4639.9 | 4312.5 | 6738.2 | 3833.8 | 2882.8 | 829.1 | 4561.5 | 829.1 | 3429.6 | 404.3
12.5 | 3283.2 | 5002.7 | 4143 | 2626.6 | 4104.1 | 4002.2 | 6253.4 | 3763.8 | 3031.9 | 251.4 | 4751.4 | 251.4 | 3613.7 | 150
12.75 | 3287.7 | 5048 | 4167.9 | 2630.1 | 4109.6 | 4038.4 | 6310 | 3799.5 | 3027.8 | 259.8 | 4788.2 | 259.8 | 3644.8 | 154.7
13 | 3303.6 | 5104.2 | 4203.9 | 2642.9 | 4129.5 | 4083.4 | 6380.2 | 3836.6 | 3016.9 | 286.7 | 4817.5 | 286.7 | 3668.1 | 168.5
13.25 | 3241.7 | 5081.9 | 4161.8 | 2593.4 | 4052.2 | 4065.5 | 6352.4 | 3834.1 | 3005.5 | 236.2 | 4845.7 | 236.2 | 3690.3 | 143.8
13.5 | 36030 | 37914.9 | 36972.4 | 28824 | 45037.5 | 30331.9 | 47393.6 | 12581.9 | 3348 | 32681.9 | 5232.9 | 32681.9 | 3804.4 | 8777.5
13.75 | 17545.7 | 19488 | 18516.9 | 14036.5 | 21932.1 | 15590.4 | 24360.1 | 8212.9 | 3290.6 | 14255.1 | 5232.9 | 14255.1 | 3804.4 | 4408.5
14 | 4878.6 | 7128.1 | 6003.4 | 3902.9 | 6098.3 | 5702.5 | 8910.1 | 4284.1 | 4829.1 | 49.6 | 7078.5 | 49.6 | 4244.6 | 39.5
14.25 | 43090 | 45505.7 | 44297.9 | 34472 | 53862.5 | 36404.6 | 56882.2 | 14398.7 | 5008.7 | 38081.2 | 7424.5 | 38081.2 | 4339.8 | 10058.9
14.5 | 28976.7 | 31554.6 | 30265.6 | 23181.4 | 36220.9 | 25243.6 | 39443.2 | 11238.9 | 4846.6 | 24130.1 | 7424.5 | 24130.1 | 4339.8 | 6899.1
14.75 | 16223.3 | 18952.4 | 17587.9 | 12978.7 | 20279.2 | 15161.9 | 23690.5 | 8079.2 | 4695.5 | 11527.9 | 7424.5 | 11527.9 | 4339.8 | 3739.4
15 | 8845.1 | 12557.2 | 10701.2 | 7076.1 | 11056.4 | 10045.8 | 15696.6 | 5747.8 | 7618.8 | 1226.3 | 11331 | 1226.3 | 5168.2 | 579.6

## SRD WTG-18
Depth (m) | SRD AH-FF (kN) | SRD AH-NFF (kN) | SRD MEAN (kN) | SRD AH-FF-LB (kN) | SRD AH-FF-UB (kN) | SRD AH-NFF-LB (kN) | SRD AH-NFF-UB (kN) | Static Cap (kN) | Shaft AH-FF (kN) | Tip AH-FF (kN) | Shaft AH-NFF (kN) | Tip AH-NFF (kN) | Shaft SC (kN) | Tip SC (kN)
0.5 | 134.1 | 135 | 134.5 | 107.3 | 167.6 | 108 | 168.7 | 135 | 33.6 | 100.5 | 34.5 | 100.5 | 34.5 | 100.5
0.75 | 150.3 | 152.2 | 151.2 | 120.2 | 187.8 | 121.8 | 190.2 | 152.2 | 49.8 | 100.5 | 51.7 | 100.5 | 51.7 | 100.5
1 | 174.7 | 178.1 | 176.4 | 139.8 | 218.4 | 142.4 | 222.6 | 178.1 | 74.3 | 100.5 | 77.6 | 100.5 | 77.6 | 100.5
1.25 | 190.3 | 195.3 | 192.8 | 152.3 | 237.9 | 156.2 | 244.1 | 195.3 | 89.9 | 100.5 | 94.8 | 100.5 | 94.8 | 100.5
1.5 | 155.8 | 162.6 | 159.2 | 124.6 | 194.7 | 130.1 | 203.2 | 142.1 | 110.3 | 45.5 | 117 | 45.5 | 117 | 25.1
1.75 | 162.5 | 171.2 | 166.8 | 130 | 203.1 | 136.9 | 214 | 148.4 | 111.7 | 50.7 | 120.4 | 50.7 | 120.2 | 28.2
2 | 306.5 | 317.2 | 311.9 | 245.2 | 383.2 | 253.7 | 396.5 | 316.7 | 132.3 | 174.2 | 142.9 | 174.2 | 142.4 | 174.2
2.25 | 372.8 | 385.9 | 379.4 | 298.3 | 466 | 308.7 | 482.4 | 385.4 | 180.7 | 192.1 | 193.8 | 192.1 | 193.3 | 192.1
2.5 | 428 | 444.2 | 436.1 | 342.4 | 535 | 355.3 | 555.2 | 443.7 | 234.3 | 193.7 | 250.5 | 193.7 | 250 | 193.7
2.75 | 482.8 | 502.7 | 492.7 | 386.2 | 603.5 | 402.2 | 628.4 | 502.2 | 282.3 | 200.5 | 302.2 | 200.5 | 301.7 | 200.5
3 | 547 | 571.2 | 559.1 | 437.6 | 683.8 | 457 | 714.1 | 570.8 | 341.5 | 205.5 | 365.8 | 205.5 | 365.3 | 205.5
3.25 | 594.8 | 624 | 609.4 | 475.8 | 743.5 | 499.2 | 780 | 623.5 | 390.9 | 203.9 | 420.1 | 203.9 | 419.6 | 203.9
3.5 | 650.3 | 685 | 667.6 | 520.2 | 812.9 | 548 | 856.2 | 684.5 | 441.7 | 208.6 | 476.3 | 208.6 | 475.8 | 208.6
3.75 | 698 | 738.6 | 718.3 | 558.4 | 872.5 | 590.9 | 923.3 | 738.2 | 484.6 | 213.4 | 525.3 | 213.4 | 524.8 | 213.4
4 | 763.5 | 810.5 | 787 | 610.8 | 954.4 | 648.4 | 1013.2 | 810 | 534.1 | 229.5 | 581.1 | 229.5 | 580.6 | 229.5
4.25 | 824 | 877.9 | 851 | 659.2 | 1030 | 702.3 | 1097.4 | 877.4 | 587.3 | 236.7 | 641.2 | 236.7 | 640.7 | 236.7
4.5 | 876.9 | 938.2 | 907.5 | 701.5 | 1096.1 | 750.5 | 1172.7 | 937.7 | 641.6 | 235.3 | 702.8 | 235.3 | 702.4 | 235.3
4.75 | 901.7 | 970.8 | 936.3 | 721.4 | 1127.1 | 776.7 | 1213.5 | 970.3 | 686.9 | 214.7 | 756.1 | 214.7 | 755.6 | 214.7
5 | 993 | 1070.4 | 1031.7 | 794.4 | 1241.3 | 856.3 | 1338 | 1069.9 | 740.9 | 252.1 | 818.3 | 252.1 | 817.8 | 252.1
5.25 | 1042.6 | 1128.7 | 1085.6 | 834.1 | 1303.2 | 903 | 1410.9 | 1128.2 | 792.3 | 250.3 | 878.4 | 250.3 | 877.9 | 250.3
5.5 | 1103.7 | 1199 | 1151.3 | 883 | 1379.6 | 959.2 | 1498.7 | 1198.5 | 848 | 255.7 | 943.3 | 255.7 | 942.8 | 255.7
5.75 | 1162.4 | 1267.4 | 1214.9 | 930 | 1453.1 | 1013.9 | 1584.2 | 1266.9 | 896.3 | 266.1 | 1001.3 | 266.1 | 1000.8 | 266.1
6 | 1239.7 | 1354.6 | 1297.1 | 991.7 | 1549.6 | 1083.7 | 1693.3 | 1353.9 | 942.3 | 297.3 | 1057.3 | 297.3 | 1056.6 | 297.3
6.25 | 1267.5 | 1392.9 | 1330.2 | 1014 | 1584.4 | 1114.3 | 1741.1 | 1392.2 | 999.2 | 268.4 | 1124.5 | 268.4 | 1123.8 | 268.4
6.5 | 1326.2 | 1462.4 | 1394.3 | 1061 | 1657.8 | 1169.9 | 1828 | 1461.7 | 1050.6 | 275.6 | 1186.8 | 275.6 | 1186.1 | 275.6
6.75 | 1381.1 | 1528.5 | 1454.8 | 1104.9 | 1726.4 | 1222.8 | 1910.7 | 1527.7 | 1091.5 | 289.6 | 1238.9 | 289.6 | 1238 | 289.6
7 | 1462 | 1620.8 | 1541.4 | 1169.6 | 1827.5 | 1296.7 | 2026 | 1619 | 1123.9 | 338.1 | 1282.8 | 338.1 | 1280.9 | 338.1
7.25 | 1455.8 | 1626.4 | 1541.1 | 1164.6 | 1819.8 | 1301.1 | 2033 | 1624 | 1170.5 | 285.4 | 1341.1 | 285.4 | 1338.6 | 285.4
7.5 | 1516.2 | 1698.9 | 1607.5 | 1212.9 | 1895.2 | 1359.1 | 2123.6 | 1696.3 | 1224.7 | 291.5 | 1407.4 | 291.5 | 1404.9 | 291.5
7.75 | 1584 | 1779.2 | 1681.6 | 1267.2 | 1980 | 1423.4 | 2224 | 1776.7 | 1279.4 | 304.6 | 1474.7 | 304.6 | 1472.1 | 304.6
8 | 1667.2 | 1875.3 | 1771.3 | 1333.7 | 2084 | 1500.3 | 2344.2 | 1872.8 | 1340.4 | 326.8 | 1548.6 | 326.8 | 1546 | 326.8
8.25 | 1711.4 | 1933 | 1822.2 | 1369.2 | 2139.3 | 1546.4 | 2416.3 | 1930.5 | 1400.1 | 311.4 | 1621.6 | 311.4 | 1619.1 | 311.4
8.5 | 1763.9 | 1999.3 | 1881.6 | 1411.2 | 2204.9 | 1599.5 | 2499.2 | 1996.7 | 1453.5 | 310.5 | 1688.9 | 310.5 | 1686.2 | 310.5
8.75 | 1588.6 | 1837.9 | 1713.3 | 1270.9 | 1985.7 | 1470.3 | 2297.4 | 1785.2 | 1458.6 | 130 | 1707.9 | 130 | 1704.2 | 81
9 | 1821.2 | 2084.6 | 1952.9 | 1457 | 2276.6 | 1667.7 | 2605.7 | 2080.3 | 1499 | 322.2 | 1762.4 | 322.2 | 1758.1 | 322.2
9.25 | 2007.2 | 2284.9 | 2146.1 | 1605.8 | 2509 | 1828 | 2856.2 | 2279.4 | 1542.2 | 465 | 1819.9 | 465 | 1814.4 | 465
9.5 | 1950.7 | 2243.3 | 2097 | 1560.6 | 2438.4 | 1794.7 | 2804.2 | 2237.6 | 1622.6 | 328.1 | 1915.2 | 328.1 | 1909.5 | 328.1
9.75 | 2006 | 2313.9 | 2160 | 1604.8 | 2507.5 | 1851.1 | 2892.4 | 2308.2 | 1679.7 | 326.3 | 1987.6 | 326.3 | 1981.9 | 326.3
10 | 2090.2 | 2413.9 | 2252.1 | 1672.2 | 2612.8 | 1931.1 | 3017.4 | 2408.1 | 1742.2 | 348 | 2065.9 | 348 | 2060.1 | 348
10.25 | 2146 | 2485.8 | 2315.9 | 1716.8 | 2682.5 | 1988.6 | 3107.2 | 2480 | 1804.3 | 341.7 | 2144.1 | 341.7 | 2138.3 | 341.7
10.5 | 2216 | 2572.2 | 2394.1 | 1772.8 | 2770 | 2057.8 | 3215.3 | 2565 | 1846.7 | 369.3 | 2202.9 | 369.3 | 2195.7 | 369.3
10.75 | 2252.9 | 2625.9 | 2439.4 | 1802.3 | 2816.1 | 2100.7 | 3282.4 | 2618.7 | 1905.7 | 347.1 | 2278.8 | 347.1 | 2271.6 | 347.1
11 | 2341.3 | 2731.6 | 2536.5 | 1873.1 | 2926.7 | 2185.3 | 3414.5 | 2724.4 | 1982.9 | 358.4 | 2373.2 | 358.4 | 2366 | 358.4
11.25 | 2394.8 | 2802.8 | 2598.8 | 1915.8 | 2993.5 | 2242.3 | 3503.6 | 2795.6 | 2047.7 | 347.1 | 2455.7 | 347.1 | 2448.5 | 347.1
11.5 | 2502 | 2928.2 | 2715.1 | 2001.6 | 3127.6 | 2342.6 | 3660.3 | 2921 | 2110.6 | 391.5 | 2536.7 | 391.5 | 2529.5 | 391.5
11.75 | 2322.2 | 2766.9 | 2544.5 | 1857.8 | 2902.7 | 2213.5 | 3458.6 | 2704.6 | 2170.1 | 152.1 | 2614.8 | 152.1 | 2607.6 | 97
12 | 2672.7 | 3136.1 | 2904.4 | 2138.2 | 3340.9 | 2508.9 | 3920.2 | 3126 | 2185.7 | 487 | 2649.1 | 487 | 2639 | 487
12.25 | 2391.5 | 2873.9 | 2632.7 | 1913.2 | 2989.4 | 2299.2 | 3592.4 | 2807.3 | 2235.8 | 155.7 | 2718.2 | 155.7 | 2707.7 | 99.6
12.5 | 2754.6 | 3256.3 | 3005.4 | 2203.7 | 3443.2 | 2605 | 4070.3 | 3243.9 | 2298.9 | 455.7 | 2800.5 | 455.7 | 2788.2 | 455.7
12.75 | 2576.8 | 3098.2 | 2837.5 | 2061.4 | 3221 | 2478.6 | 3872.8 | 3002.2 | 2363.6 | 213.2 | 2885.1 | 213.2 | 2872 | 130.3
13 | 3032.4 | 3574 | 3303.2 | 2425.9 | 3790.5 | 2859.2 | 4467.5 | 3559 | 2430.9 | 601.5 | 2972.5 | 601.5 | 2957.5 | 601.5
13.25 | 3104.8 | 3667.5 | 3386.2 | 2483.9 | 3881 | 2934 | 4584.4 | 3652.5 | 2544.1 | 560.7 | 3106.8 | 560.7 | 3091.8 | 560.7
13.5 | 3178.1 | 3762.7 | 3470.4 | 2542.5 | 3972.6 | 3010.2 | 4703.4 | 3747.7 | 2646.3 | 531.8 | 3230.9 | 531.8 | 3215.9 | 531.8
13.75 | 3307.4 | 3914.6 | 3611 | 2645.9 | 4134.2 | 3131.7 | 4893.2 | 3898.6 | 2731.5 | 575.9 | 3338.7 | 575.9 | 3322.7 | 575.9
14 | 3564.4 | 4194.9 | 3879.7 | 2851.6 | 4455.5 | 3356 | 5243.7 | 4176.4 | 2834.9 | 729.6 | 3465.4 | 729.6 | 3446.8 | 729.6
14.25 | 3476.4 | 4131.3 | 3803.9 | 2781.1 | 4345.5 | 3305.1 | 5164.2 | 4112.7 | 2951.4 | 525 | 3606.3 | 525 | 3587.8 | 525
14.5 | 3590.5 | 4270.6 | 3930.5 | 2872.4 | 4488.1 | 3416.5 | 5338.2 | 4251.7 | 3038.4 | 552.1 | 3718.4 | 552.1 | 3699.5 | 552.1
14.75 | 3683.2 | 4388.9 | 4036.1 | 2946.6 | 4604 | 3511.1 | 5486.1 | 4368.1 | 3088.1 | 595.1 | 3793.8 | 595.1 | 3773 | 595.1
15 | 3841.2 | 4573.1 | 4207.1 | 3072.9 | 4801.5 | 3658.5 | 5716.4 | 4552.3 | 3198.1 | 643.1 | 3930 | 643.1 | 3909.2 | 643.1
15.25 | 3888.3 | 4647.4 | 4267.9 | 3110.7 | 4860.4 | 3717.9 | 5809.2 | 4626.6 | 3314.5 | 573.9 | 4073.5 | 573.9 | 4052.7 | 573.9
15.5 | 3592.9 | 4379.8 | 3986.3 | 2874.3 | 4491.1 | 3503.8 | 5474.7 | 4270.6 | 3364.1 | 228.8 | 4151 | 228.8 | 4127.9 | 142.8
15.75 | 3730.9 | 4545.8 | 4138.3 | 2984.7 | 4663.6 | 3636.6 | 5682.2 | 4397 | 3423.6 | 307.3 | 4238.5 | 307.3 | 4213.9 | 183.1
16 | 4103.9 | 4947.4 | 4525.6 | 3283.1 | 5129.8 | 3957.9 | 6184.2 | 4921.2 | 3530.4 | 573.4 | 4373.9 | 573.4 | 4347.7 | 573.4
16.25 | 4184.1 | 5057.1 | 4620.6 | 3347.3 | 5230.2 | 4045.7 | 6321.4 | 5030.9 | 3623.6 | 560.5 | 4496.6 | 560.5 | 4470.4 | 560.5
16.5 | 4297.6 | 5200.6 | 4749.1 | 3438.1 | 5372 | 4160.5 | 6500.7 | 5174.4 | 3720.1 | 577.5 | 4623.1 | 577.5 | 4596.9 | 577.5
16.75 | 4297.9 | 5231.3 | 4764.6 | 3438.3 | 5372.3 | 4185.1 | 6539.2 | 5203 | 3775.1 | 522.7 | 4708.6 | 522.7 | 4680.3 | 522.7
17 | 4406.8 | 5371.1 | 4888.9 | 3525.5 | 5508.5 | 4296.8 | 6713.8 | 5339.7 | 3804.9 | 601.9 | 4769.1 | 601.9 | 4737.8 | 601.9
17.25 | 4143.2 | 5138.5 | 4640.8 | 3314.5 | 5179 | 4110.8 | 6423.1 | 4989.9 | 3849.4 | 293.8 | 4844.7 | 293.8 | 4810.8 | 179.1
17.5 | 4189.7 | 5216.4 | 4703.1 | 3351.8 | 5237.1 | 4173.1 | 6520.5 | 5081.7 | 3928.6 | 261.1 | 4955.3 | 261.1 | 4919 | 162.7
17.75 | 4643.3 | 5702 | 5172.6 | 3714.6 | 5804.1 | 4561.6 | 7127.5 | 5665.5 | 4022.4 | 620.9 | 5081 | 620.9 | 5044.5 | 620.9
18 | 4812.1 | 5903.4 | 5357.8 | 3849.7 | 6015.1 | 4722.7 | 7379.3 | 5866.9 | 4128.7 | 683.4 | 5220 | 683.4 | 5183.5 | 683.4
18.25 | 4476.2 | 5601 | 5038.6 | 3581 | 5595.3 | 4480.8 | 7001.2 | 5470.5 | 4223.1 | 253.1 | 5347.9 | 253.1 | 5310.8 | 159.6
18.5 | 4970.6 | 6129.2 | 5549.9 | 3976.5 | 6213.3 | 4903.3 | 7661.4 | 6089.3 | 4276.8 | 693.8 | 5435.4 | 693.8 | 5395.5 | 693.8
18.75 | 5076.9 | 6269.6 | 5673.2 | 4061.5 | 6346.1 | 5015.7 | 7837 | 6226.4 | 4350.7 | 726.2 | 5543.5 | 726.2 | 5500.2 | 726.2
19 | 4786.1 | 6014.2 | 5400.1 | 3828.9 | 5982.6 | 4811.3 | 7517.7 | 5865.6 | 4506.1 | 280 | 5734.2 | 280 | 5690.7 | 174.8
19.25 | 4781.3 | 6045.1 | 5413.2 | 3825.1 | 5976.7 | 4836.1 | 7556.4 | 5891.4 | 4502.6 | 278.7 | 5766.4 | 278.7 | 5716.9 | 174.5
19.5 | 4785.9 | 6085.4 | 5435.6 | 3828.7 | 5982.4 | 4868.3 | 7606.7 | 5923.1 | 4502.9 | 283 | 5802.3 | 283 | 5745.9 | 177.2
19.75 | 4968.1 | 6303 | 5635.6 | 3974.5 | 6210.1 | 5042.4 | 7878.8 | 6048.5 | 4513.5 | 454.6 | 5848.5 | 454.6 | 5785 | 263.5
20 | 5974.3 | 7345.6 | 6660 | 4779.4 | 7467.9 | 5876.5 | 9182 | 7274.7 | 4709.8 | 1264.5 | 6081.1 | 1264.5 | 6010.2 | 1264.5
20.25 | 6395.6 | 7807 | 7101.3 | 5116.5 | 7994.5 | 6245.6 | 9758.7 | 7736 | 5141.5 | 1254.1 | 6552.9 | 1254.1 | 6481.9 | 1254.1
20.5 | 6948.5 | 8406.3 | 7677.4 | 5558.8 | 8685.6 | 6725 | 10507.9 | 8335.3 | 5717 | 1231.5 | 7174.8 | 1231.5 | 7103.9 | 1231.5
20.75 | 7188.3 | 8698.8 | 7943.5 | 5750.7 | 8985.4 | 6959 | 10873.5 | 8627.8 | 6241.8 | 946.6 | 7752.2 | 946.6 | 7681.2 | 946.6
21 | 7454.4 | 9022.9 | 8238.6 | 5963.5 | 9317.9 | 7218.3 | 11278.6 | 8951.9 | 6580.4 | 873.9 | 8149 | 873.9 | 8078 | 873.9
21.25 | 7934.4 | 9564.5 | 8749.5 | 6347.5 | 9918 | 7651.6 | 11955.7 | 9479 | 7105 | 829.3 | 8735.2 | 829.3 | 8649.6 | 829.3
21.5 | 8780 | 10479.3 | 9629.6 | 7024 | 10975 | 8383.4 | 13099.1 | 10393.7 | 7527.7 | 1252.3 | 9227 | 1252.3 | 9141.4 | 1252.3
21.75 | 8557.2 | 10327.5 | 9442.3 | 6845.7 | 10696.5 | 8262 | 12909.3 | 10237 | 7658.4 | 898.8 | 9428.7 | 898.8 | 9338.1 | 898.8
22 | 8602.2 | 10445.1 | 9523.6 | 6881.7 | 10752.7 | 8356.1 | 13056.3 | 10354.3 | 7861.3 | 740.9 | 9704.2 | 740.9 | 9613.4 | 740.9
22.25 | 9167 | 11083.3 | 10125.1 | 7333.6 | 11458.7 | 8866.6 | 13854.1 | 10986.9 | 7910.1 | 1256.8 | 9826.5 | 1256.8 | 9730 | 1256.8
22.5 | 9432.3 | 11423.7 | 10428 | 7545.9 | 11790.4 | 9139 | 14279.6 | 11327.3 | 8249.3 | 1183 | 10240.7 | 1183 | 10144.3 | 1183
22.75 | 14716.5 | 16786.1 | 15751.3 | 11773.2 | 18395.7 | 13428.8 | 20982.6 | 12823.4 | 8471.4 | 6245.1 | 10540.9 | 6245.1 | 10427.9 | 2395.4
23 | 16647.6 | 18812 | 17729.8 | 13318 | 20809.4 | 15049.6 | 23515 | 14236.7 | 9655.7 | 6991.9 | 11820.2 | 6991.9 | 11599.6 | 2637.2
23.25 | 19767 | 22047.7 | 20907.4 | 15813.6 | 24708.8 | 17638.2 | 27559.7 | 15264.1 | 10070.8 | 9696.2 | 12351.5 | 9696.2 | 11793.3 | 3470.8
23.5 | 12965.9 | 15379.3 | 14172.6 | 10372.7 | 16207.4 | 12303.4 | 19224.1 | 14551.1 | 10736.1 | 2229.9 | 13149.4 | 2229.9 | 12321.3 | 2229.9
23.75 | 24087.6 | 26646.1 | 25366.9 | 19270.1 | 30109.5 | 21316.9 | 33307.6 | 17356.9 | 11291.9 | 12795.7 | 13850.4 | 12795.7 | 12966.5 | 4390.4
24 | 35399.7 | 38126 | 36762.9 | 28319.8 | 44249.6 | 30500.8 | 47657.6 | 20517.9 | 12211.4 | 23188.2 | 14937.8 | 23188.2 | 13296.5 | 7221.4

## SRD WTG-19
Depth (m) | SRD AH-FF (kN) | SRD AH-NFF (kN) | SRD MEAN (kN) | SRD AH-FF-LB (kN) | SRD AH-FF-UB (kN) | SRD AH-NFF-LB (kN) | SRD AH-NFF-UB (kN) | Static Cap (kN) | Shaft AH-FF (kN) | Tip AH-FF (kN) | Shaft AH-NFF (kN) | Tip AH-NFF (kN) | Shaft SC (kN) | Tip SC (kN)
0.5 | 101 | 101.1 | 101.1 | 80.8 | 126.2 | 80.9 | 126.4 | 42.8 | 6.5 | 94.5 | 6.7 | 94.5 | 4.2 | 38.6
0.75 | 97 | 97.5 | 97.3 | 77.6 | 121.3 | 78 | 121.8 | 45.4 | 9.9 | 87.1 | 10.4 | 87.1 | 6.9 | 38.6
1 | 97.6 | 98.4 | 98 | 78.1 | 122 | 78.7 | 123 | 49.8 | 15.4 | 82.2 | 16.1 | 82.2 | 11.2 | 38.6
1.25 | 97.9 | 99 | 98.4 | 78.3 | 122.3 | 79.2 | 123.8 | 53 | 19 | 78.9 | 20.1 | 78.9 | 14.4 | 38.6
1.5 | 120.2 | 121.8 | 121 | 96.1 | 150.2 | 97.4 | 152.2 | 66 | 25.2 | 95 | 26.8 | 95 | 19.7 | 46.3
1.75 | 192 | 194.2 | 193.1 | 153.6 | 240 | 155.3 | 242.7 | 98.6 | 33 | 158.9 | 35.2 | 158.9 | 25.8 | 72.9
2 | 192.3 | 195.2 | 193.8 | 153.9 | 240.4 | 156.2 | 244 | 104 | 42.6 | 149.7 | 45.5 | 149.7 | 33.1 | 70.8
2.25 | 209.1 | 212.9 | 211 | 167.3 | 261.4 | 170.3 | 266.1 | 115.6 | 51.4 | 157.7 | 55.1 | 157.7 | 40.2 | 75.4
2.5 | 210.3 | 215 | 212.6 | 168.2 | 262.8 | 172 | 268.8 | 121.4 | 61.2 | 149.1 | 66 | 149.1 | 48.2 | 73.2
2.75 | 202.7 | 208.5 | 205.6 | 162.1 | 253.3 | 166.8 | 260.7 | 123.1 | 69.8 | 132.8 | 75.7 | 132.8 | 55.6 | 67.5
3 | 219.6 | 226.7 | 223.1 | 175.7 | 274.5 | 181.4 | 283.4 | 135.6 | 79.5 | 140.1 | 86.6 | 140.1 | 63.9 | 71.6
3.25 | 229 | 237.5 | 233.3 | 183.2 | 286.3 | 190 | 296.9 | 144.7 | 88.4 | 140.7 | 96.8 | 140.7 | 71.9 | 72.8
3.5 | 252.4 | 262.4 | 257.4 | 201.9 | 315.5 | 209.9 | 327.9 | 160.5 | 99.3 | 153.1 | 109.3 | 153.1 | 81.4 | 79.1
3.75 | 255.9 | 267.4 | 261.7 | 204.7 | 319.9 | 214 | 334.3 | 167.4 | 108.9 | 147 | 120.5 | 147 | 90.1 | 77.3
4 | 278.6 | 291.8 | 285.2 | 222.9 | 348.2 | 233.5 | 364.8 | 183.3 | 119.7 | 158.9 | 133 | 158.9 | 99.9 | 83.4
4.25 | 272.2 | 287.3 | 279.7 | 217.7 | 340.2 | 229.8 | 359.1 | 186.1 | 129.3 | 142.9 | 144.4 | 142.9 | 109 | 77.1
4.5 | 289.8 | 306.8 | 298.3 | 231.8 | 362.2 | 245.4 | 383.5 | 200 | 139.9 | 149.9 | 156.9 | 149.9 | 119 | 81
4.75 | 432.3 | 451.3 | 441.8 | 345.9 | 540.4 | 361.1 | 564.2 | 267.5 | 151.7 | 280.6 | 170.7 | 280.6 | 129.6 | 137.9
5 | 637.5 | 658.7 | 648.1 | 510 | 796.8 | 527 | 823.4 | 357.1 | 170.9 | 466.5 | 192.2 | 466.5 | 144.6 | 212.5
5.25 | 478.8 | 502.9 | 490.8 | 383 | 598.5 | 402.3 | 628.6 | 334.2 | 241.6 | 237.2 | 265.7 | 237.2 | 212.2 | 122
5.5 | 537.4 | 565.1 | 551.3 | 429.9 | 671.8 | 452.1 | 706.4 | 368 | 260.4 | 277 | 288.1 | 277 | 228 | 140
5.75 | 619.1 | 650.5 | 634.8 | 495.3 | 773.9 | 520.4 | 813.1 | 410.7 | 277.2 | 341.9 | 308.6 | 341.9 | 242.6 | 168.1
6 | 550.5 | 585.9 | 568.2 | 440.4 | 688.1 | 468.7 | 732.4 | 391.4 | 297 | 253.4 | 332.5 | 253.4 | 259.5 | 131.9
6.25 | 631.1 | 670.8 | 651 | 504.9 | 788.9 | 536.6 | 838.5 | 443.3 | 327.3 | 303.8 | 367 | 303.8 | 288.8 | 154.6
6.5 | 621.3 | 665.6 | 643.4 | 497 | 776.6 | 532.5 | 832 | 449.1 | 348.8 | 272.5 | 393.1 | 272.5 | 307 | 142.1
6.75 | 613.2 | 662.4 | 637.8 | 490.5 | 766.5 | 529.9 | 828 | 462.9 | 378.4 | 234.7 | 427.6 | 234.7 | 336.6 | 126.3
7 | 669.2 | 723.6 | 696.4 | 535.3 | 836.5 | 578.9 | 904.5 | 501.5 | 402.4 | 266.8 | 456.8 | 266.8 | 360.1 | 141.4
7.25 | 736.9 | 796.7 | 766.8 | 589.5 | 921.1 | 637.4 | 995.9 | 541 | 419.7 | 317.1 | 479.6 | 317.1 | 376.7 | 164.3
7.5 | 1143.6 | 1209.3 | 1176.4 | 914.9 | 1429.5 | 967.5 | 1511.7 | 1099.6 | 503.6 | 639.9 | 569.4 | 639.9 | 459.6 | 639.9
7.75 | 1356.4 | 1429.5 | 1392.9 | 1085.1 | 1695.5 | 1143.6 | 1786.8 | 1317.2 | 601.1 | 755.4 | 674.1 | 755.4 | 561.9 | 755.4
8 | 1361.3 | 1443 | 1402.2 | 1089.1 | 1701.7 | 1154.4 | 1803.8 | 1326.6 | 703.3 | 658 | 785 | 658 | 668.5 | 658
8.25 | 1533.2 | 1624.9 | 1579 | 1226.5 | 1916.4 | 1299.9 | 2031.1 | 1506.7 | 839.8 | 693.3 | 931.5 | 693.3 | 813.3 | 693.3
8.5 | 1774.4 | 1877.8 | 1826.1 | 1419.5 | 2218 | 1502.2 | 2347.2 | 1753.5 | 978.3 | 796.1 | 1081.7 | 796.1 | 957.5 | 796.1
8.75 | 1994.4 | 2111.4 | 2052.9 | 1595.6 | 2493.1 | 1689.1 | 2639.2 | 1981.9 | 1081.6 | 912.8 | 1198.5 | 912.8 | 1069.1 | 912.8
9 | 2238.4 | 2370.8 | 2304.6 | 1790.7 | 2798 | 1896.7 | 2963.5 | 2239.2 | 1314.7 | 923.7 | 1447.1 | 923.7 | 1315.5 | 923.7
9.25 | 2113.3 | 2264.3 | 2188.8 | 1690.7 | 2641.7 | 1811.4 | 2830.4 | 2128.9 | 1515.7 | 597.6 | 1666.7 | 597.6 | 1531.3 | 597.6
9.5 | 1823.5 | 1994.7 | 1909.1 | 1458.8 | 2279.3 | 1595.7 | 2493.4 | 1734.1 | 1553.6 | 269.8 | 1724.9 | 269.8 | 1583.7 | 150.5
9.75 | 2336.2 | 2527.7 | 2432 | 1869 | 2920.3 | 2022.1 | 3159.6 | 2379.8 | 1559.6 | 776.6 | 1751.1 | 776.6 | 1603.2 | 776.6
10 | 2059.8 | 2272.3 | 2166 | 1647.9 | 2574.8 | 1817.8 | 2840.3 | 1935.5 | 1665.4 | 394.4 | 1877.9 | 394.4 | 1727.2 | 208.3
10.25 | 2070.3 | 2304.4 | 2187.4 | 1656.2 | 2587.9 | 1843.5 | 2880.5 | 1991.4 | 1727.5 | 342.8 | 1961.6 | 342.8 | 1805.3 | 186.1
10.5 | 2167 | 2423.2 | 2295.1 | 1733.6 | 2708.7 | 1938.6 | 3029 | 2070.2 | 1763 | 404 | 2019.2 | 404 | 1855.9 | 214.3
10.75 | 2056.4 | 2334.9 | 2195.7 | 1645.2 | 2570.5 | 1867.9 | 2918.6 | 2039 | 1770.2 | 286.3 | 2048.6 | 286.3 | 1877.5 | 161.5
11 | 2092.7 | 2393.5 | 2243.1 | 1674.2 | 2615.9 | 1914.8 | 2991.9 | 2093.8 | 1809.5 | 283.2 | 2110.3 | 283.2 | 1933.2 | 160.7
11.25 | 2092 | 2415.3 | 2253.7 | 1673.6 | 2615 | 1932.3 | 3019.1 | 2112.6 | 1814.5 | 277.5 | 2137.8 | 277.5 | 1954 | 158.6
11.5 | 2482.2 | 2828 | 2655.1 | 1985.8 | 3102.8 | 2262.4 | 3535 | 2637.5 | 1864.9 | 617.3 | 2210.7 | 617.3 | 2020.2 | 617.3
11.75 | 2201.6 | 2570.4 | 2386 | 1761.3 | 2752 | 2056.3 | 3213 | 2241 | 1893.2 | 308.4 | 2262 | 308.4 | 2066.6 | 174.4
12 | 2162 | 2553.8 | 2357.9 | 1729.6 | 2702.5 | 2043.1 | 3192.3 | 2246.8 | 1908.1 | 254 | 2299.9 | 254 | 2097.9 | 148.9
12.25 | 2184 | 2598.8 | 2391.4 | 1747.2 | 2730 | 2079 | 3248.5 | 2277 | 1912.8 | 271.2 | 2327.6 | 271.2 | 2119.2 | 157.8
12.5 | 2211.3 | 2649 | 2430.2 | 1769.1 | 2764.2 | 2119.2 | 3311.2 | 2310.5 | 1919.7 | 291.6 | 2357.4 | 291.6 | 2142.3 | 168.2
12.75 | 2213.1 | 2673.6 | 2443.4 | 1770.5 | 2766.4 | 2138.9 | 3342 | 2331.1 | 1924.6 | 288.6 | 2385 | 288.6 | 2163.8 | 167.3
13 | 2194.1 | 2677.3 | 2435.7 | 1755.3 | 2742.6 | 2141.8 | 3346.6 | 2342.2 | 1932.5 | 261.5 | 2415.7 | 261.5 | 2187.6 | 154.7
13.25 | 2244.1 | 2750 | 2497.1 | 1795.3 | 2805.1 | 2200 | 3437.5 | 2393.9 | 1952.8 | 291.3 | 2458.7 | 291.3 | 2224.2 | 169.8
13.5 | 2236.3 | 2765 | 2500.7 | 1789 | 2795.4 | 2212 | 3456.3 | 2413.3 | 1966.3 | 270 | 2495 | 270 | 2253.4 | 159.9
13.75 | 2231.1 | 2782.5 | 2506.8 | 1784.9 | 2788.9 | 2226 | 3478.2 | 2430.6 | 1970.5 | 260.6 | 2521.9 | 260.6 | 2274.9 | 155.7
14 | 2287.2 | 2861.3 | 2574.3 | 1829.8 | 2859 | 2289 | 3576.6 | 2479.1 | 1981.7 | 305.6 | 2555.7 | 305.6 | 2300.7 | 178.3
14.25 | 2891.2 | 3488.1 | 3189.7 | 2313 | 3614 | 2790.5 | 4360.1 | 3223.4 | 2046.5 | 844.7 | 2643.3 | 844.7 | 2378.7 | 844.7
14.5 | 2377.1 | 2997.7 | 2687.4 | 1901.7 | 2971.4 | 2398.2 | 3747.1 | 2619.8 | 2106.5 | 270.7 | 2727.1 | 270.7 | 2457.6 | 162.1
14.75 | 2373.4 | 3017.7 | 2695.6 | 1898.7 | 2966.8 | 2414.2 | 3772.1 | 2638.6 | 2110.6 | 262.8 | 2754.9 | 262.8 | 2479.9 | 158.7
15 | 2396.9 | 3064.8 | 2730.8 | 1917.5 | 2996.1 | 2451.8 | 3831 | 2671.8 | 2118.1 | 278.7 | 2786.1 | 278.7 | 2504.7 | 167.1
15.25 | 2422.9 | 3114.4 | 2768.7 | 1938.3 | 3028.6 | 2491.5 | 3893 | 2705.7 | 2124.7 | 298.2 | 2816.2 | 298.2 | 2528.4 | 177.3
15.5 | 2431.6 | 3146.6 | 2789.1 | 1945.3 | 3039.5 | 2517.3 | 3933.3 | 2731.9 | 2135.5 | 296.1 | 2850.5 | 296.1 | 2555.1 | 176.7
15.75 | 2538.8 | 3277.3 | 2908 | 2031.1 | 3173.5 | 2621.8 | 4096.6 | 2805.2 | 2144.2 | 394.7 | 2882.6 | 394.7 | 2580 | 225.2
16 | 2635 | 3397.3 | 3016.2 | 2108 | 3293.8 | 2717.9 | 4246.7 | 2911.3 | 2226.9 | 408.1 | 2989.2 | 408.1 | 2679.1 | 232.2
16.25 | 2554.4 | 3340.9 | 2947.6 | 2043.5 | 3192.9 | 2672.7 | 4176.2 | 2904.8 | 2254.3 | 300 | 3040.9 | 300 | 2724.7 | 180.1
16.5 | 2577.6 | 3388.4 | 2983 | 2062.1 | 3222 | 2710.7 | 4235.5 | 2938.8 | 2263.6 | 314 | 3074.4 | 314 | 2751.2 | 187.6
16.75 | 2579.8 | 3414.8 | 2997.3 | 2063.9 | 3224.8 | 2731.8 | 4268.5 | 2961.8 | 2271.8 | 308 | 3106.8 | 308 | 2776.7 | 185
17 | 2596.4 | 3455.5 | 3025.9 | 2077.1 | 3245.4 | 2764.4 | 4319.4 | 3003.4 | 2302.9 | 293.5 | 3162 | 293.5 | 2825.2 | 178.2
17.25 | 2635.4 | 3518.7 | 3077.1 | 2108.3 | 3294.2 | 2815 | 4398.4 | 3045 | 2312.3 | 323.1 | 3195.7 | 323.1 | 2851.5 | 193.5
17.5 | 2692.7 | 3600.3 | 3146.5 | 2154.2 | 3365.9 | 2880.3 | 4500.4 | 3102.3 | 2337 | 355.8 | 3244.6 | 355.8 | 2892.1 | 210.2
17.75 | 4252.8 | 5185 | 4718.9 | 3402.2 | 5315.9 | 4148 | 6481.3 | 3775.5 | 2398.5 | 1854.2 | 3330.8 | 1854.2 | 2941.2 | 834.3
18 | 4081.6 | 5041.7 | 4561.6 | 3265.2 | 5101.9 | 4033.3 | 6302.1 | 4603.2 | 2819.3 | 1262.2 | 3779.4 | 1262.2 | 3341 | 1262.2
18.25 | 3748.1 | 4744 | 4246 | 2998.4 | 4685.1 | 3795.2 | 5930 | 4059.2 | 3196.4 | 551.7 | 4192.3 | 551.7 | 3753.9 | 305.3
18.5 | 4948.9 | 5984.3 | 5466.6 | 3959.1 | 6186.1 | 4787.4 | 7480.3 | 5518.9 | 3653.6 | 1295.3 | 4689 | 1295.3 | 4223.7 | 1295.3
18.75 | 8954.8 | 10036.7 | 9495.7 | 7163.8 | 11193.5 | 8029.3 | 12545.8 | 9554.6 | 4091.1 | 4863.6 | 5173 | 4863.6 | 4691 | 4863.6
19 | 9401 | 10554.6 | 9977.8 | 7520.8 | 11751.3 | 8443.7 | 13193.3 | 10066.2 | 6389.6 | 3011.5 | 7543.2 | 3011.5 | 7054.8 | 3011.5
19.25 | 9356.9 | 10619.3 | 9988.1 | 7485.5 | 11696.1 | 8495.4 | 13274.1 | 10130.9 | 8160 | 1196.8 | 9422.4 | 1196.8 | 8934 | 1196.8
19.5 | 11024.8 | 12413.1 | 11719 | 8819.8 | 13781 | 9930.5 | 15516.4 | 10520.8 | 8576.3 | 2448.6 | 9964.6 | 2448.6 | 9451.7 | 1069.1
19.75 | 10685.9 | 12213.5 | 11449.7 | 8548.7 | 13357.4 | 9770.8 | 15266.9 | 11696.4 | 9848.9 | 837 | 11376.5 | 837 | 10859.3 | 837
20 | 11044.6 | 12719 | 11881.8 | 8835.7 | 13805.8 | 10175.2 | 15898.8 | 12201.7 | 9953 | 1091.6 | 11627.4 | 1091.6 | 11110 | 1091.6
20.25 | 11197.7 | 13018.9 | 12108.3 | 8958.2 | 13997.2 | 10415.1 | 16273.6 | 12499.8 | 10059.3 | 1138.5 | 11880.4 | 1138.5 | 11361.4 | 1138.5
20.5 | 11419.2 | 13387.3 | 12403.2 | 9135.3 | 14274 | 10709.9 | 16734.2 | 12855.7 | 10204 | 1215.2 | 12172.2 | 1215.2 | 11640.5 | 1215.2
20.75 | 12454 | 14570 | 13512 | 9963.2 | 15567.5 | 11656 | 18212.5 | 14022.8 | 10309.4 | 2144.5 | 12425.5 | 2144.5 | 11878.3 | 2144.5
21 | 12044.5 | 14311.3 | 13177.9 | 9635.6 | 15055.6 | 11449 | 17889.1 | 13763.5 | 10697.6 | 1346.9 | 12964.4 | 1346.9 | 12416.6 | 1346.9
21.25 | 11658.1 | 14078.1 | 12868.1 | 9326.5 | 14572.7 | 11262.4 | 17597.6 | 13191.2 | 10919.5 | 738.6 | 13339.4 | 738.6 | 12791.6 | 399.6
21.5 | 11861.6 | 14435.3 | 13148.4 | 9489.3 | 14827 | 11548.2 | 18044.1 | 13491.5 | 11032 | 829.6 | 13605.7 | 829.6 | 13050.5 | 441
21.75 | 19665.1 | 22393.8 | 21029.5 | 15732.1 | 24581.4 | 17915.1 | 27992.3 | 21675.6 | 11161.4 | 8503.7 | 13890.1 | 8503.7 | 13171.9 | 8503.7
22 | 17686.8 | 20591.7 | 19139.3 | 14149.5 | 22108.5 | 16473.4 | 25739.6 | 16604.9 | 12375 | 5311.8 | 15279.9 | 5311.8 | 14523.4 | 2081.5
22.25 | 21172 | 24282.5 | 22727.2 | 16937.6 | 26465 | 19426 | 30353.1 | 23462.5 | 13544.7 | 7627.3 | 16655.2 | 7627.3 | 15835.2 | 7627.3
22.5 | 30001.4 | 33350.4 | 31675.9 | 24001.1 | 37501.7 | 26680.3 | 41688 | 21757.4 | 14317.8 | 15683.5 | 17666.9 | 15683.5 | 16604.3 | 5153.1
22.75 | 23740.2 | 27352.7 | 25546.4 | 18992.1 | 29675.2 | 21882.1 | 34190.8 | 20066.7 | 14987.8 | 8752.3 | 18600.3 | 8752.3 | 16890.1 | 3176.5
23 | 29210.7 | 33112.7 | 31161.7 | 23368.6 | 36513.4 | 26490.2 | 41390.9 | 21779.4 | 15547.6 | 13663.1 | 19449.6 | 13663.1 | 17165.1 | 4614.4
23.25 | 26298.7 | 30512.6 | 28405.7 | 21039 | 32873.4 | 24410.1 | 38140.7 | 21067.3 | 16024.9 | 10273.9 | 20238.7 | 10273.9 | 17420.8 | 3646.5
23.5 | 27094.3 | 31635.5 | 29364.9 | 21675.4 | 33867.8 | 25308.4 | 39544.4 | 21440.1 | 16429.3 | 10665 | 20970.6 | 10665 | 17670.3 | 3769.9
23.75 | 23936.4 | 28817.8 | 26377.1 | 19149.1 | 29920.4 | 23054.2 | 36022.2 | 20659.7 | 16747.8 | 7188.6 | 21629.2 | 7188.6 | 17940.4 | 2719.3
24 | 22600.5 | 27848.3 | 25224.4 | 18080.4 | 28250.6 | 22278.6 | 34810.3 | 21507.6 | 18202.5 | 4398 | 23450.3 | 4398 | 19698.6 | 1809.1
24.25 | 24361.5 | 29990.7 | 27176.1 | 19489.2 | 30451.9 | 23992.5 | 37488.4 | 22250.8 | 18271.8 | 6089.7 | 23901 | 6089.7 | 19873.2 | 2377.6
24.5 | 26637.1 | 32648.3 | 29642.7 | 21309.7 | 33296.3 | 26118.6 | 40810.4 | 23133.7 | 18386.6 | 8250.5 | 24397.8 | 8250.5 | 20065.2 | 3068.5
24.75 | 25248.6 | 31647 | 28447.8 | 20198.9 | 31560.8 | 25317.6 | 39558.8 | 22846.8 | 18624.9 | 6623.8 | 25023.2 | 6623.8 | 20286.1 | 2560.6
25 | 24141.1 | 30929 | 27535 | 19312.9 | 30176.4 | 24743.2 | 38661.2 | 22650.4 | 18638.9 | 5502.1 | 25426.8 | 5502.1 | 20452.4 | 2198.1
25.25 | 20985.5 | 28160.2 | 24572.9 | 16788.4 | 26231.9 | 22528.1 | 35200.2 | 21695.9 | 18611.5 | 2374.1 | 25786.1 | 2374.1 | 20602.7 | 1093.1
25.5 | 21427.7 | 28986.5 | 25207.1 | 17142.1 | 26784.6 | 23189.2 | 36233.1 | 23791 | 19019.5 | 2408.2 | 26578.3 | 2408.2 | 21382.9 | 2408.2
25.75 | 22152.5 | 30094.9 | 26123.7 | 17722 | 27690.6 | 24075.9 | 37618.7 | 24899.5 | 19349.7 | 2802.8 | 27292.1 | 2802.8 | 22096.6 | 2802.8
26 | 23817.5 | 32142.7 | 27980.1 | 19054 | 29771.8 | 25714.1 | 40178.3 | 26947.2 | 19785.4 | 4032 | 28110.6 | 4032 | 22915.2 | 4032
26.25 | 23625.8 | 32335.9 | 27980.9 | 18900.7 | 29532.3 | 25868.7 | 40419.8 | 27140.4 | 20265.7 | 3360.2 | 28975.7 | 3360.2 | 23780.2 | 3360.2
26.5 | 23294.2 | 32393.9 | 27844.1 | 18635.4 | 29117.8 | 25915.1 | 40492.3 | 27198.4 | 20933.6 | 2360.6 | 30033.2 | 2360.6 | 24837.8 | 2360.6
26.75 | 23845.8 | 33336.5 | 28591.2 | 19076.7 | 29807.3 | 26669.2 | 41670.7 | 26549.8 | 21063.3 | 2782.6 | 30554 | 2782.6 | 25289.8 | 1260
27 | 27496.5 | 37376.8 | 32436.6 | 21997.2 | 34370.6 | 29901.4 | 46721 | 32097.4 | 21589.4 | 5907 | 31469.7 | 5907 | 26190.4 | 5907
27.25 | 28578.8 | 38861.2 | 33720 | 22863.1 | 35723.6 | 31089 | 48576.5 | 33581.9 | 22631.1 | 5947.8 | 32913.4 | 5947.8 | 27634.1 | 5947.8
27.5 | 24333 | 35033.4 | 29683.2 | 19466.4 | 30416.2 | 28026.8 | 43791.8 | 29093.9 | 22984.8 | 1348.1 | 33685.3 | 1348.1 | 28401.8 | 692.1
27.75 | 25127.9 | 36240.7 | 30684.3 | 20102.3 | 31409.9 | 28992.6 | 45300.9 | 30941.4 | 22942.7 | 2185.3 | 34055.5 | 2185.3 | 28756.2 | 2185.3
28 | 24922 | 36442.2 | 30682.1 | 19937.6 | 31152.4 | 29153.8 | 45552.7 | 31142.9 | 23077.2 | 1844.7 | 34597.5 | 1844.7 | 29298.2 | 1844.7
28.25 | 24698.9 | 36620.6 | 30659.7 | 19759.1 | 30873.6 | 29296.5 | 45775.7 | 31255.2 | 23059.2 | 1639.7 | 34980.9 | 1639.7 | 29615.5 | 1639.7
28.5 | 24683.3 | 37001.9 | 30842.6 | 19746.6 | 30854.1 | 29601.5 | 46252.3 | 31615.4 | 23075.3 | 1608 | 35393.9 | 1608 | 30007.4 | 1608
28.75 | 25967.8 | 38677.9 | 32322.9 | 20774.3 | 32459.8 | 30942.3 | 48347.3 | 33273.1 | 23261 | 2706.9 | 35971 | 2706.9 | 30566.2 | 2706.9
29 | 26511.8 | 39618.1 | 33065 | 21209.4 | 33139.7 | 31694.5 | 49522.7 | 34213.3 | 24149.3 | 2362.5 | 37255.7 | 2362.5 | 31850.9 | 2362.5
29.25 | 26116.3 | 39624.5 | 32870.4 | 20893 | 32645.3 | 31699.6 | 49530.6 | 34219.7 | 24661.7 | 1454.6 | 38169.9 | 1454.6 | 32765.1 | 1454.6
29.5 | 30715.9 | 44625.5 | 37670.7 | 24572.7 | 38394.9 | 35700.4 | 55781.8 | 39196.2 | 25025.2 | 5690.7 | 38934.7 | 5690.7 | 33505.5 | 5690.7
29.75 | 30180.3 | 44509.4 | 37344.9 | 24144.3 | 37725.4 | 35607.5 | 55636.7 | 39080.1 | 26908.7 | 3271.7 | 41237.7 | 3271.7 | 35808.4 | 3271.7
30 | 32632.4 | 47412.1 | 40022.3 | 26105.9 | 40790.5 | 37929.7 | 59265.2 | 41982.9 | 28827.1 | 3805.3 | 43606.9 | 3805.3 | 38177.6 | 3805.3
30.25 | 34361.1 | 49619.2 | 41990.2 | 27488.9 | 42951.4 | 39695.4 | 62024 | 44189.9 | 30383.9 | 3977.3 | 45641.9 | 3977.3 | 40212.7 | 3977.3
30.5 | 33591.9 | 49345.5 | 41468.7 | 26873.6 | 41989.9 | 39476.4 | 61681.9 | 43900.9 | 30900 | 2691.9 | 46653.6 | 2691.9 | 41208.9 | 2691.9
30.75 | 38551.9 | 54805.7 | 46678.8 | 30841.5 | 48189.8 | 43844.6 | 68507.2 | 49361.1 | 31954.9 | 6597 | 48208.7 | 6597 | 42764.1 | 6597
31 | 37117.3 | 53892.2 | 45504.7 | 29693.8 | 46396.6 | 43113.8 | 67365.3 | 48447.5 | 33307.5 | 3809.8 | 50082.4 | 3809.8 | 44637.7 | 3809.8
31.25 | 40725.7 | 58047.9 | 49386.8 | 32580.6 | 50907.2 | 46438.3 | 72559.8 | 52603.2 | 35234.2 | 5491.6 | 52556.3 | 5491.6 | 47111.6 | 5491.6
31.5 | 41942.7 | 59851.1 | 50896.9 | 33554.2 | 52428.4 | 47880.9 | 74813.9 | 54406.4 | 37559.5 | 4383.2 | 55467.9 | 4383.2 | 50023.2 | 4383.2
31.75 | 39587.6 | 58116.6 | 48852.1 | 31670.1 | 49484.5 | 46493.3 | 72645.7 | 52672 | 39303.2 | 284.4 | 57832.1 | 284.4 | 52387.6 | 284.4
32 | 48324.3 | 67483.2 | 57903.8 | 38659.5 | 60405.4 | 53986.5 | 84354 | 61873.8 | 39422.6 | 8901.8 | 58581.4 | 8901.8 | 52972.1 | 8901.8
32.25 | 48303.3 | 68123.6 | 58213.5 | 38642.6 | 60379.1 | 54498.9 | 85154.5 | 62514.3 | 41959.8 | 6343.6 | 61780.1 | 6343.6 | 56170.7 | 6343.6
32.5 | 50564 | 71116.4 | 60840.2 | 40451.2 | 63205 | 56893.1 | 88895.4 | 65507 | 45969.4 | 4594.6 | 66521.8 | 4594.6 | 60912.4 | 4594.6
32.75 | 56620.1 | 77963.9 | 67292 | 45296.1 | 70775.1 | 62371.1 | 97454.9 | 72354.6 | 48141.5 | 8478.6 | 69485.3 | 8478.6 | 63876 | 8478.6
33 | 58681.1 | 80862.3 | 69771.7 | 46944.9 | 73351.4 | 64689.9 | 101077.9 | 75253 | 50899.5 | 7781.6 | 73080.7 | 7781.6 | 67471.4 | 7781.6
33.25 | 60417 | 83518.9 | 71968 | 48333.6 | 75521.3 | 66815.1 | 104398.6 | 77909.5 | 54433.7 | 5983.3 | 77535.6 | 5983.3 | 71926.2 | 5983.3
33.5 | 65729 | 89830.8 | 77779.9 | 52583.2 | 82161.3 | 71864.7 | 112288.5 | 84221.5 | 58515.4 | 7213.6 | 82617.2 | 7213.6 | 77007.8 | 7213.6
33.75 | 62210.4 | 87395.4 | 74802.9 | 49768.3 | 77763 | 69916.3 | 109244.3 | 81786.1 | 61453.3 | 757.2 | 86638.3 | 757.2 | 81029 | 757.2
34 | 66075.3 | 92360 | 79217.6 | 52860.2 | 82594.1 | 73888 | 115450 | 86719.2 | 61294.7 | 4780.6 | 87579.4 | 4780.6 | 81938.6 | 4780.6
34.25 | 68735.7 | 96133.1 | 82434.4 | 54988.6 | 85919.7 | 76906.5 | 120166.3 | 90492.3 | 63206.4 | 5529.4 | 90603.7 | 5529.4 | 84962.9 | 5529.4
34.5 | 74229.1 | 102787.8 | 88508.4 | 59383.3 | 92786.4 | 82230.2 | 128484.7 | 97147 | 66421.2 | 7807.9 | 94979.9 | 7807.9 | 89339.1 | 7807.9
34.75 | 70749.1 | 100521.2 | 85635.1 | 56599.3 | 88436.3 | 80417 | 125651.5 | 94880.4 | 68064.6 | 2684.5 | 97836.8 | 2684.5 | 92196 | 2684.5
35 | 76355.9 | 107349 | 91852.4 | 61084.7 | 95444.8 | 85879.2 | 134186.3 | 101708.2 | 69025 | 7330.9 | 100018.2 | 7330.9 | 94377.4 | 7330.9
35.25 | 77725.6 | 109975.6 | 93850.6 | 62180.5 | 97157 | 87980.5 | 137469.5 | 104334.8 | 71623.7 | 6101.9 | 103873.7 | 6101.9 | 98232.9 | 6101.9
35.5 | 83971.9 | 117554.1 | 100763 | 67177.5 | 104964.9 | 94043.2 | 146942.6 | 111913.3 | 75522.3 | 8449.6 | 109104.4 | 8449.6 | 103463.6 | 8449.6
35.75 | 88163.3 | 123174.8 | 105669 | 70530.6 | 110204.1 | 98539.8 | 153968.5 | 117534 | 79643.1 | 8520.2 | 114654.5 | 8520.2 | 109013.7 | 8520.2
36 | 87637.1 | 124152.8 | 105895 | 70109.7 | 109546.4 | 99322.3 | 155191 | 114313.3 | 80814.3 | 6822.8 | 117330 | 6822.8 | 111499.4 | 2813.9
36.25 | 83244.5 | 121260 | 102252.3 | 66595.6 | 104055.6 | 97008 | 151575 | 113278.8 | 79314.5 | 3930 | 117330 | 3930 | 111499.4 | 1779.4
36.5 | 79228.6 | 118710 | 98969.3 | 63382.9 | 99035.7 | 94968 | 148387.5 | 84373.6 | 77848.6 | 1380 | 117330 | 1380 | 59035.3 | 25338.3
36.75 | 97409.8 | 139462.5 | 118436.2 | 77927.9 | 121762.3 | 111570 | 174328.2 | 133590.9 | 88052.6 | 9357.3 | 130105.3 | 9357.3 | 124233.6 | 9357.3
37 | 96083.4 | 139913.9 | 117998.7 | 76866.7 | 120104.2 | 111931.1 | 174892.4 | 134042.3 | 90842.5 | 5240.9 | 134673.1 | 5240.9 | 128801.4 | 5240.9
37.25 | 96685.8 | 142319.7 | 119502.8 | 77348.7 | 120857.3 | 113855.8 | 177899.7 | 136448.1 | 91996.2 | 4689.6 | 137630.1 | 4689.6 | 131758.5 | 4689.6
37.5 | 97128.4 | 144566.2 | 120847.3 | 77702.7 | 121410.5 | 115652.9 | 180707.7 | 138694.5 | 92893.2 | 4235.2 | 140330.9 | 4235.2 | 134459.3 | 4235.2
37.75 | 98620.6 | 147856 | 123238.3 | 78896.5 | 123275.8 | 118284.8 | 184820 | 141976.2 | 93035.1 | 5585.5 | 142270.5 | 5585.5 | 136390.8 | 5585.5
38 | 107112.5 | 158157.3 | 132634.9 | 85690 | 133890.6 | 126525.8 | 197696.6 | 152277.5 | 95802.6 | 11309.9 | 146847.4 | 11309.9 | 140967.6 | 11309.9
38.25 | 98870.4 | 151762.7 | 125316.5 | 79096.3 | 123588 | 121410.2 | 189703.4 | 139439.1 | 94643 | 4227.4 | 147535.3 | 4227.4 | 74442.9 | 64996.2
38.5 | 94323 | 149020.5 | 121671.8 | 75458.4 | 117903.8 | 119216.4 | 186275.6 | 101652.9 | 92837.8 | 1485.2 | 147535.3 | 1485.2 | 74442.9 | 27209.9
38.75 | 101718.1 | 159031.1 | 130374.6 | 81374.5 | 127147.6 | 127224.8 | 198788.8 | 153151.3 | 101585.9 | 132.2 | 158898.9 | 132.2 | 153019.2 | 132.2
39 | 109190.9 | 168504.2 | 138847.5 | 87352.7 | 136488.6 | 134803.3 | 210630.2 | 156857.7 | 99996.2 | 9194.7 | 159309.4 | 9194.7 | 153195.3 | 3662.4
39.25 | 126443.6 | 187771.2 | 157107.4 | 101154.9 | 158054.5 | 150216.9 | 234714 | 165584.1 | 102150.7 | 24292.9 | 163478.3 | 24292.9 | 157345.2 | 8238.9

## SRD WTG-20
Depth (m) | SRD AH-FF (kN) | SRD AH-NFF (kN) | SRD MEAN (kN) | SRD AH-FF-LB (kN) | SRD AH-FF-UB (kN) | SRD AH-NFF-LB (kN) | SRD AH-NFF-UB (kN) | Static Cap (kN) | Shaft AH-FF (kN) | Tip AH-FF (kN) | Shaft AH-NFF (kN) | Tip AH-NFF (kN) | Shaft SC (kN) | Tip SC (kN)
0.5 | 153.1 | 155 | 154.1 | 122.5 | 191.4 | 124 | 193.7 | 155 | 75.7 | 77.4 | 77.6 | 77.4 | 77.6 | 77.4
0.75 | 189.5 | 193.8 | 191.6 | 151.6 | 236.9 | 155 | 242.2 | 193.8 | 112.1 | 77.4 | 116.4 | 77.4 | 116.4 | 77.4
1 | 244.6 | 252 | 248.3 | 195.7 | 305.7 | 201.6 | 314.9 | 252 | 167.2 | 77.4 | 174.6 | 77.4 | 174.6 | 77.4
1.25 | 279.7 | 290.7 | 285.2 | 223.7 | 349.6 | 232.6 | 363.4 | 290.7 | 202.3 | 77.4 | 213.4 | 77.4 | 213.4 | 77.4
1.5 | 350.8 | 366.1 | 358.4 | 280.6 | 438.5 | 292.9 | 457.6 | 366.1 | 261.2 | 89.6 | 276.5 | 89.6 | 276.5 | 89.6
1.75 | 605.6 | 626 | 615.8 | 484.5 | 757 | 500.8 | 782.5 | 626 | 327.1 | 278.6 | 347.4 | 278.6 | 347.4 | 278.6
2 | 785.2 | 812.3 | 798.7 | 628.1 | 981.5 | 649.9 | 1015.4 | 812.3 | 444.4 | 340.8 | 471.5 | 340.8 | 471.5 | 340.8
2.25 | 948.3 | 984.7 | 966.5 | 758.6 | 1185.4 | 787.8 | 1230.9 | 984.7 | 558.9 | 389.4 | 595.2 | 389.4 | 595.2 | 389.4
2.5 | 1043.4 | 1091.5 | 1067.5 | 834.7 | 1304.2 | 873.2 | 1364.4 | 1091.5 | 700.3 | 343.1 | 748.5 | 343.1 | 748.5 | 343.1
2.75 | 1643.5 | 1705.6 | 1674.5 | 1314.8 | 2054.4 | 1364.5 | 2132 | 1705 | 805.8 | 837.7 | 867.9 | 837.7 | 867.3 | 837.7
3 | 1501 | 1579.3 | 1540.1 | 1200.8 | 1876.2 | 1263.5 | 1974.2 | 1573.3 | 929.3 | 571.6 | 1007.7 | 571.6 | 1001.7 | 571.6
3.25 | 1477.9 | 1575.4 | 1526.6 | 1182.3 | 1847.4 | 1260.3 | 1969.2 | 1569.3 | 1071 | 406.9 | 1168.5 | 406.9 | 1162.5 | 406.9
3.5 | 1588.2 | 1706.6 | 1647.4 | 1270.5 | 1985.2 | 1365.3 | 2133.2 | 1700.5 | 1182.2 | 406 | 1300.6 | 406 | 1294.6 | 406
3.75 | 1567.1 | 1707.5 | 1637.3 | 1253.7 | 1958.9 | 1366 | 2134.4 | 1695.8 | 1282.4 | 284.7 | 1422.8 | 284.7 | 1411.1 | 284.7
4 | 1656.5 | 1820.7 | 1738.6 | 1325.2 | 2070.7 | 1456.5 | 2275.8 | 1809 | 1389.1 | 267.5 | 1553.2 | 267.5 | 1541.5 | 267.5
4.25 | 1821.5 | 2010.3 | 1915.9 | 1457.2 | 2276.9 | 1608.2 | 2512.9 | 1998.6 | 1473 | 348.5 | 1661.8 | 348.5 | 1650.2 | 348.5
4.5 | 1909.8 | 2124.4 | 2017.1 | 1527.8 | 2387.2 | 1699.5 | 2655.5 | 2112.7 | 1577.6 | 332.2 | 1792.2 | 332.2 | 1780.5 | 332.2
4.75 | 2117.6 | 2359.1 | 2238.4 | 1694.1 | 2647 | 1887.3 | 2948.9 | 2347.5 | 1666.9 | 450.8 | 1908.4 | 450.8 | 1896.7 | 450.8
5 | 2246.1 | 2515.6 | 2380.9 | 1796.9 | 2807.6 | 2012.5 | 3144.6 | 2504 | 1776.3 | 469.8 | 2045.9 | 469.8 | 2034.2 | 469.8
5.25 | 2281 | 2579.8 | 2430.4 | 1824.8 | 2851.3 | 2063.8 | 3224.7 | 2568.1 | 1863.1 | 418 | 2161.8 | 418 | 2150.1 | 418
5.5 | 2363.7 | 2692.5 | 2528.1 | 1891 | 2954.6 | 2154 | 3365.6 | 2680.8 | 1963.2 | 400.5 | 2292 | 400.5 | 2280.3 | 400.5
5.75 | 2378.6 | 2738.4 | 2558.5 | 1902.9 | 2973.3 | 2190.7 | 3423 | 2726.7 | 2041.9 | 336.7 | 2401.7 | 336.7 | 2390 | 336.7
6 | 2517.9 | 2909.4 | 2713.7 | 2014.4 | 3147.4 | 2327.5 | 3636.7 | 2897.7 | 2134.2 | 383.8 | 2525.6 | 383.8 | 2513.9 | 383.8
6.25 | 2611.2 | 3035.1 | 2823.2 | 2089 | 3264.1 | 2428 | 3793.8 | 3022.1 | 2203.7 | 407.5 | 2627.5 | 407.5 | 2614.6 | 407.5
6.5 | 2671.6 | 3128.7 | 2900.2 | 2137.3 | 3339.6 | 2503 | 3910.9 | 3115.8 | 2315.5 | 356.2 | 2772.6 | 356.2 | 2759.6 | 356.2
6.75 | 2869.6 | 3360.8 | 3115.2 | 2295.7 | 3587 | 2688.6 | 4201 | 3347.9 | 2401.2 | 468.4 | 2892.4 | 468.4 | 2879.5 | 468.4
7 | 3119 | 3645.3 | 3382.2 | 2495.2 | 3898.8 | 2916.2 | 4556.6 | 3631.4 | 2520.7 | 598.3 | 3047 | 598.3 | 3033.1 | 598.3
7.25 | 3056.2 | 3619.1 | 3337.7 | 2445 | 3820.3 | 2895.3 | 4523.8 | 3605.3 | 2654.8 | 401.4 | 3217.6 | 401.4 | 3203.8 | 401.4
7.5 | 3366.8 | 3967.5 | 3667.2 | 2693.5 | 4208.5 | 3174 | 4959.4 | 3953 | 2784.8 | 582 | 3385.5 | 582 | 3370.9 | 582
7.75 | 3488.6 | 4128.3 | 3808.5 | 2790.9 | 4360.8 | 3302.6 | 5160.4 | 4110.3 | 2865.9 | 622.7 | 3505.6 | 622.7 | 3487.6 | 622.7
8 | 3617.6 | 4297.7 | 3957.6 | 2894 | 4521.9 | 3438.2 | 5372.1 | 4279.7 | 3044.6 | 573 | 3724.7 | 573 | 3706.7 | 573
8.25 | 3846.5 | 4568.8 | 4207.7 | 3077.2 | 4808.2 | 3655 | 5711 | 4550.8 | 3187.8 | 658.7 | 3910.1 | 658.7 | 3892.1 | 658.7
8.5 | 4020.7 | 4786.9 | 4403.8 | 3216.6 | 5025.9 | 3829.5 | 5983.6 | 4764.9 | 3319.2 | 701.5 | 4085.4 | 701.5 | 4063.4 | 701.5
8.75 | 3964.6 | 4776.5 | 4370.5 | 3171.7 | 4955.8 | 3821.2 | 5970.6 | 4754.5 | 3508.6 | 456 | 4320.5 | 456 | 4298.6 | 456
9 | 4167.7 | 5026.8 | 4597.2 | 3334.1 | 5209.6 | 4021.5 | 6283.5 | 5004.9 | 3636.4 | 531.3 | 4495.5 | 531.3 | 4473.5 | 531.3
9.25 | 4160 | 5067.2 | 4613.6 | 3328 | 5199.9 | 4053.8 | 6334 | 5045.3 | 3721.6 | 438.3 | 4628.9 | 438.3 | 4607 | 438.3
9.5 | 4346 | 5302 | 4824 | 3476.8 | 5432.5 | 4241.6 | 6627.5 | 5280.1 | 3828.7 | 517.3 | 4784.7 | 517.3 | 4762.8 | 517.3
9.75 | 4595.8 | 5601.4 | 5098.6 | 3676.7 | 5744.8 | 4481.1 | 7001.7 | 5579.4 | 3919.7 | 676.2 | 4925.2 | 676.2 | 4903.3 | 676.2
10 | 4517.4 | 5573.5 | 5045.5 | 3613.9 | 5646.8 | 4458.8 | 6966.9 | 5551.6 | 4050.8 | 466.6 | 5106.9 | 466.6 | 5085 | 466.6
10.25 | 4601.4 | 5708.7 | 5155.1 | 3681.2 | 5751.8 | 4567 | 7135.9 | 5686.8 | 4128.3 | 473.2 | 5235.6 | 473.2 | 5213.6 | 473.2
10.5 | 4744.9 | 5903.9 | 5324.4 | 3795.9 | 5931.1 | 4723.1 | 7379.8 | 5881.9 | 4210.8 | 534 | 5369.8 | 534 | 5347.9 | 534
10.75 | 4786.2 | 5997.3 | 5391.8 | 3829 | 5982.8 | 4797.9 | 7496.7 | 5975.4 | 4294.3 | 492 | 5505.4 | 492 | 5483.4 | 492
11 | 4847.1 | 6111 | 5479 | 3877.7 | 6058.9 | 4888.8 | 7638.7 | 6089 | 4390.4 | 456.7 | 5654.3 | 456.7 | 5632.4 | 456.7
11.25 | 4927.6 | 6244.6 | 5586.1 | 3942.1 | 6159.5 | 4995.7 | 7805.7 | 6222.6 | 4457.1 | 470.5 | 5774.1 | 470.5 | 5752.2 | 470.5
11.5 | 5132.2 | 6502.7 | 5817.5 | 4105.8 | 6415.3 | 5202.1 | 8128.3 | 6480.3 | 4522.2 | 610.1 | 5892.6 | 610.1 | 5870.2 | 610.1
11.75 | 5132.3 | 6556.4 | 5844.4 | 4105.8 | 6415.4 | 5245.1 | 8195.5 | 6534.1 | 4601.4 | 530.9 | 6025.6 | 530.9 | 6003.2 | 530.9
12 | 5260.9 | 6739.3 | 6000.1 | 4208.7 | 6576.1 | 5391.4 | 8424.1 | 6716.9 | 4709.6 | 551.2 | 6188.1 | 551.2 | 6165.7 | 551.2
12.25 | 5265.4 | 6798.6 | 6032 | 4212.3 | 6581.7 | 5438.9 | 8498.3 | 6776.3 | 4789.5 | 475.9 | 6322.7 | 475.9 | 6300.4 | 475.9
12.5 | 5359.6 | 6948.1 | 6153.9 | 4287.7 | 6699.6 | 5558.5 | 8685.1 | 6925.7 | 4868.1 | 491.5 | 6456.6 | 491.5 | 6434.2 | 491.5
12.75 | 5404 | 7047.9 | 6226 | 4323.2 | 6755 | 5638.4 | 8809.9 | 7025.6 | 4933.6 | 470.5 | 6577.5 | 470.5 | 6555.1 | 470.5
13 | 5547.7 | 7247.6 | 6397.6 | 4438.2 | 6934.7 | 5798 | 9059.5 | 7225.2 | 5049 | 498.7 | 6748.8 | 498.7 | 6726.4 | 498.7
13.25 | 5665.1 | 7421.5 | 6543.3 | 4532.1 | 7081.4 | 5937.2 | 9276.9 | 7399.2 | 5129.1 | 536.1 | 6885.5 | 536.1 | 6863.1 | 536.1
13.5 | 5729.8 | 7543.2 | 6636.5 | 4583.9 | 7162.3 | 6034.5 | 9429 | 7520.8 | 5218.9 | 511 | 7032.2 | 511 | 7009.8 | 511
13.75 | 5827.8 | 7698.6 | 6763.2 | 4662.3 | 7284.8 | 6158.9 | 9623.2 | 7676.2 | 5293.8 | 534 | 7164.5 | 534 | 7142.2 | 534
14 | 5985.9 | 7914.4 | 6950.1 | 4788.7 | 7482.3 | 6331.5 | 9893 | 7890.8 | 5375.3 | 610.5 | 7303.9 | 610.5 | 7280.2 | 610.5
14.25 | 6117 | 8103.8 | 7110.4 | 4893.6 | 7646.2 | 6483.1 | 10129.8 | 8080.2 | 5475.2 | 641.8 | 7462.1 | 641.8 | 7438.4 | 641.8
14.5 | 6131.8 | 8177.6 | 7154.7 | 4905.5 | 7664.8 | 6542.1 | 10222 | 8153.3 | 5567.5 | 564.4 | 7613.2 | 564.4 | 7589 | 564.4
14.75 | 6211.8 | 8316.9 | 7264.3 | 4969.5 | 7764.8 | 6653.5 | 10396.1 | 8292.6 | 5645.9 | 565.9 | 7750.9 | 565.9 | 7726.7 | 565.9
15 | 6178.1 | 8342.9 | 7260.5 | 4942.5 | 7722.7 | 6674.3 | 10428.6 | 8122.4 | 5738.6 | 439.5 | 7903.4 | 439.5 | 7877.8 | 244.6
15.25 | 6379.7 | 8604.6 | 7492.2 | 5103.8 | 7974.7 | 6883.7 | 10755.8 | 8576.2 | 5824.6 | 555.1 | 8049.5 | 555.1 | 8021.1 | 555.1
15.5 | 6424.8 | 8710.3 | 7567.5 | 5139.8 | 8031 | 6968.2 | 10887.8 | 8681.8 | 5904.7 | 520 | 8190.3 | 520 | 8161.8 | 520
15.75 | 6477.9 | 8824.3 | 7651.1 | 5182.3 | 8097.4 | 7059.4 | 11030.3 | 8795.8 | 5971.7 | 506.2 | 8318.1 | 506.2 | 8289.6 | 506.2
16 | 6648.5 | 9056 | 7852.3 | 5318.8 | 8310.7 | 7244.8 | 11320 | 9027.6 | 6059.3 | 589.3 | 8466.8 | 589.3 | 8438.3 | 589.3
16.25 | 6676.5 | 9145.5 | 7911 | 5341.2 | 8345.7 | 7316.4 | 11431.9 | 9117.1 | 6136.2 | 540.4 | 8605.1 | 540.4 | 8576.7 | 540.4
16.5 | 6826.5 | 9357.3 | 8091.9 | 5461.2 | 8533.2 | 7485.8 | 11696.6 | 9328.9 | 6223.7 | 602.8 | 8754.5 | 602.8 | 8726 | 602.8
16.75 | 6857.7 | 9450.6 | 8154.1 | 5486.2 | 8572.1 | 7560.5 | 11813.3 | 9421.7 | 6288.1 | 569.6 | 8881 | 569.6 | 8852.1 | 569.6
17 | 6932.1 | 9587.4 | 8259.7 | 5545.7 | 8665.1 | 7669.9 | 11984.3 | 9558.5 | 6381.3 | 550.8 | 9036.6 | 550.8 | 9007.7 | 550.8
17.25 | 7014.8 | 9732.7 | 8373.7 | 5611.8 | 8768.5 | 7786.1 | 12165.9 | 9699.5 | 6414.2 | 600.6 | 9132.1 | 600.6 | 9099 | 600.6
17.5 | 6793.6 | 9574.2 | 8183.9 | 5434.8 | 8491.9 | 7659.4 | 11967.7 | 9415.7 | 6479.2 | 314.4 | 9259.8 | 314.4 | 9225.9 | 189.9
17.75 | 7149.5 | 9993.1 | 8571.3 | 5719.6 | 8936.9 | 7994.5 | 12491.3 | 9958.8 | 6553.3 | 596.3 | 9396.8 | 596.3 | 9362.5 | 596.3
18 | 7247.1 | 10153.9 | 8700.5 | 5797.7 | 9058.9 | 8123.1 | 12692.4 | 10119.3 | 6661.9 | 585.2 | 9568.8 | 585.2 | 9534.1 | 585.2
18.25 | 7222.2 | 10192.6 | 8707.4 | 5777.8 | 9027.7 | 8154.1 | 12740.8 | 9912.6 | 6684.3 | 537.9 | 9654.7 | 537.9 | 9613.4 | 299.2
18.5 | 7980.7 | 11015 | 9497.8 | 6384.5 | 9975.8 | 8812 | 13768.7 | 10969.8 | 6830.7 | 1150 | 9865 | 1150 | 9819.8 | 1150
18.75 | 8553 | 11655 | 10104 | 6842.4 | 10691.3 | 9324 | 14568.7 | 11609.8 | 7287.2 | 1265.9 | 10389.1 | 1265.9 | 10343.9 | 1265.9
19 | 9186.7 | 12362.7 | 10774.7 | 7349.3 | 11483.3 | 9890.2 | 15453.4 | 12317.5 | 7847.9 | 1338.7 | 11024 | 1338.7 | 10978.8 | 1338.7
19.25 | 10036.2 | 13293.3 | 11664.8 | 8029 | 12545.3 | 10634.7 | 16616.7 | 13248.1 | 8385.2 | 1651 | 11642.3 | 1651 | 11597.1 | 1651
19.5 | 10427.4 | 13773.7 | 12100.5 | 8341.9 | 13034.3 | 11018.9 | 17217.1 | 13728.5 | 9080.5 | 1346.9 | 12426.8 | 1346.9 | 12381.6 | 1346.9
19.75 | 10608.4 | 14052.3 | 12330.4 | 8486.8 | 13260.6 | 11241.8 | 17565.3 | 14007.1 | 9561.6 | 1046.8 | 13005.5 | 1046.8 | 12960.2 | 1046.8
20 | 11273 | 14818.9 | 13045.9 | 9018.4 | 14091.2 | 11855.1 | 18523.6 | 14773.7 | 10007.6 | 1265.4 | 13553.5 | 1265.4 | 13508.3 | 1265.4
20.25 | 11453.7 | 15107 | 13280.3 | 9162.9 | 14317.1 | 12085.6 | 18883.7 | 15061.8 | 10425.4 | 1028.3 | 14078.7 | 1028.3 | 14033.5 | 1028.3
20.5 | 11608.9 | 15373.4 | 13491.1 | 9287.1 | 14511.1 | 12298.7 | 19216.7 | 15328.2 | 10769.8 | 839.1 | 14534.3 | 839.1 | 14489.1 | 839.1
20.75 | 11845.5 | 15723.4 | 13784.4 | 9476.4 | 14806.9 | 12578.7 | 19654.2 | 15678.2 | 10970.4 | 875.1 | 14848.3 | 875.1 | 14803.1 | 875.1
21 | 11935.6 | 15928.5 | 13932 | 9548.5 | 14919.5 | 12742.8 | 19910.6 | 15883.3 | 11206.5 | 729.1 | 15199.4 | 729.1 | 15154.2 | 729.1
21.25 | 12079.4 | 16188.3 | 14133.8 | 9663.5 | 15099.3 | 12950.6 | 20235.3 | 16143 | 11303.5 | 775.9 | 15412.3 | 775.9 | 15367.1 | 775.9
21.5 | 12424.5 | 16649.6 | 14537.1 | 9939.6 | 15530.7 | 13319.7 | 20812 | 16604.4 | 11437 | 987.5 | 15662.1 | 987.5 | 15616.9 | 987.5
21.75 | 12549.2 | 16891.7 | 14720.5 | 10039.4 | 15686.5 | 13513.4 | 21114.7 | 16846.5 | 11641.1 | 908.1 | 15983.6 | 908.1 | 15938.4 | 908.1
22 | 12916.6 | 17378.7 | 15147.6 | 10333.3 | 16145.7 | 13903 | 21723.4 | 17333.5 | 11887.9 | 1028.7 | 16350 | 1028.7 | 16304.8 | 1028.7
22.25 | 13011.4 | 17594.8 | 15303.1 | 10409.1 | 16264.3 | 14075.8 | 21993.5 | 17549.6 | 12056.7 | 954.7 | 16640.1 | 954.7 | 16594.9 | 954.7
22.5 | 13101.9 | 17807.6 | 15454.7 | 10481.5 | 16377.4 | 14246 | 22259.5 | 17761 | 12209 | 892.9 | 16914.6 | 892.9 | 16868 | 892.9
22.75 | 15526.5 | 20355.7 | 17941.1 | 12421.2 | 19408.1 | 16284.5 | 25444.6 | 18388.1 | 12306.4 | 3220 | 17135.6 | 3220 | 17008.9 | 1379.2
23 | 32755.4 | 37714.6 | 35235 | 26204.3 | 40944.2 | 30171.7 | 47143.2 | 23545.1 | 12780.3 | 19975.1 | 17739.5 | 19975.1 | 17219.2 | 6325.9
23.25 | 37570 | 42704.6 | 40137.3 | 30056 | 46962.5 | 34163.7 | 53380.7 | 24875.7 | 13998.4 | 23571.7 | 19132.9 | 23571.7 | 17597.6 | 7278.2
23.5 | 36615.5 | 41993.1 | 39304.3 | 29292.4 | 45769.3 | 33594.5 | 52491.4 | 24707.8 | 15356.9 | 21258.6 | 20734.5 | 21258.6 | 18015.4 | 6692.4
23.75 | 17467.7 | 23197.9 | 20332.8 | 13974.2 | 21834.6 | 18558.3 | 28997.4 | 20284.2 | 17309.5 | 158.2 | 23039.7 | 158.2 | 20126 | 158.2
24 | 44990 | 51097.1 | 48043.5 | 35992 | 56237.5 | 40877.7 | 63871.3 | 28636.2 | 17829.9 | 27160.2 | 23936.9 | 27160.2 | 20395 | 8241.2
24.25 | 35144.3 | 41688.4 | 38416.3 | 28115.5 | 43930.4 | 33350.7 | 52110.4 | 37394.3 | 19901 | 15243.3 | 26445.1 | 15243.3 | 22151 | 15243.3
24.5 | 34629.8 | 41698.2 | 38164 | 27703.8 | 43287.2 | 33358.5 | 52122.7 | 28633.6 | 21443.5 | 13186.3 | 28511.9 | 13186.3 | 24102.4 | 4531.2
24.75 | 26588 | 34197.4 | 30392.7 | 21270.4 | 33235 | 27357.9 | 42746.7 | 29376.6 | 22362.9 | 4225 | 29972.3 | 4225 | 25151.5 | 4225
25 | 25809.8 | 33982.1 | 29895.9 | 20647.8 | 32262.2 | 27185.7 | 42477.6 | 29161.3 | 23499.4 | 2310.4 | 31671.7 | 2310.4 | 26850.8 | 2310.4
25.25 | 30827.4 | 39553.8 | 35190.6 | 24661.9 | 38534.3 | 31643 | 49442.2 | 34708.7 | 23671.9 | 7155.5 | 32398.3 | 7155.5 | 27553.2 | 7155.5
25.5 | 28068.7 | 37340.8 | 32704.7 | 22454.9 | 35085.9 | 29872.6 | 46676 | 32346.2 | 23712.2 | 4356.5 | 32984.3 | 4356.5 | 27989.7 | 4356.5
25.75 | 28140.4 | 37949 | 33044.7 | 22512.3 | 35175.5 | 30359.2 | 47436.2 | 30673.6 | 24182.3 | 3958 | 33990.9 | 3958 | 28996.3 | 1677.3
26 | 25825.7 | 36165.3 | 30995.5 | 20660.5 | 32282.1 | 28932.2 | 45206.6 | 31019.7 | 24563.9 | 1261.8 | 34903.5 | 1261.8 | 29758 | 1261.8
26.25 | 25596.9 | 36458.9 | 31027.9 | 20477.5 | 31996.2 | 29167.1 | 45573.6 | 31287.1 | 24541.5 | 1055.4 | 35403.5 | 1055.4 | 30231.6 | 1055.4
26.5 | 27531.5 | 38900.6 | 33216.1 | 22025.2 | 34414.4 | 31120.5 | 48625.8 | 33725.2 | 24631.9 | 2899.7 | 36001 | 2899.7 | 30825.5 | 2899.7
26.75 | 25894.3 | 37762.7 | 31828.5 | 20715.5 | 32367.9 | 30210.2 | 47203.4 | 32587.2 | 24724 | 1170.4 | 36592.3 | 1170.4 | 31416.9 | 1170.4
27 | 25822.3 | 38175.6 | 31998.9 | 20657.9 | 32277.9 | 30540.4 | 47719.5 | 32388.1 | 24564.1 | 1258.3 | 36917.3 | 1258.3 | 31737.5 | 650.6
27.25 | 29702 | 42530.6 | 36116.3 | 23761.6 | 37127.5 | 34024.5 | 53163.3 | 34513.8 | 24913.3 | 4788.7 | 37741.9 | 4788.7 | 32529 | 1984.8
27.5 | 28816.5 | 42118.1 | 35467.3 | 23053.2 | 36020.6 | 33694.5 | 52647.6 | 34590.2 | 25041.8 | 3774.6 | 38343.4 | 3774.6 | 32959.6 | 1630.6
27.75 | 31375.3 | 45145.6 | 38260.5 | 25100.3 | 39219.1 | 36116.5 | 56432 | 35659.3 | 25028.1 | 6347.2 | 38798.4 | 6347.2 | 33140.4 | 2518.9
28 | 31418.9 | 45652.9 | 38535.9 | 25135.1 | 39273.6 | 36522.3 | 57066.1 | 35867.9 | 24992.9 | 6426 | 39226.9 | 6426 | 33318.5 | 2549.4
28.25 | 32807 | 47501.5 | 40154.3 | 26245.6 | 41008.8 | 38001.2 | 59376.9 | 36502.9 | 25093.5 | 7713.6 | 39787.9 | 7713.6 | 33529.2 | 2973.7
28.5 | 32861.7 | 48017.2 | 40439.5 | 26289.4 | 41077.2 | 38413.8 | 60021.5 | 36707.2 | 25244.7 | 7617 | 40400.2 | 7617 | 33759.2 | 2948
28.75 | 28059.3 | 43674.4 | 35866.8 | 22447.4 | 35074.1 | 34939.5 | 54593 | 36796.9 | 25291.1 | 2768.2 | 40906.2 | 2768.2 | 34028.8 | 2768.2
29 | 26933.3 | 43004.4 | 34968.8 | 21546.6 | 33666.6 | 34403.5 | 53755.5 | 36126.9 | 25649.3 | 1284 | 41720.4 | 1284 | 34843 | 1284
29.25 | 28306.8 | 44824.1 | 36565.5 | 22645.4 | 35383.5 | 35859.3 | 56030.2 | 37941.4 | 25664.9 | 2641.9 | 42182.2 | 2641.9 | 35299.5 | 2641.9
29.5 | 35422.4 | 52382.3 | 43902.4 | 28337.9 | 44278 | 41905.8 | 65477.9 | 39293.5 | 25954.3 | 9468.1 | 42914.2 | 9468.1 | 35738 | 3555.6
29.75 | 30705 | 48110.1 | 39407.6 | 24564 | 38381.3 | 38488.1 | 60137.7 | 40625.5 | 26015 | 4690.1 | 43420.1 | 4690.1 | 35935.4 | 4690.1
30 | 30006.4 | 47855 | 38930.7 | 24005.1 | 37508 | 38284 | 59818.8 | 40295.8 | 26402.9 | 3603.4 | 44251.6 | 3603.4 | 36692.4 | 3603.4
30.25 | 37724.5 | 56016 | 46870.2 | 30179.6 | 47155.6 | 44812.8 | 70020 | 41578.1 | 26952.9 | 10771.5 | 45244.4 | 10771.5 | 37601.1 | 3977
30.5 | 53378.7 | 72132.8 | 62755.8 | 42703 | 66723.4 | 57706.2 | 90166 | 46159.4 | 27916.4 | 25462.3 | 46670.5 | 25462.3 | 38000.6 | 8158.8
30.75 | 52100.1 | 71365 | 61732.6 | 41680.1 | 65125.2 | 57092 | 89206.2 | 45970.8 | 28836.1 | 23264 | 48101 | 23264 | 38390.9 | 7579.9
31 | 64335.9 | 84161.4 | 74248.6 | 51468.7 | 80419.8 | 67329.1 | 105201.8 | 49276.5 | 30176.6 | 34159.2 | 50002.2 | 34159.2 | 38819.7 | 10456.8
31.25 | 60078 | 80533.2 | 70305.6 | 48062.4 | 75097.5 | 64426.6 | 100666.6 | 48267.9 | 31148.6 | 28929.4 | 51603.9 | 28929.4 | 39149.5 | 9118.3
31.5 | 50352.4 | 71442.1 | 60897.3 | 40281.9 | 62940.4 | 57153.7 | 89302.7 | 45816.8 | 30514.1 | 19838.3 | 51603.9 | 19838.3 | 39149.5 | 6667.2
31.75 | 41332.4 | 63032.6 | 52182.5 | 33065.9 | 51665.5 | 50426.1 | 78790.7 | 43365.6 | 29903.7 | 11428.7 | 51603.9 | 11428.7 | 39149.5 | 4216.1
32 | 33329.8 | 55617.4 | 44473.6 | 26663.9 | 41662.3 | 44493.9 | 69521.7 | 40914.5 | 29316.3 | 4013.5 | 51603.9 | 4013.5 | 39149.5 | 1764.9
32.25 | 32074.6 | 55575.6 | 43825.1 | 25659.7 | 40093.2 | 44460.4 | 69469.4 | 40157.4 | 31887.4 | 187.1 | 55388.4 | 187.1 | 39970.3 | 187.1
32.5 | 34661.3 | 58839.4 | 46750.3 | 27729 | 43326.6 | 47071.5 | 73549.2 | 41569.3 | 31284.4 | 3376.9 | 55462.5 | 3376.9 | 40037.1 | 1532.2
32.75 | 47066 | 71902.6 | 59484.3 | 37652.8 | 58832.5 | 57522.1 | 89878.3 | 56257.2 | 31710 | 15356 | 56546.6 | 15356 | 40901.2 | 15356
33 | 37015.5 | 62541.3 | 49778.4 | 29612.4 | 46269.4 | 50033.1 | 78176.7 | 46776.8 | 33646.1 | 3369.4 | 59171.9 | 3369.4 | 43407.4 | 3369.4
33.25 | 36672.9 | 62903.7 | 49788.3 | 29338.3 | 45841.1 | 50323 | 78629.6 | 47139.2 | 34568.8 | 2104 | 60799.7 | 2104 | 45035.2 | 2104
33.5 | 37927.7 | 64851.9 | 51389.8 | 30342.2 | 47409.6 | 51881.5 | 81064.8 | 49087.4 | 35178.3 | 2749.4 | 62102.4 | 2749.4 | 46337.9 | 2749.4
33.75 | 39306.3 | 66917.1 | 53111.7 | 31445.1 | 49132.9 | 53533.7 | 83646.4 | 51152.6 | 36005.2 | 3301.1 | 63616 | 3301.1 | 47851.5 | 3301.1
34 | 40025.1 | 68322.7 | 54173.9 | 32020.1 | 50031.4 | 54658.1 | 85403.3 | 52558.2 | 37272.1 | 2753 | 65569.6 | 2753 | 49805.1 | 2753
34.25 | 42747.1 | 71736.2 | 57241.6 | 34197.6 | 53433.8 | 57389 | 89670.2 | 55971.7 | 38803.3 | 3943.8 | 67792.4 | 3943.8 | 52027.9 | 3943.8
34.5 | 45758.6 | 75458.4 | 60608.5 | 36606.9 | 57198.2 | 60366.7 | 94323 | 59693.9 | 40859 | 4899.6 | 70558.8 | 4899.6 | 54794.3 | 4899.6
34.75 | 47969.4 | 78414.2 | 63191.8 | 38375.5 | 59961.8 | 62731.4 | 98017.8 | 62649.7 | 43588.5 | 4381 | 74033.3 | 4381 | 58268.8 | 4381
35 | 52338.2 | 83572.9 | 67955.6 | 41870.6 | 65422.8 | 66858.3 | 104466.2 | 67808.4 | 46532.1 | 5806.1 | 77766.8 | 5806.1 | 62002.3 | 5806.1
35.25 | 55716.8 | 87802.2 | 71759.5 | 44573.4 | 69646 | 70241.7 | 109752.7 | 72037.7 | 49987.2 | 5729.6 | 82072.5 | 5729.6 | 66308.1 | 5729.6
35.5 | 50870.3 | 83846.2 | 67358.2 | 40696.2 | 63587.9 | 67076.9 | 104807.7 | 68081.7 | 50654.4 | 215.9 | 83630.3 | 215.9 | 67865.8 | 215.9
35.75 | 54991.3 | 88838.6 | 71915 | 43993.1 | 68739.2 | 71070.9 | 111048.3 | 73058.2 | 50456.3 | 4535.1 | 84303.6 | 4535.1 | 68523.2 | 4535.1
36 | 55549.9 | 90276.5 | 72913.2 | 44440 | 69437.4 | 72221.2 | 112845.6 | 74496.1 | 52446.6 | 3103.3 | 87173.1 | 3103.3 | 71392.7 | 3103.3
36.25 | 58305.2 | 93924.9 | 76115.1 | 46644.2 | 72881.5 | 75139.9 | 117406.2 | 78144.5 | 53942.8 | 4362.4 | 89562.5 | 4362.4 | 73782.1 | 4362.4
36.5 | 59307 | 95840.3 | 77573.6 | 47445.6 | 74133.7 | 76672.2 | 119800.3 | 80059.9 | 56047.1 | 3259.9 | 92580.4 | 3259.9 | 76800 | 3259.9
36.75 | 61101.5 | 98563.7 | 79832.6 | 48881.2 | 76376.9 | 78850.9 | 123204.6 | 82783.3 | 57394.5 | 3707.1 | 94856.6 | 3707.1 | 79076.2 | 3707.1
37 | 66020 | 104427.4 | 85223.7 | 52816 | 82525 | 83541.9 | 130534.2 | 88647 | 59597.4 | 6422.5 | 98004.8 | 6422.5 | 82224.4 | 6422.5
37.25 | 72934.7 | 112341.5 | 92638.1 | 58347.7 | 91168.4 | 89873.2 | 140426.9 | 96561.1 | 63030.2 | 9904.4 | 102437.1 | 9904.4 | 86656.7 | 9904.4
37.5 | 78317.9 | 118799.6 | 98558.7 | 62654.3 | 97897.3 | 95039.7 | 148499.5 | 103019.2 | 66484.8 | 11833.1 | 106966.5 | 11833.1 | 91186.1 | 11833.1
37.75 | 74405.6 | 116059.5 | 95232.6 | 59524.5 | 93007 | 92847.6 | 145074.4 | 100275.7 | 69582.9 | 4822.7 | 111236.9 | 4822.7 | 95453.1 | 4822.7
38 | 75629.6 | 118484 | 97056.8 | 60503.7 | 94537 | 94787.2 | 148105 | 102684.9 | 70890.6 | 4738.9 | 113745.1 | 4738.9 | 97945.9 | 4738.9
38.25 | 87189.4 | 131286.9 | 109238.1 | 69751.5 | 108986.7 | 105029.5 | 164108.6 | 115487.7 | 73701 | 13488.4 | 117798.5 | 13488.4 | 101999.3 | 13488.4
38.5 | 97903.9 | 143353.3 | 120628.6 | 78323.1 | 122379.9 | 114682.7 | 179191.7 | 127554.2 | 78163.4 | 19740.5 | 123612.8 | 19740.5 | 107813.6 | 19740.5
38.75 | 100062.7 | 146994.1 | 123528.4 | 80050.2 | 125078.4 | 117595.3 | 183742.7 | 131195 | 81812.7 | 18250 | 128744.2 | 18250 | 112945 | 18250

## SRD WTG-21
Depth (m) | SRD AH-FF (kN) | SRD AH-NFF (kN) | SRD MEAN (kN) | SRD AH-FF-LB (kN) | SRD AH-FF-UB (kN) | SRD AH-NFF-LB (kN) | SRD AH-NFF-UB (kN) | Static Cap (kN) | Shaft AH-FF (kN) | Tip AH-FF (kN) | Shaft AH-NFF (kN) | Tip AH-NFF (kN) | Shaft SC (kN) | Tip SC (kN)
0.5 | 129.1 | 130 | 129.6 | 103.3 | 161.4 | 104 | 162.5 | 130 | 33.6 | 95.5 | 34.5 | 95.5 | 34.5 | 95.5
0.75 | 145.3 | 147.2 | 146.3 | 116.3 | 181.7 | 117.8 | 184 | 147.2 | 49.8 | 95.5 | 51.7 | 95.5 | 51.7 | 95.5
1 | 169.8 | 173.1 | 171.4 | 135.9 | 212.3 | 138.5 | 216.3 | 173.1 | 74.3 | 95.5 | 77.6 | 95.5 | 77.6 | 95.5
1.25 | 185.5 | 190.3 | 187.9 | 148.4 | 231.8 | 152.3 | 237.9 | 190.3 | 90 | 95.5 | 94.8 | 95.5 | 94.8 | 95.5
1.5 | 209.5 | 216.2 | 212.8 | 167.6 | 261.9 | 172.9 | 270.2 | 216.2 | 114 | 95.5 | 120.7 | 95.5 | 120.7 | 95.5
1.75 | 181 | 189.7 | 185.3 | 144.8 | 226.2 | 151.7 | 237.1 | 168.5 | 132.7 | 48.3 | 141.4 | 48.3 | 141.4 | 27.2
2 | 311.4 | 322.1 | 316.7 | 249.1 | 389.2 | 257.7 | 402.7 | 228 | 138.3 | 173.1 | 149.1 | 173.1 | 147.7 | 80.3
2.25 | 502.7 | 515.9 | 509.3 | 402.1 | 628.3 | 412.7 | 644.8 | 331.4 | 186 | 316.7 | 199.2 | 316.7 | 195.8 | 135.5
2.5 | 762.8 | 779.9 | 771.3 | 610.2 | 953.5 | 623.9 | 974.8 | 469.2 | 262 | 500.8 | 279.1 | 500.8 | 267 | 202.2
2.75 | 824.9 | 847.8 | 836.4 | 659.9 | 1031.1 | 678.3 | 1059.8 | 833.3 | 376.6 | 448.3 | 399.6 | 448.3 | 385.1 | 448.3
3 | 1044.1 | 1075.1 | 1059.6 | 835.2 | 1305.1 | 860.1 | 1343.9 | 1056.5 | 465.7 | 578.4 | 496.7 | 578.4 | 478.2 | 578.4
3.25 | 1067.9 | 1108.9 | 1088.4 | 854.3 | 1334.9 | 887.2 | 1386.2 | 1090.4 | 602.9 | 465 | 643.9 | 465 | 625.4 | 465
3.5 | 1105.5 | 1158.7 | 1132.1 | 884.4 | 1381.9 | 927 | 1448.4 | 1136.9 | 725.8 | 379.7 | 779 | 379.7 | 757.2 | 379.7
3.75 | 1205.4 | 1272.3 | 1238.8 | 964.3 | 1506.7 | 1017.8 | 1590.4 | 1248.6 | 807.6 | 397.8 | 874.5 | 397.8 | 850.8 | 397.8
4 | 1350.5 | 1432.4 | 1391.4 | 1080.4 | 1688.1 | 1145.9 | 1790.5 | 1406.2 | 902.4 | 448.1 | 984.3 | 448.1 | 958.1 | 448.1
4.25 | 1436.3 | 1534.9 | 1485.6 | 1149 | 1795.3 | 1227.9 | 1918.6 | 1508.7 | 1013.1 | 423.2 | 1111.7 | 423.2 | 1085.5 | 423.2
4.5 | 1544.4 | 1660.7 | 1602.5 | 1235.5 | 1930.5 | 1328.6 | 2075.9 | 1631.7 | 1083.7 | 460.7 | 1200 | 460.7 | 1170.9 | 460.7
4.75 | 1636.1 | 1771.2 | 1703.6 | 1308.8 | 2045.1 | 1416.9 | 2213.9 | 1737.6 | 1162.7 | 473.4 | 1297.8 | 473.4 | 1264.2 | 473.4
5 | 1812.6 | 1968 | 1890.3 | 1450.1 | 2265.8 | 1574.4 | 2460 | 1934.4 | 1292.6 | 520 | 1448 | 520 | 1414.4 | 520
5.25 | 1846.7 | 2023.6 | 1935.2 | 1477.3 | 2308.4 | 1618.9 | 2529.5 | 1988.7 | 1398.9 | 447.8 | 1575.8 | 447.8 | 1540.9 | 447.8
5.5 | 1923 | 2122.9 | 2023 | 1538.4 | 2403.8 | 1698.4 | 2653.7 | 2086.7 | 1497.6 | 425.4 | 1697.5 | 425.4 | 1661.3 | 425.4
5.75 | 1979.2 | 2203.2 | 2091.2 | 1583.4 | 2474 | 1762.5 | 2754 | 2166.6 | 1568.8 | 410.5 | 1792.7 | 410.5 | 1756.1 | 410.5
6 | 2045.3 | 2293.8 | 2169.5 | 1636.2 | 2556.6 | 1835 | 2867.2 | 2257.2 | 1637.5 | 407.8 | 1886 | 407.8 | 1849.4 | 407.8
6.25 | 2197.7 | 2471.3 | 2334.5 | 1758.2 | 2747.1 | 1977 | 3089.1 | 2433.1 | 1726.6 | 471.1 | 2000.2 | 471.1 | 1962 | 471.1
6.5 | 2223.1 | 2522.8 | 2372.9 | 1778.5 | 2778.9 | 2018.2 | 3153.5 | 2484.6 | 1806.3 | 416.8 | 2106 | 416.8 | 2067.8 | 416.8
6.75 | 2348.2 | 2674.6 | 2511.4 | 1878.6 | 2935.3 | 2139.6 | 3343.2 | 2634.9 | 1850.6 | 497.6 | 2176.9 | 497.6 | 2137.3 | 497.6
7 | 2446.5 | 2800 | 2623.2 | 1957.2 | 3058.1 | 2240 | 3500 | 2758.1 | 1958.2 | 488.3 | 2311.7 | 488.3 | 2269.7 | 488.3
7.25 | 2795.9 | 3177.8 | 2986.9 | 2236.7 | 3494.9 | 2542.3 | 3972.3 | 3130.5 | 2079.3 | 716.7 | 2461.2 | 716.7 | 2413.9 | 716.7
7.5 | 2857 | 3269.9 | 3063.4 | 2285.6 | 3571.2 | 2615.9 | 4087.4 | 3222.6 | 2270.9 | 586.1 | 2683.8 | 586.1 | 2636.5 | 586.1
7.75 | 2944.9 | 3390.5 | 3167.7 | 2355.9 | 3681.2 | 2712.4 | 4238.1 | 3343.2 | 2396.6 | 548.3 | 2842.2 | 548.3 | 2794.9 | 548.3
8 | 3154.6 | 3634 | 3394.3 | 2523.7 | 3943.3 | 2907.2 | 4542.5 | 3585.9 | 2497.9 | 656.7 | 2977.3 | 656.7 | 2929.2 | 656.7
8.25 | 3522 | 4036.7 | 3779.4 | 2817.6 | 4402.6 | 3229.4 | 5045.9 | 3988.7 | 2671.2 | 850.8 | 3185.9 | 850.8 | 3137.8 | 850.8
8.5 | 3526.3 | 4078.4 | 3802.4 | 2821.1 | 4407.9 | 3262.8 | 5098.1 | 4024 | 2803.5 | 722.8 | 3355.7 | 722.8 | 3301.2 | 722.8
8.75 | 3526 | 4117.2 | 3821.6 | 2820.8 | 4407.5 | 3293.8 | 5146.5 | 4062.8 | 2957.8 | 568.2 | 3549 | 568.2 | 3494.5 | 568.2
9 | 3657.7 | 4288.9 | 3973.3 | 2926.2 | 4572.1 | 3431.1 | 5361.1 | 4232.6 | 3061.2 | 596.5 | 3692.4 | 596.5 | 3636.1 | 596.5
9.25 | 3653.2 | 4325.9 | 3989.6 | 2922.6 | 4566.6 | 3460.7 | 5407.3 | 4269.6 | 3194.8 | 458.5 | 3867.4 | 458.5 | 3811.1 | 458.5
9.5 | 3872.1 | 4586.9 | 4229.5 | 3097.7 | 4840.2 | 3669.5 | 5733.6 | 4528.9 | 3251.7 | 620.5 | 3966.4 | 620.5 | 3908.4 | 620.5
9.75 | 3927 | 4684.5 | 4305.7 | 3141.6 | 4908.7 | 3747.6 | 5855.6 | 4626.5 | 3370.3 | 556.7 | 4127.8 | 556.7 | 4069.8 | 556.7
10 | 4039.1 | 4840.5 | 4439.8 | 3231.3 | 5048.9 | 3872.4 | 6050.7 | 4778.7 | 3509.6 | 529.5 | 4311 | 529.5 | 4249.2 | 529.5
10.25 | 3876.5 | 4722.9 | 4299.7 | 3101.2 | 4845.7 | 3778.3 | 5903.6 | 4533.2 | 3585.8 | 290.7 | 4432.1 | 290.7 | 4370.3 | 162.8
10.5 | 4252.1 | 5143.9 | 4698 | 3401.7 | 5315.1 | 4115.1 | 6429.9 | 5080.8 | 3683.2 | 568.9 | 4575 | 568.9 | 4511.9 | 568.9
10.75 | 4313 | 5250.9 | 4781.9 | 3450.4 | 5391.2 | 4200.7 | 6563.6 | 5185.9 | 3733.9 | 579.1 | 4671.8 | 579.1 | 4606.9 | 579.1
11 | 4409.2 | 5393.6 | 4901.4 | 3527.4 | 5511.6 | 4314.9 | 6742 | 5328 | 3826.3 | 582.9 | 4810.7 | 582.9 | 4745.1 | 582.9
11.25 | 4508.7 | 5539.7 | 5024.2 | 3606.9 | 5635.8 | 4431.7 | 6924.6 | 5470.4 | 3849.5 | 659.2 | 4880.5 | 659.2 | 4811.2 | 659.2
11.5 | 4452 | 5530.1 | 4991 | 3561.6 | 5565 | 4424.1 | 6912.6 | 5459.4 | 3922.9 | 529.1 | 5001 | 529.1 | 4930.4 | 529.1
11.75 | 5019.9 | 6145.1 | 5582.5 | 4015.9 | 6274.9 | 4916 | 7681.3 | 6067 | 3958.8 | 1061.1 | 5084 | 1061.1 | 5006 | 1061.1
12 | 4695.6 | 5869.4 | 5282.5 | 3756.5 | 5869.5 | 4695.5 | 7336.8 | 5791.4 | 4163.8 | 531.8 | 5337.7 | 531.8 | 5259.6 | 531.8
12.25 | 4711.1 | 5934.7 | 5322.9 | 3768.9 | 5888.9 | 4747.7 | 7418.3 | 5855.5 | 4231.2 | 480 | 5454.7 | 480 | 5375.6 | 480
12.5 | 4813.8 | 6087.2 | 5450.5 | 3851 | 6017.2 | 4869.8 | 7609 | 6006.6 | 4278.4 | 535.4 | 5551.8 | 535.4 | 5471.2 | 535.4
12.75 | 5163.2 | 6486.6 | 5824.9 | 4130.5 | 6454 | 5189.3 | 8108.3 | 5981.2 | 4345.8 | 817.4 | 5669.3 | 817.4 | 5581.6 | 399.6
13 | 5161.2 | 6536 | 5848.6 | 4128.9 | 6451.5 | 5228.8 | 8170 | 6443.7 | 4540.7 | 620.5 | 5915.5 | 620.5 | 5823.2 | 620.5
13.25 | 5605.2 | 7032.9 | 6319.1 | 4484.2 | 7006.5 | 5626.3 | 8791.1 | 6934.8 | 4639.2 | 966 | 6066.9 | 966 | 5968.7 | 966
13.5 | 5084.6 | 6566.5 | 5825.5 | 4067.6 | 6355.7 | 5253.2 | 8208.2 | 6353.2 | 4804.2 | 280.4 | 6286.2 | 280.4 | 6187.8 | 165.4
13.75 | 5197.4 | 6734.2 | 5965.8 | 4157.9 | 6496.7 | 5387.3 | 8417.7 | 6487.3 | 4855.2 | 342.2 | 6392 | 342.2 | 6291.4 | 195.9
14 | 5303 | 6895 | 6099 | 4242.4 | 6628.7 | 5516 | 8618.8 | 6645.7 | 4960 | 343 | 6552.1 | 343 | 6448.8 | 196.9
14.25 | 5839.8 | 7487.7 | 6663.8 | 4671.9 | 7299.8 | 5990.2 | 9359.7 | 7379.1 | 5040.6 | 799.3 | 6688.5 | 799.3 | 6579.8 | 799.3
14.5 | 5999.4 | 7704.2 | 6851.8 | 4799.5 | 7499.2 | 6163.3 | 9630.2 | 7595.5 | 5185.2 | 814.2 | 6890 | 814.2 | 6781.3 | 814.2
14.75 | 5938.2 | 7700.5 | 6819.4 | 4750.6 | 7422.8 | 6160.4 | 9625.6 | 7589.1 | 5241 | 697.2 | 7003.3 | 697.2 | 6891.9 | 697.2
15 | 5939.3 | 7759.3 | 6849.3 | 4751.5 | 7424.2 | 6207.4 | 9699.1 | 7647.7 | 5323.8 | 615.5 | 7143.8 | 615.5 | 7032.2 | 615.5
15.25 | 6749.4 | 8627.3 | 7688.3 | 5399.5 | 8436.7 | 6901.9 | 10784.1 | 7772.3 | 5375.3 | 1374.1 | 7253.2 | 1374.1 | 7137.5 | 634.9
15.5 | 6349.9 | 8287.2 | 7318.6 | 5079.9 | 7937.4 | 6629.7 | 10359 | 8158.4 | 5638.5 | 711.5 | 7575.7 | 711.5 | 7447 | 711.5
15.75 | 6270.4 | 8268.7 | 7269.6 | 5016.3 | 7838 | 6615 | 10335.9 | 8140 | 5719.9 | 550.6 | 7718.2 | 550.6 | 7589.4 | 550.6
16 | 6416.4 | 8476.1 | 7446.3 | 5133.2 | 8020.6 | 6780.9 | 10595.2 | 8347.4 | 5805.9 | 610.5 | 7865.6 | 610.5 | 7736.9 | 610.5
16.25 | 6502.5 | 8623.9 | 7563.2 | 5202 | 8128.1 | 6899.1 | 10779.8 | 8495.1 | 5903.2 | 599.2 | 8024.6 | 599.2 | 7895.9 | 599.2
16.5 | 6590.2 | 8773.9 | 7682.1 | 5272.2 | 8237.8 | 7019.1 | 10967.4 | 8645.2 | 6003.7 | 586.5 | 8187.4 | 586.5 | 8058.6 | 586.5
16.75 | 6353.2 | 8599.5 | 7476.4 | 5082.6 | 7941.5 | 6879.6 | 10749.4 | 8368.1 | 6085.7 | 267.5 | 8332 | 267.5 | 8203.2 | 164.9
17 | 6909.2 | 9218.3 | 8063.8 | 5527.3 | 8636.5 | 7374.7 | 11522.9 | 9086.3 | 6176.9 | 732.3 | 8486.1 | 732.3 | 8354.1 | 732.3
17.25 | 6806.6 | 9179.2 | 7992.9 | 5445.3 | 8508.3 | 7343.4 | 11474 | 8810.3 | 6277.9 | 528.7 | 8650.5 | 528.7 | 8517.9 | 292.4
17.5 | 7014.2 | 9451.2 | 8232.7 | 5611.4 | 8767.8 | 7560.9 | 11813.9 | 9316 | 6415.4 | 598.8 | 8852.4 | 598.8 | 8717.2 | 598.8
17.75 | 7142.6 | 9644.4 | 8393.5 | 5714.1 | 8928.3 | 7715.6 | 12055.5 | 9506.2 | 6445.2 | 697.4 | 8947 | 697.4 | 8808.8 | 697.4
18 | 7231.4 | 9798.4 | 8514.9 | 5785.1 | 9039.2 | 7838.7 | 12247.9 | 9660.2 | 6564.8 | 666.6 | 9131.7 | 666.6 | 8993.5 | 666.6
18.25 | 7285.1 | 9917.7 | 8601.4 | 5828.1 | 9106.4 | 7934.1 | 12397.1 | 9779.5 | 6651.7 | 633.4 | 9284.3 | 633.4 | 9146.1 | 633.4
18.5 | 7443.1 | 10141.8 | 8792.4 | 5954.5 | 9303.9 | 8113.4 | 12677.2 | 10002.9 | 6774.6 | 668.5 | 9473.3 | 668.5 | 9334.4 | 668.5
18.75 | 8130.4 | 10895.7 | 9513.1 | 6504.3 | 10163 | 8716.6 | 13619.7 | 10753.6 | 6861.4 | 1269 | 9626.7 | 1269 | 9484.6 | 1269
19 | 8629.8 | 11464.6 | 10047.2 | 6903.8 | 10787.2 | 9171.7 | 14330.8 | 11322.5 | 7353 | 1276.7 | 10187.9 | 1276.7 | 10045.8 | 1276.7
19.25 | 9113.4 | 12024.7 | 10569.1 | 7290.7 | 11391.8 | 9619.8 | 15030.9 | 11882.7 | 7882 | 1231.5 | 10793.3 | 1231.5 | 10651.2 | 1231.5
19.5 | 9749 | 12744.3 | 11246.6 | 7799.2 | 12186.3 | 10195.4 | 15930.3 | 12602.2 | 8632.1 | 1117 | 11627.3 | 1117 | 11485.2 | 1117
19.75 | 10305.8 | 13393.2 | 11849.5 | 8244.6 | 12882.2 | 10714.6 | 16741.5 | 13251.1 | 9138.1 | 1167.7 | 12225.6 | 1167.7 | 12083.5 | 1167.7
20 | 10644 | 13829.4 | 12236.7 | 8515.2 | 13305 | 11063.5 | 17286.7 | 13687.3 | 9622 | 1021.9 | 12807.5 | 1021.9 | 12665.4 | 1021.9
20.25 | 11144.2 | 14432 | 12788.1 | 8915.4 | 13930.2 | 11545.6 | 18040 | 14288.8 | 9902.5 | 1241.6 | 13190.4 | 1241.6 | 13047.2 | 1241.6
20.5 | 11603.9 | 14997.4 | 13300.7 | 9283.1 | 14504.9 | 11997.9 | 18746.8 | 14854.2 | 10273.8 | 1330.1 | 13667.3 | 1330.1 | 13524.1 | 1330.1
20.75 | 13305.9 | 16810.6 | 15058.2 | 10644.7 | 16632.4 | 13448.5 | 21013.2 | 16667.4 | 10725.8 | 2580.1 | 14230.4 | 2580.1 | 14087.3 | 2580.1
21 | 12468.6 | 16091.3 | 14280 | 9974.9 | 15585.8 | 12873 | 20114.1 | 15948.1 | 11343.5 | 1125.1 | 14966.2 | 1125.1 | 14823 | 1125.1
21.25 | 14118.7 | 17866.8 | 15992.7 | 11295 | 17648.4 | 14293.4 | 22333.5 | 17723.6 | 11887.7 | 2231 | 15635.8 | 2231 | 15492.6 | 2231
21.5 | 13835.6 | 17719.3 | 15777.5 | 11068.5 | 17294.5 | 14175.5 | 22149.2 | 17576.2 | 12619.1 | 1216.5 | 16502.8 | 1216.5 | 16359.6 | 1216.5
21.75 | 14200.9 | 18225.6 | 16213.2 | 11360.7 | 17751.1 | 14580.4 | 22781.9 | 18082.4 | 12921.2 | 1279.7 | 16945.9 | 1279.7 | 16802.7 | 1279.7
22 | 16201.2 | 20370.5 | 18285.9 | 12961 | 20251.5 | 16296.4 | 25463.1 | 20227.3 | 13302.5 | 2898.8 | 17471.7 | 2898.8 | 17328.6 | 2898.8
22.25 | 15574.9 | 19895.4 | 17735.1 | 12459.9 | 19468.6 | 15916.3 | 24869.3 | 19752.2 | 13981.6 | 1593.3 | 18302.1 | 1593.3 | 18158.9 | 1593.3
22.5 | 16133.9 | 20614.8 | 18374.3 | 12907.1 | 20167.4 | 16491.8 | 25768.5 | 20471.6 | 14505.1 | 1628.8 | 18985.9 | 1628.8 | 18842.8 | 1628.8
22.75 | 21189.8 | 25836.7 | 23513.2 | 16951.8 | 26487.2 | 20669.3 | 32295.8 | 21839.1 | 14978 | 6211.8 | 19624.9 | 6211.8 | 19453.3 | 2385.8
23 | 31059.2 | 35889.9 | 33474.6 | 24847.4 | 38824 | 28711.9 | 44862.4 | 24825.4 | 15660.4 | 15398.8 | 20491.1 | 15398.8 | 19730.1 | 5095.3
23.25 | 30671.2 | 35718 | 33194.6 | 24537 | 38339 | 28574.4 | 44647.5 | 24822.7 | 16281 | 14390.2 | 21327.8 | 14390.2 | 19996.1 | 4826.6
23.5 | 29513.6 | 34804.8 | 32159.2 | 23610.9 | 36892 | 27843.8 | 43505.9 | 24604.4 | 16993.8 | 12519.8 | 22284.9 | 12519.8 | 20297 | 4307.4
23.75 | 36982.8 | 42545.3 | 39764 | 29586.3 | 46228.5 | 34036.2 | 53181.6 | 26785 | 17648.6 | 19334.3 | 23211 | 19334.3 | 20584.2 | 6200.8
24 | 41328.3 | 47203.2 | 44265.7 | 33062.6 | 51660.3 | 37762.5 | 59004 | 28056.9 | 18694.7 | 22633.5 | 24569.7 | 22633.5 | 20970.7 | 7086.1
24.25 | 35309.4 | 41543.4 | 38426.4 | 28247.5 | 44136.7 | 33234.7 | 51929.2 | 26577.8 | 19469.7 | 15839.7 | 25703.7 | 15839.7 | 21303.4 | 5274.3
24.5 | 39180.8 | 45802.3 | 42491.5 | 31344.6 | 48976 | 36641.8 | 57252.8 | 27790.8 | 20149.2 | 19031.6 | 26770.6 | 19031.6 | 21631.6 | 6159.2
24.75 | 33294.5 | 40332.8 | 36813.7 | 26635.6 | 41618.2 | 32266.2 | 50416 | 26302.6 | 20752.7 | 12541.8 | 27791 | 12541.8 | 21942.4 | 4360.2
25 | 31728.7 | 39195.7 | 35462.2 | 25383 | 39660.9 | 31356.6 | 48994.6 | 25987.1 | 20679.6 | 11049.1 | 28146.6 | 11049.1 | 22057.1 | 3930
25.25 | 26628.1 | 34510.1 | 30569.1 | 21302.5 | 33285.1 | 27608.1 | 43137.6 | 24542.3 | 20264.6 | 6363.5 | 28146.6 | 6363.5 | 22057.1 | 2485.2
25.5 | 22099 | 30380.7 | 26239.9 | 17679.2 | 27623.8 | 24304.6 | 37975.9 | 23097.5 | 19864.9 | 2234.1 | 28146.6 | 2234.1 | 22057.1 | 1040.4
25.75 | 21061.6 | 29924.5 | 25493.1 | 16849.3 | 26327 | 23939.6 | 37405.6 | 22754.3 | 20872.7 | 189 | 29735.5 | 189 | 22565.4 | 189
26 | 37626.7 | 46916.5 | 42271.6 | 30101.4 | 47033.4 | 37533.2 | 58645.6 | 39422.9 | 21359.7 | 16267 | 30649.5 | 16267 | 23155.9 | 16267
26.25 | 34309.6 | 44054.8 | 39182.2 | 27447.7 | 42887 | 35243.9 | 55068.6 | 36435.9 | 22831.3 | 11478.3 | 32576.6 | 11478.3 | 24957.7 | 11478.3
26.5 | 33070.4 | 43344.7 | 38207.5 | 26456.3 | 41338 | 34675.7 | 54180.9 | 35725.8 | 25720.5 | 7349.9 | 35994.8 | 7349.9 | 28375.9 | 7349.9
26.75 | 32668.4 | 43513.2 | 38090.8 | 26134.7 | 40835.5 | 34810.5 | 54391.5 | 35894.3 | 26863 | 5805.4 | 37707.7 | 5805.4 | 30088.8 | 5805.4
27 | 29915.7 | 41344.6 | 35630.1 | 23932.5 | 37394.6 | 33075.7 | 51680.8 | 33725.7 | 28066.4 | 1849.2 | 39495.4 | 1849.2 | 31876.5 | 1849.2
27.25 | 29851.9 | 41861.3 | 35856.6 | 23881.5 | 37314.9 | 33489.1 | 52326.7 | 34242.4 | 28258.2 | 1593.8 | 40267.6 | 1593.8 | 32648.7 | 1593.8
27.5 | 29422.7 | 42001.2 | 35712 | 23538.2 | 36778.4 | 33601 | 52501.6 | 34382.3 | 28244.7 | 1178.1 | 40823.2 | 1178.1 | 33204.3 | 1178.1
27.75 | 29186.2 | 42319.3 | 35752.8 | 23349 | 36482.8 | 33855.5 | 52899.1 | 34700.4 | 28062.9 | 1123.3 | 41196 | 1123.3 | 33577.1 | 1123.3
28 | 28925.1 | 42598.3 | 35761.7 | 23140.1 | 36156.4 | 34078.6 | 53247.8 | 34979.3 | 27872.9 | 1052.2 | 41546 | 1052.2 | 33927.1 | 1052.2
28.25 | 28503.9 | 42702.4 | 35603.2 | 22803.1 | 35629.9 | 34161.9 | 53378 | 35083.5 | 27613 | 890.9 | 41811.5 | 890.9 | 34192.6 | 890.9
28.5 | 28058.4 | 42767.6 | 35413 | 22446.7 | 35073 | 34214.1 | 53459.6 | 33246.1 | 27348.5 | 709.9 | 42057.8 | 709.9 | 19376.3 | 13869.8
28.75 | 29630.8 | 44841 | 37235.9 | 23704.6 | 37038.4 | 35872.8 | 56051.2 | 37218.3 | 27687.8 | 1942.9 | 42898.1 | 1942.9 | 35275.4 | 1942.9
29 | 30316.4 | 46022.4 | 38169.4 | 24253.1 | 37895.5 | 36817.9 | 57527.9 | 38399.7 | 27763.9 | 2552.5 | 43469.8 | 2552.5 | 35847.2 | 2552.5
29.25 | 39535 | 55730.7 | 47632.8 | 31628 | 49418.7 | 44584.5 | 69663.4 | 40449.6 | 27908.7 | 11626.3 | 44104.4 | 11626.3 | 36239.7 | 4209.8
29.5 | 41174.4 | 57869.3 | 49521.9 | 32939.5 | 51468 | 46295.5 | 72336.7 | 41128.3 | 28353.2 | 12821.3 | 45048.1 | 12821.3 | 36553.3 | 4575
29.75 | 39249.1 | 56459.7 | 47854.4 | 31399.3 | 49061.4 | 45167.7 | 70574.6 | 47711.5 | 29335.9 | 9913.3 | 46546.4 | 9913.3 | 37798.2 | 9913.3
30 | 42260.3 | 60016.1 | 51138.2 | 33808.2 | 52825.4 | 48012.9 | 75020.1 | 51097.5 | 30685.6 | 11574.7 | 48441.4 | 11574.7 | 39522.8 | 11574.7
30.25 | 46579.8 | 64943.8 | 55761.8 | 37263.8 | 58224.7 | 51955 | 81179.7 | 56025.1 | 33308.9 | 13270.9 | 51672.8 | 13270.9 | 42754.2 | 13270.9
30.5 | 55770.8 | 74812.9 | 65291.9 | 44616.6 | 69713.5 | 59850.3 | 93516.1 | 52385.7 | 35669.4 | 20101.4 | 54711.5 | 20101.4 | 45690.1 | 6695.5
30.75 | 60103.4 | 79881.7 | 69992.5 | 48082.7 | 75129.2 | 63905.4 | 99852.1 | 70350.4 | 37202 | 22901.3 | 56980.4 | 22901.3 | 47449 | 22901.3
31 | 48341.1 | 68898.5 | 58619.8 | 38672.9 | 60426.4 | 55118.8 | 86123.1 | 52022.8 | 36753.6 | 11587.5 | 57311 | 11587.5 | 47779.6 | 4243.2
31.25 | 42675.2 | 63986.3 | 53330.8 | 34140.2 | 53344.1 | 51189 | 79982.8 | 50462.8 | 35999.9 | 6675.3 | 57311 | 6675.3 | 47779.6 | 2683.2
31.5 | 37615 | 59655.1 | 48635.1 | 30092 | 47018.8 | 47724.1 | 74568.9 | 48902.9 | 35270.8 | 2344.2 | 57311 | 2344.2 | 47779.6 | 1123.3
31.75 | 41299.7 | 65127.3 | 53213.5 | 33039.8 | 51624.7 | 52101.8 | 81409.1 | 55596 | 41099 | 200.7 | 64926.6 | 200.7 | 55395.3 | 200.7
32 | 53348.5 | 78113.2 | 65730.8 | 42678.8 | 66685.6 | 62490.5 | 97641.5 | 68404 | 41650.7 | 11697.8 | 66415.4 | 11697.8 | 56706.2 | 11697.8
32.25 | 56531.1 | 82291 | 69411 | 45224.9 | 70663.9 | 65832.8 | 102863.7 | 72581.8 | 45189 | 11342.1 | 70948.9 | 11342.1 | 61239.8 | 11342.1
32.5 | 50617.6 | 77443.4 | 64030.5 | 40494.1 | 63272 | 61954.7 | 96804.3 | 67734.3 | 47730.2 | 2887.4 | 74556 | 2887.4 | 64846.8 | 2887.4
32.75 | 52693.7 | 80600.6 | 66647.1 | 42155 | 65867.2 | 64480.5 | 100750.7 | 70891.4 | 48714 | 3979.7 | 76620.8 | 3979.7 | 66911.7 | 3979.7
33 | 51801.3 | 80791.9 | 66296.6 | 41441.1 | 64751.6 | 64633.5 | 100989.9 | 71082.8 | 49835.8 | 1965.5 | 78826.4 | 1965.5 | 69117.2 | 1965.5
33.25 | 52724.5 | 82785.7 | 67755.1 | 42179.6 | 65905.6 | 66228.6 | 103482.2 | 73076.6 | 49978.7 | 2745.8 | 80039.9 | 2745.8 | 70330.8 | 2745.8
33.5 | 52493.7 | 83610.8 | 68052.2 | 41994.9 | 65617.1 | 66888.6 | 104513.4 | 73901.6 | 50570.7 | 1923 | 81687.8 | 1923 | 71978.6 | 1923
33.75 | 54399.6 | 86559.9 | 70479.7 | 43519.7 | 67999.5 | 69247.9 | 108199.9 | 76850.8 | 51207.8 | 3191.8 | 83368.1 | 3191.8 | 73658.9 | 3191.8
34 | 56080.9 | 89281 | 72681 | 44864.8 | 70101.2 | 71424.8 | 111601.3 | 79571.9 | 52589.3 | 3491.6 | 85789.4 | 3491.6 | 76080.2 | 3491.6
34.25 | 59040.9 | 93288.5 | 76164.7 | 47232.7 | 73801.1 | 74630.8 | 116610.7 | 83579.4 | 54213.5 | 4827.4 | 88461.1 | 4827.4 | 78752 | 4827.4
34.5 | 62008.2 | 97330.2 | 79669.2 | 49606.6 | 77510.2 | 77864.2 | 121662.8 | 87621 | 56956.1 | 5052.1 | 92278.1 | 5052.1 | 82568.9 | 5052.1
34.75 | 67447.3 | 103886.1 | 85666.7 | 53957.8 | 84309.1 | 83108.9 | 129857.6 | 94176.9 | 59345 | 8102.3 | 95783.8 | 8102.3 | 86074.7 | 8102.3
35 | 68598.4 | 106197.8 | 87398.1 | 54878.7 | 85748 | 84958.2 | 132747.2 | 96488.6 | 62123.3 | 6475 | 99722.8 | 6475 | 90013.6 | 6475
35.25 | 71156.9 | 109965.3 | 90561.1 | 56925.6 | 88946.2 | 87972.3 | 137456.7 | 100256.2 | 64366.5 | 6790.5 | 103174.9 | 6790.5 | 93465.7 | 6790.5
35.5 | 78266.7 | 118322.9 | 98294.8 | 62613.4 | 97833.4 | 94658.3 | 147903.6 | 108613.7 | 66802.9 | 11463.8 | 106859.1 | 11463.8 | 97149.9 | 11463.8
35.75 | 83746.6 | 125128.8 | 104437.7 | 66997.3 | 104683.3 | 100103 | 156411 | 115419.6 | 70313.4 | 13433.2 | 111695.6 | 13433.2 | 101986.4 | 13433.2
36 | 91040.2 | 133854.5 | 112447.3 | 72832.2 | 113800.2 | 107083.6 | 167318.1 | 124145.3 | 73909.7 | 17130.5 | 116724 | 17130.5 | 107014.8 | 17130.5
36.25 | 83126.1 | 127452.1 | 105289.1 | 66500.8 | 103907.6 | 101961.7 | 159315.1 | 117742.9 | 76055.2 | 7070.8 | 120381.2 | 7070.8 | 110672.1 | 7070.8
36.5 | 92647.8 | 138549.6 | 115598.7 | 74118.2 | 115809.8 | 110839.7 | 173187 | 128840.4 | 80464.9 | 12182.9 | 126366.7 | 12182.9 | 116657.5 | 12182.9
36.75 | 93528.9 | 141108.7 | 117318.8 | 74823.1 | 116911.2 | 112886.9 | 176385.8 | 131399.5 | 85155.8 | 8373.1 | 132735.5 | 8373.1 | 123026.4 | 8373.1
37 | 97453.8 | 146818.2 | 122136 | 77963.1 | 121817.3 | 117454.5 | 183522.7 | 137109 | 89883.1 | 7570.7 | 139247.5 | 7570.7 | 129538.3 | 7570.7
37.25 | 99978.4 | 151215.6 | 125597 | 79982.8 | 124973.1 | 120972.5 | 189019.5 | 141506.4 | 92709.8 | 7268.6 | 143946.9 | 7268.6 | 134237.8 | 7268.6
37.5 | 107233.5 | 160389.8 | 133811.6 | 85786.8 | 134041.9 | 128311.8 | 200487.2 | 150680.6 | 95601.8 | 11631.7 | 148758.1 | 11631.7 | 139048.9 | 11631.7
37.75 | 112610.8 | 167798 | 140204.4 | 90088.7 | 140763.5 | 134238.4 | 209747.5 | 158088.9 | 100725.7 | 11885.1 | 155912.9 | 11885.1 | 146203.7 | 11885.1
38 | 117761.1 | 175131.3 | 146446.2 | 94208.8 | 147201.3 | 140105 | 218914.1 | 165422.1 | 106106.7 | 11654.3 | 163477 | 11654.3 | 153767.8 | 11654.3
38.25 | 123405.9 | 183089.9 | 153247.9 | 98724.7 | 154257.3 | 146471.9 | 228862.3 | 173380.7 | 110097.6 | 13308.3 | 169781.6 | 13308.3 | 160072.4 | 13308.3
38.5 | 121075 | 183175.2 | 152125.1 | 96860 | 151343.8 | 146540.2 | 228969 | 169178.7 | 113780.9 | 7294.1 | 175881.1 | 7294.1 | 166171.9 | 3006.8
38.75 | 115558.4 | 180084.5 | 147821.4 | 92446.7 | 144448 | 144067.6 | 225105.6 | 151791.6 | 111354.9 | 4203.5 | 175881.1 | 4203.5 | 87118.2 | 64673.4
39 | 110471.2 | 177357.7 | 143914.5 | 88377 | 138089 | 141886.2 | 221697.2 | 114193 | 108994.6 | 1476.7 | 175881.1 | 1476.7 | 87118.2 | 27074.8
39.25 | 118579.6 | 188777.1 | 153678.3 | 94863.6 | 148224.4 | 151021.7 | 235971.4 | 109626.5 | 117775 | 804.5 | 187972.6 | 804.5 | 93287.9 | 16338.6
39.5 | 133463.7 | 206213.5 | 169838.6 | 106770.9 | 166829.6 | 164970.8 | 257766.9 | 196303.8 | 117745.6 | 15718 | 190495.5 | 15718 | 180585.8 | 15718

## SRD WTG-22
Depth (m) | SRD AH-FF (kN) | SRD AH-NFF (kN) | SRD MEAN (kN) | SRD AH-FF-LB (kN) | SRD AH-FF-UB (kN) | SRD AH-NFF-LB (kN) | SRD AH-NFF-UB (kN) | Static Cap (kN) | Shaft AH-FF (kN) | Tip AH-FF (kN) | Shaft AH-NFF (kN) | Tip AH-NFF (kN) | Shaft SC (kN) | Tip SC (kN)
0.5 | 94.6 | 95.1 | 94.8 | 75.7 | 118.2 | 76.1 | 118.9 | 95.1 | 25.3 | 69.2 | 25.9 | 69.2 | 25.9 | 69.2
0.75 | 106.8 | 108 | 107.4 | 85.5 | 133.5 | 86.4 | 135 | 108 | 37.6 | 69.2 | 38.8 | 69.2 | 38.8 | 69.2
1 | 125.4 | 127.4 | 126.4 | 100.3 | 156.7 | 101.9 | 159.3 | 127.4 | 56.1 | 69.2 | 58.2 | 69.2 | 58.2 | 69.2
1.25 | 96.1 | 99.2 | 97.6 | 76.9 | 120.1 | 79.3 | 124 | 85 | 63.5 | 32.6 | 66.5 | 32.6 | 66.5 | 18.5
1.5 | 162.4 | 166.5 | 164.5 | 129.9 | 203 | 133.2 | 208.2 | 166.6 | 71.9 | 90.5 | 76 | 90.5 | 76 | 90.5
1.75 | 201.8 | 207.2 | 204.5 | 161.5 | 252.3 | 165.7 | 259 | 207.2 | 95.5 | 106.4 | 100.8 | 106.4 | 100.8 | 106.4
2 | 232.4 | 239.3 | 235.8 | 185.9 | 290.5 | 191.4 | 299.1 | 239.3 | 122 | 110.4 | 128.8 | 110.4 | 128.8 | 110.4
2.25 | 280.7 | 289.2 | 285 | 224.5 | 350.8 | 231.4 | 361.6 | 289.3 | 147.6 | 133.1 | 156.2 | 133.1 | 156.2 | 133.1
2.5 | 368.1 | 378.8 | 373.4 | 294.5 | 460.2 | 303 | 473.4 | 378.8 | 183.9 | 184.2 | 194.6 | 184.2 | 194.6 | 184.2
2.75 | 452.9 | 466.1 | 459.5 | 362.4 | 566.2 | 372.9 | 582.6 | 464.2 | 219 | 234 | 232.1 | 234 | 230.2 | 234
3 | 481 | 497.3 | 489.1 | 384.8 | 601.2 | 397.8 | 621.6 | 495.2 | 274.6 | 206.4 | 290.9 | 206.4 | 288.8 | 206.4
3.25 | 401.2 | 421 | 411.1 | 321 | 501.5 | 336.8 | 526.3 | 373.8 | 302 | 99.2 | 321.8 | 99.2 | 319.3 | 54.5
3.5 | 548.8 | 572.4 | 560.6 | 439 | 686 | 457.9 | 715.5 | 569.2 | 327.9 | 220.9 | 351.5 | 220.9 | 348.3 | 220.9
3.75 | 572.8 | 600.5 | 586.6 | 458.2 | 716 | 480.4 | 750.6 | 597.2 | 367.7 | 205 | 395.5 | 205 | 392.2 | 205
4 | 602.7 | 634.9 | 618.8 | 482.2 | 753.4 | 507.9 | 793.6 | 631 | 387.3 | 215.4 | 419.5 | 215.4 | 415.6 | 215.4
4.25 | 659.5 | 696.4 | 678 | 527.6 | 824.4 | 557.1 | 870.5 | 692.3 | 424.4 | 235.1 | 461.3 | 235.1 | 457.2 | 235.1
4.5 | 549.9 | 591.8 | 570.8 | 439.9 | 687.4 | 473.4 | 739.7 | 538.9 | 439 | 110.9 | 480.8 | 110.9 | 475.8 | 63.1
4.75 | 592.1 | 639.2 | 615.7 | 473.7 | 740.2 | 511.3 | 799 | 586.3 | 480.6 | 111.6 | 527.6 | 111.6 | 522.3 | 64
5 | 722.5 | 775.1 | 748.8 | 578 | 903.2 | 620 | 968.8 | 663.4 | 505.3 | 217.2 | 557.8 | 217.2 | 550.8 | 112.6
5.25 | 817.4 | 875.9 | 846.6 | 653.9 | 1021.8 | 700.7 | 1094.8 | 868.7 | 566 | 251.4 | 624.5 | 251.4 | 617.3 | 251.4
5.5 | 846.4 | 911.2 | 878.8 | 677.1 | 1058 | 728.9 | 1139 | 903.4 | 591.2 | 255.3 | 655.9 | 255.3 | 648.1 | 255.3
5.75 | 908 | 979.3 | 943.7 | 726.4 | 1135 | 783.5 | 1224.2 | 971.3 | 634 | 274 | 705.3 | 274 | 697.3 | 274
6 | 769.8 | 848.1 | 808.9 | 615.8 | 962.2 | 678.5 | 1060.1 | 794.4 | 658.3 | 111.5 | 736.6 | 111.5 | 727.7 | 66.6
6.25 | 775.7 | 861 | 818.4 | 620.6 | 969.6 | 688.8 | 1076.3 | 807.4 | 665.4 | 110.3 | 750.7 | 110.3 | 740.9 | 66.5
6.5 | 789.9 | 882.2 | 836 | 631.9 | 987.4 | 705.8 | 1102.7 | 823 | 669.8 | 120.1 | 762.1 | 120.1 | 751.1 | 71.8
6.75 | 1025.8 | 1125.4 | 1075.6 | 820.7 | 1282.3 | 900.3 | 1406.8 | 1112.3 | 747.5 | 278.3 | 847.1 | 278.3 | 834 | 278.3
7 | 1186.6 | 1294.3 | 1240.4 | 949.2 | 1483.2 | 1035.4 | 1617.9 | 1280.2 | 801 | 385.6 | 908.7 | 385.6 | 894.6 | 385.6
7.25 | 1242.9 | 1359.3 | 1301.1 | 994.4 | 1553.7 | 1087.4 | 1699.1 | 1343.5 | 883.8 | 359.1 | 1000.2 | 359.1 | 984.4 | 359.1
7.5 | 1272.3 | 1398.3 | 1335.3 | 1017.8 | 1590.4 | 1118.6 | 1747.8 | 1381.8 | 949.2 | 323.1 | 1075.1 | 323.1 | 1058.7 | 323.1
7.75 | 1135.1 | 1271.1 | 1203.1 | 908.1 | 1418.8 | 1016.8 | 1588.8 | 1207 | 1012.5 | 122.5 | 1148.5 | 122.5 | 1131.7 | 75.3
8 | 1407.1 | 1553.4 | 1480.3 | 1125.7 | 1758.9 | 1242.7 | 1941.8 | 1535.2 | 1029.2 | 377.9 | 1175.5 | 377.9 | 1157.3 | 377.9
8.25 | 1438.1 | 1595.1 | 1516.6 | 1150.5 | 1797.7 | 1276.1 | 1993.9 | 1576.3 | 1078.8 | 359.3 | 1235.8 | 359.3 | 1216.9 | 359.3
8.5 | 1302 | 1470.1 | 1386 | 1041.6 | 1627.5 | 1176.1 | 1837.6 | 1377.5 | 1126.1 | 175.9 | 1294.1 | 175.9 | 1274.1 | 103.4
8.75 | 1593.8 | 1773.3 | 1683.6 | 1275.1 | 1992.3 | 1418.7 | 2216.7 | 1752.3 | 1177.7 | 416.1 | 1357.2 | 416.1 | 1336.2 | 416.1
9 | 1636.3 | 1827.7 | 1732 | 1309 | 2045.3 | 1462.2 | 2284.7 | 1806.6 | 1264.2 | 372 | 1455.7 | 372 | 1434.6 | 372
9.25 | 1530.6 | 1734.8 | 1632.7 | 1224.5 | 1913.2 | 1387.8 | 2168.4 | 1629.5 | 1329.6 | 201 | 1533.8 | 201 | 1512.3 | 117.2
9.5 | 1752 | 1969.3 | 1860.7 | 1401.6 | 2190 | 1575.5 | 2461.7 | 1946.7 | 1389.5 | 362.5 | 1606.8 | 362.5 | 1584.2 | 362.5
9.75 | 1876.6 | 2107.5 | 1992 | 1501.3 | 2345.7 | 1686 | 2634.4 | 2083.9 | 1472.4 | 404.2 | 1703.4 | 404.2 | 1679.7 | 404.2
10 | 2070.8 | 2316.4 | 2193.6 | 1656.6 | 2588.5 | 1853.1 | 2895.5 | 2291.8 | 1563.9 | 506.9 | 1809.5 | 506.9 | 1784.9 | 506.9
10.25 | 1824.6 | 2085.6 | 1955.1 | 1459.7 | 2280.8 | 1668.5 | 2607 | 1989.4 | 1644.1 | 180.5 | 1905.2 | 180.5 | 1880.3 | 109.1
10.5 | 2491.7 | 2768.6 | 2630.2 | 1993.4 | 3114.7 | 2214.9 | 3460.7 | 2738.7 | 1707.9 | 783.9 | 1984.7 | 783.9 | 1954.8 | 783.9
10.75 | 2605.8 | 2899.7 | 2752.8 | 2084.7 | 3257.3 | 2319.8 | 3624.6 | 2843.8 | 1825.6 | 780.2 | 2119.4 | 780.2 | 2063.5 | 780.2
11 | 2962.9 | 3277.1 | 3120 | 2370.3 | 3703.6 | 2621.7 | 4096.4 | 3221.2 | 2122 | 840.9 | 2436.3 | 840.9 | 2380.3 | 840.9
11.25 | 2767.4 | 3104.9 | 2936.2 | 2213.9 | 3459.3 | 2483.9 | 3881.1 | 3042.2 | 2272.7 | 494.7 | 2610.2 | 494.7 | 2547.6 | 494.7
11.5 | 2849.6 | 3211.7 | 3030.7 | 2279.7 | 3562 | 2569.3 | 4014.6 | 3147.4 | 2379.9 | 469.8 | 2741.9 | 469.8 | 2677.6 | 469.8
11.75 | 2917.7 | 3304.9 | 3111.3 | 2334.2 | 3647.1 | 2643.9 | 4131.1 | 3240.3 | 2455.2 | 462.5 | 2842.3 | 462.5 | 2777.8 | 462.5
12 | 3257.1 | 3669.9 | 3463.5 | 2605.7 | 4071.3 | 2935.9 | 4587.4 | 3234.3 | 2534.1 | 722.9 | 2947 | 722.9 | 2878.1 | 356.2
12.25 | 3295.7 | 3735.3 | 3515.5 | 2636.5 | 4119.6 | 2988.2 | 4669.1 | 3658.1 | 2703.7 | 592 | 3143.3 | 592 | 3066.1 | 592
12.5 | 3147.3 | 3615.1 | 3381.2 | 2517.9 | 3934.2 | 2892.1 | 4518.9 | 3369.8 | 2774.1 | 373.2 | 3241.9 | 373.2 | 3163.1 | 206.7
12.75 | 3477.4 | 3973.9 | 3725.6 | 2781.9 | 4346.7 | 3179.1 | 4967.4 | 3892.8 | 2901.2 | 576.1 | 3397.8 | 576.1 | 3316.7 | 576.1
13 | 3135.1 | 3661.2 | 3398.2 | 2508.1 | 3918.8 | 2929 | 4576.6 | 3523.7 | 2978 | 157.1 | 3504.2 | 157.1 | 3422.5 | 101.2
13.25 | 3443.9 | 3999.8 | 3721.9 | 2755.1 | 4304.8 | 3199.9 | 4999.8 | 3916.4 | 3000.1 | 443.8 | 3556.1 | 443.8 | 3472.7 | 443.8
13.5 | 3454.7 | 4040.5 | 3747.6 | 2763.7 | 4318.3 | 3232.4 | 5050.6 | 3767.4 | 3037 | 417.7 | 3622.8 | 417.7 | 3537.4 | 230
13.75 | 3735.1 | 4351.5 | 4043.3 | 2988 | 4668.8 | 3481.2 | 5439.3 | 4251.3 | 3179.1 | 556 | 3795.5 | 556 | 3695.3 | 556
14 | 3517 | 4165.9 | 3841.5 | 2813.6 | 4396.2 | 3332.7 | 5207.4 | 3980.5 | 3297.6 | 219.4 | 3946.6 | 219.4 | 3845.2 | 135.3
14.25 | 3543.9 | 4225.5 | 3884.7 | 2835.1 | 4429.9 | 3380.4 | 5281.9 | 4046.6 | 3340.4 | 203.5 | 4022 | 203.5 | 3919.1 | 127.5
14.5 | 3625.7 | 4340.2 | 3983 | 2900.6 | 4532.2 | 3472.2 | 5425.3 | 4134.2 | 3371.8 | 253.9 | 4086.3 | 253.9 | 3980.5 | 153.8
14.75 | 3963.1 | 4710.5 | 4336.8 | 3170.4 | 4953.8 | 3768.4 | 5888.2 | 4602.5 | 3429.7 | 533.4 | 4177.2 | 533.4 | 4069.1 | 533.4
15 | 3876.8 | 4657.8 | 4267.3 | 3101.4 | 4846 | 3726.2 | 5822.3 | 4377.6 | 3486.7 | 390.1 | 4267.7 | 390.1 | 4156.4 | 221.2
15.25 | 5609.1 | 6424.7 | 6016.9 | 4487.3 | 7011.4 | 5139.8 | 8030.9 | 6277.1 | 3646.3 | 1962.8 | 4461.9 | 1962.8 | 4314.3 | 1962.8
15.5 | 5230.5 | 6085.6 | 5658 | 4184.4 | 6538.1 | 4868.5 | 7607 | 5938 | 4103.1 | 1127.4 | 4958.2 | 1127.4 | 4810.6 | 1127.4
15.75 | 5709.6 | 6608 | 6158.8 | 4567.7 | 7137 | 5286.4 | 8260 | 5682.1 | 4295.6 | 1414 | 5193.9 | 1414 | 5029.8 | 652.4
16 | 7129.7 | 8074.7 | 7602.2 | 5703.8 | 8912.2 | 6459.8 | 10093.4 | 7882.3 | 4632.4 | 2497.3 | 5577.4 | 2497.3 | 5384.9 | 2497.3
16.25 | 6693.3 | 7692.6 | 7193 | 5354.6 | 8366.6 | 6154.1 | 9615.7 | 7495.4 | 5084.6 | 1608.7 | 6083.9 | 1608.7 | 5886.8 | 1608.7
16.5 | 6080 | 7138.8 | 6609.4 | 4864 | 7599.9 | 5711 | 8923.5 | 6937.1 | 5354 | 725.9 | 6412.9 | 725.9 | 6211.2 | 725.9
16.75 | 6188.7 | 7309.2 | 6748.9 | 4951 | 7735.9 | 5847.3 | 9136.5 | 7107.5 | 5537.2 | 651.5 | 6657.7 | 651.5 | 6456 | 651.5
17 | 6125.8 | 7308.4 | 6717.1 | 4900.6 | 7657.2 | 5846.8 | 9135.6 | 7104.2 | 5563.2 | 562.6 | 6745.9 | 562.6 | 6541.6 | 562.6
17.25 | 5847.5 | 7092.1 | 6469.8 | 4678 | 7309.4 | 5673.7 | 8865.2 | 6788 | 5590.9 | 256.6 | 6835.5 | 256.6 | 6628.2 | 159.8
17.5 | 6483.4 | 7789.8 | 7136.6 | 5186.7 | 8104.2 | 6231.8 | 9737.2 | 7579 | 5638 | 845.4 | 6944.4 | 845.4 | 6733.6 | 845.4
17.75 | 6287.4 | 7655.8 | 6971.6 | 5029.9 | 7859.3 | 6124.6 | 9569.7 | 7442.3 | 5707.2 | 580.2 | 7075.6 | 580.2 | 6862.1 | 580.2
18 | 6144.8 | 7575.1 | 6859.9 | 4915.8 | 7681 | 6060.1 | 9468.9 | 7181.2 | 5727.1 | 417.7 | 7157.4 | 417.7 | 6939.6 | 241.6
18.25 | 6277.4 | 7769.5 | 7023.4 | 5021.9 | 7846.7 | 6215.6 | 9711.9 | 7549.7 | 5761.7 | 515.7 | 7253.8 | 515.7 | 7034 | 515.7
18.5 | 5937.5 | 7491.2 | 6714.3 | 4750 | 7421.9 | 5992.9 | 9364 | 7217.8 | 5773 | 164.6 | 7326.6 | 164.6 | 7106.2 | 111.7
18.75 | 6310.8 | 7925.3 | 7118.1 | 5048.7 | 7888.5 | 6340.3 | 9906.7 | 7702.5 | 5754.4 | 556.4 | 7368.9 | 556.4 | 7146.1 | 556.4
19 | 5969.7 | 7644.6 | 6807.1 | 4775.7 | 7462.1 | 6115.7 | 9555.8 | 7344.2 | 5755.3 | 214.4 | 7430.2 | 214.4 | 7204.4 | 139.8
19.25 | 5988.9 | 7724 | 6856.5 | 4791.1 | 7486.2 | 6179.2 | 9655 | 7426.4 | 5781.5 | 207.4 | 7516.6 | 207.4 | 7290.1 | 136.3
19.5 | 6051.5 | 7846.4 | 6948.9 | 4841.2 | 7564.3 | 6277.1 | 9808 | 7540.9 | 5826.7 | 224.7 | 7621.6 | 224.7 | 7394.8 | 146.1
19.75 | 6453.9 | 8308.6 | 7381.3 | 5163.2 | 8067.4 | 6646.9 | 10385.7 | 8081 | 5876.9 | 577 | 7731.5 | 577 | 7503.9 | 577
20 | 6486.1 | 8400.4 | 7443.3 | 5188.9 | 8107.7 | 6720.3 | 10500.5 | 8171.4 | 5919 | 567.1 | 7833.3 | 567.1 | 7604.3 | 567.1
20.25 | 6479.2 | 8453 | 7466.1 | 5183.3 | 8099 | 6762.4 | 10566.3 | 8223.2 | 5951 | 528.2 | 7924.9 | 528.2 | 7695.1 | 528.2
20.5 | 6607.4 | 8640.5 | 7624 | 5285.9 | 8259.3 | 6912.4 | 10800.7 | 8408 | 5961.1 | 646.3 | 7994.2 | 646.3 | 7761.7 | 646.3
20.75 | 6635.1 | 8727.5 | 7681.3 | 5308.1 | 8293.9 | 6982 | 10909.4 | 8494.9 | 6063.5 | 571.6 | 8155.9 | 571.6 | 7923.3 | 571.6
21 | 6391.9 | 8543.9 | 7467.9 | 5113.5 | 7989.8 | 6835.1 | 10679.8 | 8212.8 | 6122.1 | 269.7 | 8274.1 | 269.7 | 8040.6 | 172.2
21.25 | 6641.9 | 8853.3 | 7747.6 | 5313.5 | 8302.4 | 7082.6 | 11066.6 | 8401.1 | 6137.7 | 504.2 | 8349.1 | 504.2 | 8110.5 | 290.6
21.5 | 7851.7 | 10123.7 | 8987.7 | 6281.4 | 9814.7 | 8099 | 12654.6 | 9883.2 | 6472.7 | 1379 | 8744.7 | 1379 | 8504.2 | 1379
21.75 | 8337.5 | 10676 | 9506.7 | 6670 | 10421.9 | 8540.8 | 13344.9 | 10435.5 | 7069.4 | 1268.1 | 9407.8 | 1268.1 | 9167.4 | 1268.1
22 | 8583.8 | 10995.5 | 9789.6 | 6867 | 10729.7 | 8796.4 | 13744.4 | 10755 | 7629.3 | 954.5 | 10041 | 954.5 | 9800.5 | 954.5
22.25 | 8623.6 | 11112.6 | 9868.1 | 6898.9 | 10779.5 | 8890.1 | 13890.7 | 10872.1 | 7884.8 | 738.8 | 10373.8 | 738.8 | 10133.3 | 738.8
22.5 | 8357.7 | 10924.4 | 9641.1 | 6686.2 | 10447.1 | 8739.6 | 13655.6 | 10469.6 | 7886.5 | 471.2 | 10453.3 | 471.2 | 10192.3 | 277.3
22.75 | 8185.8 | 10830.3 | 9508 | 6548.7 | 10232.3 | 8664.2 | 13537.8 | 10479.9 | 7932.9 | 252.9 | 10577.4 | 252.9 | 10314.5 | 165.4
23 | 8157.7 | 10879.4 | 9518.5 | 6526.2 | 10197.1 | 8703.5 | 13599.2 | 10517.1 | 7887.4 | 270.3 | 10609.1 | 270.3 | 10342 | 175.1
23.25 | 8421 | 11219.1 | 9820.1 | 6736.8 | 10526.2 | 8975.3 | 14023.9 | 10700.6 | 7855.2 | 565.8 | 10653.4 | 565.8 | 10375.8 | 324.8
23.5 | 8911.4 | 11785.9 | 10348.6 | 7129.1 | 11139.3 | 9428.7 | 14732.3 | 11482.1 | 7918.5 | 993 | 10792.9 | 993 | 10489.2 | 993
23.75 | 9600 | 12552.4 | 11076.2 | 7680 | 12000 | 10041.9 | 15690.5 | 11511.5 | 8153.2 | 1446.8 | 11105.6 | 1446.8 | 10798.6 | 712.9
24 | 9745.2 | 12780.8 | 11263 | 7796.2 | 12181.5 | 10224.6 | 15976 | 12432.7 | 8876.7 | 868.5 | 11912.3 | 868.5 | 11564.2 | 868.5
24.25 | 9916.1 | 13040.6 | 11478.4 | 7932.9 | 12395.1 | 10432.5 | 16300.8 | 12692.5 | 9077 | 839.1 | 12201.5 | 839.1 | 11853.4 | 839.1
24.5 | 10186.7 | 13401 | 11793.9 | 8149.4 | 12733.4 | 10720.8 | 16751.2 | 13051.2 | 9190.6 | 996.1 | 12404.9 | 996.1 | 12055.1 | 996.1
24.75 | 10539.6 | 13844.1 | 12191.8 | 8431.7 | 13174.5 | 11075.2 | 17305.1 | 13490 | 9338.7 | 1200.9 | 12643.1 | 1200.9 | 12289.1 | 1200.9
25 | 12828.9 | 16225.6 | 14527.2 | 10263.1 | 16036.1 | 12980.4 | 20282 | 15818.7 | 9567.6 | 3261.3 | 12964.3 | 3261.3 | 12557.4 | 3261.3
25.25 | 13478.9 | 16976.7 | 15227.8 | 10783.1 | 16848.6 | 13581.4 | 21220.9 | 14768.4 | 10310.5 | 3168.4 | 13808.4 | 3168.4 | 13384 | 1384.4
25.5 | 12072.5 | 15680.7 | 13876.6 | 9658 | 15090.7 | 12544.6 | 19600.9 | 15195.8 | 10772.3 | 1300.3 | 14380.5 | 1300.3 | 13895.5 | 1300.3
25.75 | 13876 | 17600.4 | 15738.2 | 11100.8 | 17345 | 14080.3 | 22000.4 | 17077.4 | 11070.3 | 2805.8 | 14794.6 | 2805.8 | 14271.6 | 2805.8
26 | 14237.6 | 18084.9 | 16161.3 | 11390.1 | 17797 | 14467.9 | 22606.2 | 17551.7 | 11600.5 | 2637.2 | 15447.8 | 2637.2 | 14914.6 | 2637.2
26.25 | 19268.4 | 23244.6 | 21256.5 | 15414.7 | 24085.5 | 18595.7 | 29055.8 | 17921.6 | 11859.4 | 7409 | 15835.6 | 7409 | 15091.7 | 2829.9
26.5 | 25888.8 | 30008.9 | 27948.9 | 20711.1 | 32361 | 24007.2 | 37511.2 | 20001.3 | 12515.2 | 13373.6 | 16635.3 | 13373.6 | 15363 | 4638.4
26.75 | 26954.9 | 31244.8 | 29099.9 | 21563.9 | 33693.7 | 24995.9 | 39056 | 20396.9 | 13209.4 | 13745.5 | 17499.3 | 13745.5 | 15642 | 4754.9
27 | 28571.8 | 33057.2 | 30814.5 | 22857.5 | 35714.8 | 26445.8 | 41321.5 | 20968.6 | 13837.5 | 14734.3 | 18322.9 | 14734.3 | 15920.5 | 5048.1
27.25 | 38543.7 | 43259.9 | 40901.8 | 30835 | 48179.7 | 34607.9 | 54074.9 | 23785 | 14953.1 | 23590.6 | 19669.3 | 23590.6 | 16298.2 | 7486.8
27.5 | 43598.1 | 48606.6 | 46102.3 | 34878.5 | 54497.6 | 38885.3 | 60758.3 | 25184 | 16355.2 | 27242.8 | 21363.8 | 27242.8 | 16727 | 8457
27.75 | 51333.5 | 56694.9 | 54014.2 | 41066.8 | 64166.9 | 45355.9 | 70868.6 | 27249.1 | 17426.5 | 33907 | 22787.8 | 33907 | 17081.3 | 10167.7
28 | 48175.6 | 53914.1 | 51044.9 | 38540.5 | 60219.5 | 43131.3 | 67392.7 | 26554.9 | 17209.3 | 30966.3 | 22947.9 | 30966.3 | 17114.3 | 9440.6
28.25 | 44810.7 | 50911.1 | 47860.9 | 35848.6 | 56013.4 | 40728.9 | 63638.9 | 25797.4 | 16847.4 | 27963.3 | 22947.9 | 27963.3 | 17114.3 | 8683.1
28.5 | 41521.5 | 47969.3 | 44745.4 | 33217.2 | 51901.8 | 38375.4 | 59961.6 | 25040 | 16500 | 25021.4 | 22947.9 | 25021.4 | 17114.3 | 7925.7
28.75 | 38310.6 | 45092 | 41701.3 | 30648.5 | 47888.2 | 36073.6 | 56365.1 | 24282.5 | 16166.4 | 22144.2 | 22947.9 | 22144.2 | 17114.3 | 7168.2
29 | 35181.7 | 42283.6 | 38732.6 | 28145.3 | 43977.1 | 33826.9 | 52854.5 | 23525.1 | 15845.9 | 19335.8 | 22947.9 | 19335.8 | 17114.3 | 6410.7
29.25 | 32139.1 | 39549.1 | 35844.1 | 25711.3 | 40173.9 | 31639.3 | 49436.4 | 22767.6 | 15537.9 | 16601.3 | 22947.9 | 16601.3 | 17114.3 | 5653.3
29.5 | 29188.9 | 36895 | 33042 | 23351.1 | 36486.1 | 29516 | 46118.8 | 22010.1 | 15241.7 | 13947.2 | 22947.9 | 13947.2 | 17114.3 | 4895.8
29.75 | 26338.7 | 34329.6 | 30334.2 | 21071 | 32923.4 | 27463.7 | 42912 | 21252.7 | 14956.9 | 11381.8 | 22947.9 | 11381.8 | 17114.3 | 4138.4
30 | 23599.1 | 31864.1 | 27731.6 | 18879.3 | 29498.9 | 25491.2 | 39830.1 | 20495.2 | 14682.9 | 8916.2 | 22947.9 | 8916.2 | 17114.3 | 3380.9
30.25 | 20985.4 | 29514.1 | 25249.8 | 16788.3 | 26231.8 | 23611.3 | 36892.6 | 19737.8 | 14419.2 | 6566.3 | 22947.9 | 6566.3 | 17114.3 | 2623.4
30.5 | 18521.3 | 27303.9 | 22912.6 | 14817 | 23151.6 | 21843.2 | 34129.9 | 18980.3 | 14165.2 | 4356.1 | 22947.9 | 4356.1 | 17114.3 | 1866
30.75 | 16248.9 | 25276.2 | 20762.5 | 12999.1 | 20311.2 | 20220.9 | 31595.2 | 18222.9 | 13920.6 | 2328.3 | 22947.9 | 2328.3 | 17114.3 | 1108.5
31 | 14269.9 | 23532.9 | 18901.4 | 11415.9 | 17837.4 | 18826.3 | 29416.1 | 17465.4 | 13684.9 | 585 | 22947.9 | 585 | 17114.3 | 351.1
31.25 | 28544.3 | 44316.8 | 36430.5 | 22835.5 | 35680.4 | 35453.4 | 55396 | 23064.6 | 20850 | 7694.3 | 36622.4 | 7694.3 | 20054.9 | 3009.7
31.5 | 28518.8 | 44794.2 | 36656.5 | 22815 | 35648.5 | 35835.4 | 55992.8 | 23263 | 20867.3 | 7651.5 | 37142.7 | 7651.5 | 20262.6 | 3000.5
31.75 | 38826 | 55598.5 | 47212.2 | 31060.8 | 48532.4 | 44478.8 | 69498.1 | 26564.3 | 21274.5 | 17551.4 | 38047 | 17551.4 | 20561.3 | 6003
32 | 48208.7 | 65501.6 | 56855.2 | 38566.9 | 60260.8 | 52401.3 | 81877 | 29284.9 | 22360.6 | 25848.1 | 39653.5 | 25848.1 | 20983 | 8301.9
32.25 | 39839.7 | 57689.6 | 48764.6 | 31871.7 | 49799.6 | 46151.7 | 72112 | 27149.2 | 23092.4 | 16747.3 | 40942.3 | 16747.3 | 21357.5 | 5791.7
32.5 | 36167.1 | 54589.8 | 45378.4 | 28933.6 | 45208.8 | 43671.8 | 68237.2 | 26267.9 | 23689.2 | 12477.8 | 42112 | 12477.8 | 21728.6 | 4539.4
32.75 | 34058 | 53057.6 | 43557.8 | 27246.4 | 42572.5 | 42446.1 | 66322 | 25832.3 | 23919.7 | 10138.4 | 42919.2 | 10138.4 | 22008.3 | 3824.1
33 | 62779.6 | 82366.1 | 72572.8 | 50223.7 | 78474.5 | 65892.9 | 102957.6 | 33875 | 24811 | 37968.6 | 44397.5 | 37968.6 | 22365.1 | 11509.9
33.25 | 58508.8 | 78690 | 68599.4 | 46807.1 | 73136 | 62952 | 98362.6 | 32950.8 | 24216.3 | 34292.6 | 44397.5 | 34292.6 | 22365.1 | 10585.7
33.5 | 54339 | 75087.1 | 64713.1 | 43471.2 | 67923.7 | 60069.7 | 93858.9 | 32026.6 | 23649.3 | 30689.7 | 44397.5 | 30689.7 | 22365.1 | 9661.5
33.75 | 50273 | 71561.7 | 60917.3 | 40218.4 | 62841.2 | 57249.4 | 89452.1 | 31102.4 | 23108.7 | 27164.2 | 44397.5 | 27164.2 | 22365.1 | 8737.3
34 | 46314.6 | 68119 | 57216.8 | 37051.7 | 57893.3 | 54495.2 | 85148.8 | 30178.2 | 22593 | 23721.6 | 44397.5 | 23721.6 | 22365.1 | 7813.1
34.25 | 42469.1 | 64765.5 | 53617.3 | 33975.3 | 53086.4 | 51812.4 | 80956.9 | 29254 | 22101.1 | 20368.1 | 44397.5 | 20368.1 | 22365.1 | 6888.9
34.5 | 38743.3 | 61509.2 | 50126.3 | 30994.6 | 48429.1 | 49207.4 | 76886.5 | 28329.8 | 21631.5 | 17111.8 | 44397.5 | 17111.8 | 22365.1 | 5964.7
34.75 | 35146.3 | 58360.5 | 46753.4 | 28117 | 43932.9 | 46688.4 | 72950.6 | 27405.6 | 21183.2 | 13963 | 44397.5 | 13963 | 22365.1 | 5040.5
35 | 31690.9 | 55333.2 | 43512 | 25352.7 | 39613.6 | 44266.5 | 69166.5 | 26481.4 | 20755.2 | 10935.7 | 44397.5 | 10935.7 | 22365.1 | 4116.4
35.25 | 28395.6 | 52446.8 | 40421.2 | 22716.5 | 35494.6 | 41957.5 | 65558.6 | 25557.2 | 20346.3 | 8049.4 | 44397.5 | 8049.4 | 22365.1 | 3192.2
35.5 | 25289.6 | 49731.5 | 37510.6 | 20231.7 | 31612 | 39785.2 | 62164.4 | 24633 | 19955.5 | 5334.1 | 44397.5 | 5334.1 | 22365.1 | 2268
35.75 | 22424.7 | 47240.1 | 34832.4 | 17939.8 | 28030.9 | 37792.1 | 59050.1 | 23708.8 | 19582.1 | 2842.6 | 44397.5 | 2842.6 | 22365.1 | 1343.8
36 | 19927.3 | 45099.8 | 32513.5 | 15941.8 | 24909.1 | 36079.8 | 56374.7 | 22784.6 | 19225 | 702.3 | 44397.5 | 702.3 | 22365.1 | 419.6
36.25 | 31322.2 | 63302.5 | 47312.3 | 25057.7 | 39152.7 | 50642 | 79128.1 | 26935.6 | 27129.3 | 4192.9 | 59109.6 | 4192.9 | 25073.6 | 1862
36.5 | 35282.4 | 67934.2 | 51608.3 | 28225.9 | 44103 | 54347.4 | 84917.8 | 33814.3 | 30307.7 | 4974.7 | 62959.5 | 4974.7 | 28839.5 | 4974.7
36.75 | 37983.1 | 71352.8 | 54668 | 30386.5 | 47478.8 | 57082.3 | 89191.1 | 37232.9 | 32787.9 | 5195.1 | 66157.7 | 5195.1 | 32037.7 | 5195.1
37 | 41952.6 | 76062.3 | 59007.5 | 33562.1 | 52440.8 | 60849.8 | 95077.8 | 41942.3 | 35173 | 6779.6 | 69282.6 | 6779.6 | 35162.7 | 6779.6
37.25 | 43158.9 | 78042.1 | 60600.5 | 34527.1 | 53948.6 | 62433.7 | 97552.7 | 43922.2 | 38262.7 | 4896.2 | 73145.9 | 4896.2 | 39026 | 4896.2
37.5 | 46137.3 | 81833.6 | 63985.5 | 36909.8 | 57671.6 | 65466.9 | 102292 | 47713.7 | 40961.1 | 5176.1 | 76657.5 | 5176.1 | 42537.5 | 5176.1
37.75 | 49066.6 | 85599 | 67332.8 | 39253.3 | 61333.3 | 68479.2 | 106998.7 | 51479 | 43105.5 | 5961.1 | 79637.8 | 5961.1 | 45517.9 | 5961.1
38 | 50830.8 | 88231.4 | 69531.1 | 40664.6 | 63538.5 | 70585.1 | 110289.2 | 54111.4 | 46170.2 | 4660.6 | 83570.7 | 4660.6 | 49450.8 | 4660.6
38.25 | 52113.9 | 90409.3 | 71261.6 | 41691.1 | 65142.4 | 72327.5 | 113011.7 | 56289.4 | 48024 | 4089.9 | 86319.4 | 4089.9 | 52199.4 | 4089.9
38.5 | 53385.1 | 92585.3 | 72985.2 | 42708.1 | 66731.4 | 74068.2 | 115731.6 | 58465.3 | 49966.8 | 3418.3 | 89167 | 3418.3 | 55047 | 3418.3
38.75 | 55410.5 | 95518 | 75464.3 | 44328.4 | 69263.1 | 76414.4 | 119397.5 | 61398 | 50648 | 4762.5 | 90755.5 | 4762.5 | 56635.6 | 4762.5
39 | 62821.5 | 103849.5 | 83335.5 | 50257.2 | 78526.9 | 83079.6 | 129811.9 | 69729.5 | 53443.2 | 9378.3 | 94471.2 | 9378.3 | 60351.2 | 9378.3

## SRD WTG-23
Depth (m) | SRD AH-FF (kN) | SRD AH-NFF (kN) | SRD MEAN (kN) | SRD AH-FF-LB (kN) | SRD AH-FF-UB (kN) | SRD AH-NFF-LB (kN) | SRD AH-NFF-UB (kN) | Static Cap (kN) | Shaft AH-FF (kN) | Tip AH-FF (kN) | Shaft AH-NFF (kN) | Tip AH-NFF (kN) | Shaft SC (kN) | Tip SC (kN)
0.5 | 35.2 | 35.2 | 35.2 | 28.1 | 43.9 | 28.2 | 44 | 18.1 | 2.7 | 32.5 | 2.7 | 32.5 | 2.3 | 15.8
0.75 | 34.1 | 34.2 | 34.1 | 27.3 | 42.6 | 27.3 | 42.7 | 19.5 | 4.1 | 29.9 | 4.3 | 29.9 | 3.7 | 15.8
1 | 34.7 | 34.9 | 34.8 | 27.7 | 43.3 | 27.9 | 43.6 | 21.9 | 6.4 | 28.3 | 6.6 | 28.3 | 6 | 15.8
1.25 | 35 | 35.3 | 35.1 | 28 | 43.7 | 28.2 | 44.1 | 23.6 | 7.9 | 27 | 8.3 | 27 | 7.7 | 15.8
1.5 | 69.3 | 69.8 | 69.5 | 55.5 | 86.6 | 55.8 | 87.2 | 41.8 | 10.9 | 58.4 | 11.4 | 58.4 | 10.8 | 31
1.75 | 99.9 | 100.5 | 100.2 | 79.9 | 124.9 | 80.4 | 125.6 | 58.1 | 15.7 | 84.2 | 16.3 | 84.2 | 15 | 43.1
2 | 99.3 | 100.2 | 99.8 | 79.5 | 124.2 | 80.2 | 125.2 | 61.3 | 21.1 | 78.2 | 22 | 78.2 | 19.9 | 41.4
2.25 | 98.8 | 100 | 99.4 | 79.1 | 123.5 | 80 | 125 | 64.3 | 26.5 | 72.4 | 27.6 | 72.4 | 24.8 | 39.5
2.5 | 129.6 | 131.2 | 130.4 | 103.7 | 162 | 104.9 | 163.9 | 81.7 | 32.3 | 97.3 | 33.8 | 97.3 | 30.2 | 51.5
2.75 | 121.5 | 123.4 | 122.4 | 97.2 | 151.8 | 98.7 | 154.3 | 81.6 | 38.6 | 82.9 | 40.5 | 82.9 | 35.9 | 45.7
3 | 165.1 | 167.5 | 166.3 | 132.1 | 206.3 | 134 | 209.4 | 105.3 | 45.8 | 119.3 | 48.3 | 119.3 | 42.5 | 62.8
3.25 | 168.8 | 171.9 | 170.4 | 135.1 | 211 | 137.5 | 214.9 | 111.2 | 53.4 | 115.4 | 56.5 | 115.4 | 49.3 | 61.9
3.5 | 178.9 | 182.6 | 180.7 | 143.1 | 223.6 | 146.1 | 228.3 | 120.4 | 61.9 | 117 | 65.6 | 117 | 57 | 63.4
3.75 | 143.5 | 148 | 145.7 | 114.8 | 179.3 | 118.4 | 185 | 107.6 | 67.6 | 75.8 | 72.1 | 75.8 | 63 | 44.6
4 | 184.7 | 190 | 187.3 | 147.7 | 230.8 | 152 | 237.5 | 131.6 | 74.8 | 109.9 | 80.1 | 109.9 | 70.2 | 61.4
4.25 | 180.1 | 186.3 | 183.2 | 144 | 225.1 | 149 | 232.8 | 133.8 | 82.1 | 98 | 88.3 | 98 | 77.4 | 56.4
4.5 | 194.9 | 202 | 198.4 | 155.9 | 243.6 | 161.6 | 252.5 | 145.6 | 90.3 | 104.5 | 97.5 | 104.5 | 85.5 | 60.1
4.75 | 211.5 | 219.7 | 215.6 | 169.2 | 264.3 | 175.7 | 274.6 | 158.1 | 98.2 | 113.3 | 106.4 | 113.3 | 93.3 | 64.8
5 | 205.2 | 214.5 | 209.9 | 164.2 | 256.5 | 171.6 | 268.1 | 160.1 | 106.7 | 98.5 | 116.1 | 98.5 | 101.9 | 58.2
5.25 | 209.6 | 220.1 | 214.9 | 167.7 | 262 | 176.1 | 275.2 | 166.9 | 114.1 | 95.5 | 124.7 | 95.5 | 109.7 | 57.1
5.5 | 222.4 | 234.1 | 228.3 | 177.9 | 278 | 187.3 | 292.7 | 178.2 | 122.4 | 100 | 134.1 | 100 | 118.3 | 59.9
5.75 | 238.7 | 251.8 | 245.3 | 191 | 298.4 | 201.4 | 314.8 | 191.2 | 130.4 | 108.3 | 143.5 | 108.3 | 126.8 | 64.4
6 | 244.1 | 258.6 | 251.3 | 195.3 | 305.2 | 206.9 | 323.2 | 199.2 | 139.1 | 105.1 | 153.5 | 105.1 | 136 | 63.2
6.25 | 256.2 | 272.1 | 264.1 | 204.9 | 320.2 | 217.6 | 340.1 | 210.4 | 147.7 | 108.5 | 163.6 | 108.5 | 145 | 65.4
6.5 | 261.2 | 278.7 | 270 | 209 | 326.6 | 222.9 | 348.3 | 218.6 | 157.4 | 103.9 | 174.8 | 103.9 | 155.1 | 63.5
6.75 | 279.4 | 298.4 | 288.9 | 223.5 | 349.2 | 238.7 | 373 | 233.2 | 166.8 | 112.5 | 185.8 | 112.5 | 164.9 | 68.3
7 | 291.4 | 312.1 | 301.8 | 233.1 | 364.3 | 249.7 | 390.2 | 245.2 | 176.9 | 114.5 | 197.6 | 114.5 | 175.5 | 69.7
7.25 | 320.8 | 343.3 | 332.1 | 256.7 | 401.1 | 274.6 | 429.1 | 265.8 | 186.8 | 134.1 | 209.3 | 134.1 | 185.8 | 79.9
7.5 | 316.9 | 341.3 | 329.1 | 253.5 | 396.2 | 273 | 426.6 | 270.2 | 198.7 | 118.3 | 223 | 118.3 | 197.8 | 72.4
7.75 | 376.6 | 402.9 | 389.7 | 301.3 | 470.8 | 322.3 | 503.6 | 305.9 | 208.2 | 168.4 | 234.4 | 168.4 | 208.1 | 97.8
8 | 335.2 | 363.5 | 349.4 | 268.2 | 419 | 290.8 | 454.4 | 291.9 | 220 | 115.2 | 248.3 | 115.2 | 220.3 | 71.6
8.25 | 344 | 374.4 | 359.2 | 275.2 | 430 | 299.5 | 468 | 302.5 | 229.4 | 114.5 | 259.9 | 114.5 | 230.9 | 71.6
8.5 | 354.2 | 386.8 | 370.5 | 283.3 | 442.7 | 309.4 | 483.5 | 314.3 | 239.9 | 114.3 | 272.5 | 114.3 | 242.5 | 71.8
8.75 | 377.4 | 412.3 | 394.8 | 301.9 | 471.8 | 329.8 | 515.3 | 332.7 | 250 | 127.4 | 284.9 | 127.4 | 253.7 | 79
9 | 388.8 | 426 | 407.4 | 311 | 486 | 340.8 | 532.5 | 345.5 | 261.5 | 127.2 | 298.7 | 127.2 | 266.2 | 79.3
9.25 | 425.7 | 465.4 | 445.5 | 340.6 | 532.2 | 372.3 | 581.7 | 371.5 | 274.9 | 150.8 | 314.5 | 150.8 | 279.7 | 91.8
9.5 | 455.4 | 497.5 | 476.5 | 364.3 | 569.2 | 398 | 621.9 | 394 | 288 | 167.4 | 330.2 | 167.4 | 293.4 | 100.6
9.75 | 465 | 509.8 | 487.4 | 372 | 581.2 | 407.8 | 637.2 | 406.3 | 301.6 | 163.3 | 346.4 | 163.3 | 307.3 | 99
10 | 477.3 | 524.9 | 501.1 | 381.9 | 596.7 | 420 | 656.2 | 420.7 | 317.1 | 160.3 | 364.7 | 160.3 | 322.8 | 97.9
10.25 | 491.1 | 541.6 | 516.3 | 392.9 | 613.9 | 433.3 | 677 | 435.3 | 330.2 | 160.9 | 380.7 | 160.9 | 336.7 | 98.6
10.5 | 504.7 | 558.2 | 531.5 | 403.8 | 630.9 | 446.6 | 697.8 | 450.4 | 344.3 | 160.5 | 397.8 | 160.5 | 351.7 | 98.8
10.75 | 505.5 | 562.1 | 533.8 | 404.4 | 631.9 | 449.7 | 702.6 | 458.6 | 357.5 | 148 | 414.1 | 148 | 365.9 | 92.7
11 | 534.7 | 594.5 | 564.6 | 427.8 | 668.4 | 475.6 | 743.1 | 482.2 | 372.9 | 161.8 | 432.7 | 161.8 | 381.9 | 100.2
11.25 | 540.6 | 603.8 | 572.2 | 432.5 | 675.8 | 483 | 754.7 | 493.2 | 385.3 | 155.3 | 448.5 | 155.3 | 396 | 97.2
11.5 | 572.5 | 639.1 | 605.8 | 458 | 715.7 | 511.2 | 798.8 | 518.4 | 400.4 | 172.1 | 466.9 | 172.1 | 412.1 | 106.4
11.75 | 1033.9 | 1104 | 1068.9 | 827.1 | 1292.4 | 883.2 | 1380 | 738.2 | 419.4 | 614.5 | 489.5 | 614.5 | 429.9 | 308.3
12 | 932.9 | 1006.9 | 969.9 | 746.3 | 1166.1 | 805.5 | 1258.6 | 934.2 | 461.8 | 471.1 | 535.7 | 471.1 | 463.1 | 471.1
12.25 | 850 | 928.3 | 889.2 | 680 | 1062.5 | 742.7 | 1160.4 | 694.2 | 493.3 | 356.7 | 571.7 | 356.7 | 496.8 | 197.4
12.5 | 1096.1 | 1179 | 1137.5 | 876.9 | 1370.1 | 943.2 | 1473.7 | 1095.5 | 539.4 | 556.7 | 622.3 | 556.7 | 538.8 | 556.7
12.75 | 1218.5 | 1306.8 | 1262.6 | 974.8 | 1523.1 | 1045.4 | 1633.5 | 1214.7 | 623.6 | 594.9 | 711.9 | 594.9 | 619.7 | 594.9
13 | 1799 | 1893.7 | 1846.4 | 1439.2 | 2248.8 | 1515 | 2367.1 | 1789 | 726.9 | 1072.2 | 821.6 | 1072.2 | 716.8 | 1072.2
13.25 | 4124.2 | 4228 | 4176.1 | 3299.4 | 5155.2 | 3382.4 | 5285 | 2086 | 948 | 3176.2 | 1051.9 | 3176.2 | 847.5 | 1238.6
13.5 | 2561.3 | 2680.3 | 2620.8 | 2049.1 | 3201.7 | 2144.2 | 3350.3 | 1574.8 | 1128.6 | 1432.7 | 1247.6 | 1432.7 | 934.4 | 640.4
13.75 | 3909.2 | 4046.6 | 3977.9 | 3127.4 | 4886.5 | 3237.3 | 5058.3 | 2164.7 | 1326.8 | 2582.4 | 1464.3 | 2582.4 | 1114.8 | 1049.9
14 | 2818.6 | 2979 | 2898.8 | 2254.9 | 3523.3 | 2383.2 | 3723.8 | 2521.6 | 1603.9 | 1214.7 | 1764.3 | 1214.7 | 1306.8 | 1214.7
14.25 | 4159.3 | 4348.7 | 4254 | 3327.4 | 5199.1 | 3479 | 5435.9 | 2597.3 | 1960.3 | 2199 | 2149.7 | 2199 | 1672.9 | 924.4
14.5 | 3590.6 | 3811.9 | 3701.3 | 2872.5 | 4488.3 | 3049.5 | 4764.9 | 3262.3 | 2084.4 | 1506.2 | 2305.7 | 1506.2 | 1756.1 | 1506.2
14.75 | 3592.1 | 3847.8 | 3719.9 | 2873.6 | 4490.1 | 3078.2 | 4809.7 | 2609.1 | 2321 | 1271 | 2576.7 | 1271 | 2020 | 589.1
15 | 3024.1 | 3315.8 | 3170 | 2419.3 | 3780.2 | 2652.6 | 4144.7 | 2748.7 | 2498.2 | 525.9 | 2789.9 | 525.9 | 2222.8 | 525.9
15.25 | 3162.9 | 3491.3 | 3327.1 | 2530.3 | 3953.7 | 2793.1 | 4364.2 | 2917 | 2561.7 | 601.2 | 2890.1 | 601.2 | 2315.8 | 601.2
15.5 | 2754.1 | 3119.5 | 2936.8 | 2203.3 | 3442.6 | 2495.6 | 3899.3 | 2482.7 | 2585 | 169.1 | 2950.4 | 169.1 | 2372.1 | 110.7
15.75 | 2901.6 | 3303.4 | 3102.5 | 2321.3 | 3627 | 2642.7 | 4129.3 | 2585.8 | 2575.3 | 326.3 | 2977.1 | 326.3 | 2393.9 | 191.9
16 | 2798.2 | 3236.1 | 3017.2 | 2238.6 | 3497.7 | 2588.9 | 4045.1 | 2586.9 | 2617.7 | 180.5 | 3055.7 | 180.5 | 2469.5 | 117.4
16.25 | 3014.9 | 3488.6 | 3251.7 | 2411.9 | 3768.6 | 2790.9 | 4360.7 | 2723.1 | 2609.1 | 405.7 | 3082.9 | 405.7 | 2491.7 | 231.3
16.5 | 3574.3 | 4083.8 | 3829.1 | 2859.4 | 4467.9 | 3267 | 5104.7 | 3471.5 | 2712.6 | 861.7 | 3222.1 | 861.7 | 2609.8 | 861.7
16.75 | 3281.7 | 3828.4 | 3555.1 | 2625.4 | 4102.1 | 3062.7 | 4785.5 | 3016.2 | 2829.7 | 452 | 3376.4 | 452 | 2761.7 | 254.5
17 | 3673.4 | 4257.6 | 3965.5 | 2938.7 | 4591.8 | 3406.1 | 5322 | 3630.2 | 2947 | 726.4 | 3531.2 | 726.4 | 2903.8 | 726.4
17.25 | 3760.4 | 4383 | 4071.7 | 3008.4 | 4700.5 | 3506.4 | 5478.8 | 3746.5 | 3038.1 | 722.3 | 3660.7 | 722.3 | 3024.2 | 722.3
17.5 | 3450.2 | 4111.9 | 3781.1 | 2760.2 | 4312.8 | 3289.5 | 5139.9 | 3347.6 | 3136.8 | 313.4 | 3798.5 | 313.4 | 3158.7 | 189
17.75 | 3577.1 | 4277.7 | 3927.4 | 2861.7 | 4471.3 | 3422.2 | 5347.1 | 3439.4 | 3137 | 440.1 | 3837.6 | 440.1 | 3188 | 251.4
18 | 3565.1 | 4304.8 | 3935 | 2852.1 | 4456.4 | 3443.9 | 5381 | 3519.2 | 3237.8 | 327.3 | 3977.5 | 327.3 | 3322.3 | 196.9
18.25 | 3446.2 | 4225 | 3835.6 | 2757 | 4307.8 | 3380 | 5281.3 | 3487.1 | 3225.8 | 220.4 | 4004.6 | 220.4 | 3345.1 | 141.9
18.5 | 3441.6 | 4258.9 | 3850.2 | 2753.2 | 4301.9 | 3407.1 | 5323.7 | 3514.7 | 3217 | 224.6 | 4034.4 | 224.6 | 3370.2 | 144.5
18.75 | 3458.4 | 4313.9 | 3886.2 | 2766.8 | 4323.1 | 3451.2 | 5392.4 | 3553 | 3207.8 | 250.6 | 4063.3 | 250.6 | 3394.3 | 158.7
19 | 4065.6 | 4958.8 | 4512.2 | 3252.5 | 5082 | 3967.1 | 6198.5 | 4279.2 | 3218.8 | 846.8 | 4112.1 | 846.8 | 3432.4 | 846.8
19.25 | 3476 | 4407 | 3941.5 | 2780.8 | 4345 | 3525.6 | 5508.7 | 3637.7 | 3239.3 | 236.7 | 4170.3 | 236.7 | 3485.7 | 152
19.5 | 3501.7 | 4470 | 3985.8 | 2801.4 | 4377.1 | 3576 | 5587.5 | 3681.2 | 3235.1 | 266.7 | 4203.3 | 266.7 | 3513 | 168.2
19.75 | 3500.1 | 4505.4 | 4002.8 | 2800.1 | 4375.2 | 3604.3 | 5631.8 | 3726.5 | 3266.5 | 233.7 | 4271.7 | 233.7 | 3575.4 | 151
20 | 3477.1 | 4519.2 | 3998.2 | 2781.7 | 4346.4 | 3615.4 | 5649.1 | 3745.6 | 3263.4 | 213.7 | 4305.5 | 213.7 | 3605 | 140.5
20.25 | 3606.3 | 4684.9 | 4145.6 | 2885.1 | 4507.9 | 3747.9 | 5856.1 | 3842.4 | 3263.1 | 343.2 | 4341.7 | 343.2 | 3633.4 | 209
20.5 | 3991.5 | 5106.3 | 4548.9 | 3193.2 | 4989.3 | 4085 | 6382.9 | 4386.2 | 3290.9 | 700.6 | 4405.7 | 700.6 | 3685.6 | 700.6
20.75 | 3578.3 | 4729.3 | 4153.8 | 2862.6 | 4472.9 | 3783.4 | 5911.6 | 3897.5 | 3288.2 | 290.1 | 4439.1 | 290.1 | 3715 | 182.4
21 | 3496.3 | 4683.1 | 4089.7 | 2797 | 4370.4 | 3746.4 | 5853.8 | 3882.9 | 3288.4 | 207.9 | 4475.2 | 207.9 | 3744.4 | 138.5
21.25 | 3612 | 4834.2 | 4223.1 | 2889.6 | 4515 | 3867.3 | 6042.7 | 3972.6 | 3277.6 | 334.4 | 4499.8 | 334.4 | 3766.4 | 206.2
21.5 | 3490.5 | 4747.6 | 4119.1 | 2792.4 | 4363.1 | 3798.1 | 5934.6 | 3937 | 3272.8 | 217.7 | 4529.9 | 217.7 | 3792.5 | 144.5
21.75 | 3496.6 | 4788.4 | 4142.5 | 2797.3 | 4370.7 | 3830.7 | 5985.5 | 3968.5 | 3264.2 | 232.4 | 4556 | 232.4 | 3815.6 | 152.9
22 | 3496.9 | 4823 | 4160 | 2797.5 | 4371.2 | 3858.4 | 6028.8 | 3997.4 | 3259.1 | 237.8 | 4585.2 | 237.8 | 3841.3 | 156.1
22.25 | 3489 | 4849 | 4169 | 2791.2 | 4361.3 | 3879.2 | 6061.3 | 4020.9 | 3251.9 | 237.1 | 4611.9 | 237.1 | 3864.9 | 156
22.5 | 3517 | 4910.6 | 4213.8 | 2813.6 | 4396.3 | 3928.5 | 6138.2 | 4064.7 | 3248.9 | 268.2 | 4642.4 | 268.2 | 3891.5 | 173.2
22.75 | 3510.1 | 4936.8 | 4223.5 | 2808.1 | 4387.6 | 3949.5 | 6171.1 | 4088.8 | 3245.2 | 264.8 | 4672 | 264.8 | 3917 | 171.8
23 | 3477.4 | 4937 | 4207.2 | 2781.9 | 4346.7 | 3949.6 | 6171.3 | 4099.2 | 3242.3 | 235.1 | 4701.9 | 235.1 | 3943.4 | 155.8
23.25 | 3470.5 | 4962.8 | 4216.6 | 2776.4 | 4338.1 | 3970.2 | 6203.5 | 4122.9 | 3237.5 | 233 | 4729.7 | 233 | 3967.9 | 155
23.5 | 3444.4 | 4969 | 4206.7 | 2755.5 | 4305.5 | 3975.2 | 6211.2 | 4136.3 | 3234.6 | 209.8 | 4759.2 | 209.8 | 3994.1 | 142.2
23.75 | 3437 | 4993.5 | 4215.2 | 2749.6 | 4296.2 | 3994.8 | 6241.8 | 4159.3 | 3229.6 | 207.4 | 4786.1 | 207.4 | 4018.2 | 141.1
24 | 3457.5 | 5045.6 | 4251.5 | 2766 | 4321.8 | 4036.5 | 6307 | 4198.5 | 3226.4 | 231 | 4814.5 | 231 | 4043.9 | 154.7
24.25 | 3445.9 | 5065.3 | 4255.6 | 2756.7 | 4307.4 | 4052.3 | 6331.7 | 4219.2 | 3225.8 | 220.1 | 4845.3 | 220.1 | 4070.4 | 148.8
24.5 | 3448.6 | 5099.2 | 4273.9 | 2758.9 | 4310.8 | 4079.3 | 6374 | 4248.5 | 3225.6 | 223 | 4876.2 | 223 | 4097.8 | 150.7
24.75 | 3460.7 | 5142 | 4301.3 | 2768.5 | 4325.8 | 4113.6 | 6427.5 | 4282.1 | 3224.5 | 236.2 | 4905.9 | 236.2 | 4123.8 | 158.3
25 | 3556.2 | 5268.2 | 4412.2 | 2845 | 4445.3 | 4214.5 | 6585.2 | 4361.7 | 3226.6 | 329.6 | 4938.5 | 329.6 | 4152.3 | 209.4
25.25 | 4388.5 | 6130.9 | 5259.7 | 3510.8 | 5485.6 | 4904.7 | 7663.6 | 5334.4 | 3292.6 | 1095.9 | 5035 | 1095.9 | 4238.4 | 1095.9
25.5 | 4321.7 | 6096.4 | 5209 | 3457.4 | 5402.1 | 4877.1 | 7620.5 | 5299.3 | 3555.9 | 765.8 | 5330.6 | 765.8 | 4533.5 | 765.8
25.75 | 4046.2 | 5854.4 | 4950.3 | 3237 | 5057.8 | 4683.5 | 7318 | 4926.4 | 3692.5 | 353.7 | 5500.6 | 353.7 | 4703.2 | 223.2
26 | 3990.6 | 5832.5 | 4911.5 | 3192.5 | 4988.2 | 4666 | 7290.6 | 4949.4 | 3743.4 | 247.2 | 5585.3 | 247.2 | 4783.6 | 165.9
26.25 | 3976.3 | 5851.9 | 4914.1 | 3181.1 | 4970.4 | 4681.6 | 7314.9 | 4970.3 | 3739.2 | 237.2 | 5614.8 | 237.2 | 4809.8 | 160.5
26.5 | 4013 | 5922.2 | 4967.6 | 3210.4 | 5016.3 | 4737.7 | 7402.7 | 5020.5 | 3740.4 | 272.7 | 5649.5 | 272.7 | 4839.9 | 180.6
26.75 | 4679.1 | 6621.5 | 5650.3 | 3743.3 | 5848.9 | 5297.2 | 8276.9 | 5376.5 | 3758.8 | 920.3 | 5701.2 | 920.3 | 4878 | 498.5
27 | 6444.4 | 8421.7 | 7433.1 | 5155.5 | 8055.5 | 6737.3 | 10527.1 | 6241.4 | 4017.7 | 2426.8 | 5994.9 | 2426.8 | 5121.2 | 1120.1
27.25 | 5951.5 | 7966.2 | 6958.9 | 4761.2 | 7439.4 | 6373 | 9957.8 | 6087.1 | 4116.5 | 1835 | 6131.3 | 1835 | 5198.2 | 888.9
27.5 | 5336.9 | 7391.3 | 6364.1 | 4269.5 | 6671.1 | 5913 | 9239.1 | 6410.1 | 4435.8 | 901.1 | 6490.2 | 901.1 | 5509 | 901.1
27.75 | 4836.2 | 6933 | 5884.6 | 3868.9 | 6045.2 | 5546.4 | 8666.2 | 5854.4 | 4554.1 | 282 | 6650.9 | 282 | 5667.1 | 187.3
28 | 4824.7 | 6963.8 | 5894.2 | 3859.7 | 6030.9 | 5571.1 | 8704.8 | 5883.2 | 4549.5 | 275.2 | 6688.6 | 275.2 | 5699.5 | 183.7
28.25 | 4819.5 | 7000.6 | 5910 | 3855.6 | 6024.4 | 5600.5 | 8750.7 | 5914.5 | 4543.1 | 276.4 | 6724.2 | 276.4 | 5729.9 | 184.7
28.5 | 4801.3 | 7024 | 5912.7 | 3841.1 | 6001.6 | 5619.2 | 8780 | 5939.3 | 4539 | 262.3 | 6761.7 | 262.3 | 5762.2 | 177.1
28.75 | 4796 | 7060 | 5928 | 3836.8 | 5995 | 5648 | 8825 | 5970.3 | 4533.1 | 263 | 6797.1 | 263 | 5792.6 | 177.7
29 | 5076.6 | 7381.6 | 6229.1 | 4061.3 | 6345.7 | 5905.3 | 9227 | 6153.2 | 4538.8 | 537.8 | 6843.8 | 537.8 | 5830.2 | 323
29.25 | 9984.1 | 12331 | 11157.6 | 7987.3 | 12480.1 | 9864.8 | 15413.8 | 8179.3 | 4751.8 | 5232.3 | 7098.7 | 5232.3 | 6024.9 | 2154.4
29.5 | 10748.7 | 13145.3 | 11947 | 8599 | 13435.9 | 10516.2 | 16431.6 | 8564.3 | 5259.9 | 5488.8 | 7656.5 | 5488.8 | 6318.5 | 2245.8
29.75 | 9105.3 | 11561.6 | 10333.4 | 7284.2 | 11381.6 | 9249.3 | 14452 | 8131 | 5664.9 | 3440.4 | 8121.1 | 3440.4 | 6606.9 | 1524.1
30 | 8770.1 | 11294 | 10032.1 | 7016.1 | 10962.7 | 9035.2 | 14117.5 | 8086.2 | 5976.7 | 2793.4 | 8500.6 | 2793.4 | 6802.9 | 1283.3
30.25 | 16194 | 18792.3 | 17493.2 | 12955.2 | 20242.5 | 15033.8 | 23490.4 | 10709.6 | 6392.2 | 9801.8 | 8990.5 | 9801.8 | 7050.7 | 3658.9
30.5 | 15387.2 | 18075.1 | 16731.2 | 12309.8 | 19234 | 14460.1 | 22593.9 | 10524.3 | 6975.6 | 8411.6 | 9663.5 | 8411.6 | 7298 | 3226.3
30.75 | 23332.7 | 26146.6 | 24739.7 | 18666.2 | 29165.9 | 20917.3 | 32683.3 | 14394.8 | 9034.5 | 14298.2 | 11848.5 | 14298.2 | 9366.9 | 5027.9
31 | 27058.9 | 30048.8 | 28553.8 | 21647.1 | 33823.6 | 24039 | 37561 | 15563 | 9984.5 | 17074.3 | 12974.5 | 17074.3 | 9724 | 5839
31.25 | 26148.2 | 29351.4 | 27749.8 | 20918.6 | 32685.3 | 23481.1 | 36689.3 | 15390.4 | 10980.8 | 15167.4 | 14184 | 15167.4 | 10091.3 | 5299.1
31.5 | 17662.7 | 21109.3 | 19386 | 14130.2 | 22078.4 | 16887.5 | 26386.7 | 13097 | 11703.4 | 5959.3 | 15150.1 | 5959.3 | 10660.5 | 2436.6
31.75 | 16371.7 | 20068.9 | 18220.3 | 13097.4 | 20464.7 | 16055.2 | 25086.2 | 12770 | 11818.1 | 4553.7 | 15515.3 | 4553.7 | 10819.7 | 1950.3
32 | 31911.7 | 35865.1 | 33888.4 | 25529.3 | 39889.6 | 28692.1 | 44831.4 | 17674.1 | 12457.9 | 19453.8 | 16411.4 | 19453.8 | 11122.8 | 6551.3
32.25 | 23365.4 | 27605.5 | 25485.5 | 18692.3 | 29206.8 | 22084.4 | 34506.9 | 15270.5 | 13227.1 | 10138.4 | 17467.2 | 10138.4 | 11458.4 | 3812.1
32.5 | 23787.3 | 28330 | 26058.6 | 19029.8 | 29734.1 | 22664 | 35412.5 | 15540 | 13678.8 | 10108.5 | 18221.6 | 10108.5 | 11731.5 | 3808.6
32.75 | 24671.9 | 29530 | 27101 | 19737.5 | 30839.9 | 23624 | 36912.5 | 15947 | 14196.9 | 10475 | 19055 | 10475 | 12017.7 | 3929.3
33 | 16936.5 | 22124.4 | 19530.5 | 13549.2 | 21170.7 | 17699.5 | 27655.5 | 14719.8 | 15041.6 | 1894.9 | 20229.5 | 1894.9 | 12824.8 | 1894.9
33.25 | 20503.8 | 26028.3 | 23266.1 | 16403.1 | 25629.8 | 20822.7 | 32535.4 | 18607.6 | 15423.6 | 5080.2 | 20948.2 | 5080.2 | 13527.4 | 5080.2
33.5 | 36287.9 | 42154.9 | 39221.4 | 29030.4 | 45359.9 | 33724 | 52693.7 | 20755 | 16184.1 | 20103.9 | 22051.1 | 20103.9 | 13961.6 | 6793.4
33.75 | 32733.2 | 38978.1 | 35855.7 | 26186.6 | 40916.5 | 31182.5 | 48722.7 | 19870 | 17086.7 | 15646.5 | 23331.6 | 15646.5 | 14349 | 5521.1
34 | 35224.7 | 41873.6 | 38549.2 | 28179.8 | 44030.9 | 33498.8 | 52341.9 | 20759.7 | 17791.3 | 17433.4 | 24440.1 | 17433.4 | 14709 | 6050.7
34.25 | 39549.1 | 46628.7 | 43088.9 | 31639.2 | 49436.3 | 37302.9 | 58285.8 | 22971.9 | 19197.3 | 20351.8 | 26276.9 | 20351.8 | 16078.3 | 6893.6
34.5 | 29022.4 | 36584.3 | 32803.4 | 23217.9 | 36278 | 29267.5 | 45730.4 | 19918.3 | 20242.8 | 8779.6 | 27804.7 | 8779.6 | 16492.2 | 3426.1
34.75 | 32342.4 | 40406.1 | 36374.3 | 25874 | 40428.1 | 32324.9 | 50507.7 | 21356 | 20608.2 | 11734.2 | 28671.9 | 11734.2 | 16987 | 4369
35 | 44807.3 | 53391.1 | 49099.2 | 35845.9 | 56009.2 | 42712.9 | 66738.9 | 41407.7 | 22828.4 | 21979 | 31412.2 | 21979 | 19428.7 | 21979
35.25 | 41878 | 51043.2 | 46460.6 | 33502.4 | 52347.5 | 40834.6 | 63804 | 26565.1 | 23805.4 | 18072.6 | 32970.6 | 18072.6 | 20286.3 | 6278.8
35.5 | 43863.7 | 53631.7 | 48747.7 | 35091 | 54829.7 | 42905.3 | 67039.6 | 27350.8 | 24524.8 | 19338.9 | 34292.7 | 19338.9 | 20697.9 | 6652.9
35.75 | 51243 | 61639.5 | 56441.2 | 40994.4 | 64053.8 | 49311.6 | 77049.4 | 29606.2 | 25264.5 | 25978.5 | 35661 | 25978.5 | 21086.1 | 8520.2

## SRD WTG-24
Depth (m) | SRD AH-FF (kN) | SRD AH-NFF (kN) | SRD MEAN (kN) | SRD AH-FF-LB (kN) | SRD AH-FF-UB (kN) | SRD AH-NFF-LB (kN) | SRD AH-NFF-UB (kN) | Static Cap (kN) | Shaft AH-FF (kN) | Tip AH-FF (kN) | Shaft AH-NFF (kN) | Tip AH-NFF (kN) | Shaft SC (kN) | Tip SC (kN)
0.5 | 74.2 | 74.8 | 74.5 | 59.3 | 92.7 | 59.9 | 93.5 | 74.8 | 59.7 | 14.5 | 60.3 | 14.5 | 60.3 | 14.5
0.75 | 110.9 | 112.4 | 111.6 | 88.7 | 138.6 | 89.9 | 140.5 | 112.4 | 95 | 15.8 | 96.5 | 15.8 | 96.5 | 15.8
1 | 333.4 | 336.1 | 334.8 | 266.8 | 416.8 | 268.9 | 420.2 | 336.1 | 135.7 | 197.8 | 138.4 | 197.8 | 138.4 | 197.8
1.25 | 617.9 | 622.4 | 620.1 | 494.3 | 772.3 | 497.9 | 778 | 333 | 167.5 | 450.4 | 172.1 | 450.4 | 169.9 | 163.2
1.5 | 999.3 | 1006.4 | 1002.8 | 799.4 | 1249.1 | 805.1 | 1258 | 461.7 | 193.1 | 806.2 | 200.2 | 806.2 | 187.8 | 273.9
1.75 | 599.5 | 610.1 | 604.8 | 479.6 | 749.4 | 488.1 | 762.7 | 352.8 | 217.7 | 381.8 | 228.3 | 381.8 | 201.8 | 151
2 | 595.3 | 610 | 602.6 | 476.2 | 744.1 | 488 | 762.4 | 574.4 | 244.1 | 351.2 | 258.8 | 351.2 | 223.2 | 351.2
2.25 | 1018.7 | 1038.6 | 1028.6 | 814.9 | 1273.3 | 830.9 | 1298.2 | 553 | 310.8 | 707.9 | 330.7 | 707.9 | 288.9 | 264.1
2.5 | 720.5 | 746.8 | 733.7 | 576.4 | 900.6 | 597.5 | 933.5 | 485.8 | 358 | 362.5 | 384.3 | 362.5 | 331.8 | 154
2.75 | 1039.9 | 1073.6 | 1056.8 | 832 | 1299.9 | 858.9 | 1342 | 624.1 | 398.8 | 641.2 | 432.4 | 641.2 | 372.3 | 251.8
3 | 1599.1 | 1641 | 1620.1 | 1279.3 | 1998.8 | 1312.8 | 2051.3 | 815.5 | 442.2 | 1156.8 | 484.2 | 1156.8 | 397.3 | 418.3
3.25 | 1479.4 | 1531.5 | 1505.5 | 1183.5 | 1849.3 | 1225.2 | 1914.4 | 1405.9 | 501.2 | 978.2 | 553.3 | 978.2 | 427.7 | 978.2
3.5 | 916.4 | 980.8 | 948.6 | 733.1 | 1145.5 | 784.6 | 1226 | 854.3 | 628.6 | 287.8 | 693 | 287.8 | 566.5 | 287.8
3.75 | 927.7 | 1005.7 | 966.7 | 742.2 | 1159.7 | 804.6 | 1257.2 | 879.3 | 708.9 | 218.8 | 786.9 | 218.8 | 660.4 | 218.8
4 | 895 | 987.3 | 941.2 | 716 | 1118.8 | 789.9 | 1234.2 | 860.9 | 777.8 | 117.2 | 870.1 | 117.2 | 743.6 | 117.2
4.25 | 944.1 | 1050.8 | 997.4 | 755.3 | 1180.1 | 840.6 | 1313.5 | 924.3 | 820.1 | 124 | 926.8 | 124 | 800.3 | 124
4.5 | 991.7 | 1112.9 | 1052.3 | 793.3 | 1239.6 | 890.3 | 1391.1 | 986.4 | 867.2 | 124.5 | 988.4 | 124.5 | 862 | 124.5
4.75 | 1051.5 | 1187.3 | 1119.4 | 841.2 | 1314.4 | 949.9 | 1484.2 | 1060.9 | 911.4 | 140.1 | 1047.3 | 140.1 | 920.8 | 140.1
5 | 1081.5 | 1232.1 | 1156.8 | 865.2 | 1351.9 | 985.7 | 1540.1 | 1105.6 | 960.7 | 120.8 | 1111.3 | 120.8 | 984.8 | 120.8
5.25 | 1132 | 1297.5 | 1214.8 | 905.6 | 1415 | 1038 | 1621.9 | 1171 | 1005.1 | 126.9 | 1170.5 | 126.9 | 1044.1 | 126.9
5.5 | 1246.9 | 1427.4 | 1337.2 | 997.6 | 1558.7 | 1141.9 | 1784.3 | 1300.9 | 1057.3 | 189.6 | 1237.8 | 189.6 | 1111.3 | 189.6
5.75 | 1298.1 | 1493.8 | 1396 | 1038.5 | 1622.6 | 1195 | 1867.2 | 1367.3 | 1113 | 185.1 | 1308.7 | 185.1 | 1182.2 | 185.1
6 | 1377.3 | 1588.5 | 1482.9 | 1101.8 | 1721.6 | 1270.8 | 1985.6 | 1462 | 1176.8 | 200.5 | 1388 | 200.5 | 1261.5 | 200.5
6.25 | 1413 | 1640 | 1526.5 | 1130.4 | 1766.2 | 1312 | 2050 | 1513.6 | 1229.7 | 183.3 | 1456.7 | 183.3 | 1330.3 | 183.3
6.5 | 1489.8 | 1733 | 1611.4 | 1191.8 | 1862.2 | 1386.4 | 2166.2 | 1606.5 | 1305.6 | 184.2 | 1548.8 | 184.2 | 1422.3 | 184.2
6.75 | 1662.4 | 1922.1 | 1792.2 | 1329.9 | 2078 | 1537.7 | 2402.7 | 1654.9 | 1369.6 | 292.8 | 1629.4 | 292.8 | 1502.9 | 152
7 | 1834 | 2111 | 1972.5 | 1467.2 | 2292.5 | 1688.8 | 2638.7 | 1980 | 1486.9 | 347.1 | 1763.9 | 347.1 | 1632.8 | 347.1
7.25 | 1814.3 | 2109.7 | 1962 | 1451.5 | 2267.9 | 1687.8 | 2637.1 | 1978.7 | 1571.3 | 243 | 1866.7 | 243 | 1735.6 | 243
7.5 | 1850.7 | 2164.9 | 2007.8 | 1480.6 | 2313.4 | 1731.9 | 2706.1 | 2033.8 | 1625.8 | 224.9 | 1939.9 | 224.9 | 1808.9 | 224.9
7.75 | 1910.1 | 2243.4 | 2076.8 | 1528.1 | 2387.7 | 1794.7 | 2804.2 | 2112.3 | 1684.3 | 225.8 | 2017.5 | 225.8 | 1886.5 | 225.8
8 | 1964.2 | 2316.8 | 2140.5 | 1571.3 | 2455.2 | 1853.4 | 2896 | 2185.8 | 1748.8 | 215.4 | 2101.4 | 215.4 | 1970.3 | 215.4
8.25 | 2119 | 2491.3 | 2305.1 | 1695.2 | 2648.7 | 1993 | 3114.1 | 2360.2 | 1801 | 317.9 | 2173.3 | 317.9 | 2042.3 | 317.9
8.5 | 2071.3 | 2463.5 | 2267.4 | 1657 | 2589.1 | 1970.8 | 3079.4 | 2332.5 | 1856.3 | 215 | 2248.6 | 215 | 2117.5 | 215
8.75 | 2152 | 2564.4 | 2358.2 | 1721.6 | 2690 | 2051.5 | 3205.5 | 2433.3 | 1910.1 | 241.9 | 2322.5 | 241.9 | 2191.4 | 241.9
9 | 2205.8 | 2638.6 | 2422.2 | 1764.7 | 2757.3 | 2110.9 | 3298.2 | 2507.6 | 1971.4 | 234.4 | 2404.2 | 234.4 | 2273.1 | 234.4
9.25 | 2258.2 | 2711.6 | 2484.9 | 1806.6 | 2822.7 | 2169.3 | 3389.5 | 2580.5 | 2021 | 237.2 | 2474.4 | 237.2 | 2343.4 | 237.2
9.5 | 2391.1 | 2865.4 | 2628.3 | 1912.9 | 2988.9 | 2292.3 | 3581.7 | 2734.3 | 2082.9 | 308.2 | 2557.2 | 308.2 | 2426.1 | 308.2
9.75 | 2522.3 | 3017.8 | 2770.1 | 2017.9 | 3152.9 | 2414.3 | 3772.3 | 2886.8 | 2158.2 | 364.1 | 2653.7 | 364.1 | 2522.7 | 364.1
10 | 2569.7 | 3086.9 | 2828.3 | 2055.7 | 3212.1 | 2469.5 | 3858.7 | 2955.9 | 2243.4 | 326.3 | 2760.6 | 326.3 | 2629.6 | 326.3
10.25 | 2733.9 | 3273.4 | 3003.6 | 2187.1 | 3417.3 | 2618.7 | 4091.8 | 3142.4 | 2324.3 | 409.6 | 2863.9 | 409.6 | 2732.8 | 409.6
10.5 | 2769.8 | 3332.4 | 3051.1 | 2215.9 | 3462.3 | 2665.9 | 4165.5 | 3200.5 | 2416.4 | 353.5 | 2978.9 | 353.5 | 2847.1 | 353.5
10.75 | 2859.6 | 3445.9 | 3152.8 | 2287.7 | 3574.6 | 2756.7 | 4307.3 | 3314 | 2521.8 | 337.8 | 3108 | 337.8 | 2976.1 | 337.8
11 | 2922.4 | 3533 | 3227.7 | 2338 | 3653.1 | 2826.4 | 4416.3 | 3401.2 | 2609.7 | 312.7 | 3220.3 | 312.7 | 3088.4 | 312.7
11.25 | 3050.7 | 3686.1 | 3368.4 | 2440.5 | 3813.3 | 2948.8 | 4607.6 | 3554.2 | 2674.4 | 376.3 | 3309.7 | 376.3 | 3177.9 | 376.3
11.5 | 3086.1 | 3746.8 | 3416.4 | 2468.9 | 3857.6 | 2997.4 | 4683.4 | 3614.9 | 2761.1 | 325 | 3421.8 | 325 | 3289.9 | 325
11.75 | 3315.4 | 4001.8 | 3658.6 | 2652.3 | 4144.3 | 3201.4 | 5002.2 | 3869.9 | 2826.6 | 488.8 | 3513 | 488.8 | 3381.1 | 488.8
12 | 3214.7 | 3927.2 | 3570.9 | 2571.7 | 4018.4 | 3141.8 | 4909 | 3795.3 | 2924.6 | 290.1 | 3637.1 | 290.1 | 3505.2 | 290.1
12.25 | 3303.8 | 4043 | 3673.4 | 2643.1 | 4129.8 | 3234.4 | 5053.7 | 3911.1 | 2985.7 | 318.2 | 3724.8 | 318.2 | 3592.9 | 318.2
12.5 | 3398.7 | 4164.8 | 3781.8 | 2719 | 4248.4 | 3331.8 | 5206 | 4032.9 | 3052.1 | 346.7 | 3818.1 | 346.7 | 3686.3 | 346.7
12.75 | 3474.9 | 4268.3 | 3871.6 | 2779.9 | 4343.6 | 3414.6 | 5335.4 | 4136.4 | 3127.5 | 347.4 | 3920.9 | 347.4 | 3789.1 | 347.4
13 | 3568.5 | 4389.7 | 3979.1 | 2854.8 | 4460.6 | 3511.7 | 5487.1 | 4257.8 | 3215.9 | 352.6 | 4037.1 | 352.6 | 3905.2 | 352.6
13.25 | 3623.7 | 4473.1 | 4048.4 | 2898.9 | 4529.6 | 3578.5 | 5591.3 | 4185.8 | 3269.5 | 354.2 | 4118.9 | 354.2 | 3986.1 | 199.8
13.5 | 11615.5 | 12495.8 | 12055.6 | 9292.4 | 14519.3 | 9996.6 | 15619.7 | 6830.2 | 3528.5 | 8086.9 | 4408.8 | 8086.9 | 4112.2 | 2718
13.75 | 9577.5 | 10501.1 | 10039.3 | 7662 | 11971.9 | 8400.8 | 13126.3 | 6291.5 | 3853.4 | 5724.1 | 4777 | 5724.1 | 4246 | 2045.4
14 | 9670 | 10647.6 | 10158.8 | 7736 | 12087.5 | 8518 | 13309.4 | 9961.3 | 4325.5 | 5344.5 | 5303.1 | 5344.5 | 4616.8 | 5344.5
14.25 | 8012.8 | 9056.6 | 8534.7 | 6410.2 | 10015.9 | 7245.3 | 11320.8 | 6114.1 | 4583.1 | 3429.6 | 5627 | 3429.6 | 4770 | 1344.1
14.5 | 10490.4 | 11610.1 | 11050.3 | 8392.3 | 13113 | 9288.1 | 14512.6 | 7211.9 | 5118.5 | 5372 | 6238.1 | 5372 | 5251.9 | 1960
14.75 | 10856.2 | 12061.9 | 11459 | 8685 | 13570.3 | 9649.5 | 15077.4 | 7382.1 | 5356.3 | 5499.9 | 6561.9 | 5499.9 | 5376.4 | 2005.7
15 | 10806.4 | 12106.7 | 11456.6 | 8645.1 | 13508 | 9685.4 | 15133.4 | 7428.5 | 5658.4 | 5148 | 6958.7 | 5148 | 5524.1 | 1904.4
15.25 | 10123.3 | 11525.9 | 10824.6 | 8098.7 | 12654.2 | 9220.7 | 14407.4 | 7276.8 | 5859.1 | 4264.2 | 7261.7 | 4264.2 | 5643.9 | 1632.8
15.5 | 11766.8 | 13277.6 | 12522.2 | 9413.5 | 14708.5 | 10622.1 | 16597 | 7855.7 | 6109.7 | 5657.1 | 7620.5 | 5657.1 | 5782.6 | 2073.1
15.75 | 11413.4 | 13040.8 | 12227.1 | 9130.8 | 14266.8 | 10432.6 | 16301 | 7812.9 | 6367.8 | 5045.6 | 7995.1 | 5045.6 | 5922.4 | 1890.5
16 | 9681.9 | 11432.3 | 10557.1 | 7745.5 | 12102.4 | 9145.8 | 14290.4 | 7414.9 | 6635.4 | 3046.5 | 8385.8 | 3046.5 | 6169.6 | 1245.3
16.25 | 12127.4 | 14005.5 | 13066.5 | 9701.9 | 15159.3 | 11204.4 | 17506.9 | 8277.9 | 6802.3 | 5325.1 | 8680.4 | 5325.1 | 6288.7 | 1989.2
16.5 | 11362.3 | 13373.5 | 12367.9 | 9089.8 | 14202.8 | 10698.8 | 16716.9 | 8110.2 | 7025.8 | 4336.5 | 9037.1 | 4336.5 | 6429 | 1681.2
16.75 | 11754.3 | 13903.4 | 12828.8 | 9403.4 | 14692.9 | 11122.7 | 17379.2 | 8364.3 | 7200.1 | 4554.2 | 9349.2 | 4554.2 | 6608.1 | 1756.2
17 | 12658.8 | 14950.4 | 13804.6 | 10127 | 15823.5 | 11960.3 | 18688 | 8729.1 | 7443.9 | 5214.9 | 9735.4 | 5214.9 | 6757.4 | 1971.7
17.25 | 10785.8 | 13225.7 | 12005.7 | 8628.6 | 13482.3 | 10580.5 | 16532.1 | 8269.3 | 7706.5 | 3079.3 | 10146.4 | 3079.3 | 6994.8 | 1274.5
17.5 | 10492.5 | 13088.1 | 11790.3 | 8394 | 13115.6 | 10470.5 | 16360.1 | 8412.3 | 7990.2 | 2502.3 | 10585.8 | 2502.3 | 7337.3 | 1075
17.75 | 10316.1 | 13069 | 11692.6 | 8252.9 | 12895.2 | 10455.2 | 16336.2 | 9801.1 | 8317.8 | 1998.4 | 11070.6 | 1998.4 | 7802.8 | 1998.4
18 | 9128.6 | 12039.2 | 10583.9 | 7302.9 | 11410.8 | 9631.3 | 15049 | 8755.4 | 8516.7 | 611.9 | 11427.3 | 611.9 | 8143.5 | 611.9
18.25 | 11207 | 14273.6 | 12740.3 | 8965.6 | 14008.8 | 11418.9 | 17842 | 9418 | 8536.3 | 2670.7 | 11602.9 | 2670.7 | 8275.1 | 1142.9
18.5 | 12048.9 | 15271 | 13659.9 | 9639.1 | 15061.1 | 12216.8 | 19088.7 | 11825 | 8675.8 | 3373.1 | 11897.9 | 3373.1 | 8451.9 | 3373.1
18.75 | 10930.8 | 14310.9 | 12620.8 | 8744.6 | 13663.5 | 11448.7 | 17888.6 | 10852.7 | 8965.9 | 1964.9 | 12346 | 1964.9 | 8887.9 | 1964.9
19 | 9818.7 | 13356.5 | 11587.6 | 7854.9 | 12273.3 | 10685.2 | 16695.7 | 9896 | 9158.8 | 659.9 | 12696.7 | 659.9 | 9236.2 | 659.9
19.25 | 10405 | 14098 | 12251.5 | 8324 | 13006.2 | 11278.4 | 17622.5 | 10633.9 | 9157.9 | 1247.1 | 12850.9 | 1247.1 | 9386.8 | 1247.1
19.5 | 9666.4 | 13512.4 | 11589.4 | 7733.2 | 12083.1 | 10809.9 | 16890.5 | 9888.9 | 9273.3 | 393.1 | 13119.3 | 393.1 | 9654.8 | 234.1
19.75 | 9712.7 | 13708.7 | 11710.7 | 7770.2 | 12140.9 | 10967 | 17135.9 | 10231.2 | 9246.1 | 466.6 | 13242.1 | 466.6 | 9764.6 | 466.6
20 | 9514.5 | 13658.3 | 11586.4 | 7611.6 | 11893.2 | 10926.6 | 17072.9 | 10121 | 9329.2 | 185.3 | 13473 | 185.3 | 9995.5 | 125.6
20.25 | 9797.3 | 14085.6 | 11941.4 | 7837.8 | 12246.6 | 11268.5 | 17607 | 10607.8 | 9290.2 | 507.1 | 13578.5 | 507.1 | 10100.7 | 507.1
20.5 | 9733.8 | 14163.7 | 11948.8 | 7787.1 | 12167.3 | 11331 | 17704.6 | 10685.6 | 9288.1 | 445.8 | 13717.9 | 445.8 | 10239.8 | 445.8
20.75 | 9707.6 | 14276.2 | 11991.9 | 7766.1 | 12134.5 | 11421 | 17845.3 | 10798.1 | 9284 | 423.6 | 13852.6 | 423.6 | 10374.5 | 423.6
21 | 9530.1 | 14234.7 | 11882.4 | 7624.1 | 11912.7 | 11387.8 | 17793.4 | 10660.3 | 9261.6 | 268.5 | 13966.2 | 268.5 | 10487.9 | 172.4
21.25 | 9691.5 | 14529.1 | 12110.3 | 7753.2 | 12114.3 | 11623.3 | 18161.3 | 11049.6 | 9224.4 | 467.1 | 14062 | 467.1 | 10582.5 | 467.1
21.5 | 9652.8 | 14620.6 | 12136.7 | 7722.2 | 12065.9 | 11696.5 | 18275.7 | 11141 | 9203.3 | 449.4 | 14171.2 | 449.4 | 10691.6 | 449.4
21.75 | 9703.8 | 14799 | 12251.4 | 7763 | 12129.7 | 11839.2 | 18498.8 | 11318.7 | 9143.9 | 559.8 | 14239.2 | 559.8 | 10758.9 | 559.8
22 | 9643.3 | 14863.3 | 12253.3 | 7714.6 | 12054.1 | 11890.7 | 18579.1 | 11383 | 9150 | 493.3 | 14370 | 493.3 | 10889.7 | 493.3
22.25 | 9316.7 | 14659.1 | 11987.9 | 7453.4 | 11645.9 | 11727.3 | 18323.8 | 11113.5 | 9113.9 | 202.8 | 14456.3 | 202.8 | 10975.8 | 137.8
22.5 | 9678.2 | 15140.4 | 12409.3 | 7742.5 | 12097.7 | 12112.3 | 18925.4 | 11656.2 | 9123.3 | 554.9 | 14585.5 | 554.9 | 11101.3 | 554.9
22.75 | 9629.9 | 15209.9 | 12419.9 | 7703.9 | 12037.4 | 12167.9 | 19012.4 | 11725.6 | 9116.7 | 513.2 | 14696.7 | 513.2 | 11212.3 | 513.2
23 | 9702.2 | 15397.8 | 12550 | 7761.7 | 12127.7 | 12318.2 | 19247.2 | 11913.3 | 9110.6 | 591.5 | 14806.3 | 591.5 | 11321.8 | 591.5
23.25 | 9557.7 | 15366.8 | 12462.3 | 7646.2 | 11947.1 | 12293.5 | 19208.5 | 11875.3 | 9114.2 | 443.5 | 14923.3 | 443.5 | 11431.8 | 443.5
23.5 | 9645.5 | 15566.2 | 12605.9 | 7716.4 | 12056.9 | 12453 | 19457.8 | 12074.1 | 9097 | 548.5 | 15017.7 | 548.5 | 11525.6 | 548.5
23.75 | 9263.6 | 15293.8 | 12278.7 | 7410.9 | 11579.5 | 12235 | 19117.2 | 11470.6 | 9080.8 | 182.8 | 15111 | 182.8 | 7127.6 | 4343
24 | 9509.4 | 15647 | 12578.2 | 7607.6 | 11886.8 | 12517.6 | 19558.7 | 12154.2 | 9055.5 | 453.9 | 15193.1 | 453.9 | 11700.2 | 453.9
24.25 | 9229.7 | 15472.6 | 12351.2 | 7383.8 | 11537.1 | 12378.1 | 19340.8 | 11917.1 | 9028.3 | 201.4 | 15271.2 | 201.4 | 11778.2 | 138.9
24.5 | 9142.8 | 15489 | 12315.9 | 7314.2 | 11428.5 | 12391.2 | 19361.2 | 11054.8 | 8987.9 | 154.9 | 15334.1 | 154.9 | 7252.6 | 3802.3
24.75 | 9455 | 15902.4 | 12678.7 | 7564 | 11818.8 | 12722 | 19878.1 | 12408.1 | 8964.6 | 490.4 | 15412.1 | 490.4 | 11917.7 | 490.4
25 | 9474.9 | 16021.9 | 12748.4 | 7579.9 | 11843.6 | 12817.5 | 20027.3 | 12527.2 | 8970.7 | 504.2 | 15517.7 | 504.2 | 12023 | 504.2
25.25 | 9076.5 | 15721.3 | 12398.9 | 7261.2 | 11345.6 | 12577 | 19651.6 | 10862.2 | 8938.5 | 138 | 15583.3 | 138 | 7390.9 | 3471.3
25.5 | 9359.6 | 16100.3 | 12730 | 7487.7 | 11699.5 | 12880.3 | 20125.4 | 12605.3 | 8917.9 | 441.7 | 15658.6 | 441.7 | 12163.6 | 441.7
25.75 | 9087.4 | 15922.5 | 12504.9 | 7269.9 | 11359.2 | 12738 | 19903.1 | 11945 | 8901.3 | 186.1 | 15736.4 | 186.1 | 7476.9 | 4468.1
26 | 9444.8 | 16372.6 | 12908.7 | 7555.8 | 11805.9 | 13098 | 20465.7 | 12876.2 | 8888.5 | 556.2 | 15816.3 | 556.2 | 12320 | 556.2
26.25 | 9091.7 | 16110.8 | 12601.3 | 7273.4 | 11364.7 | 12888.6 | 20138.5 | 12375.3 | 8889.5 | 202.2 | 15908.6 | 202.2 | 7572.5 | 4802.9
26.5 | 9450.5 | 16559.1 | 13004.8 | 7560.4 | 11813.1 | 13247.3 | 20698.9 | 13060.8 | 8863 | 587.4 | 15971.7 | 587.4 | 12473.3 | 587.4
26.75 | 9432.4 | 16629.5 | 13031 | 7545.9 | 11790.5 | 13303.6 | 20786.9 | 13131.2 | 8897 | 535.4 | 16094.1 | 535.4 | 12595.8 | 535.4
27 | 9339.5 | 16623.9 | 12981.7 | 7471.6 | 11674.4 | 13299.1 | 20779.8 | 12956.4 | 8905.6 | 433.9 | 16189.9 | 433.9 | 12688.3 | 268
27.25 | 10462.7 | 17833.8 | 14148.3 | 8370.2 | 13078.4 | 14267 | 22292.3 | 14328.1 | 9100.7 | 1362 | 16471.8 | 1362 | 12966.1 | 1362
27.5 | 11236.5 | 18697.2 | 14966.8 | 8989.2 | 14045.6 | 14957.8 | 23371.5 | 15177.6 | 9676.4 | 1560 | 17137.2 | 1560 | 13617.6 | 1560
27.75 | 11585.5 | 19143 | 15364.2 | 9268.4 | 14481.8 | 15314.4 | 23928.7 | 15623.3 | 10178.2 | 1407.3 | 17735.7 | 1407.3 | 14216 | 1407.3
28 | 12228.2 | 19886.2 | 16057.2 | 9782.5 | 15285.2 | 15908.9 | 24857.7 | 16360.7 | 10610.6 | 1617.5 | 18268.7 | 1617.5 | 14743.2 | 1617.5
28.25 | 12011.6 | 19775.2 | 15893.4 | 9609.3 | 15014.6 | 15820.1 | 24718.9 | 16249.7 | 11150.6 | 861 | 18914.1 | 861 | 15388.7 | 861
28.5 | 12027.2 | 19897.8 | 15962.5 | 9621.8 | 15034.1 | 15918.3 | 24872.3 | 16372.4 | 11328 | 699.2 | 19198.6 | 699.2 | 15673.2 | 699.2
28.75 | 12105.2 | 20082.6 | 16093.9 | 9684.2 | 15131.5 | 16066.1 | 25103.3 | 16557.2 | 11435.6 | 669.6 | 19413 | 669.6 | 15887.6 | 669.6
29 | 12265.9 | 20349.7 | 16307.8 | 9812.7 | 15332.3 | 16279.7 | 25437.1 | 16824.2 | 11537.2 | 728.7 | 19621 | 728.7 | 16095.6 | 728.7
29.25 | 12399.8 | 20589.5 | 16494.6 | 9919.8 | 15499.7 | 16471.6 | 25736.9 | 17064.1 | 11630.4 | 769.4 | 19820.1 | 769.4 | 16294.7 | 769.4
29.5 | 12486.5 | 20781.9 | 16634.2 | 9989.2 | 15608.1 | 16625.5 | 25977.3 | 17256.4 | 11755.5 | 730.9 | 20051 | 730.9 | 16525.5 | 730.9
29.75 | 12576.3 | 20977.1 | 16776.7 | 10061.1 | 15720.4 | 16781.7 | 26221.4 | 17451.7 | 11849.7 | 726.6 | 20250.5 | 726.6 | 16725.1 | 726.6
30 | 12646.7 | 21152.5 | 16899.6 | 10117.4 | 15808.4 | 16922 | 26440.7 | 17627.1 | 11943.4 | 703.3 | 20449.2 | 703.3 | 16923.8 | 703.3
30.25 | 12716.5 | 21326.8 | 17021.6 | 10173.2 | 15895.6 | 17061.4 | 26658.4 | 17801.3 | 12002.3 | 714.2 | 20612.6 | 714.2 | 17087.1 | 714.2
30.5 | 12732.3 | 21446.5 | 17089.4 | 10185.9 | 15915.4 | 17157.2 | 26808.1 | 17921 | 12061.6 | 670.7 | 20775.7 | 670.7 | 17250.3 | 670.7
30.75 | 14855.6 | 23673.2 | 19264.4 | 11884.5 | 18569.5 | 18938.5 | 29591.5 | 18630.4 | 12143.3 | 2712.3 | 20960.9 | 2712.3 | 17369.3 | 1261.2
31 | 18618.7 | 27542.6 | 23080.7 | 14895 | 23273.4 | 22034.1 | 34428.3 | 20156 | 12434.4 | 6184.3 | 21358.3 | 6184.3 | 17645.8 | 2510.2
31.25 | 22535.4 | 31574.4 | 27054.9 | 18028.3 | 28169.2 | 25259.5 | 39468 | 21503.9 | 12895.8 | 9639.5 | 21934.9 | 9639.5 | 17864.3 | 3639.6
31.5 | 17098.7 | 26269 | 21683.8 | 13679 | 21373.4 | 21015.2 | 32836.2 | 19744.4 | 13406.4 | 3692.3 | 22576.7 | 3692.3 | 18105.9 | 1638.6
31.75 | 14310 | 23618.2 | 18964.1 | 11448 | 17887.5 | 18894.6 | 29522.8 | 18893.7 | 13729.7 | 580.3 | 23037.9 | 580.3 | 18542.6 | 351
32 | 24911.7 | 34361.5 | 29636.6 | 19929.4 | 31139.7 | 27489.2 | 42951.9 | 22773.3 | 14094.9 | 10816.8 | 23544.7 | 10816.8 | 18749 | 4024.3
32.25 | 20462.5 | 30068.6 | 25265.5 | 16370 | 25578.1 | 24054.9 | 37585.8 | 24953.3 | 14675.4 | 5787.1 | 24281.5 | 5787.1 | 19166.2 | 5787.1
32.5 | 25974.8 | 35751 | 30862.9 | 20779.8 | 32468.5 | 28600.8 | 44688.7 | 23562.3 | 15293 | 10681.8 | 25069.1 | 10681.8 | 19567.8 | 3994.5
32.75 | 25565.5 | 35527.4 | 30546.5 | 20452.4 | 31956.8 | 28422 | 44409.3 | 23533.1 | 15788.7 | 9776.8 | 25750.6 | 9776.8 | 19817.1 | 3716.1
33 | 25248 | 35409.6 | 30328.8 | 20198.4 | 31560 | 28327.6 | 44261.9 | 23539.5 | 16262.2 | 8985.8 | 26423.8 | 8985.8 | 20070.6 | 3468.9
33.25 | 25582.6 | 35962.7 | 30772.6 | 20466 | 31978.2 | 28770.2 | 44953.4 | 24256 | 17353.6 | 8229 | 27733.8 | 8229 | 21027.7 | 3228.4
33.5 | 32101 | 42725.6 | 37413.3 | 25680.8 | 40126.3 | 34180.5 | 53407 | 26402 | 17983.9 | 14117.2 | 28608.5 | 14117.2 | 21332.7 | 5069.3
33.75 | 35793.4 | 46718.6 | 41256 | 28634.7 | 44741.7 | 37374.9 | 58398.3 | 39315.3 | 21121.3 | 14672.1 | 32046.5 | 14672.1 | 24643.2 | 14672.1
34 | 30710.5 | 42007.5 | 36359 | 24568.4 | 38388.1 | 33606 | 52509.4 | 28911.6 | 21967.7 | 8742.9 | 33264.6 | 8742.9 | 25501.7 | 3409.9
34.25 | 29284.2 | 40959.1 | 35121.7 | 23427.3 | 36605.2 | 32767.3 | 51198.9 | 28602.5 | 22166.9 | 7117.3 | 33841.8 | 7117.3 | 25725.7 | 2876.8
34.5 | 26624.3 | 38691.1 | 32657.7 | 21299.5 | 33280.4 | 30952.9 | 48363.9 | 30505.8 | 23876.3 | 2748.1 | 35943 | 2748.1 | 27757.7 | 2748.1
34.75 | 26021 | 38486.5 | 32253.7 | 20816.8 | 32526.2 | 30789.2 | 48108.2 | 30301.2 | 24242.6 | 1778.4 | 36708.1 | 1778.4 | 28522.8 | 1778.4
35 | 37173.1 | 50036.2 | 43604.6 | 29738.5 | 46466.3 | 40029 | 62545.3 | 33830.6 | 24611.4 | 12561.7 | 37474.5 | 12561.7 | 29194.2 | 4636.3
35.25 | 42544.6 | 55819.2 | 49181.9 | 34035.6 | 53180.7 | 44655.4 | 69774 | 35591.1 | 25353.7 | 17190.9 | 38628.4 | 17190.9 | 29560.8 | 6030.3
35.5 | 36612.4 | 50327.2 | 43469.8 | 29289.9 | 45765.5 | 40261.7 | 62909 | 33956.6 | 26053.8 | 10558.6 | 39768.6 | 10558.6 | 29933.6 | 4023
35.75 | 30301.5 | 44471.5 | 37386.5 | 24241.2 | 37876.9 | 35577.2 | 55589.4 | 34527.8 | 26862.8 | 3438.7 | 41032.8 | 3438.7 | 31089.1 | 3438.7
36 | 45299.7 | 59936.4 | 52618 | 36239.7 | 56624.6 | 47949.1 | 74920.5 | 38029.2 | 27516 | 17783.7 | 42152.7 | 17783.7 | 31801.1 | 6228
36.25 | 41020.7 | 56144.2 | 48582.4 | 32816.6 | 51275.9 | 44915.3 | 70180.2 | 36932.7 | 28063.6 | 12957.1 | 43187 | 12957.1 | 32142.5 | 4790.3
36.5 | 44081 | 59706.8 | 51893.9 | 35264.8 | 55101.2 | 47765.5 | 74633.5 | 38054.9 | 28641.7 | 15439.3 | 44267.5 | 15439.3 | 32503.7 | 5551.2
36.75 | 54858.7 | 71003.8 | 62931.2 | 43887 | 68573.4 | 56803 | 88754.8 | 41332.2 | 29201.6 | 25657.1 | 45346.7 | 25657.1 | 32844.6 | 8487.6
37 | 57835.1 | 74525.1 | 66180.1 | 46268.1 | 72293.9 | 59620.1 | 93156.4 | 42271.1 | 29268.7 | 28566.4 | 45958.7 | 28566.4 | 32976.5 | 9294.6
37.25 | 48341.4 | 65562.4 | 56951.9 | 38673.1 | 60426.7 | 52449.9 | 81953 | 39776.8 | 28737.7 | 19603.7 | 45958.7 | 19603.7 | 32976.5 | 6800.2
37.5 | 39534.6 | 57270.2 | 48402.4 | 31627.7 | 49418.3 | 45816.1 | 71587.7 | 37282.4 | 28223.2 | 11311.4 | 45958.7 | 11311.4 | 32976.5 | 4305.8
37.75 | 31720.8 | 49954.7 | 40837.7 | 25376.6 | 39651 | 39963.8 | 62443.4 | 34788 | 27724.8 | 3996 | 45958.7 | 3996 | 32976.5 | 1811.5
38 | 36886 | 56448.7 | 46667.3 | 29508.8 | 46107.5 | 45158.9 | 70560.8 | 36446.6 | 31765.4 | 5120.5 | 51328.1 | 5120.5 | 34216.5 | 2230.1
38.25 | 67459.2 | 87664.6 | 77561.9 | 53967.4 | 84324 | 70131.7 | 109580.7 | 45692 | 31984.9 | 35474.3 | 52190.3 | 35474.3 | 34488.1 | 11203.9
38.5 | 56242.8 | 77085.5 | 66664.1 | 44994.2 | 70303.4 | 61668.4 | 96356.9 | 42838 | 31347.5 | 24895.2 | 52190.3 | 24895.2 | 34488.1 | 8349.9
38.75 | 45784.8 | 67241.7 | 56513.2 | 36627.8 | 57230.9 | 53793.4 | 84052.1 | 39984 | 30733.3 | 15051.4 | 52190.3 | 15051.4 | 34488.1 | 5495.9
39 | 36382.6 | 58431.6 | 47407.1 | 29106.1 | 45478.2 | 46745.3 | 73039.5 | 37130.1 | 30141.3 | 6241.3 | 52190.3 | 6241.3 | 34488.1 | 2642
39.25 | 34460 | 57805.6 | 46132.8 | 27568 | 43075 | 46244.5 | 72257 | 35963 | 33474.6 | 985.4 | 56820.3 | 985.4 | 35395 | 568
39.5 | 37684.5 | 61739.1 | 49711.8 | 30147.6 | 47105.6 | 49391.3 | 77173.9 | 37604 | 33056.2 | 4628.3 | 57110.8 | 4628.3 | 35540 | 2064
39.75 | 37130.1 | 61872.7 | 49501.4 | 29704.1 | 46412.7 | 49498.2 | 77340.9 | 37685.7 | 32782.3 | 4347.8 | 57524.9 | 4347.8 | 35724.1 | 1961.5
40 | 39844 | 65255.6 | 52549.8 | 31875.2 | 49805.1 | 52204.5 | 81569.5 | 38940.8 | 32592.9 | 7251.1 | 58004.5 | 7251.1 | 35933.2 | 3007.6
40.25 | 37319.9 | 63385.6 | 50352.7 | 29855.9 | 46649.8 | 50708.5 | 79232 | 38306.6 | 32468.9 | 4851 | 58534.6 | 4851 | 36152.6 | 2154
40.5 | 36012.8 | 62716.6 | 49364.7 | 28810.2 | 45016 | 50173.3 | 78395.8 | 38088.7 | 32249.6 | 3763.2 | 58953.4 | 3763.2 | 36343.4 | 1745.3
40.75 | 37794.2 | 65119.6 | 51456.9 | 30235.3 | 47242.7 | 52095.7 | 81399.5 | 39014.7 | 32081.8 | 5712.4 | 59407.2 | 5712.4 | 36540.7 | 2474.1
41 | 34833 | 62766.4 | 48799.7 | 27866.4 | 43541.3 | 50213.1 | 78458 | 38153.1 | 31920 | 2913 | 59853.4 | 2913 | 36740 | 1413.1
41.25 | 36195.4 | 64721.8 | 50458.6 | 28956.3 | 45244.2 | 51777.4 | 80902.2 | 38937.4 | 31787.6 | 4407.8 | 60314 | 4407.8 | 36939.6 | 1997.8
41.5 | 35992.9 | 65099.3 | 50546.1 | 28794.3 | 44991.1 | 52079.4 | 81374.1 | 39115.4 | 31636.7 | 4356.2 | 60743.1 | 4356.2 | 37134.9 | 1980.5
41.75 | 36704.8 | 66377.9 | 51541.4 | 29363.9 | 45881.1 | 53102.4 | 82972.4 | 39625.8 | 31501.7 | 5203.1 | 61174.8 | 5203.1 | 37326.7 | 2299.1
42 | 35979.1 | 66207.4 | 51093.2 | 28783.3 | 44973.8 | 52965.9 | 82759.2 | 39598.5 | 31410.5 | 4568.6 | 61638.7 | 4568.6 | 37533.2 | 2065.2
42.25 | 36888.1 | 67660.1 | 52274.1 | 29510.5 | 46110.2 | 54128.1 | 84575.2 | 40217.6 | 31337.4 | 5550.8 | 62109.4 | 5550.8 | 37785.9 | 2431.8
42.5 | 38288.1 | 69596.2 | 53942.2 | 30630.5 | 47860.2 | 55677 | 86995.3 | 40941.9 | 31480.7 | 6807.4 | 62788.8 | 6807.4 | 38056.2 | 2885.7
42.75 | 36960.4 | 68799.7 | 52880.1 | 29568.4 | 46200.6 | 55039.8 | 85999.7 | 40689.6 | 31489.5 | 5470.9 | 63328.8 | 5470.9 | 38281.7 | 2407.9
43 | 36444.9 | 68807.8 | 52626.3 | 29155.9 | 45556.1 | 55046.2 | 86009.7 | 40728.3 | 31481.6 | 4963.2 | 63844.5 | 4963.2 | 38505.7 | 2222.6
43.25 | 39231.3 | 72110 | 55670.7 | 31385.1 | 49039.2 | 57688 | 90137.5 | 41949.6 | 31490.6 | 7740.7 | 64369.3 | 7740.7 | 38727.2 | 3222.4
43.5 | 39851.2 | 73242.4 | 56546.8 | 31881 | 49814 | 58593.9 | 91553 | 42376.4 | 31737 | 8114.2 | 65128.2 | 8114.2 | 39021.4 | 3355.1
43.75 | 36449.1 | 70351.5 | 53400.3 | 29159.3 | 45561.3 | 56281.2 | 87939.4 | 41370.1 | 31787.5 | 4661.6 | 65689.9 | 4661.6 | 39253.8 | 2116.3
44 | 42666.9 | 77074.5 | 59870.7 | 34133.5 | 53333.6 | 61659.6 | 96343.2 | 43764.2 | 31904 | 10762.9 | 66311.7 | 10762.9 | 39509.6 | 4254.6
44.25 | 38799.3 | 73714.6 | 56256.9 | 31039.4 | 48499.1 | 58971.7 | 92143.2 | 42642 | 32206.9 | 6592.4 | 67122.2 | 6592.4 | 39811.1 | 2830.9
44.5 | 38462.6 | 73885.6 | 56174.1 | 30770.1 | 48078.3 | 59108.5 | 92357.1 | 42734.5 | 32387.1 | 6075.5 | 67810.1 | 6075.5 | 40087 | 2647.6
44.75 | 37278 | 73204.8 | 55241.4 | 29822.4 | 46597.5 | 58563.9 | 91506.1 | 42517.3 | 32373.2 | 4904.8 | 68300.1 | 4904.8 | 40299.9 | 2217.3
45 | 45158.4 | 81582.2 | 63370.3 | 36126.8 | 56448 | 65265.7 | 101977.7 | 45450.9 | 32344 | 12814.4 | 68767.7 | 12814.4 | 40509.5 | 4941.4

## SRD WTG-25
Depth (m) | SRD AH-FF (kN) | SRD AH-NFF (kN) | SRD MEAN (kN) | SRD AH-FF-LB (kN) | SRD AH-FF-UB (kN) | SRD AH-NFF-LB (kN) | SRD AH-NFF-UB (kN) | Static Cap (kN) | Shaft AH-FF (kN) | Tip AH-FF (kN) | Shaft AH-NFF (kN) | Tip AH-NFF (kN) | Shaft SC (kN) | Tip SC (kN)
0.5 | 51.7 | 51.8 | 51.8 | 41.4 | 64.7 | 41.4 | 64.8 | 24.8 | 3.7 | 48 | 3.8 | 48 | 2.8 | 22
0.75 | 50 | 50.2 | 50.1 | 40 | 62.5 | 40.1 | 62.7 | 26.6 | 5.7 | 44.3 | 5.9 | 44.3 | 4.6 | 22
1 | 50.6 | 51 | 50.8 | 40.5 | 63.3 | 40.8 | 63.7 | 29.5 | 8.8 | 41.8 | 9.2 | 41.8 | 7.6 | 22
1.25 | 50.9 | 51.4 | 51.2 | 40.7 | 63.6 | 41.1 | 64.3 | 31.7 | 10.9 | 40 | 11.4 | 40 | 9.7 | 22
1.5 | 1515.8 | 1516.6 | 1516.2 | 1212.6 | 1894.7 | 1213.2 | 1895.7 | 480.3 | 28 | 1487.8 | 28.8 | 1487.8 | 19.1 | 461.2
1.75 | 1046.3 | 1048.4 | 1047.3 | 837.1 | 1307.9 | 838.7 | 1310.5 | 370.8 | 55.3 | 991.1 | 57.3 | 991.1 | 33.3 | 337.6
2 | 2096.5 | 2101.5 | 2099 | 1677.2 | 2620.6 | 1681.2 | 2626.9 | 675.9 | 121 | 1975.6 | 125.9 | 1975.6 | 61.3 | 614.6
2.25 | 1247.4 | 1258.7 | 1253 | 997.9 | 1559.2 | 1006.9 | 1573.4 | 464.3 | 195.8 | 1051.6 | 207.1 | 1051.6 | 93 | 371.3
2.5 | 2254.3 | 2274.2 | 2264.2 | 1803.4 | 2817.9 | 1819.3 | 2842.7 | 792.7 | 268.5 | 1985.8 | 288.3 | 1985.8 | 150.8 | 642
2.75 | 1506.5 | 1537.2 | 1521.8 | 1205.2 | 1883.1 | 1229.7 | 1921.5 | 603.3 | 320.8 | 1185.7 | 351.5 | 1185.7 | 178.5 | 424.7
3 | 1129.3 | 1172.5 | 1150.9 | 903.5 | 1411.7 | 938 | 1465.7 | 504.6 | 380.7 | 748.7 | 423.9 | 748.7 | 210.5 | 294.1
3.25 | 1981.8 | 2039.7 | 2010.8 | 1585.5 | 2477.3 | 1631.7 | 2549.6 | 810 | 472.2 | 1509.6 | 530.1 | 1509.6 | 275.1 | 534.9
3.5 | 2863.6 | 2939 | 2901.3 | 2290.9 | 3579.5 | 2351.2 | 3673.7 | 1088.8 | 562.7 | 2300.9 | 638 | 2300.9 | 318.8 | 770.1
3.75 | 1640.8 | 1736.8 | 1688.8 | 1312.6 | 2051 | 1389.4 | 2171 | 1371.2 | 624.1 | 1016.7 | 720.1 | 1016.7 | 354.4 | 1016.7
4 | 2073.3 | 2191.2 | 2132.2 | 1658.6 | 2591.6 | 1753 | 2739 | 938 | 688.5 | 1384.8 | 806.3 | 1384.8 | 422 | 515.9
4.25 | 1237.5 | 1378.2 | 1307.8 | 990 | 1546.9 | 1102.5 | 1722.7 | 986.2 | 804.2 | 433.3 | 944.8 | 433.3 | 552.9 | 433.3
4.5 | 1159.3 | 1323.2 | 1241.3 | 927.5 | 1449.2 | 1058.6 | 1654 | 929.2 | 836.6 | 322.7 | 1000.5 | 322.7 | 606.5 | 322.7
4.75 | 1412.9 | 1599.7 | 1506.3 | 1130.3 | 1766.1 | 1279.7 | 1999.6 | 1198.4 | 843.5 | 569.3 | 1030.3 | 569.3 | 629.1 | 569.3
5 | 1689.3 | 1899.2 | 1794.3 | 1351.5 | 2111.7 | 1519.4 | 2374 | 1058.8 | 931.9 | 757.4 | 1141.8 | 757.4 | 735.5 | 323.4
5.25 | 2002.1 | 2235.7 | 2118.9 | 1601.7 | 2502.6 | 1788.6 | 2794.6 | 1806.6 | 994.7 | 1007.4 | 1228.3 | 1007.4 | 799.2 | 1007.4
5.5 | 2127.3 | 2386.3 | 2256.8 | 1701.9 | 2659.2 | 1909.1 | 2982.9 | 1329.3 | 1096.1 | 1031.3 | 1355.1 | 1031.3 | 904.5 | 424.9
5.75 | 5300.2 | 5587.3 | 5443.8 | 4240.2 | 6625.3 | 4469.9 | 6984.2 | 2311.7 | 1232.1 | 4068.2 | 1519.2 | 4068.2 | 967.3 | 1344.3
6 | 5371.3 | 5692.9 | 5532.1 | 4297.1 | 6714.1 | 4554.3 | 7116.1 | 2393.9 | 1418.2 | 3953.1 | 1739.8 | 3953.1 | 1071.1 | 1322.9
6.25 | 7732.7 | 8096 | 7914.3 | 6186.2 | 9665.9 | 6476.8 | 10120 | 3073.6 | 1629.6 | 6103.1 | 1992.9 | 6103.1 | 1159.2 | 1914.4
6.5 | 6587.1 | 7003.1 | 6795.1 | 5269.7 | 8233.9 | 5602.5 | 8753.9 | 2816.1 | 1877.3 | 4709.8 | 2293.3 | 4709.8 | 1262.2 | 1553.9
6.75 | 5925.7 | 6401.8 | 6163.8 | 4740.6 | 7407.1 | 5121.5 | 8002.3 | 2677.9 | 2025.1 | 3900.6 | 2501.3 | 3900.6 | 1340.6 | 1337.3
7 | 6281.4 | 6821.8 | 6551.6 | 5025.1 | 7851.8 | 5457.5 | 8527.3 | 2828.3 | 2161.5 | 4119.9 | 2701.9 | 4119.9 | 1419.4 | 1408.9
7.25 | 7707.6 | 8317.8 | 8012.7 | 6166 | 9634.5 | 6654.2 | 10397.2 | 3277.2 | 2355.9 | 5351.6 | 2966.1 | 5351.6 | 1513.8 | 1763.4
7.5 | 4511.9 | 5198.9 | 4855.4 | 3609.5 | 5639.9 | 4159.1 | 6498.7 | 2410.4 | 2534.1 | 1977.8 | 3221.1 | 1977.8 | 1636.5 | 773.9
7.75 | 5996.2 | 6762.9 | 6379.5 | 4797 | 7495.2 | 5410.3 | 8453.6 | 2920.3 | 2650.9 | 3345.3 | 3417.5 | 3345.3 | 1714 | 1206.3
8 | 4454.1 | 5303.8 | 4878.9 | 3563.3 | 5567.6 | 4243 | 6629.7 | 2480.8 | 2761.3 | 1692.8 | 3611 | 1692.8 | 1793.1 | 687.7
8.25 | 3888.2 | 4822.4 | 4355.3 | 3110.6 | 4860.3 | 3857.9 | 6028 | 2985.2 | 2931 | 957.2 | 3865.2 | 957.2 | 2028 | 957.2
8.5 | 3744 | 4763.2 | 4253.6 | 2995.2 | 4680 | 3810.6 | 5954 | 2925.2 | 3086 | 658 | 4105.2 | 658 | 2267.2 | 658
8.75 | 3998.1 | 5101 | 4549.6 | 3198.5 | 4997.7 | 4080.8 | 6376.2 | 3263 | 3171.5 | 826.6 | 4274.4 | 826.6 | 2436.4 | 826.6
9 | 4019.5 | 5204.9 | 4612.2 | 3215.6 | 5024.4 | 4163.9 | 6506.1 | 3365.6 | 3295.8 | 723.7 | 4481.2 | 723.7 | 2641.9 | 723.7
9.25 | 4625 | 5891.8 | 5258.4 | 3700 | 5781.3 | 4713.4 | 7364.7 | 3265.6 | 3305.3 | 1319.7 | 4572.1 | 1319.7 | 2693.9 | 571.8
9.5 | 7157.8 | 8505.7 | 7831.8 | 5726.3 | 8947.3 | 6804.6 | 10632.2 | 4144.2 | 3408.2 | 3749.6 | 4756.1 | 3749.6 | 2772.6 | 1371.7
9.75 | 6886.7 | 8319.1 | 7602.9 | 5509.4 | 8608.4 | 6655.3 | 10398.8 | 4113.5 | 3532.6 | 3354.1 | 4965 | 3354.1 | 2857.6 | 1255.8
10 | 6836.4 | 8356 | 7596.2 | 5469.1 | 8545.5 | 6684.8 | 10444.9 | 6184.4 | 3816.8 | 3019.6 | 5336.4 | 3019.6 | 3164.8 | 3019.6
10.25 | 8124.2 | 9735.9 | 8930.1 | 6499.4 | 10155.2 | 7788.7 | 12169.9 | 4817.8 | 4001.6 | 4122.6 | 5613.4 | 4122.6 | 3313.4 | 1504.4
10.5 | 6878.8 | 8587.8 | 7733.3 | 5503 | 8598.4 | 6870.2 | 10734.8 | 6129.8 | 4186.4 | 2692.4 | 5895.4 | 2692.4 | 3437.4 | 2692.4
10.75 | 6179.3 | 7990.2 | 7084.8 | 4943.5 | 7724.2 | 6392.2 | 9987.8 | 4573.1 | 4516 | 1663.3 | 6326.9 | 1663.3 | 3861.3 | 711.8
11 | 5310.9 | 7224.4 | 6267.7 | 4248.7 | 6638.6 | 5779.5 | 9030.5 | 4733.3 | 4635.6 | 675.2 | 6549.2 | 675.2 | 4058.1 | 675.2
11.25 | 5490.9 | 7506 | 6498.4 | 4392.7 | 6863.6 | 6004.8 | 9382.5 | 5010.6 | 4682.1 | 808.8 | 6697.3 | 808.8 | 4201.8 | 808.8
11.5 | 5728.3 | 7843.4 | 6785.8 | 4582.6 | 7160.3 | 6274.7 | 9804.2 | 5346 | 4766.5 | 961.7 | 6881.7 | 961.7 | 4384.3 | 961.7
11.75 | 5423.7 | 7637.2 | 6530.4 | 4338.9 | 6779.6 | 6109.8 | 9546.5 | 5136.3 | 4793 | 630.7 | 7006.5 | 630.7 | 4505.6 | 630.7
12 | 5327.2 | 7637.1 | 6482.2 | 4261.8 | 6659.1 | 6109.7 | 9546.4 | 5135.3 | 4812.2 | 515 | 7122.1 | 515 | 4620.2 | 515
12.25 | 5454.5 | 7858.1 | 6656.3 | 4363.6 | 6818.1 | 6286.5 | 9822.6 | 5352 | 4787.4 | 667.1 | 7191 | 667.1 | 4684.9 | 667.1
12.5 | 5844.9 | 8340.4 | 7092.6 | 4675.9 | 7306.1 | 6672.3 | 10425.5 | 5830.7 | 4868.2 | 976.7 | 7363.7 | 976.7 | 4854 | 976.7
12.75 | 5311.2 | 7897.6 | 6604.4 | 4249 | 6639.1 | 6318 | 9871.9 | 5201 | 4898.4 | 412.9 | 7484.7 | 412.9 | 4972.1 | 228.9
13 | 5976.9 | 8652 | 7314.5 | 4781.5 | 7471.1 | 6921.6 | 10815 | 6117.4 | 4908.8 | 1068.1 | 7583.9 | 1068.1 | 5049.3 | 1068.1
13.25 | 5491.3 | 8254.6 | 6872.9 | 4393 | 6864.1 | 6603.7 | 10318.2 | 5488.1 | 4992.7 | 498.6 | 7755.9 | 498.6 | 5218.6 | 269.5
13.5 | 5680.6 | 8530.9 | 7105.8 | 4544.5 | 7100.8 | 6824.7 | 10663.6 | 5649.6 | 5030.9 | 649.7 | 7881.2 | 649.7 | 5312.6 | 337.1
13.75 | 5515.3 | 8452.2 | 6983.7 | 4412.2 | 6894.1 | 6761.8 | 10565.3 | 5733.4 | 5163.6 | 351.7 | 8100.5 | 351.7 | 5530.7 | 202.7
14 | 5557.7 | 8580.1 | 7068.9 | 4446.1 | 6947.1 | 6864.1 | 10725.1 | 5835.3 | 5168.4 | 389.3 | 8190.8 | 389.3 | 5614.1 | 221.2
14.25 | 5714.4 | 8820.9 | 7267.6 | 4571.5 | 7143 | 7056.7 | 11026.1 | 6018.7 | 5221.8 | 492.6 | 8328.2 | 492.6 | 5748.8 | 269.9
14.5 | 5556 | 8745.5 | 7150.8 | 4444.8 | 6945 | 6996.4 | 10931.9 | 6055.1 | 5281.8 | 274.2 | 8471.3 | 274.2 | 5889 | 166.1
14.75 | 5587.8 | 8858.7 | 7223.2 | 4470.2 | 6984.7 | 7087 | 11073.4 | 6128.5 | 5243.2 | 344.6 | 8514.1 | 344.6 | 5927 | 201.5
15 | 5471.8 | 8822.5 | 7147.2 | 4377.5 | 6839.8 | 7058 | 11028.2 | 6156.7 | 5261.6 | 210.3 | 8612.2 | 210.3 | 6022.8 | 133.8
15.25 | 5440.3 | 8869 | 7154.7 | 4352.2 | 6800.4 | 7095.2 | 11086.3 | 6189.4 | 5208 | 232.3 | 8636.7 | 232.3 | 6043.7 | 145.8
15.5 | 5472.8 | 8977.8 | 7225.3 | 4378.3 | 6841 | 7182.3 | 11222.3 | 6287.9 | 5224.5 | 248.4 | 8729.4 | 248.4 | 6133.4 | 154.6
15.75 | 5946.1 | 9526 | 7736.1 | 4756.9 | 7432.7 | 7620.8 | 11907.5 | 6923.3 | 5220.4 | 725.7 | 8800.3 | 725.7 | 6197.6 | 725.7
16 | 5960 | 9614.3 | 7787.2 | 4768 | 7450 | 7691.5 | 12017.9 | 7011.6 | 5352.7 | 607.4 | 9007 | 607.4 | 6404.3 | 607.4
16.25 | 5958.6 | 9686.4 | 7822.5 | 4766.9 | 7448.2 | 7749.1 | 12108 | 7080.3 | 5342.8 | 615.7 | 9070.6 | 615.7 | 6464.6 | 615.7
16.5 | 5973.9 | 9773.8 | 7873.8 | 4779.1 | 7467.3 | 7819 | 12217.2 | 7164.3 | 5366.5 | 607.4 | 9166.4 | 607.4 | 6556.9 | 607.4
16.75 | 6228.3 | 10099.4 | 8163.9 | 4982.7 | 7785.4 | 8079.5 | 12624.2 | 7478.7 | 5359.6 | 868.7 | 9230.6 | 868.7 | 6609.9 | 868.7
17 | 5739.4 | 9681 | 7710.2 | 4591.5 | 7174.2 | 7744.8 | 12101.2 | 6937.2 | 5432.4 | 307 | 9373.9 | 307 | 6750.1 | 187.1
17.25 | 5729.5 | 9740.4 | 7735 | 4583.6 | 7161.8 | 7792.3 | 12175.5 | 6992.2 | 5424.1 | 305.4 | 9435 | 305.4 | 6805.5 | 186.7
17.5 | 6356.8 | 10436.1 | 8396.4 | 5085.5 | 7946 | 8348.9 | 13045.1 | 7799.8 | 5439.9 | 916.9 | 9519.2 | 916.9 | 6882.9 | 916.9
17.75 | 5932 | 10079.2 | 8005.6 | 4745.6 | 7415 | 8063.3 | 12599 | 7263.8 | 5509.9 | 422.2 | 9657 | 422.2 | 7018.1 | 245.7
18 | 5807 | 10021.3 | 7914.1 | 4645.6 | 7258.8 | 8017 | 12526.6 | 7279.6 | 5540.2 | 266.9 | 9754.4 | 266.9 | 7111.6 | 168
18.25 | 7085.2 | 11365.9 | 9225.5 | 5668.2 | 8856.5 | 9092.7 | 14207.3 | 7914.6 | 5590.8 | 1494.4 | 9871.4 | 1494.4 | 7206.9 | 707.7
18.5 | 8437.9 | 12785.7 | 10611.8 | 6750.3 | 10547.4 | 10228.6 | 15982.2 | 8470.1 | 5702.3 | 2735.6 | 10050.1 | 2735.6 | 7295.9 | 1174.2
18.75 | 7759.4 | 12177.5 | 9968.4 | 6207.5 | 9699.2 | 9742 | 15221.9 | 9388.8 | 6048.6 | 1710.7 | 10466.8 | 1710.7 | 7678 | 1710.7
19 | 7739.1 | 12232.4 | 9985.7 | 6191.3 | 9673.9 | 9785.9 | 15290.5 | 8693.5 | 6326.7 | 1412.4 | 10820 | 1412.4 | 8013.6 | 679.9
19.25 | 7299.4 | 11869.3 | 9584.4 | 5839.5 | 9124.3 | 9495.4 | 14836.6 | 9054.1 | 6507 | 792.5 | 11076.8 | 792.5 | 8261.7 | 792.5
19.5 | 7788.2 | 12435.1 | 10111.7 | 6230.5 | 9735.2 | 9948.1 | 15543.9 | 9014.2 | 6592.7 | 1195.5 | 11239.7 | 1195.5 | 8420.1 | 594.1
19.75 | 8133.4 | 12857.7 | 10495.5 | 6506.7 | 10166.8 | 10286.1 | 16072.1 | 10020.8 | 6768.5 | 1365 | 11492.7 | 1365 | 8655.8 | 1365
20 | 8263.9 | 13066.7 | 10665.3 | 6611.1 | 10329.9 | 10453.4 | 16333.4 | 10211.2 | 6910.2 | 1353.7 | 11713.1 | 1353.7 | 8857.5 | 1353.7
20.25 | 7949.4 | 12831.6 | 10390.5 | 6359.5 | 9936.7 | 10265.3 | 16039.5 | 9968.5 | 7035.6 | 913.8 | 11917.9 | 913.8 | 9054.8 | 913.8
20.5 | 8211.5 | 13173.6 | 10692.6 | 6569.2 | 10264.4 | 10538.9 | 16467 | 10307.2 | 7178.7 | 1032.8 | 12140.8 | 1032.8 | 9274.4 | 1032.8
20.75 | 7705.4 | 12747.4 | 10226.4 | 6164.3 | 9631.8 | 10198 | 15934.3 | 9686.4 | 7242.9 | 462.5 | 12284.9 | 462.5 | 9414.4 | 272
21 | 8101.3 | 13222.8 | 10662 | 6481 | 10126.6 | 10578.3 | 16528.5 | 9959.6 | 7308.8 | 792.5 | 12430.4 | 792.5 | 9532.7 | 426.9
21.25 | 8463.7 | 13665.5 | 11064.6 | 6771 | 10579.6 | 10932.4 | 17081.8 | 10764.3 | 7469.8 | 993.9 | 12671.6 | 993.9 | 9770.4 | 993.9
21.5 | 7999.7 | 13281.4 | 10640.6 | 6399.8 | 9999.6 | 10625.2 | 16601.8 | 10139.3 | 7455.5 | 544.2 | 12737.2 | 544.2 | 9826 | 313.3
21.75 | 7710.5 | 13071.2 | 10390.8 | 6168.4 | 9638.1 | 10456.9 | 16338.9 | 10045.4 | 7422.4 | 288 | 12783.1 | 288 | 9860.7 | 184.7
22 | 7672.8 | 13111.3 | 10392.1 | 6138.3 | 9591 | 10489.1 | 16389.2 | 10078.3 | 7388.5 | 284.3 | 12827 | 284.3 | 9895.2 | 183.1
22.25 | 7658.9 | 13174.1 | 10416.5 | 6127.2 | 9573.7 | 10539.3 | 16467.7 | 10122.3 | 7347.2 | 311.7 | 12862.4 | 311.7 | 9924.3 | 198
22.5 | 7789.4 | 13380.4 | 10584.9 | 6231.6 | 9736.8 | 10704.3 | 16725.5 | 10277.6 | 7378.7 | 410.7 | 12969.7 | 410.7 | 10028 | 249.6
22.75 | 8462.6 | 14129.2 | 11295.9 | 6770 | 10578.2 | 11303.4 | 17661.5 | 11164.7 | 7509.2 | 953.4 | 13175.9 | 953.4 | 10211.3 | 953.4
23 | 7974.2 | 13717.6 | 10845.9 | 6379.3 | 9967.7 | 10974 | 17146.9 | 10605.7 | 7605.1 | 369 | 13348.5 | 369 | 10376.6 | 229.1
23.25 | 7947.1 | 13766.5 | 10856.8 | 6357.6 | 9933.8 | 11013.2 | 17208.1 | 10647.1 | 7575.4 | 371.6 | 13394.9 | 371.6 | 10416.2 | 230.9
23.5 | 7903.8 | 13798.3 | 10851 | 6323 | 9879.7 | 11038.6 | 17247.9 | 10681.9 | 7553.9 | 349.9 | 13448.4 | 349.9 | 10461.9 | 220
23.75 | 7817 | 13785.6 | 10801.3 | 6253.6 | 9771.2 | 11028.5 | 17232 | 10686.4 | 7519.3 | 297.7 | 13487.9 | 297.7 | 10493.8 | 192.6
24 | 7806.7 | 13848.4 | 10827.5 | 6245.3 | 9758.3 | 11078.7 | 17310.5 | 10731.8 | 7483 | 323.7 | 13524.7 | 323.7 | 10525 | 206.8
24.25 | 7764.5 | 13878.5 | 10821.5 | 6211.6 | 9705.7 | 11102.8 | 17348.1 | 10764.6 | 7466.3 | 298.2 | 13580.3 | 298.2 | 10571.1 | 193.5
24.5 | 7722.4 | 13907.7 | 10815.1 | 6178 | 9653.1 | 11126.2 | 17384.7 | 10792.1 | 7431.9 | 290.5 | 13617.2 | 290.5 | 10602.5 | 189.6
24.75 | 7719.6 | 13975.3 | 10847.4 | 6175.7 | 9649.5 | 11180.2 | 17469.1 | 10839.5 | 7396.2 | 323.4 | 13651.9 | 323.4 | 10631.8 | 207.7
25 | 7613.4 | 13938.5 | 10775.9 | 6090.7 | 9516.7 | 11150.8 | 17423.1 | 10831 | 7365.3 | 248.1 | 13690.5 | 248.1 | 10664.2 | 166.8
25.25 | 7648.8 | 14042.5 | 10845.6 | 6119 | 9561 | 11234 | 17553.1 | 10898.8 | 7330.8 | 318 | 13724.5 | 318 | 10693.3 | 205.5
25.5 | 7632.3 | 14093.7 | 10863 | 6105.9 | 9540.4 | 11275 | 17617.1 | 10942.5 | 7312 | 320.4 | 13773.3 | 320.4 | 10735.4 | 207.1
25.75 | 7593 | 14121.2 | 10857.1 | 6074.4 | 9491.2 | 11297 | 17651.5 | 10968.6 | 7282.1 | 310.9 | 13810.3 | 310.9 | 10766.4 | 202.2
26 | 7596.7 | 14191.1 | 10893.9 | 6077.4 | 9495.9 | 11352.9 | 17738.8 | 11018.7 | 7259.1 | 337.7 | 13853.4 | 337.7 | 10801.7 | 217
26.25 | 7552.1 | 14211.7 | 10881.9 | 6041.7 | 9440.1 | 11369.4 | 17764.6 | 11041.4 | 7232.7 | 319.3 | 13892.4 | 319.3 | 10833.9 | 207.5
26.5 | 8047.8 | 14772 | 11409.9 | 6438.2 | 10059.7 | 11817.6 | 18465 | 11707 | 7236.3 | 811.5 | 13960.5 | 811.5 | 10895.5 | 811.5
26.75 | 7593.4 | 14381.6 | 10987.5 | 6074.7 | 9491.7 | 11505.3 | 17977 | 11172.1 | 7218.3 | 375.1 | 14006.5 | 375.1 | 10934.2 | 237.9
27 | 7812.6 | 14664.2 | 11238.4 | 6250.1 | 9765.7 | 11731.4 | 18330.3 | 11337.2 | 7231.4 | 581.2 | 14083.1 | 581.2 | 10993.9 | 343.3
27.25 | 9313.3 | 16228.2 | 12770.8 | 7450.7 | 11641.7 | 12982.5 | 20285.2 | 13112.4 | 7264.3 | 2049 | 14179.1 | 2049 | 11063.4 | 2049
27.5 | 8702.2 | 15681.4 | 12191.8 | 6961.7 | 10877.7 | 12545.1 | 19601.7 | 12547 | 7439.5 | 1262.7 | 14418.7 | 1262.7 | 11284.3 | 1262.7
27.75 | 10992.8 | 18037.8 | 14515.3 | 8794.2 | 13741 | 14430.2 | 22547.2 | 12909.6 | 7603.6 | 3389.3 | 14648.5 | 3389.3 | 11410.3 | 1499.2
28 | 8608.4 | 15723.1 | 12165.7 | 6886.7 | 10760.5 | 12578.5 | 19653.9 | 12133.3 | 7898.7 | 709.7 | 15013.4 | 709.7 | 11725.3 | 408
28.25 | 12705.4 | 19891.6 | 16298.5 | 10164.4 | 15881.8 | 15913.3 | 24864.5 | 13791.9 | 7985.7 | 4719.7 | 15171.9 | 4719.7 | 11810.1 | 1981.8
28.5 | 9799.1 | 17061.6 | 13430.4 | 7839.3 | 12248.9 | 13649.3 | 21327 | 12745.8 | 8256 | 1543.1 | 15518.5 | 1543.1 | 11963.9 | 781.9
28.75 | 11084.6 | 18430.1 | 14757.4 | 8867.7 | 13855.8 | 14744.1 | 23037.6 | 13581.2 | 8784.8 | 2299.9 | 16130.2 | 2299.9 | 12489.1 | 1092.1
29 | 14204.7 | 21640.9 | 17922.8 | 11363.7 | 17755.8 | 17312.7 | 27051.1 | 17979.3 | 9461.2 | 4743.5 | 16897.4 | 4743.5 | 13235.8 | 4743.5
29.25 | 14485.7 | 22021.1 | 18253.4 | 11588.5 | 18107.1 | 17616.8 | 27526.3 | 15421.7 | 9759.7 | 4726 | 17295.1 | 4726 | 13425.3 | 1996.4
29.5 | 15592.3 | 23235 | 19413.6 | 12473.8 | 19490.3 | 18588 | 29043.7 | 15877.1 | 10126.2 | 5466 | 17768.9 | 5466 | 13619.8 | 2257.3
29.75 | 17321 | 25080 | 21200.5 | 13856.8 | 21651.3 | 20064 | 31350 | 16534.1 | 10494.5 | 6826.5 | 18253.5 | 6826.5 | 13813.1 | 2721
30 | 18664.1 | 26550.3 | 22607.2 | 14931.3 | 23330.1 | 21240.2 | 33187.9 | 17055.8 | 10960.4 | 7703.7 | 18846.6 | 7703.7 | 14041.7 | 3014.2
30.25 | 18340.8 | 26365.9 | 22353.3 | 14672.6 | 22926 | 21092.7 | 32957.4 | 17031.7 | 11358.1 | 6982.7 | 19383.3 | 6982.7 | 14250.1 | 2781.5
30.5 | 16435.1 | 24608.5 | 20521.8 | 13148.1 | 20543.9 | 19686.8 | 30760.6 | 16465.5 | 11706.9 | 4728.3 | 19880.2 | 4728.3 | 14452.4 | 2013.1
30.75 | 15811.2 | 24138.4 | 19974.8 | 12648.9 | 19764 | 19310.7 | 30173 | 18536.5 | 11909.9 | 3901.2 | 20237.2 | 3901.2 | 14635.2 | 3901.2
31 | 14119.4 | 22609.1 | 18364.2 | 11295.5 | 17649.2 | 18087.3 | 28261.4 | 16259.7 | 12614.4 | 1505 | 21104.1 | 1505 | 15482 | 777.6
31.25 | 19664.3 | 28320.7 | 23992.5 | 15731.5 | 24580.4 | 22656.6 | 35400.9 | 18392.9 | 12885.3 | 6779 | 21541.7 | 6779 | 15663.1 | 2729.8
31.5 | 20073.9 | 28905.4 | 24489.6 | 16059.1 | 25092.3 | 23124.3 | 36131.8 | 18627.1 | 13267.6 | 6806.3 | 22099.1 | 6806.3 | 15883.9 | 2743.2
31.75 | 27315.6 | 36333.8 | 31824.7 | 21852.5 | 34144.5 | 29067 | 45417.3 | 21007.2 | 13802.4 | 13513.2 | 22820.6 | 13513.2 | 16141.7 | 4865.6
32 | 28589.9 | 37821 | 33205.5 | 22871.9 | 35737.4 | 30256.8 | 47276.3 | 21486.5 | 14715.9 | 13874 | 23947 | 13874 | 16505.2 | 4981.3
32.25 | 27429.4 | 36900.7 | 32165.1 | 21943.5 | 34286.8 | 29520.6 | 46125.9 | 21247.6 | 15358.5 | 12071 | 24829.7 | 12071 | 16805.1 | 4442.5
32.5 | 20919 | 30648.7 | 25783.9 | 16735.2 | 26148.7 | 24519 | 38310.9 | 19236.9 | 15851.3 | 5067.7 | 25581 | 5067.7 | 17078.3 | 2158.6
32.75 | 27914.3 | 37908.1 | 32911.2 | 22331.4 | 34892.8 | 30326.5 | 47385.2 | 21658.4 | 16102.1 | 11812.2 | 26095.9 | 11812.2 | 17282.5 | 4375.9
33 | 24955.8 | 35226.5 | 30091.2 | 19964.7 | 31194.8 | 28181.2 | 44033.1 | 20845.6 | 16635.9 | 8319.9 | 26906.6 | 8319.9 | 17573.2 | 3272.4
33.25 | 23419.7 | 33975.8 | 28697.8 | 18735.8 | 29274.7 | 27180.7 | 42469.8 | 20465.8 | 16859.8 | 6559.9 | 27415.9 | 6559.9 | 17777.6 | 2688.1
33.5 | 22304.9 | 33152.8 | 27728.8 | 17843.9 | 27881.1 | 26522.3 | 41441 | 20198.6 | 17287.8 | 5017.1 | 28135.7 | 5017.1 | 18045.7 | 2152.9
33.75 | 28572.1 | 39726.9 | 34149.5 | 22857.6 | 35715.1 | 31781.5 | 49658.6 | 22978.2 | 18270.9 | 10301.2 | 29425.7 | 10301.2 | 19051.7 | 3926.6
34 | 34305.2 | 45782.8 | 40044 | 27444.2 | 42881.6 | 36626.2 | 57228.5 | 24879.2 | 18877.8 | 15427.5 | 30355.3 | 15427.5 | 19373.6 | 5505.6
34.25 | 47750.7 | 59579.3 | 53665 | 38200.6 | 59688.4 | 47663.4 | 74474.1 | 28788.9 | 19846.7 | 27904 | 31675.3 | 27904 | 19754.4 | 9034.5

## SRD WTG-26
Depth (m) | SRD AH-FF (kN) | SRD AH-NFF (kN) | SRD MEAN (kN) | SRD AH-FF-LB (kN) | SRD AH-FF-UB (kN) | SRD AH-NFF-LB (kN) | SRD AH-NFF-UB (kN) | Static Cap (kN) | Shaft AH-FF (kN) | Tip AH-FF (kN) | Shaft AH-NFF (kN) | Tip AH-NFF (kN) | Shaft SC (kN) | Tip SC (kN)
0.5 | 75.9 | 76 | 75.9 | 60.7 | 94.8 | 60.8 | 95 | 33.9 | 5.1 | 70.8 | 5.2 | 70.8 | 3.6 | 30.3
0.75 | 73.1 | 73.4 | 73.2 | 58.5 | 91.4 | 58.7 | 91.7 | 36.1 | 7.8 | 65.2 | 8.1 | 65.2 | 5.8 | 30.3
1 | 73.7 | 74.3 | 74 | 59 | 92.2 | 59.4 | 92.8 | 39.8 | 12.1 | 61.6 | 12.7 | 61.6 | 9.5 | 30.3
1.25 | 74.1 | 74.9 | 74.5 | 59.3 | 92.6 | 59.9 | 93.6 | 42.5 | 15 | 59.1 | 15.8 | 59.1 | 12.2 | 30.3
1.5 | 78 | 79.1 | 78.6 | 62.4 | 97.5 | 63.3 | 98.9 | 47.3 | 19.5 | 58.5 | 20.7 | 58.5 | 16.4 | 30.9
1.75 | 94.6 | 96.1 | 95.3 | 75.7 | 118.2 | 76.9 | 120.1 | 57.4 | 23.2 | 71.4 | 24.7 | 71.4 | 20.1 | 37.4
2 | 199.6 | 201.6 | 200.6 | 159.7 | 249.5 | 161.3 | 252 | 106.8 | 34.4 | 165.2 | 36.4 | 165.2 | 29.8 | 76.9
2.25 | 397.1 | 399.9 | 398.5 | 317.7 | 496.4 | 319.9 | 499.9 | 196.5 | 62.8 | 334.4 | 65.5 | 334.4 | 55.2 | 141.3
2.5 | 951.6 | 955.9 | 953.8 | 761.3 | 1189.6 | 764.7 | 1194.8 | 938.7 | 125.2 | 826.4 | 129.5 | 826.4 | 112.3 | 826.4
2.75 | 712.2 | 720.8 | 716.5 | 569.7 | 890.2 | 576.7 | 901 | 702.7 | 281.5 | 430.6 | 290.2 | 430.6 | 272.1 | 430.6
3 | 781.3 | 796.8 | 789.1 | 625.1 | 976.6 | 637.5 | 996 | 778.3 | 384.9 | 396.5 | 400.4 | 396.5 | 381.8 | 396.5
3.25 | 871.5 | 894.9 | 883.2 | 697.2 | 1089.4 | 716 | 1118.7 | 873.3 | 431.2 | 440.4 | 454.6 | 440.4 | 433 | 440.4
3.5 | 2358.5 | 2391 | 2374.7 | 1886.8 | 2948.1 | 1912.8 | 2988.7 | 1165.7 | 542.4 | 1816.1 | 574.9 | 1816.1 | 541.2 | 624.6
3.75 | 3151.8 | 3203.2 | 3177.5 | 2521.5 | 3939.8 | 2562.5 | 4004 | 1661.7 | 902 | 2249.8 | 953.4 | 2249.8 | 906.1 | 755.7
4 | 2360.7 | 2443.9 | 2402.3 | 1888.6 | 2950.9 | 1955.1 | 3054.8 | 2305.6 | 1317.1 | 1043.6 | 1400.2 | 1043.6 | 1262 | 1043.6
4.25 | 2377 | 2503.7 | 2440.3 | 1901.6 | 2971.2 | 2003 | 3129.6 | 2358.1 | 1430.2 | 946.8 | 1556.9 | 946.8 | 1411.3 | 946.8
4.5 | 2959.8 | 3131.5 | 3045.6 | 2367.8 | 3699.7 | 2505.2 | 3914.4 | 2019.3 | 1513.9 | 1445.9 | 1685.6 | 1445.9 | 1479.1 | 540.3
4.75 | 2394.1 | 2614.4 | 2504.3 | 1915.3 | 2992.7 | 2091.5 | 3268 | 2406.1 | 1772.3 | 621.8 | 1992.6 | 621.8 | 1784.2 | 621.8
5 | 2390.9 | 2661.2 | 2526.1 | 1912.8 | 2988.7 | 2129 | 3326.5 | 2447.5 | 1827.9 | 563 | 2098.2 | 563 | 1884.5 | 563
5.25 | 2400.3 | 2720.1 | 2560.2 | 1920.3 | 3000.4 | 2176.1 | 3400.1 | 2502.7 | 1875.4 | 525 | 2195.1 | 525 | 1977.7 | 525
5.5 | 2211.4 | 2580.4 | 2395.9 | 1769.1 | 2764.2 | 2064.3 | 3225.5 | 2217.6 | 1922.5 | 288.9 | 2291.5 | 288.9 | 2071.6 | 146
5.75 | 2570.5 | 2987.8 | 2779.1 | 2056.4 | 3213.1 | 2390.2 | 3734.7 | 2755.1 | 1939.6 | 630.9 | 2356.9 | 630.9 | 2124.2 | 630.9
6 | 2638.8 | 3104.5 | 2871.6 | 2111 | 3298.5 | 2483.6 | 3880.6 | 2871.2 | 2043.2 | 595.6 | 2508.9 | 595.6 | 2275.6 | 595.6
6.25 | 2536.6 | 3050.6 | 2793.6 | 2029.3 | 3170.8 | 2440.5 | 3813.2 | 2815.6 | 2066.8 | 469.8 | 2580.8 | 469.8 | 2345.8 | 469.8
6.5 | 2630.4 | 3191.8 | 2911.1 | 2104.3 | 3287.9 | 2553.4 | 3989.7 | 2954.4 | 2095 | 535.4 | 2656.4 | 535.4 | 2419 | 535.4
6.75 | 2778.3 | 3386.4 | 3082.4 | 2222.7 | 3472.9 | 2709.1 | 4233 | 3140.8 | 2135.2 | 643.1 | 2743.3 | 643.1 | 2497.6 | 643.1
7 | 2854.7 | 3509.7 | 3182.2 | 2283.8 | 3568.4 | 2807.8 | 4387.1 | 3261.5 | 2226.1 | 628.6 | 2881.1 | 628.6 | 2632.9 | 628.6
7.25 | 3223.5 | 3925.5 | 3574.5 | 2578.8 | 4029.3 | 3140.4 | 4906.9 | 3123.8 | 2271.3 | 952.2 | 2973.3 | 952.2 | 2710.7 | 413.1
7.5 | 2953.4 | 3703 | 3328.2 | 2362.7 | 3691.7 | 2962.4 | 4628.8 | 3434.9 | 2424.3 | 529.1 | 3174 | 529.1 | 2905.8 | 529.1
7.75 | 2982.8 | 3780.7 | 3381.8 | 2386.3 | 3728.5 | 3024.6 | 4725.9 | 3510 | 2463.1 | 519.8 | 3260.9 | 519.8 | 2990.2 | 519.8
8 | 2717.2 | 3563 | 3140.1 | 2173.7 | 3396.5 | 2850.4 | 4453.8 | 3196.6 | 2502.2 | 215 | 3348 | 215 | 3075.1 | 121.5
8.25 | 2981.4 | 3874.3 | 3427.9 | 2385.1 | 3726.8 | 3099.5 | 4842.9 | 3597.5 | 2499.9 | 481.5 | 3392.8 | 481.5 | 3116 | 481.5
8.5 | 2843.2 | 3782.5 | 3312.8 | 2274.5 | 3553.9 | 3026 | 4728.2 | 3368.7 | 2548.2 | 294.9 | 3487.6 | 294.9 | 3208.9 | 159.8
8.75 | 2969.1 | 3954.5 | 3461.8 | 2375.3 | 3711.4 | 3163.6 | 4943.1 | 3477.6 | 2571.5 | 397.6 | 3556.9 | 397.6 | 3271.7 | 205.9
9 | 2915.5 | 3946.7 | 3431.1 | 2332.4 | 3644.3 | 3157.4 | 4933.4 | 3524.9 | 2620.4 | 295 | 3651.7 | 295 | 3363.5 | 161.3
9.25 | 3021.5 | 4097.9 | 3559.7 | 2417.2 | 3776.9 | 3278.3 | 5122.4 | 3805.8 | 2623 | 398.5 | 3699.4 | 398.5 | 3407.3 | 398.5
9.5 | 2863.9 | 3984.7 | 3424.3 | 2291.1 | 3579.9 | 3187.8 | 4980.9 | 3582 | 2616.4 | 247.5 | 3737.2 | 247.5 | 3441.4 | 140.6
9.75 | 2891.1 | 4055.5 | 3473.3 | 2312.8 | 3613.8 | 3244.4 | 5069.4 | 3635.4 | 2617 | 274 | 3781.5 | 274 | 3481.7 | 153.8
10 | 2849.5 | 4056.9 | 3453.2 | 2279.6 | 3561.9 | 3245.6 | 5071.2 | 3661.4 | 2628.4 | 221.1 | 3835.9 | 221.1 | 3532.3 | 129.1
10.25 | 2835 | 4084.7 | 3459.8 | 2268 | 3543.7 | 3267.7 | 5105.8 | 3682.3 | 2608.2 | 226.8 | 3857.8 | 226.8 | 3549.8 | 132.4
10.5 | 2860.7 | 4151.9 | 3506.3 | 2288.5 | 3575.9 | 3321.5 | 5189.9 | 3739.6 | 2621.4 | 239.3 | 3912.6 | 239.3 | 3600.6 | 139.1
10.75 | 2839.5 | 4171.6 | 3505.5 | 2271.6 | 3549.3 | 3337.3 | 5214.5 | 3764.5 | 2616.8 | 222.7 | 3948.9 | 222.7 | 3633 | 131.5
11 | 4207.8 | 5580.2 | 4894 | 3366.3 | 5259.8 | 4464.2 | 6975.2 | 5252 | 2654.6 | 1553.2 | 4026.9 | 1553.2 | 3698.8 | 1553.2
11.25 | 26293.9 | 27712.9 | 27003.4 | 21035.1 | 32867.4 | 22170.4 | 34641.2 | 10512.1 | 3241.3 | 23052.6 | 4660.4 | 23052.6 | 4181 | 6331.1

## SRD OSS
Depth (m) | SRD AH-FF (kN) | SRD AH-NFF (kN) | SRD MEAN (kN) | SRD AH-FF-LB (kN) | SRD AH-FF-UB (kN) | SRD AH-NFF-LB (kN) | SRD AH-NFF-UB (kN) | Static Cap (kN) | Shaft AH-FF (kN) | Tip AH-FF (kN) | Shaft AH-NFF (kN) | Tip AH-NFF (kN) | Shaft SC (kN) | Tip SC (kN)
0.5 | 81.5 | 82 | 81.7 | 65.2 | 101.9 | 65.6 | 102.5 | 82 | 25.4 | 56.1 | 25.9 | 56.1 | 25.9 | 56.1
0.75 | 93.8 | 94.9 | 94.4 | 75 | 117.2 | 75.9 | 118.6 | 94.9 | 37.7 | 56.1 | 38.8 | 56.1 | 38.8 | 56.1
1 | 112.4 | 114.3 | 113.3 | 89.9 | 140.5 | 91.4 | 142.9 | 114.3 | 56.3 | 56.1 | 58.2 | 56.1 | 58.2 | 56.1
1.25 | 133 | 135.9 | 134.5 | 106.4 | 166.3 | 108.7 | 169.9 | 135.9 | 70.8 | 62.2 | 73.7 | 62.2 | 73.7 | 62.2
1.5 | 149.4 | 153.4 | 151.4 | 119.5 | 186.8 | 122.7 | 191.8 | 153.4 | 86.5 | 62.9 | 90.5 | 62.9 | 90.5 | 62.9
1.75 | 164.4 | 169.6 | 167 | 131.5 | 205.5 | 135.7 | 212 | 169.6 | 100.8 | 63.6 | 106 | 63.6 | 106 | 63.6
2 | 181 | 187.6 | 184.3 | 144.8 | 226.2 | 150 | 234.5 | 187.6 | 116.2 | 64.7 | 122.8 | 64.7 | 122.8 | 64.7
2.25 | 210.1 | 218.2 | 214.1 | 168.1 | 262.6 | 174.5 | 272.7 | 218.2 | 131.8 | 78.3 | 139.9 | 78.3 | 139.9 | 78.3
2.5 | 242.2 | 251.9 | 247 | 193.7 | 302.7 | 201.5 | 314.8 | 214.9 | 161.3 | 80.8 | 171 | 80.8 | 171 | 43.9
2.75 | 363.4 | 375.2 | 369.3 | 290.7 | 454.3 | 300.1 | 469 | 375 | 196 | 167.5 | 207.7 | 167.5 | 207.6 | 167.5
3 | 328.6 | 342.8 | 335.7 | 262.9 | 410.7 | 274.2 | 428.5 | 299.4 | 233.7 | 94.9 | 247.9 | 94.9 | 247.7 | 51.7
3.25 | 451.9 | 468.9 | 460.4 | 361.5 | 564.9 | 375.1 | 586.1 | 468.7 | 270.9 | 181 | 287.8 | 181 | 287.6 | 181
3.5 | 486 | 506.2 | 496.1 | 388.8 | 607.5 | 404.9 | 632.7 | 505.9 | 314 | 172 | 334.2 | 172 | 334 | 172
3.75 | 539.3 | 563.2 | 551.3 | 431.5 | 674.2 | 450.5 | 703.9 | 563 | 356.1 | 183.3 | 379.9 | 183.3 | 379.7 | 183.3
4 | 584.4 | 612.3 | 598.3 | 467.5 | 730.5 | 489.8 | 765.3 | 612 | 402 | 182.4 | 429.9 | 182.4 | 429.7 | 182.4
4.25 | 634.9 | 667.2 | 651 | 507.9 | 793.6 | 533.7 | 834 | 667 | 444.1 | 190.8 | 476.4 | 190.8 | 476.2 | 190.8
4.5 | 719.2 | 756.4 | 737.8 | 575.4 | 899 | 605.1 | 945.5 | 756.2 | 492.9 | 226.3 | 530.1 | 226.3 | 529.9 | 226.3
4.75 | 826 | 868.5 | 847.3 | 660.8 | 1032.5 | 694.8 | 1085.6 | 867.8 | 529.8 | 296.2 | 572.3 | 296.2 | 571.6 | 296.2
5 | 818.1 | 866.3 | 842.2 | 654.5 | 1022.6 | 693 | 1082.8 | 864.5 | 589.5 | 228.6 | 637.7 | 228.6 | 636 | 228.6
5.25 | 869 | 923.6 | 896.3 | 695.2 | 1086.3 | 738.9 | 1154.5 | 921.8 | 645.2 | 223.8 | 699.8 | 223.8 | 698 | 223.8
5.5 | 930.7 | 992.1 | 961.4 | 744.6 | 1163.4 | 793.7 | 1240.1 | 990.2 | 687.7 | 243 | 749 | 243 | 747.2 | 243
5.75 | 971.1 | 1039.7 | 1005.4 | 776.9 | 1213.9 | 831.7 | 1299.6 | 1037.8 | 738.3 | 232.9 | 806.8 | 232.9 | 805 | 232.9
6 | 1032.7 | 1108.8 | 1070.7 | 826.2 | 1290.9 | 887 | 1386 | 1107 | 791.5 | 241.2 | 867.6 | 241.2 | 865.7 | 241.2
6.25 | 1069.1 | 1153.2 | 1111.2 | 855.3 | 1336.4 | 922.6 | 1441.5 | 1151 | 832.2 | 236.9 | 916.3 | 236.9 | 914.1 | 236.9
6.5 | 1120.2 | 1212.7 | 1166.4 | 896.1 | 1400.2 | 970.1 | 1515.8 | 1210.5 | 888 | 232.2 | 980.5 | 232.2 | 978.3 | 232.2
6.75 | 1215.7 | 1317.1 | 1266.4 | 972.6 | 1519.7 | 1053.6 | 1646.3 | 1314.9 | 936.9 | 278.8 | 1038.3 | 278.8 | 1036.1 | 278.8
7 | 1346.9 | 1457.4 | 1402.2 | 1077.5 | 1683.7 | 1166 | 1821.8 | 1454.6 | 983 | 363.9 | 1093.6 | 363.9 | 1090.8 | 363.9
7.25 | 1305.5 | 1425.7 | 1365.6 | 1044.4 | 1631.9 | 1140.6 | 1782.1 | 1422.4 | 1043.5 | 262 | 1163.7 | 262 | 1160.4 | 262
7.5 | 1366.9 | 1497.3 | 1432.1 | 1093.5 | 1708.7 | 1197.8 | 1871.6 | 1493.8 | 1097.2 | 269.7 | 1227.5 | 269.7 | 1224.1 | 269.7
7.75 | 1465.8 | 1606.6 | 1536.2 | 1172.6 | 1832.2 | 1285.3 | 2008.3 | 1602.8 | 1142.6 | 323.1 | 1283.5 | 323.1 | 1279.7 | 323.1
8 | 1541.2 | 1692.9 | 1617.1 | 1233 | 1926.5 | 1354.4 | 2116.2 | 1688.8 | 1196.4 | 344.9 | 1348.1 | 344.9 | 1344 | 344.9
8.25 | 1623.5 | 1786.4 | 1704.9 | 1298.8 | 2029.3 | 1429.2 | 2233.1 | 1780.7 | 1240.8 | 382.7 | 1403.8 | 382.7 | 1398 | 382.7
8.5 | 1818.1 | 1992.8 | 1905.4 | 1454.5 | 2272.6 | 1594.2 | 2491 | 1984 | 1317.5 | 500.6 | 1492.2 | 500.6 | 1483.4 | 500.6
8.75 | 1730.7 | 1918.1 | 1824.4 | 1384.6 | 2163.4 | 1534.5 | 2397.6 | 1908.9 | 1399.7 | 331.1 | 1587 | 331.1 | 1577.9 | 331.1
9 | 1754.5 | 1954.9 | 1854.7 | 1403.6 | 2193.1 | 1564 | 2443.7 | 1945.5 | 1451.7 | 302.8 | 1652.2 | 302.8 | 1642.7 | 302.8
9.25 | 1812.8 | 2026.7 | 1919.7 | 1450.2 | 2265.9 | 1621.4 | 2533.4 | 2017.3 | 1509.8 | 303 | 1723.7 | 303 | 1714.3 | 303
9.5 | 1908.5 | 2136.3 | 2022.4 | 1526.8 | 2385.6 | 1709.1 | 2670.4 | 2126.6 | 1560 | 348.5 | 1787.8 | 348.5 | 1778.2 | 348.5
9.75 | 1975.7 | 2218 | 2096.9 | 1580.6 | 2469.7 | 1774.4 | 2772.5 | 2208.3 | 1636.8 | 339 | 1879 | 339 | 1869.3 | 339
10 | 2161.2 | 2418.3 | 2289.8 | 1729 | 2701.5 | 1934.7 | 3022.9 | 2408.3 | 1695.1 | 466.2 | 1952.2 | 466.2 | 1942.1 | 466.2
10.25 | 2332.8 | 2605.2 | 2469 | 1866.2 | 2916 | 2084.2 | 3256.5 | 2592.9 | 1775.2 | 557.6 | 2047.7 | 557.6 | 2035.4 | 557.6
10.5 | 2351.8 | 2640.6 | 2496.2 | 1881.4 | 2939.7 | 2112.5 | 3300.7 | 2627.6 | 1883.3 | 468.4 | 2172.2 | 468.4 | 2159.2 | 468.4
10.75 | 2187.5 | 2493.7 | 2340.6 | 1750 | 2734.4 | 1994.9 | 3117.1 | 2390.5 | 1969.5 | 218 | 2275.7 | 218 | 2261.9 | 128.6
11 | 2510.5 | 2834.8 | 2672.6 | 2008.4 | 3138.1 | 2267.8 | 3543.4 | 2820.5 | 2076.5 | 434 | 2400.7 | 434 | 2386.5 | 434
11.25 | 2564.6 | 2907.6 | 2736.1 | 2051.6 | 3205.7 | 2326.1 | 3634.5 | 2893.4 | 2148.2 | 416.4 | 2491.2 | 416.4 | 2477 | 416.4
11.5 | 2516.5 | 2878.9 | 2697.7 | 2013.2 | 3145.6 | 2303.1 | 3598.6 | 2864.5 | 2216 | 300.5 | 2578.4 | 300.5 | 2564 | 300.5
11.75 | 2721.3 | 3103.5 | 2912.4 | 2177 | 3401.6 | 2482.8 | 3879.3 | 3089.1 | 2289.3 | 432 | 2671.5 | 432 | 2657.1 | 432
12 | 2793.1 | 3195.8 | 2994.4 | 2234.5 | 3491.4 | 2556.6 | 3994.7 | 3181.1 | 2375.8 | 417.3 | 2778.5 | 417.3 | 2763.8 | 417.3
12.25 | 2940.4 | 3364 | 3152.2 | 2352.3 | 3675.5 | 2691.2 | 4205 | 3107 | 2438.3 | 502 | 2862 | 502 | 2843.5 | 263.5
12.5 | 3438.3 | 3884.2 | 3661.3 | 2750.7 | 4297.9 | 3107.4 | 4855.3 | 3863.3 | 2612.4 | 826 | 3058.2 | 826 | 3037.4 | 826
12.75 | 3514.3 | 3984.5 | 3749.4 | 2811.5 | 4392.9 | 3187.6 | 4980.6 | 3617.3 | 2824.8 | 689.5 | 3295 | 689.5 | 3271.7 | 345.6
13 | 3566.8 | 4063.5 | 3815.1 | 2853.4 | 4458.5 | 3250.8 | 5079.4 | 4034.9 | 3035.9 | 530.9 | 3532.6 | 530.9 | 3504 | 530.9
13.25 | 3650.7 | 4175.8 | 3913.3 | 2920.6 | 4563.4 | 3340.7 | 5219.8 | 4135.1 | 3144.3 | 506.4 | 3669.4 | 506.4 | 3628.7 | 506.4
13.5 | 4236.5 | 4791.9 | 4514.2 | 3389.2 | 5295.7 | 3833.5 | 5989.9 | 4746.2 | 3311.9 | 924.6 | 3867.3 | 924.6 | 3821.6 | 924.6
13.75 | 3959.3 | 4546.9 | 4253.1 | 3167.5 | 4949.2 | 3637.5 | 5683.6 | 4302.2 | 3519.9 | 439.5 | 4107.4 | 439.5 | 4061.7 | 240.5
14 | 4838.6 | 5459.8 | 5149.2 | 3870.8 | 6048.2 | 4367.9 | 6824.8 | 5398.2 | 3648.3 | 1190.3 | 4269.5 | 1190.3 | 4207.9 | 1190.3
14.25 | 4750 | 5407.4 | 5078.7 | 3800 | 5937.4 | 4325.9 | 6759.2 | 5312.2 | 3808.4 | 941.6 | 4465.8 | 941.6 | 4370.7 | 941.6
14.5 | 4699.8 | 5396.5 | 5048.1 | 3759.8 | 5874.7 | 4317.2 | 6745.6 | 5301.4 | 4094.7 | 605.1 | 4791.4 | 605.1 | 4696.3 | 605.1
14.75 | 4552.1 | 5289.5 | 4920.8 | 3641.7 | 5690.1 | 4231.6 | 6611.9 | 5055.4 | 4220.6 | 331.5 | 4958 | 331.5 | 4862.9 | 192.5
15 | 5416 | 6195.2 | 5805.6 | 4332.8 | 6770 | 4956.1 | 7743.9 | 5520.3 | 4340 | 1076.1 | 5119.1 | 1076.1 | 5005.3 | 515
15.25 | 4893.7 | 5716.8 | 5305.3 | 3915 | 6117.1 | 4573.5 | 7146 | 5466.1 | 4572.4 | 321.3 | 5395.5 | 321.3 | 5277.5 | 188.6
15.5 | 4985.8 | 5854.3 | 5420 | 3988.6 | 6232.2 | 4683.5 | 7317.9 | 5591.6 | 4650.1 | 335.7 | 5518.6 | 335.7 | 5395.4 | 196.2
15.75 | 5619.4 | 6534.5 | 6076.9 | 4495.5 | 7024.3 | 5227.6 | 8168.1 | 6411 | 4835.8 | 783.6 | 5750.8 | 783.6 | 5627.4 | 783.6
16 | 5622.9 | 6585.8 | 6104.3 | 4498.3 | 7028.6 | 5268.6 | 8232.2 | 6457.2 | 5004.2 | 618.7 | 5967.1 | 618.7 | 5838.6 | 618.7
16.25 | 6124.1 | 7136.4 | 6630.3 | 4899.3 | 7655.2 | 5709.1 | 8920.5 | 7000.9 | 5128 | 996.1 | 6140.3 | 996.1 | 6004.7 | 996.1
16.5 | 6127.2 | 7190.6 | 6658.9 | 4901.8 | 7659.1 | 5752.5 | 8988.2 | 7054 | 5301.7 | 825.5 | 6365.1 | 825.5 | 6228.5 | 825.5
16.75 | 6074 | 7189.6 | 6631.8 | 4859.2 | 7592.4 | 5751.6 | 8987 | 6754.2 | 5443.8 | 630.2 | 6559.4 | 630.2 | 6418.2 | 336
17 | 6345.9 | 7515.1 | 6930.5 | 5076.7 | 7932.3 | 6012.1 | 9393.9 | 7371.6 | 5638.5 | 707.4 | 6807.8 | 707.4 | 6664.2 | 707.4
17.25 | 6639.8 | 7863.9 | 7251.8 | 5311.8 | 8299.7 | 6291.1 | 9829.8 | 7715.7 | 5736.4 | 903.3 | 6960.5 | 903.3 | 6812.3 | 903.3
17.5 | 7055.5 | 8335.5 | 7695.5 | 5644.4 | 8819.3 | 6668.4 | 10419.4 | 8177.8 | 5902.7 | 1152.7 | 7182.8 | 1152.7 | 7025.1 | 1152.7
17.75 | 6562.2 | 7899.6 | 7230.9 | 5249.7 | 8202.7 | 6319.6 | 9874.4 | 7741.4 | 6000.5 | 561.6 | 7337.9 | 561.6 | 7179.7 | 561.6
18 | 6911.2 | 8306.4 | 7608.8 | 5529 | 8639 | 6645.1 | 10383 | 8146.6 | 6118.3 | 792.9 | 7513.5 | 792.9 | 7353.7 | 792.9
18.25 | 6884 | 8337.8 | 7610.9 | 5507.2 | 8604.9 | 6670.3 | 10422.3 | 8176.5 | 6204.2 | 679.8 | 7658.1 | 679.8 | 7496.7 | 679.8
18.5 | 6474.2 | 7987 | 7230.6 | 5179.3 | 8092.7 | 6389.6 | 9983.8 | 7746.5 | 6254.9 | 219.3 | 7767.7 | 219.3 | 7604.7 | 141.8
18.75 | 6523.6 | 8095.4 | 7309.5 | 5218.9 | 8154.5 | 6476.3 | 10119.2 | 7850.1 | 6296.1 | 227.5 | 7867.9 | 227.5 | 7703.6 | 146.5
19 | 6664.6 | 8295.4 | 7480 | 5331.7 | 8330.7 | 6636.3 | 10369.3 | 8005.8 | 6346.3 | 318.3 | 7977.1 | 318.3 | 7811.5 | 194.3
19.25 | 7126.4 | 8816.4 | 7971.4 | 5701.1 | 8908 | 7053.2 | 11020.6 | 8648.1 | 6398.6 | 727.7 | 8088.7 | 727.7 | 7920.3 | 727.7
19.5 | 6632.1 | 8381.4 | 7506.8 | 5305.7 | 8290.1 | 6705.2 | 10476.8 | 8142.7 | 6428.8 | 203.3 | 8178.1 | 203.3 | 8008.4 | 134.3
19.75 | 7080.5 | 8889 | 7984.8 | 5664.4 | 8850.6 | 7111.2 | 11111.3 | 8717.9 | 6464.5 | 616 | 8273.1 | 616 | 8101.9 | 616
20 | 6831.2 | 8699.1 | 7765.1 | 5465 | 8539 | 6959.2 | 10873.8 | 8402.5 | 6510 | 321.2 | 8377.9 | 321.2 | 8205.1 | 197.4
20.25 | 6721 | 8648.1 | 7684.5 | 5376.8 | 8401.3 | 6918.4 | 10810.1 | 8357.4 | 6552.2 | 168.8 | 8479.3 | 168.8 | 4420.5 | 3937
20.5 | 7100.6 | 9086.7 | 8093.7 | 5680.5 | 8875.8 | 7269.3 | 11358.4 | 8908.8 | 6535.4 | 565.3 | 8521.4 | 565.3 | 8343.6 | 565.3
20.75 | 7146.7 | 9191.7 | 8169.2 | 5717.3 | 8933.4 | 7353.3 | 11489.6 | 9012 | 6581.6 | 565 | 8626.6 | 565 | 8447 | 565
21 | 6846.8 | 8950.8 | 7898.8 | 5477.4 | 8558.5 | 7160.7 | 11188.5 | 8698.6 | 6632.8 | 213.9 | 8736.9 | 213.9 | 8556.7 | 141.9
21.25 | 6806.8 | 8969.7 | 7888.3 | 5445.5 | 8508.6 | 7175.7 | 11212.1 | 8726 | 6619.4 | 187.5 | 8782.2 | 187.5 | 8598.7 | 127.3
21.5 | 6788.7 | 9010 | 7899.4 | 5431 | 8485.9 | 7208 | 11262.5 | 8762.8 | 6598.2 | 190.5 | 8819.5 | 190.5 | 8633.5 | 129.3
21.75 | 6910.9 | 9190.4 | 8050.7 | 5528.7 | 8638.6 | 7352.3 | 11488 | 8908.8 | 6645.3 | 265.6 | 8924.9 | 265.6 | 8737.9 | 170.9
22 | 6872.7 | 9210.4 | 8041.5 | 5498.1 | 8590.8 | 7368.3 | 11513 | 8954.5 | 6667.4 | 205.3 | 9005.2 | 205.3 | 8816.4 | 138.1
22.25 | 6832.1 | 9227.8 | 8030 | 5465.7 | 8540.2 | 7382.2 | 11534.7 | 8973.2 | 6636.4 | 195.8 | 9032 | 195.8 | 8840.1 | 133.1
22.5 | 6858.8 | 9311.9 | 8085.4 | 5487.1 | 8573.5 | 7449.5 | 11639.9 | 9029.6 | 6606.2 | 252.6 | 9059.3 | 252.6 | 8864.7 | 164.9
22.75 | 6789.9 | 9299.9 | 8044.9 | 5431.9 | 8487.4 | 7439.9 | 11624.9 | 9035.2 | 6581 | 208.9 | 9091 | 208.9 | 8894.2 | 141
23 | 6780 | 9346.5 | 8063.3 | 5424 | 8475 | 7477.2 | 11683.1 | 9071.1 | 6553.4 | 226.6 | 9119.9 | 226.6 | 8919.9 | 151.2
23.25 | 6772 | 9394.5 | 8083.3 | 5417.6 | 8465 | 7515.6 | 11743.2 | 9107.1 | 6525.8 | 246.2 | 9148.4 | 246.2 | 8944.9 | 162.2
23.5 | 6730.7 | 9408.8 | 8069.8 | 5384.6 | 8413.4 | 7527.1 | 11761 | 9125.4 | 6501.2 | 229.5 | 9179.3 | 229.5 | 8972 | 153.3
23.75 | 7234.2 | 9967.6 | 8600.9 | 5787.4 | 9042.8 | 7974.1 | 12459.5 | 9756.1 | 6516.5 | 717.8 | 9249.8 | 717.8 | 9038.3 | 717.8
24 | 7189.4 | 9978.3 | 8583.9 | 5751.5 | 8986.7 | 7982.7 | 12472.9 | 9512 | 6604.8 | 584.6 | 9393.7 | 584.6 | 9176.6 | 335.4
24.25 | 8555 | 11401.7 | 9978.3 | 6844 | 10693.7 | 9121.3 | 14252.1 | 11183.8 | 7024.8 | 1530.2 | 9871.5 | 1530.2 | 9653.6 | 1530.2
24.5 | 9257.5 | 12169.2 | 10713.3 | 7406 | 11571.9 | 9735.3 | 15211.4 | 11951.3 | 7772.2 | 1485.4 | 10683.8 | 1485.4 | 10465.9 | 1485.4
24.75 | 9833.3 | 12819.5 | 11326.4 | 7866.6 | 12291.6 | 10255.6 | 16024.4 | 12601.6 | 8530.8 | 1302.5 | 11517 | 1302.5 | 11299.1 | 1302.5
25 | 10464.1 | 13532.3 | 11998.2 | 8371.3 | 13080.1 | 10825.9 | 16915.4 | 13314.4 | 9122.7 | 1341.4 | 12190.9 | 1341.4 | 11973 | 1341.4
25.25 | 41763.6 | 44924.7 | 43344.2 | 33410.9 | 52204.6 | 35939.7 | 56155.8 | 21813.2 | 9554.4 | 32209.2 | 12715.4 | 32209.2 | 12259.6 | 9553.6
25.5 | 29268.9 | 32529 | 30898.9 | 23415.1 | 36586.1 | 26023.2 | 40661.3 | 18642.1 | 9455.3 | 19813.6 | 12715.4 | 19813.6 | 12259.6 | 6382.5
25.75 | 18031.8 | 21389.3 | 19710.5 | 14425.4 | 22539.7 | 17111.5 | 26736.6 | 15471.1 | 9357.9 | 8673.9 | 12715.4 | 8673.9 | 12259.6 | 3211.5
26 | 12223.4 | 16253.6 | 14238.5 | 9778.7 | 15279.3 | 13002.9 | 20317 | 8707.2 | 12178 | 45.4 | 16208.2 | 45.4 | 7333.3 | 1373.9
26.25 | 12691.2 | 16963.1 | 14827.2 | 10153 | 15864 | 13570.5 | 21203.9 | 13725 | 12038.6 | 652.6 | 16310.5 | 652.6 | 13072.4 | 652.6
26.5 | 12999.7 | 17503.2 | 15251.5 | 10399.8 | 16249.7 | 14002.6 | 21879 | 14265.1 | 12034.8 | 964.9 | 16538.3 | 964.9 | 13300.2 | 964.9
26.75 | 12911.4 | 17638.2 | 15274.8 | 10329.2 | 16139.3 | 14110.6 | 22047.8 | 14398.1 | 12156.1 | 755.4 | 16882.9 | 755.4 | 13642.8 | 755.4
27 | 12919.4 | 17861.8 | 15390.6 | 10335.5 | 16149.2 | 14289.5 | 22327.3 | 14621.8 | 12170.3 | 749 | 17112.8 | 749 | 13872.7 | 749
27.25 | 13609.3 | 18759.7 | 16184.5 | 10887.4 | 17011.6 | 15007.8 | 23449.6 | 15480.5 | 12165.4 | 1443.9 | 17315.7 | 1443.9 | 14036.5 | 1443.9
27.5 | 15784.8 | 21138.2 | 18461.5 | 12627.8 | 19731 | 16910.5 | 26422.7 | 15936 | 12402.1 | 3382.7 | 17755.5 | 3382.7 | 14454.3 | 1481.6
27.75 | 13986.8 | 19538.9 | 16762.8 | 11189.5 | 17483.5 | 15631.1 | 24423.6 | 16157.5 | 12685.7 | 1301.2 | 18237.7 | 1301.2 | 14856.3 | 1301.2
28 | 13929.4 | 19679.6 | 16804.5 | 11143.5 | 17411.7 | 15743.7 | 24599.5 | 15883.4 | 13022.5 | 906.9 | 18772.7 | 906.9 | 15387.2 | 496.3
28.25 | 14507.8 | 20452.4 | 17480.1 | 11606.2 | 18134.7 | 16361.9 | 25565.5 | 16437.6 | 13216.3 | 1291.5 | 19160.9 | 1291.5 | 15770.3 | 667.3
28.5 | 16278.2 | 22413.9 | 19346.1 | 13022.6 | 20347.8 | 17931.2 | 28017.4 | 17483.2 | 13514.5 | 2763.7 | 19650.2 | 2763.7 | 16223.4 | 1259.9
28.75 | 18474.1 | 24805.8 | 21639.9 | 14779.3 | 23092.6 | 19844.6 | 31007.2 | 18871.4 | 14216 | 4258.1 | 20547.7 | 4258.1 | 17062.3 | 1809.1
29 | 21416.2 | 27950.2 | 24683.2 | 17133 | 26770.3 | 22360.1 | 34937.7 | 19970.9 | 14516.8 | 6899.4 | 21050.7 | 6899.4 | 17261.4 | 2709.5
29.25 | 17902.8 | 24644.7 | 21273.7 | 14322.2 | 22378.5 | 19715.8 | 30805.9 | 18856 | 14704.7 | 3198.1 | 21446.7 | 3198.1 | 17426 | 1430
29.5 | 18585.1 | 25534.9 | 22060 | 14868.1 | 23231.4 | 20427.9 | 31918.6 | 19213.4 | 14825.8 | 3759.3 | 21775.6 | 3759.3 | 17574.4 | 1639
29.75 | 16715.6 | 23873 | 20294.3 | 13372.5 | 20894.5 | 19098.4 | 29841.2 | 18600.3 | 14892.4 | 1823.2 | 22049.8 | 1823.2 | 17702 | 898.3
30 | 17379.2 | 24745.8 | 21062.5 | 13903.3 | 21724 | 19796.6 | 30932.2 | 20388.6 | 15496.9 | 1882.3 | 22863.5 | 1882.3 | 18506.3 | 1882.3
30.25 | 19228.7 | 26807.7 | 23018.2 | 15382.9 | 24035.8 | 21446.2 | 33509.7 | 22450.5 | 15981.2 | 3247.5 | 23560.3 | 3247.5 | 19203 | 3247.5
30.5 | 17972.2 | 25765.1 | 21868.7 | 14377.8 | 22465.3 | 20612.1 | 32206.4 | 20441.4 | 16153.5 | 1818.8 | 23946.3 | 1818.8 | 19541.1 | 900.3
30.75 | 17758.5 | 25762.3 | 21760.4 | 14206.8 | 22198.2 | 20609.8 | 32202.9 | 20463.4 | 16111.6 | 1647 | 24115.3 | 1647 | 19633.4 | 830.1
31 | 18178.5 | 26390.1 | 22284.3 | 14542.8 | 22723.1 | 21112.1 | 32987.6 | 20746.4 | 16120.1 | 2058.4 | 24331.7 | 2058.4 | 19745.3 | 1001.1
31.25 | 23268.9 | 31690 | 27479.5 | 18615.1 | 29086.1 | 25352 | 39612.5 | 22826.8 | 16471.9 | 6797 | 24893 | 6797 | 20113.6 | 2713.1
31.5 | 22756.2 | 31393.5 | 27074.9 | 18205 | 28445.3 | 25114.8 | 39241.9 | 22765.4 | 16763.1 | 5993.2 | 25400.3 | 5993.2 | 20318.6 | 2446.9
31.75 | 21674.8 | 30533.1 | 26103.9 | 17339.8 | 27093.4 | 24426.5 | 38166.4 | 22799.1 | 17218.4 | 4456.4 | 26076.7 | 4456.4 | 20884.7 | 1914.4
32 | 21791.1 | 30878.4 | 26334.7 | 17432.8 | 27238.8 | 24702.7 | 38598 | 22991 | 17438.9 | 4352.1 | 26526.3 | 4352.1 | 21111.1 | 1879.9
32.25 | 23173 | 32492 | 27832.5 | 18538.4 | 28966.3 | 25993.6 | 40615 | 23592.1 | 17619.6 | 5553.5 | 26938.6 | 5553.5 | 21285.3 | 2306.8
32.5 | 20365.4 | 29919.8 | 25142.6 | 16292.3 | 25456.8 | 23935.9 | 37399.8 | 24074.7 | 17888 | 2477.4 | 27442.4 | 2477.4 | 21597.3 | 2477.4
32.75 | 20979 | 30773.4 | 25876.2 | 16783.2 | 26223.7 | 24618.7 | 38466.8 | 24928.2 | 18634.2 | 2344.8 | 28428.6 | 2344.8 | 22583.4 | 2344.8
33 | 22341.5 | 32381 | 27361.2 | 17873.2 | 27926.9 | 25904.8 | 40476.3 | 26535.8 | 19302.4 | 3039.1 | 29341.9 | 3039.1 | 23496.8 | 3039.1
33.25 | 36496 | 46788.8 | 41642.4 | 29196.8 | 45620 | 37431 | 58486 | 29848.1 | 19890.8 | 16605.2 | 30183.6 | 16605.2 | 24070.4 | 5777.7
33.5 | 36940.9 | 47515.4 | 42228.2 | 29552.7 | 46176.1 | 38012.3 | 59394.3 | 40833.7 | 21295.3 | 15645.6 | 31869.8 | 15645.6 | 25188.1 | 15645.6
33.75 | 37054.2 | 47979.4 | 42516.8 | 29643.4 | 46317.8 | 38383.5 | 59974.2 | 41206.5 | 24378.9 | 12675.3 | 35304 | 12675.3 | 28531.1 | 12675.3
34 | 55685.5 | 67045.8 | 61365.7 | 44548.4 | 69606.9 | 53636.6 | 83807.2 | 39437.2 | 25769.3 | 29916.2 | 37129.5 | 29916.2 | 29960.3 | 9476.9

## False Floors
WTG | Top (m) | Bottom (m) | Thickness (m) | Avg qc (MPa) | Min Criterion (m) | Below Criterion
WTG-01 | 11.38 | 11.48 | 0.1 | 3.09 | 1.05 | YES
WTG-01 | 11.78 | 11.82 | 0.04 | 2.49 | 1.05 | YES
WTG-01 | 12.44 | 12.44 | 0 | 2.15 | 1.05 | YES
WTG-01 | 12.78 | 12.84 | 0.06 | 2.4 | 1.05 | YES
WTG-01 | 12.96 | 13 | 0.04 | 2.19 | 1.05 | YES
WTG-01 | 13.74 | 13.84 | 0.1 | 2.4 | 1.05 | YES
WTG-01 | 14.46 | 14.52 | 0.06 | 2.32 | 1.05 | YES
WTG-01 | 16.12 | 16.16 | 0.04 | 1.98 | 1.05 | YES
WTG-01 | 16.38 | 16.5 | 0.12 | 2.4 | 1.05 | YES
WTG-01 | 17.36 | 17.5 | 0.14 | 3.19 | 1.05 | YES
WTG-01 | 17.64 | 17.64 | 0 | 2.33 | 1.05 | YES
WTG-01 | 24.66 | 25.28 | 0.62 | 2.39 | 1.05 | YES
WTG-01 | 25.84 | 25.88 | 0.04 | 2.05 | 1.05 | YES
WTG-01 | 26.74 | 26.84 | 0.1 | 2.42 | 1.05 | YES
WTG-01 | 26.96 | 27.08 | 0.12 | 2.59 | 1.05 | YES
WTG-01 | 27.84 | 28.06 | 0.22 | 2.24 | 1.05 | YES
WTG-01 | 29.64 | 30.02 | 0.38 | 2.3 | 1.05 | YES
WTG-02 | 9.18 | 9.84 | 0.66 | 4.33 | 1.05 | YES
WTG-02 | 12.26 | 12.36 | 0.1 | 2.33 | 1.05 | YES
WTG-02 | 12.74 | 12.84 | 0.1 | 2.19 | 1.05 | YES
WTG-02 | 12.98 | 13 | 0.02 | 2.31 | 1.05 | YES
WTG-02 | 15.68 | 15.76 | 0.08 | 2.37 | 1.05 | YES
WTG-02 | 16.14 | 16.16 | 0.02 | 2.46 | 1.05 | YES
WTG-02 | 16.38 | 16.58 | 0.2 | 2.22 | 1.05 | YES
WTG-02 | 16.72 | 16.72 | 0 | 2.36 | 1.05 | YES
WTG-02 | 17.3 | 17.32 | 0.02 | 2.04 | 1.05 | YES
WTG-02 | 18.8 | 18.84 | 0.04 | 2.3 | 1.05 | YES
WTG-02 | 19.68 | 20.22 | 0.54 | 2.32 | 1.05 | YES
WTG-02 | 20.46 | 20.84 | 0.38 | 2.21 | 1.05 | YES
WTG-02 | 20.98 | 21.1 | 0.12 | 2.35 | 1.05 | YES
WTG-02 | 21.16 | 21.54 | 0.38 | 2.52 | 1.05 | YES
WTG-02 | 21.84 | 22.12 | 0.28 | 2.15 | 1.05 | YES
WTG-02 | 22.26 | 22.56 | 0.3 | 2.67 | 1.05 | YES
WTG-02 | 22.62 | 23.48 | 0.86 | 2.55 | 1.05 | YES
WTG-02 | 23.74 | 23.92 | 0.18 | 2.29 | 1.05 | YES
WTG-02 | 23.96 | 23.96 | 0 | 2.05 | 1.05 | YES
WTG-02 | 24.04 | 24.3 | 0.26 | 2.65 | 1.05 | YES
WTG-02 | 26.04 | 26.04 | 0 | 1.99 | 1.05 | YES
WTG-02 | 26.22 | 26.34 | 0.12 | 2.19 | 1.05 | YES
WTG-02 | 26.42 | 26.52 | 0.1 | 2.19 | 1.05 | YES
WTG-02 | 26.76 | 26.86 | 0.1 | 2.15 | 1.05 | YES
WTG-02 | 27.74 | 27.78 | 0.04 | 2.06 | 1.05 | YES
WTG-02 | 28.32 | 28.5 | 0.18 | 2.12 | 1.05 | YES
WTG-02 | 29.14 | 29.16 | 0.02 | 2.14 | 1.05 | YES
WTG-02 | 30.06 | 30.16 | 0.1 | 2.16 | 1.05 | YES
WTG-02 | 30.44 | 30.48 | 0.04 | 2.14 | 1.05 | YES
WTG-02 | 30.74 | 30.76 | 0.02 | 2.09 | 1.05 | YES
WTG-02 | 31.14 | 31.98 | 0.84 | 2.18 | 1.05 | YES
WTG-02 | 32.1 | 32.54 | 0.44 | 2.24 | 1.05 | YES
WTG-02 | 32.7 | 32.78 | 0.08 | 2.08 | 1.05 | YES
WTG-02 | 38.56 | 38.82 | 0.26 | 2.02 | 1.05 | YES
WTG-02 | 39.04 | 39.9 | 0.86 | 2.08 | 1.05 | YES
WTG-03 | 3.24 | 3.9 | 0.66 | 5.73 | 1.05 | YES
WTG-03 | 4.02 | 4.24 | 0.22 | 4.78 | 1.05 | YES
WTG-03 | 8.34 | 8.44 | 0.1 | 3.01 | 1.05 | YES
WTG-03 | 8.7 | 8.82 | 0.12 | 2.34 | 1.05 | YES
WTG-03 | 11.5 | 11.52 | 0.02 | 2.32 | 1.05 | YES
WTG-03 | 11.82 | 11.88 | 0.06 | 2.14 | 1.05 | YES
WTG-03 | 12.72 | 12.78 | 0.06 | 2.39 | 1.05 | YES
WTG-03 | 22.6 | 22.96 | 0.36 | 2.42 | 1.05 | YES
WTG-03 | 23.3 | 23.38 | 0.08 | 2.21 | 1.05 | YES
WTG-03 | 25.64 | 25.76 | 0.12 | 2.37 | 1.05 | YES
WTG-03 | 25.96 | 26.3 | 0.34 | 2.61 | 1.05 | YES
WTG-03 | 26.34 | 27.04 | 0.7 | 2.32 | 1.05 | YES
WTG-03 | 27.44 | 27.7 | 0.26 | 2.14 | 1.05 | YES
WTG-04 | 9.32 | 9.38 | 0.06 | 2.31 | 1.05 | YES
WTG-04 | 10.48 | 10.58 | 0.1 | 2.84 | 1.05 | YES
WTG-04 | 10.7 | 10.84 | 0.14 | 2.52 | 1.05 | YES
WTG-04 | 10.92 | 11.06 | 0.14 | 2.56 | 1.05 | YES
WTG-04 | 11.14 | 11.4 | 0.26 | 2.71 | 1.05 | YES
WTG-04 | 11.8 | 11.9 | 0.1 | 2.29 | 1.05 | YES
WTG-04 | 12 | 12.2 | 0.2 | 2.5 | 1.05 | YES
WTG-04 | 12.4 | 12.52 | 0.12 | 2.6 | 1.05 | YES
WTG-04 | 12.86 | 13.08 | 0.22 | 2.3 | 1.05 | YES
WTG-04 | 13.9 | 13.94 | 0.04 | 2.33 | 1.05 | YES
WTG-04 | 14.06 | 14.12 | 0.06 | 2.28 | 1.05 | YES
WTG-04 | 15.72 | 15.86 | 0.14 | 2.25 | 1.05 | YES
WTG-04 | 17.46 | 17.56 | 0.1 | 2.15 | 1.05 | YES
WTG-04 | 17.74 | 17.82 | 0.08 | 2.25 | 1.05 | YES
WTG-04 | 19.38 | 19.46 | 0.08 | 2.22 | 1.05 | YES
WTG-04 | 19.66 | 19.74 | 0.08 | 2.23 | 1.05 | YES
WTG-04 | 24.5 | 24.54 | 0.04 | 2.08 | 1.05 | YES
WTG-04 | 26.12 | 26.24 | 0.12 | 2.32 | 1.05 | YES
WTG-04 | 26.32 | 26.4 | 0.08 | 2.09 | 1.05 | YES
WTG-04 | 26.9 | 26.92 | 0.02 | 2.14 | 1.05 | YES
WTG-04 | 28.04 | 28.66 | 0.62 | 2.15 | 1.05 | YES
WTG-04 | 30.76 | 30.88 | 0.12 | 2.05 | 1.05 | YES
WTG-04 | 31.24 | 31.86 | 0.62 | 2.07 | 1.05 | YES
WTG-04 | 32 | 32.82 | 0.82 | 2.08 | 1.05 | YES
WTG-05 | 2.28 | 2.74 | 0.46 | 2.83 | 1.05 | YES
WTG-05 | 2.96 | 3.04 | 0.08 | 2.51 | 1.05 | YES
WTG-05 | 3.5 | 3.8 | 0.3 | 4.61 | 1.05 | YES
WTG-05 | 3.88 | 4.06 | 0.18 | 2.58 | 1.05 | YES
WTG-05 | 4.42 | 5.42 | 1 | 3.73 | 1.05 | YES
WTG-05 | 5.72 | 5.8 | 0.08 | 2.7 | 1.05 | YES
WTG-05 | 5.94 | 6.08 | 0.14 | 2.69 | 1.05 | YES
WTG-05 | 6.2 | 6.24 | 0.04 | 2.13 | 1.05 | YES
WTG-05 | 6.62 | 6.64 | 0.02 | 2.13 | 1.05 | YES
WTG-05 | 6.74 | 6.8 | 0.06 | 2.31 | 1.05 | YES
WTG-05 | 6.88 | 7.42 | 0.54 | 2.49 | 1.05 | YES
WTG-05 | 7.64 | 7.68 | 0.04 | 2.32 | 1.05 | YES
WTG-05 | 7.8 | 7.88 | 0.08 | 2.25 | 1.05 | YES
WTG-05 | 8.16 | 8.28 | 0.12 | 2.53 | 1.05 | YES
WTG-05 | 8.4 | 8.72 | 0.32 | 3.16 | 1.05 | YES
WTG-05 | 8.8 | 8.88 | 0.08 | 2.32 | 1.05 | YES
WTG-05 | 9.2 | 9.32 | 0.12 | 2.88 | 1.05 | YES
WTG-05 | 11.54 | 11.56 | 0.02 | 2.15 | 1.05 | YES
WTG-05 | 12.1 | 12.14 | 0.04 | 2.22 | 1.05 | YES
WTG-05 | 12.76 | 12.8 | 0.04 | 2.23 | 1.05 | YES
WTG-05 | 13 | 13.12 | 0.12 | 2.44 | 1.05 | YES
WTG-05 | 13.54 | 13.9 | 0.36 | 2.77 | 1.05 | YES
WTG-05 | 14.44 | 14.54 | 0.1 | 2.41 | 1.05 | YES
WTG-05 | 14.76 | 14.88 | 0.12 | 2.56 | 1.05 | YES
WTG-05 | 15.04 | 15.32 | 0.28 | 2.22 | 1.05 | YES
WTG-05 | 15.5 | 15.5 | 0 | 1.93 | 1.05 | YES
WTG-05 | 15.54 | 15.7 | 0.16 | 2.5 | 1.05 | YES
WTG-05 | 15.84 | 16.3 | 0.46 | 2.99 | 1.05 | YES
WTG-05 | 17.52 | 18.1 | 0.58 | 2.37 | 1.05 | YES
WTG-05 | 18.2 | 18.3 | 0.1 | 2.16 | 1.05 | YES
WTG-05 | 18.46 | 18.64 | 0.18 | 2.57 | 1.05 | YES
WTG-05 | 19.02 | 19.14 | 0.12 | 2.2 | 1.05 | YES
WTG-05 | 20.62 | 20.9 | 0.28 | 2.5 | 1.05 | YES
WTG-05 | 21.06 | 21.08 | 0.02 | 2.08 | 1.05 | YES
WTG-05 | 21.56 | 21.72 | 0.16 | 2.5 | 1.05 | YES
WTG-05 | 21.8 | 21.88 | 0.08 | 2.23 | 1.05 | YES
WTG-05 | 23.04 | 23.16 | 0.12 | 2.21 | 1.05 | YES
WTG-05 | 25.22 | 25.32 | 0.1 | 2.17 | 1.05 | YES
WTG-05 | 26.6 | 27.54 | 0.94 | 3.56 | 1.05 | YES
WTG-05 | 27.6 | 27.64 | 0.04 | 2.05 | 1.05 | YES
WTG-05 | 27.86 | 28.18 | 0.32 | 2.08 | 1.05 | YES
WTG-06 | 1.84 | 2.84 | 1 | 9.3 | 1.05 | YES
WTG-06 | 3 | 3.7 | 0.7 | 5.77 | 1.05 | YES
WTG-06 | 3.88 | 3.94 | 0.06 | 2.46 | 1.05 | YES
WTG-06 | 4.14 | 4.3 | 0.16 | 3.83 | 1.05 | YES
WTG-06 | 4.5 | 4.7 | 0.2 | 5.14 | 1.05 | YES
WTG-06 | 4.88 | 4.94 | 0.06 | 2.17 | 1.05 | YES
WTG-06 | 5.18 | 5.26 | 0.08 | 2.42 | 1.05 | YES
WTG-06 | 5.86 | 5.98 | 0.12 | 3.1 | 1.05 | YES
WTG-06 | 6.04 | 6.22 | 0.18 | 3.97 | 1.05 | YES
WTG-06 | 6.66 | 6.78 | 0.12 | 2.94 | 1.05 | YES
WTG-06 | 8.24 | 8.24 | 0 | 2.27 | 1.05 | YES
WTG-06 | 10.44 | 10.48 | 0.04 | 2.3 | 1.05 | YES
WTG-06 | 11.36 | 11.56 | 0.2 | 2.33 | 1.05 | YES
WTG-06 | 11.78 | 11.8 | 0.02 | 2.2 | 1.05 | YES
WTG-06 | 13.2 | 13.2 | 0 | 2.35 | 1.05 | YES
WTG-06 | 13.44 | 13.96 | 0.52 | 2.3 | 1.05 | YES
WTG-06 | 14.22 | 14.26 | 0.04 | 2.14 | 1.05 | YES
WTG-06 | 14.52 | 15 | 0.48 | 2.74 | 1.05 | YES
WTG-06 | 15.1 | 15.18 | 0.08 | 2.19 | 1.05 | YES
WTG-06 | 15.26 | 15.34 | 0.08 | 2.15 | 1.05 | YES
WTG-06 | 15.52 | 15.84 | 0.32 | 2.59 | 1.05 | YES
WTG-06 | 16.38 | 16.5 | 0.12 | 2.21 | 1.05 | YES
WTG-06 | 16.62 | 16.72 | 0.1 | 2.21 | 1.05 | YES
WTG-06 | 17.2 | 17.4 | 0.2 | 2.15 | 1.05 | YES
WTG-06 | 19.04 | 19.12 | 0.08 | 2.24 | 1.05 | YES
WTG-06 | 19.22 | 19.42 | 0.2 | 2.2 | 1.05 | YES
WTG-06 | 19.5 | 19.86 | 0.36 | 2.92 | 1.05 | YES
WTG-06 | 20.02 | 20.06 | 0.04 | 2.13 | 1.05 | YES
WTG-06 | 20.38 | 20.48 | 0.1 | 2.33 | 1.05 | YES
WTG-06 | 21.2 | 21.22 | 0.02 | 2.18 | 1.05 | YES
WTG-06 | 21.82 | 21.92 | 0.1 | 2.09 | 1.05 | YES
WTG-06 | 23.18 | 23.28 | 0.1 | 2.12 | 1.05 | YES
WTG-06 | 23.38 | 23.4 | 0.02 | 2.03 | 1.05 | YES
WTG-06 | 23.86 | 24.06 | 0.2 | 2.41 | 1.05 | YES
WTG-06 | 25.1 | 25.24 | 0.14 | 2.06 | 1.05 | YES
WTG-06 | 26.56 | 26.84 | 0.28 | 2.13 | 1.05 | YES
WTG-06 | 27.44 | 27.5 | 0.06 | 2.09 | 1.05 | YES
WTG-06 | 27.76 | 27.8 | 0.04 | 2.03 | 1.05 | YES
WTG-06 | 28 | 28.44 | 0.44 | 2.27 | 1.05 | YES
WTG-07 | 7.12 | 7.2 | 0.08 | 2.66 | 1.05 | YES
WTG-07 | 7.26 | 7.44 | 0.18 | 3.53 | 1.05 | YES
WTG-07 | 7.52 | 7.68 | 0.16 | 2.96 | 1.05 | YES
WTG-07 | 11.92 | 12.12 | 0.2 | 3.46 | 1.05 | YES
WTG-07 | 12.18 | 12.3 | 0.12 | 2.18 | 1.05 | YES
WTG-07 | 12.34 | 12.4 | 0.06 | 2.08 | 1.05 | YES
WTG-07 | 12.56 | 12.8 | 0.24 | 2.76 | 1.05 | YES
WTG-07 | 13.52 | 13.58 | 0.06 | 2.25 | 1.05 | YES
WTG-07 | 13.82 | 13.9 | 0.08 | 2.11 | 1.05 | YES
WTG-07 | 14.64 | 14.74 | 0.1 | 2.43 | 1.05 | YES
WTG-07 | 14.94 | 14.98 | 0.04 | 2.29 | 1.05 | YES
WTG-07 | 15.1 | 15.3 | 0.2 | 2.67 | 1.05 | YES
WTG-07 | 15.44 | 15.62 | 0.18 | 2.6 | 1.05 | YES
WTG-07 | 16.2 | 16.44 | 0.24 | 2.4 | 1.05 | YES
WTG-07 | 16.52 | 16.7 | 0.18 | 2.37 | 1.05 | YES
WTG-07 | 17.06 | 17.22 | 0.16 | 2.54 | 1.05 | YES
WTG-07 | 17.46 | 17.8 | 0.34 | 2.82 | 1.05 | YES
WTG-07 | 18.04 | 18.14 | 0.1 | 2.38 | 1.05 | YES
WTG-07 | 18.24 | 18.26 | 0.02 | 2.38 | 1.05 | YES
WTG-07 | 18.5 | 18.54 | 0.04 | 2.32 | 1.05 | YES
WTG-07 | 21.42 | 21.42 | 0 | 2 | 1.05 | YES
WTG-07 | 21.46 | 21.54 | 0.08 | 2.16 | 1.05 | YES
WTG-07 | 22.42 | 22.5 | 0.08 | 2.53 | 1.05 | YES
WTG-07 | 27.08 | 27.78 | 0.7 | 2.36 | 1.05 | YES
WTG-07 | 28.58 | 28.78 | 0.2 | 2.03 | 1.05 | YES
WTG-07 | 28.9 | 29.46 | 0.56 | 2.07 | 1.05 | YES
WTG-07 | 30.08 | 30.16 | 0.08 | 2.02 | 1.05 | YES
WTG-07 | 30.3 | 30.32 | 0.02 | 2.02 | 1.05 | YES
WTG-07 | 30.44 | 30.44 | 0 | 2.01 | 1.05 | YES
WTG-08 | 3.22 | 3.72 | 0.5 | 3.09 | 1.05 | YES
WTG-08 | 3.76 | 4.06 | 0.3 | 3.06 | 1.05 | YES
WTG-08 | 4.42 | 4.66 | 0.24 | 3.65 | 1.05 | YES
WTG-08 | 4.74 | 5.2 | 0.46 | 4.64 | 1.05 | YES
WTG-08 | 5.48 | 5.82 | 0.34 | 3.94 | 1.05 | YES
WTG-08 | 6.12 | 6.3 | 0.18 | 3.11 | 1.05 | YES
WTG-08 | 6.98 | 7.08 | 0.1 | 3.07 | 1.05 | YES
WTG-08 | 7.48 | 7.56 | 0.08 | 2.71 | 1.05 | YES
WTG-08 | 7.76 | 7.8 | 0.04 | 2.44 | 1.05 | YES
WTG-08 | 7.96 | 8.1 | 0.14 | 2.64 | 1.05 | YES
WTG-08 | 8.5 | 8.5 | 0 | 2.07 | 1.05 | YES
WTG-08 | 8.54 | 8.84 | 0.3 | 6.53 | 1.05 | YES
WTG-08 | 8.94 | 9.42 | 0.48 | 4.44 | 1.05 | YES
WTG-08 | 9.5 | 9.72 | 0.22 | 6.17 | 1.05 | YES
WTG-08 | 9.84 | 9.88 | 0.04 | 2.34 | 1.05 | YES
WTG-08 | 9.98 | 10.08 | 0.1 | 2.65 | 1.05 | YES
WTG-08 | 10.94 | 10.96 | 0.02 | 2.54 | 1.05 | YES
WTG-08 | 11.08 | 11.24 | 0.16 | 3.03 | 1.05 | YES
WTG-08 | 11.32 | 11.38 | 0.06 | 2.5 | 1.05 | YES
WTG-08 | 11.76 | 11.84 | 0.08 | 2.9 | 1.05 | YES
WTG-08 | 12.32 | 12.42 | 0.1 | 2.67 | 1.05 | YES
WTG-08 | 14.24 | 14.34 | 0.1 | 2.5 | 1.05 | YES
WTG-08 | 15.64 | 15.78 | 0.14 | 3.09 | 1.05 | YES
WTG-08 | 16.1 | 16.1 | 0 | 2.39 | 1.05 | YES
WTG-08 | 16.24 | 16.6 | 0.36 | 2.56 | 1.05 | YES
WTG-08 | 16.7 | 16.9 | 0.2 | 2.77 | 1.05 | YES
WTG-08 | 17 | 17.22 | 0.22 | 2.39 | 1.05 | YES
WTG-08 | 17.42 | 17.46 | 0.04 | 2.2 | 1.05 | YES
WTG-08 | 17.52 | 17.62 | 0.1 | 2.21 | 1.05 | YES
WTG-08 | 18.32 | 18.4 | 0.08 | 2.5 | 1.05 | YES
WTG-08 | 19.02 | 19.14 | 0.12 | 2.51 | 1.05 | YES
WTG-08 | 19.3 | 19.4 | 0.1 | 2.19 | 1.05 | YES
WTG-08 | 19.54 | 19.6 | 0.06 | 2.29 | 1.05 | YES
WTG-08 | 20.18 | 20.38 | 0.2 | 2.53 | 1.05 | YES
WTG-08 | 21.84 | 21.9 | 0.06 | 2.32 | 1.05 | YES
WTG-09 | 12.08 | 12.6 | 0.52 | 6.63 | 1.05 | YES
WTG-09 | 17.42 | 17.42 | 0 | 1.88 | 1.05 | YES
WTG-09 | 17.5 | 17.6 | 0.1 | 2.39 | 1.05 | YES
WTG-09 | 18.24 | 18.42 | 0.18 | 3.26 | 1.05 | YES
WTG-09 | 19.1 | 19.16 | 0.06 | 2.36 | 1.05 | YES
WTG-09 | 19.26 | 19.32 | 0.06 | 2.69 | 1.05 | YES
WTG-09 | 19.92 | 20.06 | 0.14 | 3.27 | 1.05 | YES
WTG-09 | 21.78 | 21.86 | 0.08 | 2.32 | 1.05 | YES
WTG-09 | 22.2 | 22.24 | 0.04 | 2.31 | 1.05 | YES
WTG-09 | 22.4 | 22.52 | 0.12 | 2.61 | 1.05 | YES
WTG-09 | 29.78 | 29.96 | 0.18 | 2.39 | 1.05 | YES
WTG-09 | 30.1 | 30.18 | 0.08 | 2.12 | 1.05 | YES
WTG-09 | 30.3 | 30.42 | 0.12 | 2.11 | 1.05 | YES
WTG-10 | 1.7 | 2.34 | 0.64 | 11.88 | 1.05 | YES
WTG-10 | 2.84 | 2.98 | 0.14 | 3.32 | 1.05 | YES
WTG-10 | 21.3 | 21.38 | 0.08 | 2.26 | 1.05 | YES
WTG-10 | 21.48 | 21.5 | 0.02 | 2.05 | 1.05 | YES
WTG-10 | 22.52 | 22.54 | 0.02 | 2.24 | 1.05 | YES
WTG-10 | 23.06 | 23.1 | 0.04 | 2.21 | 1.05 | YES
WTG-10 | 23.24 | 23.3 | 0.06 | 2.16 | 1.05 | YES
WTG-10 | 23.46 | 23.5 | 0.04 | 2.09 | 1.05 | YES
WTG-10 | 23.62 | 24.66 | 1.04 | 3.57 | 1.05 | YES
WTG-11 | 9.78 | 9.84 | 0.06 | 2.31 | 1.05 | YES
WTG-11 | 10.56 | 10.56 | 0 | 2.21 | 1.05 | YES
WTG-11 | 10.68 | 10.76 | 0.08 | 2.51 | 1.05 | YES
WTG-11 | 11.12 | 11.26 | 0.14 | 2.51 | 1.05 | YES
WTG-11 | 16.22 | 16.32 | 0.1 | 2.53 | 1.05 | YES
WTG-12 | 1.38 | 2.36 | 0.98 | 4.22 | 1.05 | YES
WTG-12 | 3.2 | 3.28 | 0.08 | 2.21 | 1.05 | YES
WTG-12 | 3.32 | 3.36 | 0.04 | 2.05 | 1.05 | YES
WTG-12 | 9.28 | 9.4 | 0.12 | 2.2 | 1.05 | YES
WTG-12 | 9.66 | 9.68 | 0.02 | 2.12 | 1.05 | YES
WTG-12 | 10.18 | 10.28 | 0.1 | 2.41 | 1.05 | YES
WTG-12 | 14.54 | 14.54 | 0 | 2.23 | 1.05 | YES
WTG-12 | 17.9 | 18.1 | 0.2 | 2.63 | 1.05 | YES
WTG-13 | 1.88 | 2.12 | 0.24 | 4.67 | 1.05 | YES
WTG-13 | 2.88 | 3.08 | 0.2 | 4.99 | 1.05 | YES
WTG-13 | 3.14 | 3.32 | 0.18 | 4.09 | 1.05 | YES
WTG-13 | 3.8 | 3.9 | 0.1 | 2.98 | 1.05 | YES
WTG-13 | 4.08 | 4.2 | 0.12 | 2.61 | 1.05 | YES
WTG-13 | 4.54 | 4.58 | 0.04 | 2.37 | 1.05 | YES
WTG-13 | 7.84 | 7.84 | 0 | 2.42 | 1.05 | YES
WTG-13 | 8.54 | 8.6 | 0.06 | 2.39 | 1.05 | YES
WTG-13 | 9.22 | 9.38 | 0.16 | 2.62 | 1.05 | YES
WTG-13 | 9.78 | 9.9 | 0.12 | 2.64 | 1.05 | YES
WTG-13 | 10.9 | 10.96 | 0.06 | 2.37 | 1.05 | YES
WTG-13 | 11.46 | 11.58 | 0.12 | 2.59 | 1.05 | YES
WTG-13 | 12.1 | 12.16 | 0.06 | 2.18 | 1.05 | YES
WTG-13 | 13.92 | 13.94 | 0.02 | 2.27 | 1.05 | YES
WTG-13 | 14.14 | 14.24 | 0.1 | 2.38 | 1.05 | YES
WTG-13 | 14.84 | 14.92 | 0.08 | 2.2 | 1.05 | YES
WTG-13 | 15.62 | 15.66 | 0.04 | 2.32 | 1.05 | YES
WTG-14 | 6.28 | 6.46 | 0.18 | 3.35 | 1.05 | YES
WTG-14 | 12.18 | 12.26 | 0.08 | 2.5 | 1.05 | YES
WTG-14 | 13.02 | 13.12 | 0.1 | 2.96 | 1.05 | YES
WTG-14 | 14.02 | 14.02 | 0 | 2.28 | 1.05 | YES
WTG-14 | 15.62 | 15.68 | 0.06 | 2.45 | 1.05 | YES
WTG-14 | 15.86 | 16.08 | 0.22 | 2.66 | 1.05 | YES
WTG-14 | 16.36 | 16.7 | 0.34 | 2.62 | 1.05 | YES
WTG-14 | 17.32 | 17.34 | 0.02 | 2.31 | 1.05 | YES
WTG-15 | 9.18 | 9.38 | 0.2 | 2.82 | 1.05 | YES
WTG-15 | 12.54 | 13.18 | 0.64 | 3.57 | 1.05 | YES
WTG-15 | 13.66 | 13.84 | 0.18 | 3.04 | 1.05 | YES
WTG-15 | 14.36 | 14.48 | 0.12 | 2.65 | 1.05 | YES
WTG-15 | 14.58 | 14.76 | 0.18 | 2.59 | 1.05 | YES
WTG-15 | 15.12 | 15.24 | 0.12 | 2.47 | 1.05 | YES
WTG-15 | 15.7 | 15.72 | 0.02 | 2.19 | 1.05 | YES
WTG-15 | 15.94 | 16 | 0.06 | 2.14 | 1.05 | YES
WTG-15 | 16.18 | 16.28 | 0.1 | 2.75 | 1.05 | YES
WTG-15 | 16.9 | 16.94 | 0.04 | 2.29 | 1.05 | YES
WTG-15 | 17 | 17.12 | 0.12 | 2.33 | 1.05 | YES
WTG-15 | 17.44 | 17.66 | 0.22 | 2.39 | 1.05 | YES
WTG-15 | 17.76 | 17.9 | 0.14 | 2.21 | 1.05 | YES
WTG-15 | 17.94 | 18.1 | 0.16 | 2.24 | 1.05 | YES
WTG-15 | 19.2 | 19.32 | 0.12 | 2.43 | 1.05 | YES
WTG-15 | 21.48 | 21.54 | 0.06 | 2.37 | 1.05 | YES
WTG-16 | 13.58 | 13.64 | 0.06 | 2.72 | 1.05 | YES
WTG-16 | 13.74 | 14.22 | 0.48 | 5.35 | 1.05 | YES
WTG-16 | 19.5 | 19.56 | 0.06 | 2.28 | 1.05 | YES
WTG-16 | 19.66 | 19.74 | 0.08 | 2.35 | 1.05 | YES
WTG-16 | 20.32 | 20.44 | 0.12 | 2.54 | 1.05 | YES
WTG-16 | 20.82 | 20.82 | 0 | 1.45 | 1.05 | YES
WTG-16 | 21.62 | 21.7 | 0.08 | 2.35 | 1.05 | YES
WTG-16 | 22.52 | 22.64 | 0.12 | 2.81 | 1.05 | YES
WTG-16 | 22.72 | 23 | 0.28 | 2.75 | 1.05 | YES
WTG-16 | 29.14 | 29.2 | 0.06 | 2.18 | 1.05 | YES
WTG-16 | 29.3 | 30.08 | 0.78 | 4.02 | 1.05 | YES
WTG-16 | 30.44 | 30.52 | 0.08 | 2.08 | 1.05 | YES
WTG-16 | 30.76 | 30.84 | 0.08 | 2.13 | 1.05 | YES
WTG-16 | 31.26 | 31.42 | 0.16 | 2.08 | 1.05 | YES
WTG-16 | 31.52 | 31.82 | 0.3 | 2.11 | 1.05 | YES
WTG-16 | 31.9 | 32.18 | 0.28 | 2.08 | 1.05 | YES
WTG-16 | 32.3 | 33.18 | 0.88 | 3.43 | 1.05 | YES
WTG-16 | 33.34 | 33.52 | 0.18 | 2.23 | 1.05 | YES
WTG-17 | 4.68 | 4.76 | 0.08 | 2.2 | 1.05 | YES
WTG-17 | 5.1 | 5.18 | 0.08 | 2.13 | 1.05 | YES
WTG-17 | 5.26 | 5.3 | 0.04 | 2.24 | 1.05 | YES
WTG-17 | 5.7 | 5.76 | 0.06 | 2.5 | 1.05 | YES
WTG-17 | 6.08 | 6.12 | 0.04 | 2.19 | 1.05 | YES
WTG-17 | 6.68 | 6.72 | 0.04 | 1.96 | 1.05 | YES
WTG-17 | 7.64 | 7.84 | 0.2 | 2.33 | 1.05 | YES
WTG-17 | 9.08 | 9.14 | 0.06 | 2.24 | 1.05 | YES
WTG-17 | 9.18 | 9.32 | 0.14 | 2.43 | 1.05 | YES
WTG-17 | 9.54 | 9.88 | 0.34 | 3.78 | 1.05 | YES
WTG-17 | 9.98 | 10.02 | 0.04 | 2.35 | 1.05 | YES
WTG-17 | 10.24 | 10.42 | 0.18 | 2.28 | 1.05 | YES
WTG-17 | 10.46 | 10.96 | 0.5 | 2.73 | 1.05 | YES
WTG-17 | 11.16 | 11.24 | 0.08 | 2.38 | 1.05 | YES
WTG-17 | 11.4 | 11.48 | 0.08 | 2.23 | 1.05 | YES
WTG-17 | 12.16 | 12.32 | 0.16 | 2.71 | 1.05 | YES
WTG-18 | 21.02 | 21.24 | 0.22 | 3.77 | 1.05 | YES
WTG-18 | 21.28 | 21.38 | 0.1 | 2.24 | 1.05 | YES
WTG-18 | 21.48 | 21.86 | 0.38 | 2.47 | 1.05 | YES
WTG-19 | 8.36 | 8.46 | 0.1 | 2.43 | 1.05 | YES
WTG-19 | 8.7 | 8.76 | 0.06 | 2.13 | 1.05 | YES
WTG-19 | 8.82 | 8.92 | 0.1 | 2.25 | 1.05 | YES
WTG-19 | 9.02 | 9.14 | 0.12 | 2.51 | 1.05 | YES
WTG-19 | 14.1 | 14.24 | 0.14 | 2.34 | 1.05 | YES
WTG-19 | 15.86 | 15.98 | 0.12 | 2.12 | 1.05 | YES
WTG-19 | 19.4 | 19.66 | 0.26 | 6.06 | 1.05 | YES
WTG-19 | 19.82 | 19.82 | 0 | 2.09 | 1.05 | YES
WTG-20 | 2.82 | 2.88 | 0.06 | 2.33 | 1.05 | YES
WTG-20 | 8.44 | 8.46 | 0.02 | 2.38 | 1.05 | YES
WTG-20 | 15 | 15.04 | 0.04 | 2.3 | 1.05 | YES
WTG-20 | 18.16 | 18.28 | 0.12 | 2.38 | 1.05 | YES
WTG-20 | 21.42 | 22.12 | 0.7 | 2.37 | 1.05 | YES
WTG-20 | 22.2 | 22.28 | 0.08 | 2.09 | 1.05 | YES
WTG-21 | 2.44 | 2.48 | 0.04 | 2.27 | 1.05 | YES
WTG-21 | 7.06 | 7.12 | 0.06 | 2.47 | 1.05 | YES
WTG-21 | 8.4 | 8.46 | 0.06 | 2.65 | 1.05 | YES
WTG-21 | 9.82 | 9.84 | 0.02 | 2.4 | 1.05 | YES
WTG-21 | 11.62 | 11.82 | 0.2 | 2.19 | 1.05 | YES
WTG-21 | 12.7 | 12.86 | 0.16 | 2.66 | 1.05 | YES
WTG-21 | 13.08 | 13.16 | 0.08 | 2.52 | 1.05 | YES
WTG-21 | 15.2 | 15.36 | 0.16 | 3.62 | 1.05 | YES
WTG-21 | 17.24 | 17.34 | 0.1 | 2.22 | 1.05 | YES
WTG-22 | 10.5 | 10.74 | 0.24 | 3.52 | 1.05 | YES
WTG-22 | 10.82 | 10.94 | 0.12 | 2.41 | 1.05 | YES
WTG-22 | 11.04 | 11.16 | 0.12 | 2.52 | 1.05 | YES
WTG-22 | 11.98 | 12.08 | 0.1 | 3.13 | 1.05 | YES
WTG-22 | 13.5 | 13.66 | 0.16 | 3.22 | 1.05 | YES
WTG-22 | 15.1 | 15.34 | 0.24 | 4.97 | 1.05 | YES
WTG-22 | 16.54 | 16.58 | 0.04 | 2.31 | 1.05 | YES
WTG-22 | 21.2 | 22.02 | 0.82 | 2.7 | 1.05 | YES
WTG-22 | 22.36 | 22.52 | 0.16 | 3.57 | 1.05 | YES
WTG-22 | 23.12 | 23.98 | 0.86 | 3.78 | 1.05 | YES
WTG-22 | 24.32 | 24.38 | 0.06 | 2.11 | 1.05 | YES
WTG-23 | 11.72 | 11.9 | 0.18 | 2.3 | 1.05 | YES
WTG-23 | 12.38 | 12.42 | 0.04 | 2.42 | 1.05 | YES
WTG-23 | 12.56 | 12.66 | 0.1 | 2.44 | 1.05 | YES
WTG-23 | 14.14 | 14.54 | 0.4 | 5.93 | 1.05 | YES
WTG-23 | 14.68 | 14.82 | 0.14 | 3.5 | 1.05 | YES
WTG-23 | 15.06 | 15.14 | 0.08 | 2.37 | 1.05 | YES
WTG-23 | 16.26 | 16.48 | 0.22 | 3.37 | 1.05 | YES
WTG-23 | 16.74 | 16.9 | 0.16 | 2.95 | 1.05 | YES
WTG-23 | 17.06 | 17.2 | 0.14 | 2.54 | 1.05 | YES
WTG-23 | 17.62 | 17.82 | 0.2 | 2.19 | 1.05 | YES
WTG-23 | 18.88 | 19 | 0.12 | 2.55 | 1.05 | YES
WTG-23 | 20.12 | 20.2 | 0.08 | 2.25 | 1.05 | YES
WTG-23 | 20.26 | 20.46 | 0.2 | 2.3 | 1.05 | YES
WTG-23 | 25.06 | 25.42 | 0.36 | 2.4 | 1.05 | YES
WTG-23 | 26.64 | 27.5 | 0.86 | 5.75 | 1.05 | YES
WTG-24 | 1.48 | 1.6 | 0.12 | 2.31 | 1.05 | YES
WTG-24 | 2.2 | 2.3 | 0.1 | 2.28 | 1.05 | YES
WTG-24 | 2.74 | 3.26 | 0.52 | 3.52 | 1.05 | YES
WTG-24 | 17.7 | 17.88 | 0.18 | 3.82 | 1.05 | YES
WTG-24 | 18.04 | 18.82 | 0.78 | 6.77 | 1.05 | YES
WTG-24 | 19.12 | 19.16 | 0.04 | 2.44 | 1.05 | YES
WTG-24 | 19.24 | 19.3 | 0.06 | 2.42 | 1.05 | YES
WTG-24 | 19.52 | 19.7 | 0.18 | 2.76 | 1.05 | YES
WTG-24 | 23.08 | 23.16 | 0.08 | 2.87 | 1.05 | YES
WTG-24 | 30.58 | 31.62 | 1.04 | 17.56 | 1.05 | YES
WTG-25 | 1.46 | 1.52 | 0.06 | 3.65 | 1.05 | YES
WTG-25 | 1.66 | 2.32 | 0.66 | 4.15 | 1.05 | YES
WTG-25 | 8.9 | 8.9 | 0 | 2.34 | 1.05 | YES
WTG-25 | 11.1 | 11.16 | 0.06 | 2.24 | 1.05 | YES
WTG-25 | 11.4 | 11.5 | 0.1 | 2.07 | 1.05 | YES
WTG-25 | 12.3 | 12.34 | 0.04 | 2.34 | 1.05 | YES
WTG-25 | 12.44 | 12.5 | 0.06 | 2.33 | 1.05 | YES
WTG-25 | 12.84 | 13.1 | 0.26 | 3.16 | 1.05 | YES
WTG-25 | 13.22 | 13.6 | 0.38 | 3.39 | 1.05 | YES
WTG-25 | 13.78 | 13.82 | 0.04 | 2.25 | 1.05 | YES
WTG-25 | 14.2 | 14.26 | 0.06 | 2.25 | 1.05 | YES
WTG-25 | 15.66 | 15.7 | 0.04 | 2.21 | 1.05 | YES
WTG-25 | 16.62 | 16.78 | 0.16 | 2.6 | 1.05 | YES
WTG-25 | 17.4 | 17.5 | 0.1 | 2.24 | 1.05 | YES
WTG-25 | 19.46 | 20.24 | 0.78 | 3.41 | 1.05 | YES
WTG-25 | 20.32 | 20.56 | 0.24 | 2.27 | 1.05 | YES
WTG-25 | 20.68 | 20.78 | 0.1 | 2.21 | 1.05 | YES
WTG-25 | 20.84 | 21.26 | 0.42 | 3.27 | 1.05 | YES
WTG-25 | 21.36 | 21.66 | 0.3 | 2.35 | 1.05 | YES
WTG-25 | 21.8 | 21.9 | 0.1 | 2.21 | 1.05 | YES
WTG-25 | 22.48 | 23 | 0.52 | 3.05 | 1.05 | YES
WTG-25 | 23.18 | 23.26 | 0.08 | 2.1 | 1.05 | YES
WTG-25 | 24.1 | 24.22 | 0.12 | 2.3 | 1.05 | YES
WTG-26 | 3.38 | 4.02 | 0.64 | 6.25 | 1.05 | YES
WTG-26 | 4.12 | 4.54 | 0.42 | 4.56 | 1.05 | YES
WTG-26 | 5.6 | 5.7 | 0.1 | 2.62 | 1.05 | YES
WTG-26 | 6.56 | 6.62 | 0.06 | 2.53 | 1.05 | YES
WTG-26 | 7.1 | 7.32 | 0.22 | 2.83 | 1.05 | YES
WTG-26 | 8.68 | 8.7 | 0.02 | 1.95 | 1.05 | YES
OSS | 12.2 | 12.26 | 0.06 | 2.34 | 1.05 | YES
OSS | 12.5 | 12.6 | 0.1 | 2.42 | 1.05 | YES
OSS | 12.7 | 12.82 | 0.12 | 2.54 | 1.05 | YES
OSS | 13.08 | 13.18 | 0.1 | 3.27 | 1.05 | YES
OSS | 13.4 | 13.54 | 0.14 | 2.29 | 1.05 | YES
OSS | 13.74 | 14.26 | 0.52 | 3.69 | 1.05 | YES
OSS | 14.76 | 15.06 | 0.3 | 3.2 | 1.05 | YES
OSS | 15.46 | 15.46 | 0 | 2.63 | 1.05 | YES
OSS | 15.8 | 15.9 | 0.1 | 2.49 | 1.05 | YES
OSS | 16.04 | 16.22 | 0.18 | 2.4 | 1.05 | YES
OSS | 16.68 | 16.82 | 0.14 | 2.59 | 1.05 | YES
OSS | 17.04 | 17.1 | 0.06 | 2.35 | 1.05 | YES
OSS | 17.24 | 17.38 | 0.14 | 2.96 | 1.05 | YES
OSS | 23.78 | 23.82 | 0.04 | 2.34 | 1.05 | YES
OSS | 26.48 | 26.68 | 0.2 | 2.51 | 1.05 | YES
OSS | 27.06 | 27.3 | 0.24 | 5 | 1.05 | YES

## Risk Summary
WTG | Type | Cat. | Length (m) | Weight (t) | Embedment (m) | Vibro Depth (m) | Wp (kN) | W_total (kN) | AH-FF Vmax (m/s) | AH-FF RunEnd (m) | AH-FF Margin (m) | AH-FF Risk | AH-NFF Vmax (m/s) | AH-NFF RunEnd (m) | AH-NFF Margin (m) | AH-NFF Risk | MEAN Vmax (m/s) | MEAN RunEnd (m) | MEAN Margin (m) | MEAN Risk | VERGOTE Vmax (m/s) | VERGOTE RunEnd (m) | VERGOTE Margin (m) | VERGOTE Risk | Worst Vmax (m/s) | Overall Risk
WTG-01 | DP | 2 | 56.2 | 236.4934 | 52.3 | 22 | 2320 | 4282 | 8.272 | 18 | 4 | CAUTION | 8.117 | 17 | 5 | OK | 8.189 | 17.5 | 4.5 | OK | 8.292 | 18 | 4 | CAUTION | 8.292 | OK
WTG-02 | DP | 2 | 46.5 | 236.4934 | 45 | 17 | 2320 | 4282 | 7.65 | 14.5 | 2.5 | CAUTION | 7.623 | 13.75 | 3.2 | CAUTION | 7.629 | 14.25 | 2.8 | CAUTION | 8.566 | 15.75 | 1.2 | CAUTION | 8.566 | CAUTION
WTG-03 | DP | 2 | 47.5 | 183.4862 | 46 | 18 | 1800 | 3762 | 5.908 | 13.25 | 4.8 | OK | 5.661 | 12 | 6 | OK | 5.779 | 12.5 | 5.5 | OK | 6.508 | 13.75 | 4.2 | OK | 6.508 | OK
WTG-04 | IP | 2 | 42 | 177.37 | 40.5 | 19 | 1740 | 3702 | 7.362 | 16 | 3 | CAUTION | 7.2 | 15.25 | 3.8 | CAUTION | 7.276 | 15.5 | 3.5 | CAUTION | 7.567 | 16.5 | 2.5 | CAUTION | 7.567 | CAUTION
WTG-05 | DP | 2 | 53.5 | 209.9898 | 52 | 17 | 2060 | 4022 | 4.79 | 8.25 | 8.8 | OK | 4.673 | 7.5 | 9.5 | OK | 4.727 | 8 | 9 | OK | 6.272 | 10 | 7 | OK | 6.272 | OK
WTG-06 | IP | 2 | 36.4 | 152.9052 | 34.9 | 18 | 1500 | 3462 | 3.692 | 2.75 | 15.2 | OK | 3.339 | 2.75 | 15.2 | OK | 3.339 | 2.75 | 15.2 | OK | 4.302 | 8.25 | 9.8 | OK | 4.302 | OK
WTG-07 | IP | 2 | 39.5 | 166.157 | 37.9 | 18 | 1630 | 3592 | 6.441 | 13.25 | 4.8 | OK | 6.365 | 12.5 | 5.5 | OK | 6.403 | 12.75 | 5.2 | OK | 6.687 | 13.75 | 4.2 | OK | 6.687 | OK
WTG-08 | IP | 2 | 37.6 | 181.4475 | 36 | 30.8 | 1780 | 3742 | 6.002 | 14.75 | 16 | OK | 5.87 | 12.75 | 18 | OK | 5.92 | 13.5 | 17.3 | OK | 7.509 | 18 | 12.8 | OK | 7.509 | OK
WTG-09 | IP | 1 | 39.5 | 176.3507 | 38 | 19 | 1730 | 3692 | 6.023 | 8 | 11 | OK | 5.995 | 8 | 11 | OK | 6.009 | 8 | 11 | OK | 6.359 | 13 | 6 | OK | 6.359 | OK
WTG-10 | IP | 1 | 39.6 | 163.0989 | 38.1 | 27 | 1600 | 3562 | 13.52 | 2.25 | 24.8 | OK | 11.321 | 2.25 | 24.8 | OK | 12.413 | 2.25 | 24.8 | OK | 8.519 | 29 | -2 | ATTENTION | 13.52 | OK
WTG-11 | IP | 2 | 26.7 | 110.0917 | 25.2 | 15 | 1080 | 3042 | 4.73 | 11 | 4 | CAUTION | 4.593 | 10.25 | 4.8 | OK | 4.661 | 10.75 | 4.2 | OK | 4.923 | 11.25 | 3.8 | CAUTION | 4.923 | OK
WTG-12 | IP | 2 | 37.9 | 155.9633 | 36.4 | 16 | 1530 | 3492 | 3.471 | 8.25 | 7.8 | OK | 3.325 | 7.25 | 8.8 | OK | 3.393 | 7.75 | 8.2 | OK | 5.005 | 10.25 | 5.8 | OK | 5.005 | OK
WTG-13 | IP | 2 | 20.9 | 87.6656 | 17.1 | 13 | 860 | 2822 | 2.64 | 3.25 | 9.8 | OK | 2.623 | 3.25 | 9.8 | OK | 2.632 | 3.25 | 9.8 | OK | 2.839 | 4.5 | 8.5 | OK | 2.839 | OK
WTG-14 | IP | 3 | 21.7 | 90.7238 | 20.2 | 14.2 | 890 | 2852 | 4.863 | 10.25 | 3.9 | CAUTION | 4.798 | 9.75 | 4.4 | OK | 4.83 | 10 | 4.2 | OK | 4.871 | 10.25 | 3.9 | CAUTION | 4.871 | OK
WTG-15 | DP | 1 | 53.8 | 212.0285 | 52.3 | 27 | 2080 | 4042 | 9.651 | 25.5 | 1.5 | CAUTION | 9.559 | 24 | 3 | CAUTION | 9.605 | 24.75 | 2.2 | CAUTION | 9.92 | 27 | 0 | ATTENTION | 9.92 | CAUTION
WTG-16 | DP | 1 | 50 | 253.8226 | 48.5 | 24 | 2490 | 4452 | 9.612 | 18.5 | 5.5 | OK | 9.586 | 18 | 6 | OK | 9.599 | 18.25 | 5.8 | OK | 10.005 | 21.25 | 2.8 | CAUTION | 10.005 | OK
WTG-17 | IP | 3 | 17.7 | 76.4526 | 16.2 | 10.2 | 750 | 2712 | 3.61 | 2.25 | 8 | OK | 2.449 | 2.25 | 8 | OK | 2.449 | 2.25 | 8 | OK | 6.605 | 3.75 | 6.4 | OK | 6.605 | OK
WTG-18 | IP | 2 | 25.3 | 103.9755 | 23.8 | 17.8 | 1020 | 2982 | 4.804 | 12.75 | 5.1 | OK | 4.673 | 11.5 | 6.3 | OK | 4.735 | 12 | 5.8 | OK | 4.897 | 13 | 4.8 | OK | 4.897 | OK
WTG-19 | IP | 2 | 42 | 172.2732 | 40.5 | 19 | 1690 | 3652 | 7.36 | 19.5 | -0.5 | ATTENTION | 7.292 | 18.75 | 0.2 | CAUTION | 7.326 | 19 | 0 | ATTENTION | 7.825 | 20 | -1 | ATTENTION | 7.825 | ATTENTION
WTG-20 | IP | 2 | 42.2 | 174.3119 | 40.7 | 16 | 1710 | 3672 | 4.34 | 9 | 7 | OK | 4.194 | 8 | 8 | OK | 4.264 | 8.5 | 7.5 | OK | 4.789 | 9.5 | 6.5 | OK | 4.789 | OK
WTG-21 | IP | 2 | 49.2 | 204.893 | 47.7 | 20 | 2010 | 3972 | 5.607 | 12 | 8 | OK | 5.436 | 10.75 | 9.2 | OK | 5.514 | 11.25 | 8.8 | OK | 5.894 | 12.25 | 7.8 | OK | 5.894 | OK
WTG-22 | DP | 1 | 51.9 | 201.8349 | 48.5 | 24 | 1980 | 3942 | 7.604 | 17.25 | 6.8 | OK | 7.389 | 16.25 | 7.8 | OK | 7.49 | 16.75 | 7.2 | OK | 7.684 | 17.75 | 6.2 | OK | 7.684 | OK
WTG-23 | IP | 1 | 40.2 | 170.2345 | 38.7 | 30 | 1670 | 3632 | 9.317 | 24.5 | 5.5 | OK | 9.234 | 21.25 | 8.8 | OK | 9.276 | 22.5 | 7.5 | OK | 9.681 | 26.5 | 3.5 | CAUTION | 9.681 | OK
WTG-24 | DP | 1 | 44.4 | 242.6096 | 42.5 | 15 | 2380 | 4342 | 6.959 | 14.75 | 0.2 | CAUTION | 6.526 | 14.25 | 0.8 | CAUTION | 6.729 | 14.5 | 0.5 | CAUTION | 7.382 | 19 | -4 | ATTENTION | 7.382 | CAUTION
WTG-25 | IP | 1 | 35.1 | 156.9827 | 33.6 | 17 | 1540 | 3502 | 3.485 | 6.25 | 10.8 | OK | 3.292 | 6.25 | 10.8 | OK | 3.387 | 6.25 | 10.8 | OK | 5.481 | 11.5 | 5.5 | OK | 5.481 | OK
WTG-26 | IP | 3 | 14.7 | 59.1233 | 13.2 | 5.3 | 580 | 2542 | 3.234 | 4.5 | 0.8 | CAUTION | 3.221 | 4.5 | 0.8 | CAUTION | 3.228 | 4.5 | 0.8 | CAUTION | 3.883 | 6.5 | -1.2 | ATTENTION | 3.883 | CAUTION
OSS | OSS | 0 | 37.5 | 226.2997 | 35.5 | 25 | 2220 | 4182 | 7.767 | 17.75 | 7.2 | OK | 7.561 | 16.75 | 8.2 | OK | 7.662 | 17.25 | 7.8 | OK | 7.79 | 18 | 7 | OK | 7.79 | OK